## Sheet1
Organisation Name | Activity name | Location | Phase type | Phase Scope | Length | Special Features | Initial Benefit/Cost Ratio | Latest Benefit/Cost Ratio | Original Approved Cost when first made public | Current Approved Cost | Forecast | Completion Year at First Approval | Current forecast completion Year | Reasons for cost increase
Waka Kotahi NZ Transport Agency (National) | Innovating Streets Programme 2021-24 | Nationwide | Implementation | Project to promote walking and cycling projects in urban centres. | TBC | N/A | TBC | TBC | 30000000 | 30000000 | 30000000 | 2023/24 | 2023/24 | N/A
Waka Kotahi NZ Transport Agency (Auckland) | Glen Innes to Tāmaki Shared Path - Section 2 | Auckland City | Implementation | Glen Innes to Tāmaki Drive Section 2 Implementation | 1.3km | Inner-city suburb. Requires extensive board walks to protect coastal environment. | 0.9 | 0.9 | 47914200 | 51359631 | 42076000 | 2021/22 | 2022/23 | Cost savings of $11M are forecast due to lower tender prices received in 2020, and contingency requirements being less than expected.
Waka Kotahi NZ Transport Agency (BOP) | State Highway (SH) 2: Baypark to Bayfair Link Upgrade | Tauranga | Implementation | Construction of walking and cycling facilities | Business case is to determine | Complex, high volume intersection requiring underpasses | 2.5 | 2.1 | 12338000 | 33212656 | 33200000 | 2020/21 | 2022/23 | Significant cost increase of $18.5M in March 2020 as the initial scope of the project changed from signalised grade crossings to included a pedestrian and cycle underpass facility as part of the Bay Link project.
Waka Kotahi NZ Transport Agency (Gisborne) | Gisborne - Wainui Cycleway SH 35 | Gisborne | Implementation | Gisborne to Wainui Cycleway along SH 35 | 1.6km | Major cost for repositioning underground services | 3.1 | 2.5 | 780000 | 3028866 | 3028000 | 2014/15 | 2021/22 | Cost increases of $0.8M in Feb 2015, and a further increase in March 2018 of $1.2M to extend re-scope the programme of works. Originally the cycleway was 1.2km, and this was extended to 1.6km to complete the connection. Additional costs also stemming from soft ground conditions being identified during the geotechnical investigation which required additional rehabilitation works, and undergrounding of 11 reticulation poles as they conflicted with the proposed alignment.
Waka Kotahi NZ Transport Agency (Gisborne) | Walking and Cycling connectivity | Gisborne | Implementation | Construction | 0.2 km(est) | Includes Gladstone Bridge clip-on | 4.7 | 4.1 | 690300 | 1789000 | 1789000 | 2017/18 | 2021/22 | Increase of $0.6M in June 2018 as tender costs were higher than first estimated and Quality Assurance costs not previously included. Further increase of $0.6M in 2019/20 and $0.2M for additional traffic management costs, integrating into the Turanga Trail, and a handrail between the shared path and road.
Waka Kotahi NZ Transport Agency (Hawkes Bay) | SH50 Prebensen Drive/Hyderabad intersection | Napier | Implementation | Construction |  | Lane re-configuration changes at both the Hyderabad Rd/Prebensen Dr and Hyderabad RdHaradale Rd intersections, with associated marking and signage improvements. Connected Shared Path on Hyderabad Road, linking Pandora Road in the north to the Prebensen Drive/Marewa Shared path in the south. | 5.6 | 5.6 | 1878500 | 1977369 | 1977000 | 2019/20 | 2022/23 | N/A
Waka Kotahi NZ Transport Agency (Manawatu/Whanganui) | Manawatu River Bridge SH3 Ashhurst Cycle/walkway | Palmerston North | Pre-implementation | Detailed investigation and design | 0.2km | Bridge clip-on. | 1.6 | 1.6 | 1005480 | 1058400 | 1058400 | 2021/22 | 2021/22 | N/A
Waka Kotahi NZ Transport Agency (Otago) | SH6 SH8B SH8 Gibbston to Clyde Corridor Imps Nevis Bluff | Central Otago | Implementation | Construction of Nevis Bluff section of the Kawarau gorge (Gibbston to Bannockburn) trail. | Business case is to determine | Rockfall protection on unstable bluff. | 9.7 | 9.7 | 2592000 | 2592000 | 2592000 | 2022/23 | 2022/23 | N/A
Waka Kotahi NZ Transport Agency (Otago) | Dunedin - Port Chalmers Safety Improvements (SH88) | Dunedin | Implementation | Construction | 5km | Coastal cycle path with challenging geometry, requiring reclamation works and boardwalks. 2.4km of rail line needed to be realigned | 1.1 | 0.7 | 26500000 | 43526385 | 43804000 | 2021/22 | 2023/24 | Increase of $3.8m in Oct 2019 for increased tender price plus contingency. Increase of $0.6M in April 2020 for increase in overheads (non-core project cost, $1.4M Jul 2021 (increase in overheads). Dec 2021 increase of $0.8M for share of a watermain realignment and $10.5M in April 2022 for additonal costs for reclamation, unforseen ground conditions, temporary level crossings to enable reclamation to take place plus KiwiRail costs for block of line, track and signal work.
Waka Kotahi NZ Transport Agency (Otago) | Wakatipu Walking/Cycling Network Improvements | Queenstown | Pre-implementation | Pre-implementation | Business case is to determine | Not applicable (N/A) | 1.8 | 1.8 | 754301 | 900348 | 900000 | 2019/20 | 2021/22 | N/A
Waka Kotahi NZ Transport Agency (Otago) | Wakatipu Walking/Cycling Network Improvements | Queenstown | Implementation | Route 1 (A5,A7) and Route 4N (A2, A3/A4) construction | 5km | N/A | 1.8 | 1.8 | 11758051 | 12080709 | 12080000 | 2020/21 | 2022/23 | N/A
Waka Kotahi NZ Transport Agency (Otago) | Wakatipu Walking/Cycling Network Improvements | Queenstown | Implementation | Property | 10.82km | Property aquisition | 1.8 | 1.8 | 13640423 | 13640423 | 13640000 | 2022/23 | 2022/23 | N/A
Waka Kotahi NZ Transport Agency (Waikato) | SH1 Hamilton to Cambridge Cycle Connection - Section 1 | Hamilton | Implementation | Construction | 9.7km | Includes underpass on SH21 | 3.3 | 3.6 | 7900200 | 10968895 | 10425000 | 2020/21 | 2024/25 | Oct 2019 increase of $2.7M In the original DBC, completed in 2016, the preferred option for a grade separated crossing of SH21 was a pedestrian and cycling bridge. However during the detailed design phase the bridge costs were found to have been significantly underestimated. A re-optioneering exercise was carried out for the SH21 crossing and the options have now been re-evaluated and re-costed. This exercise has resulted in the recommendation of an underpass as the new preferred grade separated crossing. This crossing option is the lowest cost grade separated option. Increase of $0.4M in July 2021 for overheads. This PLA seeks an additional $2,667,600 for the underpass. The full cost of the underpass is $4.4 million however savings have been found on other elements of this section as detailed below.
Waka Kotahi NZ Transport Agency (Waikato) | SH1 Tamahere Interchange Pedestrian / Cycleway | Hamilton | Business Cases | Crossing the Tamahere Interchange on State Highway 1 | Business case is to determine | Crossing across State highway 1 | TBC | TBC | 100000 | 105000 | 105000 | 2021/22 | 2021/22 | N/A
Waka Kotahi NZ Transport Agency (Wellington) | Petone to Melling Walking Cycling Link | Lower Hutt | Implementation | Construction | 4.5KM | Construction alongside main trunk line requiring significant excavation works and moving underground services, KiwiRail line closures and a new underpass. | 2.3 | 0.6 | 17200000 | 63155581 | Witheld under section 9(2)(b)ii | 2017/18 | 2023/24 | May 2019 increase of $16.1M. Original funding was approved on intial estimates prior to completion of detailed design and building consents being approved. October 2021 increase of $ 30.9M for incresed in tenders, design shirtcomings, and assessed ground conditions exposing constriction issues. Increased cost for escavation and moving underground services, KiwiRail line closures and underpass.
Waka Kotahi NZ Transport Agency (Wellington) | Ngauranga to Petone Walking and Cycling Link | Wellington | Pre-implementation | Detailed design and consenting work | 7km | Coastal environment requiring extensive reclamation works and seawalls, and managing construction alongside the major rail line. | 1.1 | 1.1 | 7200000 | 9685532 | 9685000 | 2020/21 | 2021/22 | September 2020 increase of $2.5M to cover the fast track consenting process, site investigations, specimen design, and procuring the alliance. July 2021 increase of $0.228M in overheads.
Waka Kotahi NZ Transport Agency (Wellington) | Ngauranga to Petone Walking and Cycling Link | Wellington | Implementation | Construction | 7km | The project site is extremely challenging, within a sensitive coastal environment, and right alongside Wellington’s busiest rail line for commuters. These challenges add complexity and cost to delivering the project. | 1.1 | Under Review | 182628000 | 192240000 | Under review | 2023/24 | 2025/26 | Waka Kotahi and its Te Ara Tupua Alliance partners are continuing to work on design, construction planning, and estimating costs for the project. This work is the due diligence needed to deliver a challenging project of this nature in a complex coastal environment within an existing infrastructure corridor.
Waka Kotahi NZ Transport Agency (Wellington) | Wellington Cycle Network - SH1 Cobham Drive Improvements | Wellington | Implementation | Highways component of the Cobham Drive cycling improvements being led by Wellington City Council. | 0.1km | N/A | 2.5 | 2.5 | 1000000 | 1005731 | 1005000 | 2018/19 | 2021/22 | N/A
Waka Kotahi NZ Transport Agency (Wellington) | Let's Get Wellington Moving (LGWM) GWM ED Central City and SH1 walking cycling and safer speed | Wellington | Business Cases | Central City And SH1 Walking Cycling and Safer Speed | Business case is to determine | N/A | TBC | TBC | 1210697 | 1889832 | 1889800 | 2020/21 | 2021/22 | Aug 2020 $0.173M increased apportionment of costs per funding agreement. Sept 2021 increase of $0.5M for scope change for Cobham Crossing.
Waka Kotahi NZ Transport Agency (Wellington) | LGWM ED Central City and SH1 walking cycling and safer speed | Wellington | Implementation | LGWM C.City & SH1 WC+Safer Speed Implementation | 0.5km (est) | Traffic management on this major route to the airport | 1.2 | 1.2 | 2808000 | 2808000 | 2808000 | 2021/22 | 2022/23 | N/A
Waka Kotahi NZ Transport Agency (Wellington) | LGWM City Streets | Wellington | Business Cases | LGWM City Streets | Business case is to determine | Inner-city cycle connection | TBC | TBC | 4807132 | 5009032 | 5009000 | 2020/21 | 2021/22 | July 2021 $0.2M increase in overheads
Waka Kotahi NZ Transport Agency (Wellington) | LGWM CS Bowen St | Wellington | Business Cases | LGWM CS Bowen St | Business case is to determine | Inner-city cycle connection | TBC | TBC | 507587 | 507587 | 507000 | 2021/22 | 2021/22 | N/A
Waka Kotahi NZ Transport Agency (Wellington) | LGWM CS Featherston St | Wellington | Business Cases | LGWM CS Featherston St | Business case is to determine | Inner-city cycle connection | TBC | TBC | 1858662 | 1858662 | 1858600 | 2021/22 | 2021/22 | N/A
Waka Kotahi NZ Transport Agency (Wellington) | LGWM CS South West CBD | Wellington | Business Cases | LGWM CS South West CBD | Business case is to determine | Inner-city cycle connection | TBC | TBC | 1998424 | 1998424 | 1998000 | 2021/22 | 2021/22 | N/A
Note: years are for the financial years running from 1 July to 30 June.