## Naming Files
Naming Convention for Files

## Instructions
Change Management Request
From the detailed Annual Programmes the following achievement trackers are established for September Baseline:
- Pavement resurfacing (WC212) and pavement renewal (WC214)
- SCRIM (WC212)
- ATP renewal (WC222)
- Drainage renewals (WC213)
- Structures component replacement (WC215)
Changes to the programmes; including scope, site, length or value require a Change Management Request (CMR).
o Any CMR received after 15th December will require Mitigating Circumstances approved by CMT and/or Board
o No further changes to the Tracker will be accepted from 1st March.
Where change is within financial delegations (DFA) and within the regions budget allocation the following applies:
Contract variations will need to be managed within the allocations available. Where this is unable to be achieved, a Priority Funding Request can be made to the Principal Advisor - Maintenance Programmes for capture in priority matrix. If funding becomes available these applications will be considered for funding release.
CMR Application Process
1. Supplier/Network Manager (NM) prepare CMR
a) All submissions require the Change Form tab be completed
b) Changes to renewals programmes (i.e. tracker records) require the Changes to Programme tab be completed
c) Complete all fields if possible
d) Drop down fields are available for use and protected to prevent overwriting
> Network, Project Name, Project Number
> Work Category (this will assist identifying approvers)
> Nature of Change (this aligns with the Achievement tracker selections)
> Risk/Opportunity
> ALL Grey cells are to be completed on Changes to Programme tab
2. As per above, the System Manager (SM), Asset Investment Advisor (AIA), Project Manager - Structures, and/or Regional Manager may be required to approve depending on the Activity.
3. Approved forms are required to be uploaded to the Network 'Change Requests' folder, and
3a. infoHub link emailed to CMRrequest@nzta.govt.nz
4. Programme & Standards team will:
a) adjust allocations in SAP,
b) update achievement tracker (please note - the tracker is refreshed twice a month, not daily), and
c) send confirmation of action to NM as appropriate.
Links
https://www.nzta.govt.nz/roads-and-rail/highways-information-portal/processes/strategic-activity-management/annual-planning/
https://www.nzta.govt.nz/assets/Highways-Information-Portal/Processes/Strategic-activity-management/Annual-planning/Annual-planning-docs/Achievement-tracker-process-guidelines-september-2021.pdf

## Change Form $$$
Change Management Record (version refresh 22.01.2024)
[11 empty] | Year | Change No
Project Type (1) |  |  |  | Project Name (2) |  |  |  |  | Select Project number (3) |  | 23/24 | no#-yyyymmdd
Documenting the changes made from a baseline which is the current version of the annual plan on the server So, the changes include any changes made as a result of the initial moderation feedback and changes made by the initial moderation work | [10 empty] | Sign off as per the delegations in change management process
Telling us what has been changed and why | [6 empty] | By how much | Residual Risk and Management Plan
WBS | Work Category | Nature of change | What have you changed and why including link to revised programmes |  |  |  | $$$ Funding change +/- | Risk/Opportunity | The consequences of the changes on Annual Plan, Programme and/or Waka Kotahi, and how these have been considered/managed |  | SUBMITTED by | Approved (Y/N)
new |  |  | Asset management Project |  |  |  | 5000
new |  |  | ITS Communication Platforms & Channels Project |  |  |  | 100000
new |  |  | TOC Maintenance and Operations Project |  |  |  | 150000
| WC213 |  | Reduction in Drainage programme - return funds to Central Pool |  |  |  | -20000
[5 empty] | Total Requested | 235000 |  |  |  | (Requstor) INSERT: infohub file ref/link
[5 empty] | Total Approved | 0 |  |  |  | (P&S) INSERT: ServiceNow reference
Senior Network Managers Endorsment
|  |  | Name |  |  | Date
Senior Network Managers Recomendations:
Approvals (see change management process for for futher details) DO NOT TYPE OVER GREEN CELLS | [9 empty] | Comments
Required |  | Asset Investment Advisor |  |  |  | Date
Not Required |  | Principal Structural Engineer/SMC |  |  |  | Date
Not Required |  | System Manager |  |  |  | Date
|  | Endorsed by APMT |  |  |  | Date
Approval Comments:
Updates | [9 empty] | Comments
|  | Achievement tracker |  |  |  | Date
|  | Allocations |  |  |  | Date
Comments:
Note on P3: NAMING CONVENTION see also 'Naming Files' tab
Note on H24: This is the sum approved by two TAs (or equivalent)

## Preservation Tracker CMR
DO NOT TYPE OVER THESE CELLS |  |  | ALL BLUE CELLS MUST BE COMPLETED
Line item no# | Tracker ID (unless NEW) | Select Network first then State Highway to populate the RoadName lookup |  | Start | End | Length | No. of lanes | Lane Name | Lane km | Current / Proposed Treatment | What is the nature of the change? | Description/ Explanation/ Justification on Performance Impacts | $$$ Funding change +/- | Work Category | Intended month of completion. | Approval (SNM and/or AIA)
[16 empty] | Justified change to baseline? | Line approved (Y/N)
|  | State Highway | Road Name
1 |  | 002BOP_EAST | 002-0209 |  |  | 0 |  |  | 0
2 |  | 005BOP_EAST | 005-0045 |  |  | 0 |  |  | 0
3 |  | 033BOP_EAST | 033-0000 |  |  | 0 |  |  | 0
4 | [5 empty] | 0 |  |  | 0
5 | [5 empty] | 0 |  |  | 0
6 | [5 empty] | 0 |  |  | 0
7 | [5 empty] | 0 |  |  | 0
8 | [5 empty] | 0 |  |  | 0
9 | [5 empty] | 0 |  |  | 0
10 | [5 empty] | 0 |  |  | 0
11 | [5 empty] | 0 |  |  | 0
12 | [5 empty] | 0 |  |  | 0
13 | [5 empty] | 0 |  |  | 0
14 | [5 empty] | 0 |  |  | 0
15 | [5 empty] | 0 |  |  | 0
[12 empty] | Total Requested | 0
[12 empty] | Total Approved | 0

## Quarterly WC mgmt (hidden)
RECORD OF MINOR CHANGES WITHIN WC 100 SERIES - SUMMARY LEVEL (LINE ITEM BY LINE ITEM NOT REQUIRED)
WBS | Work Category | Funding Change +/- | Record of change | WBS | Work Category | Funding Change +/- | Risk/Opportunity | The consequences of the changes on Annual Plan, Programme and/or Waka Kotahi
123456 | WC113 | 2000 | reallocated funds as programme reduced in WC124, use for high lip | 456789 | WC124 | -2000 | Opportunity | n/a

## ATP Tracker CMR
DO NOT TYPE OVER THESE CELLS |  |  | ALL BLUE CELLS MUST BE COMPLETED
Line item no# | Tracker ID (unless NEW) | Select Network first then State Highway to populate the RoadName lookup |  | Start | End | Length | Side (L, R, C, All) | What is the nature of the change? | Description/ Explanation/ Justification on Performance Impacts | $$$ Funding change +/- | Work Category | Intended month of completion. | Approval (SNM and/or AIA)
[13 empty] | Justified change to baseline? | Line approved (Y/N)
|  | State Highway | Road Name
1 | [5 empty] | 0 |  |  | Where do we record the type of treatment? 150 or 200mm wide, No overtaking etc
2 | [5 empty] | 0
3 | [5 empty] | 0
4 | [5 empty] | 0
5 | [5 empty] | 0
6 | [5 empty] | 0
7 | [5 empty] | 0
8 | [5 empty] | 0
9 | [5 empty] | 0
10 | [5 empty] | 0
[9 empty] | Total Requested | 0
[9 empty] | Total Approved | 0

## Drainage Tracker CMR
DO NOT TYPE OVER THESE CELLS |  |  | ALL BLUE CELLS MUST BE COMPLETED
Line item no# | Tracker ID (unless NEW) | Select Network first then State Highway to populate the RoadName lookup |  | Start | End | Length (m) | Asset Type | Side | Dia. | Current / Proposed Treatment | What is the nature of the change? | Description/ Explanation/ Justification on Performance Impacts | $$$ Funding change +/- | Work Category | Intended month of completion. | Approval (SNM and/or AIA)
[16 empty] | Justified change to baseline? | Line approved (Y/N)
|  | State Highway | Road Name
1
2
3
4
5
6
7
8
9
10
[12 empty] | Total Requested | 0
[12 empty] | Total Approved | 0

## Structures Tracker CMR
DO NOT TYPE OVER THESE CELLS |  |  | ALL BLUE CELLS MUST BE COMPLETED
Line item no# | Tracker Row ID (unless NEW) | Select Network first then State Highway to populate the RoadName lookup |  | BSN/RP | Bridge Name | NOC/Non-NOC | Project No# | SAPR | Current / Proposed Treatment | What is the nature of the change? | Description/ Explanation/ Justification on Performance Impacts | $$$ Funding change +/- | Work Category | Intended month of completion. | Approval (SNM and/or SMC)
[15 empty] | Justified change to baseline? | Line approved (Y/N)
|  | State Highway | Road Name
1
2
3
4
5
6
7
8
9
10
[11 empty] | Total Requested | 0
[11 empty] | Total Approved | 0

## Lookups
Look Up Tables
Legitimate Change | Risk | Whats being changed | Month | Lane Name | Work_category | Approver | Sap Project Name | SAP Project Numbers |  | Length/Number of names validation
| No impact | WBS / Project Correction from Allocation | January | All | WC111 | SM |  |  |  | road_name | road_start | road_end | maxlanes
n/a | Minor risk impact | Cost Change >30% (variation) | February | L1 | WC112 | SM | Project Type (1) | Project Name (2) | Project Number (3) | 01N-0104 | 0 | 14714 | 2
Y | Moderate risk impact | Cost Change <30% (variation) | March | L2 | WC113 | AIA | NOC | Auckland Non-NMA | 60101771 | 01N-0119 | 0 | 15890 | 2
N | High risk impact | Lane Change | April | L3 | WC114 | PM / SME | Non_NOC | Auckland System Mgt Alliance | 60052404 | 01N-0134 | 0 | 14868 | 2
| Shared Risk | Length Change >30% | May | L4 | WC121 | SM | Alliance | Bay of Plenty West NMA - PSMC 4 - BayRo | 60103459 | 01N-0149 | 0 | 17363 | 3
| Opportunity | Length Change <30% | June | R1 | WC122 | SM | NMA | BOP East NOC | 60029273 | 01N-0185 | 0 | 5700 | 2
| Other (MUST specify) | Rework | July | R2 | WC123 | SM | Non_NMA | BOP East Non NOC | 60030135 | 01N-0190 | 0 | 7666 | 3
|  | Site completed in Previous Year | August | R3 | WC124 | SM | ONMC | BOP West NMC (NOC) 2023-2026 | 60073800 | 01N-0198 | 0 | 13309 | 3
|  | Site bought Forward | September | R4 | WC131 | SM | Non_ONMC | BOP West non ONMC (NOC) | 60029445 | 01N-0215 | 0 | 17693 | 3
|  | Site carried Over from Previous Year | October | L-SH | WC151 | SM | Structures | BOP West ONMC (NOC) | 60030049 | 01N-0233 | 0 | 12425 | 3
|  | Site Deferred (MUST indicate to what year) | November | R-SH | WC211 | AIA | Operations | Central Otago NOC | 60040663 | 01N-0245 | 0 | 12929 | 3
|  | Treatment Changed | December | Left Lanes | WC212 CS | AIA | National | Central Otago NON NOC | 60040705 | 01N-0258/05.04-I | 5044 | 6397 | 2
|  | Network Changed |  | Right Lanes | WC212 SCRIM | AIA |  | Central Waikato NOC | 60034133 | 01N-0258/05.04-D | 5044 | 6397 | 2
|  | Other (MUST specify) |  |  | WC212 TAC | AIA |  | Central Waikato Non-NOC | 60043298 | 01N-0258/06.40 | 6397 | 7245 | 4
|  |  |  | ATP Lanes | WC213 | AIA |  | Coastal Otago NOC | 60040085 | 01N-0258/07.25-I | 7245 | 7814 | 2
|  |  |  | Left | WC214 AWT | AIA |  | Coastal Otago NON-NOC | 60040127 | 01N-0258/07.25-D | 7245 | 7829 | 2
|  |  |  | Right | WC214 SAC | AIA |  | East Waikato NOC (est 2017) | 60047869 | 01N-0266 | 0 | 5820 | 3
|  |  |  | Centre | WC215 | PM / SME |  | East Waikato Non-NOC | 60043361 | 01N-0273 | 0 | 17852 | 4
|  |  |  | Both | WC221 | AIA |  | Hawkes Bay Network Outcomes Contract | 60038809 | 01N-0319 | 0 | 17295 | 3
[5 empty] | WC222 | AIA |  | Hawkes Bay NMA | 60101519 | 010-0000 | 0 | 7476 | 2
|  |  |  | Drainage Side | WC324 AWT |  |  | Hawkes Bay NON NOC | 60100609 | 010-0017 | 0 | 3460 | 2
|  |  |  | Left | WC324 CS |  |  | Manawatu Gorge Detour Route | 60053854 | 010-0033 | 0 | 14885 | 3
|  |  |  | Right | WC324 TAC |  |  | Manawatu New NOC | 60035142 | 010-0048 | 0 | 14730 | 3
|  |  |  | Centre | WC324 PROJ |  |  | Manawatu Non-NOC | 60035283 | 010-0063 | 0 | 14476 | 3
|  |  |  | Both |  |  |  | Marlborough New NOC 2020 | 60056127 | 010-0079 | 0 | 16136 | 2
APPROVER |  | DRAINAGE ASSET TYPE |  | Across |  |  |  | Marlborough NON NOC | 60104459 | 010-0095 | 0 | 10534 | 3
SM | WC111 | Culvert | [5 empty] | Milford Road Alliance | 60040205 | 012-0000 | 0 | 8696 | 2
| WC112 | Lined Water Channel | [5 empty] | Milford Road NON Alliance | 60041101 | 012-0017 | 0 | 16340 | 2
| WC121 | Reform Sidedrains | [5 empty] | North Canterbury NMA | 60100558 | 012-0033 | 0 | 12920 | 2
| WC122 | Subsoil Drains | [5 empty] | North Canterbury NOC | 60044014 | 012-0046 | 0 | 12589 | 2
| WC123 | [6 empty] | North Canterbury Non-NOC | 60040662 | 012-0061 | 0 | 12980 | 2
| WC124 | [6 empty] | Northland Noc (Nthld) 2018+ | 60045768 | 012-0074 | 0 | 13320 | 2
| WC131 | [6 empty] | Northland NON NOC (Nthld) 2018+ | 60045873 | 012-0089 | 0 | 16700 | 2
| WC151 | [6 empty] | South Canterbury NOC | 60029341 | 012-0106 | 0 | 15700 | 2
[8 empty] | South Canterbury Non-NOC | 60040618 | 012-0122 | 0 | 9700 | 2
PM / SME | WC114 | [6 empty] | Southland NOC | 60037613 | 012-0132 | 0 | 20940 | 2
| WC215 | [6 empty] | Southland NON-NOC | 60040154 | 012-0153 | 0 | 15930 | 2
[8 empty] | Tairawhiti NOC | 60037270 | 012-0169 | 0 | 15928 | 2
AIA | WC211 | [6 empty] | Tairawhiti Non-NOC | 60039712 | 012-0185 | 0 | 15996 | 2
| WC212 | [6 empty] | Taranaki NOC 2020 | 60057421 | 012-0202 | 0 | 20940 | 2
| WC213 | [6 empty] | Taranaki NON NOC 2020 | 60057443 | 014-0000 | 0 | 10708 | 3
| WC214 | [6 empty] | Tasman (and Nelson) non NOC | 60044169 | 014-0015 | 0 | 14200 | 2
| WC221 | [6 empty] | Tasman NoC | 60038254 | 014-0030 | 0 | 13870 | 3
| WC222 | [6 empty] | Waterview Tunnel Maintenance | 60039533 | 014-0044 | 0 | 11575 | 2
[8 empty] | Wellington NON NOC | 60046041 | 01N-0336 | 0 | 10231 | 3
[8 empty] | Wellington Transport Alliance | 60066264 | 01N-0346 | 0 | 16275 | 3
[8 empty] | West Coast NOC | 60036637 | 01N-0363 | 0 | 9918 | 5
[8 empty] | West Coast Non-NOC | 60040640 | 01N-0373 | 0 | 9557 | 3
[8 empty] | West Waikato NOC | 60062542 | 01N-0414-D | 0 | 9020 | 5
[8 empty] | West Waikato Non Noc | 60062564 | 01N-0417-R1 | 0 | 313 | 2
[8 empty] | Bay of Plenty SMC Structures | 60062483 | 01N-0417-R4 | 0 | 258 | 1
[8 empty] | Canterbury-West Coast SMC Structures | 60062628 | 01N-0417-R3 | 0 | 249 | 5
[8 empty] | Gisborne-Hawkes Bay SMC Structures | 60062683 | 01N-0417-R2 | 0 | 221 | 2
[8 empty] | Northland SMC Structures | 60062727 | 01N-0419-R1 | 0 | 256 | 2
[8 empty] | Otago-Southland SMC Structures | 60062520 | 01N-0419-R4 | 0 | 257 | 1
[8 empty] | Taranaki-Manawatu-Whanganui Structures | 60062660 | 01N-0419-R2 | 0 | 247 | 1
[8 empty] | Waikato SMC Structures | 60062461 | 01N-0419-R3 | 0 | 220 | 1
[8 empty] | Wellington-Nelson-Marlborough Structures | 60062596 | 01N-0420-R7 | 0 | 267 | 2
[8 empty] | Marlborough Local Authority | 60027164 | 01N-0422-R4 | 0 | 280 | 1
[8 empty] | Waitangi Wharf Maintenance & Operations | 60049013 | 01N-0422-R1 | 0 | 331 | 1
[8 empty] | Auckland Network Operations | 60104018 | 01N-0422-R3 | 0 | 240 | 2
[8 empty] | National Maintenance and Operations | 60063629 | 01N-0422-R2 | 0 | 507 | 1
[8 empty] | System Optimisation | 60049745 | 01N-0423-R1 | 0 | 388 | 1
[8 empty] | Tauranga TOC | 60046190 | 01N-0425-R1 | 0 | 372 | 1
[8 empty] | Waikato Traffic Signals Maintenance | 60064299 | 01N-0425-R2 | 0 | 459 | 2
[8 empty] | Wellington Journey Team | 60029228 | 01N-0426-R1 | 0 | 265 | 4
[8 empty] | Wellington TOC | 60031949 | 01N-0426-R3 | 0 | 213 | 1
[8 empty] | Asset Management Data Standard (Deft) LR | 60067372 | 01N-0427-R1 | 0 | 47 | 1
[8 empty] | Asset Management Data Standard (Deft) SH | 60067460 | 01N-0427-R4 | 0 | 219 | 1
[8 empty] | Central Pool | 60049378 | 01N-0427-I | 0 | 3452 | 5
[8 empty] | Customer Development | 60046469 | 01N-0427-D | 0 | 3389 | 5
[8 empty] | Freight | 60046455 | 01N-0427-R3 | 0 | 231 | 2
[8 empty] | Integrated Delivery Model | 60073543 | 01N-0427-R2 | 0 | 630 | 2
[8 empty] | Investment Planning | 60063605 | 01N-0428-R3 | 0 | 255 | 1
[8 empty] | National Funds | 60040862 | 016-0002-R3 | 0 | 220 | 1
[8 empty] | Procurement Team | 60035560 | 01N-0429-R1 | 0 | 232 | 1
[8 empty] | Programme & Standard- Environmental Plan | 60035513 | 01N-0429-R5 | 0 | 278 | 2
[8 empty] | Programme & Standards - Assurance | 60063507 | 01N-0428-R4 | 0 | 1075 | 2
[8 empty] | Programme & Standards - Chief Engineer | 60063582 | 01N-0430-R2 | 0 | 284 | 2
[8 empty] | Programme & Standards - Leadership Team | 60070245 | 01N-0430-R1 | 0 | 237 | 1
[8 empty] | Programme & Standards-Tactical Asset | 60049394 | 01N-0431-R1 | 0 | 205 | 2
[8 empty] | Programme$Standards-Lead Safety Advisor | 60035595 | 01N-0431-R2 | 0 | 234 | 2
[8 empty] | Programme&Standards-Engineering Standard | 60063658 | 01N-0431-I | 0 | 11155 | 4
[8 empty] | Programme&Standards-Planning & Perform | 60035416 | 01N-0432-R1 | 0 | 265 | 2
[8 empty] | Programme&Standards-Safe & Sustainable | 60063665 | 01N-0433-R1 | 0 | 180 | 1
[8 empty] | Programme&Standards-SH Mtce Fixed Costs | 60035880 | 01N-0433-R2 | 0 | 197 | 2
[8 empty] | Safety Engineers | 60063960 | 01N-0434-R1 | 0 | 175 | 2
[8 empty] | Digital Maintenance Activities | 60035647 | 01N-0434-R4 | 0 | 173 | 2
[8 empty] | Digital Renewal Activities | 60069024 | 01N-0434-W | 0 | 236 | 3
[10 empty] | 01N-0434-R2 | 0 | 210 | 2
[10 empty] | 01N-0434-R3 | 0 | 190 | 2
[10 empty] | 01N-0435-R1 | 0 | 77 | 1
[10 empty] | 01N-0435-R2 | 0 | 89 | 1
[10 empty] | 01N-0436-R1 | 0 | 220 | 2
[10 empty] | 01N-0436-R6 | 0 | 531 | 2
[10 empty] | 01N-0436-W | 0 | 340 | 2
[10 empty] | 01N-0436-R2 | 0 | 460 | 2
[10 empty] | 01N-0436-R4 | 0 | 178 | 1
[10 empty] | 01N-0436-R5 | 0 | 624 | 2
[10 empty] | 01N-0438-R4 | 0 | 341 | 1
[10 empty] | 01N-0438-R1 | 0 | 383 | 3
[10 empty] | 01N-0438-R3 | 0 | 455 | 2
[10 empty] | 01N-0438-R2 | 0 | 500 | 2
[10 empty] | 01N-0441-R1 | 0 | 249 | 1
[10 empty] | 01N-0441-R2 | 0 | 129 | 1
[10 empty] | 01N-0444-R1 | 0 | 232 | 2
[10 empty] | 01N-0444-R4 | 0 | 232 | 1
[10 empty] | 01N-0444-R3 | 0 | 209 | 1
[10 empty] | 01N-0444-R2 | 0 | 191 | 1
[10 empty] | 01N-0448-R4 | 0 | 206 | 2
[10 empty] | 01N-0448-I | 0 | 5055 | 3
[10 empty] | 01N-0448-D | 0 | 5059 | 3
[10 empty] | 01N-0451-R1 | 0 | 200 | 2
[10 empty] | 01N-0451-R2 | 0 | 220 | 1
[10 empty] | 01N-0454-R1 | 0 | 307 | 2
[10 empty] | 01N-0454-R4 | 0 | 279 | 2
[10 empty] | 01N-0454-R2 | 0 | 245 | 1
[10 empty] | 01N-0454-R3 | 0 | 437 | 2
[10 empty] | 01N-0458-R1 | 0 | 655 | 4
[10 empty] | 01N-0458-R2 | 0 | 211 | 2
[10 empty] | 01N-0458-R4 | 0 | 274 | 2
[10 empty] | 01N-0458-R3 | 0 | 301 | 2
[10 empty] | 01N-0462-R1 | 0 | 305 | 2
[10 empty] | 01N-0462-R4 | 0 | 257 | 1
[10 empty] | 01N-0461-I | 0 | 1305 | 2
[10 empty] | 01N-0461-D | 0 | 1306 | 2
[10 empty] | 01N-0462-R2 | 0 | 188 | 2
[10 empty] | 01N-0462-R3 | 0 | 260 | 2
[10 empty] | 01N-0466-R4 | 0 | 301 | 1
[10 empty] | 01N-0466-R1 | 0 | 232 | 1
[10 empty] | 01N-0461/12.98-D | 12984 | 16293 | 3
[10 empty] | 002-0018 | 0 | 13776 | 4
[10 empty] | 016-0004-R1 | 0 | 344 | 2
[10 empty] | 016-0004-R3 | 0 | 444 | 2
[10 empty] | 016-0004-R2 | 0 | 438 | 2
[10 empty] | 016-0006-R4 | 0 | 223 | 2
[10 empty] | 016-0006-R1 | 0 | 277 | 3
[10 empty] | 016-0006-R3 | 0 | 264 | 2
[10 empty] | 016-0006-R2 | 0 | 215 | 2
[10 empty] | 016-0008-R1 | 0 | 701 | 1
[10 empty] | 016-0008-R4 | 0 | 619 | 3
[10 empty] | 016-0008-R2 | 0 | 418 | 3
[10 empty] | 016-0008-R3 | 0 | 736 | 3
[10 empty] | 016-0007-I | 0 | 3517 | 6
[10 empty] | 016-0007-D | 0 | 3500 | 5
[10 empty] | 016-0011-R1 | 0 | 656 | 1
[10 empty] | 016-0012-R1 | 0 | 265 | 2
[10 empty] | 016-0012-R2 | 0 | 520 | 1
[10 empty] | 016-0011-R2 | 0 | 620 | 2
[10 empty] | 016-0014-R1 | 0 | 283 | 4
[10 empty] | 016-0014-R5 | 0 | 330 | 3
[10 empty] | 016-0014-R4 | 0 | 182 | 2
[10 empty] | 016-0014-R3 | 0 | 264 | 3
[10 empty] | 016-0014-R2 | 0 | 241 | 2
[10 empty] | 016-0016-R1 | 0 | 428 | 4
[10 empty] | 016-0016-R4 | 0 | 268 | 3
[10 empty] | 016-0016-R2 | 0 | 308 | 2
[10 empty] | 016-0016-R3 | 0 | 340 | 3
[10 empty] | 016-0018-R2 | 0 | 345 | 2
[10 empty] | 016-0018-R1 | 0 | 302 | 1
[10 empty] | 016-0037 | 0 | 9304 | 2
[10 empty] | 020-0013-R3 | 0 | 453 | 2
[10 empty] | 020-0013-R2 | 0 | 179 | 1
[10 empty] | 020-0013-R4 | 0 | 289 | 1
[10 empty] | 020-0013-R1 | 0 | 198 | 2
[10 empty] | 020-0012-R2 | 0 | 248 | 2
[10 empty] | 020-0012-R1 | 0 | 308 | 2
[10 empty] | 022-0000 | 0 | 142 | 2
[10 empty] | 022-0000/00.14-I | 142 | 608 | 2
[10 empty] | 022-0000/00.14-D | 142 | 612 | 2
[10 empty] | 022-0000/00.61 | 608 | 3705 | 2
[10 empty] | 022-0000/10.10 | 10098 | 12936 | 2
[10 empty] | 002-0283 | 0 | 11071 | 2
[10 empty] | 002-0294 | 0 | 10454 | 2
[10 empty] | 002-0304 | 0 | 13498 | 2
[10 empty] | 002-0318 | 0 | 16094 | 2
[10 empty] | 002-0334 | 0 | 11399 | 2
[10 empty] | 002-0345 | 0 | 16145 | 2
[10 empty] | 002-0375 | 0 | 15185 | 2
[10 empty] | 002-0390 | 0 | 15575 | 2
[10 empty] | 002-0406 | 0 | 9120 | 2
[10 empty] | 002-0416 | 0 | 13350 | 2
[10 empty] | 002-0429 | 0 | 14036 | 2
[10 empty] | 002-0443 | 0 | 2973 | 2
[10 empty] | 002-0461 | 0 | 13390 | 3
[10 empty] | 002-0474 | 0 | 8438 | 3
[10 empty] | 035-0000 | 0 | 10694 | 2
[10 empty] | 035-0011 | 0 | 10757 | 2
[10 empty] | 035-0021 | 0 | 6513 | 2
[10 empty] | 035-0028 | 0 | 13820 | 2
[10 empty] | 035-0041 | 0 | 7632 | 2
[10 empty] | 035-0049 | 0 | 15570 | 2
[10 empty] | 035-0065 | 0 | 13907 | 2
[10 empty] | 035-0079 | 0 | 15035 | 2
[10 empty] | 035-0094 | 0 | 12648 | 2
[10 empty] | 035-0106 | 0 | 9810 | 2
[10 empty] | 035-0116 | 0 | 8157 | 2
[10 empty] | 035-0132 | 0 | 11612 | 2
[10 empty] | 035-0144 | 0 | 14959 | 2
[10 empty] | 035-0159 | 0 | 12796 | 2
[10 empty] | 035-0172 | 0 | 8410 | 2
[10 empty] | 035-0180 | 0 | 9471 | 2
[10 empty] | 035-0190 | 0 | 10403 | 2
[10 empty] | 035-0200 | 0 | 13208 | 2
[10 empty] | 035-0213 | 0 | 11740 | 2
[10 empty] | 035-0225 | 0 | 12388 | 2
[10 empty] | 035-0238 | 0 | 12645 | 2
[10 empty] | 035-0250 | 0 | 12219 | 2
[10 empty] | 035-0263 | 0 | 11164 | 2
[10 empty] | 035-0274 | 0 | 15360 | 2
[10 empty] | 035-0289 | 0 | 10617 | 2
[10 empty] | 035-0300 | 0 | 8000 | 2
[10 empty] | 035-0308 | 0 | 11170 | 2
[10 empty] | 035-0321 | 0 | 6168 | 2
[10 empty] | 035-0327 | 0 | 8187 | 2
[10 empty] | 002-0483 | 0 | 13990 | 4
[10 empty] | 002-0497 | 0 | 18926 | 2
[10 empty] | 002-0516 | 0 | 16750 | 2
[10 empty] | 002-0533 | 0 | 10650 | 2
[10 empty] | 002-0544 | 0 | 17827 | 4
[10 empty] | 002-0562 | 0 | 14990 | 3
[10 empty] | 002-0577 | 0 | 14590 | 4
[10 empty] | 002-0592 | 0 | 15454 | 3
[10 empty] | 002-0608 | 0 | 17586 | 4
[10 empty] | 002-0626 | 0 | 11310 | 3
[10 empty] | 002-0638 | 0 | 5131 | 2
[10 empty] | 051-0013 | 0 | 5168 | 2
[10 empty] | 002-0691 | 0 | 7660 | 3
[10 empty] | 002-0707 | 0 | 7421 | 3
[10 empty] | 002-0721 | 0 | 8040 | 2
[10 empty] | 002-0729 | 0 | 13955 | 2
[10 empty] | 002-0743 | 0 | 7750 | 3
[10 empty] | 002-0758 | 0 | 13169 | 4
[10 empty] | 002-0772 | 0 | 15890 | 3
[10 empty] | 002-0788 | 0 | 14058 | 3
[10 empty] | 002-0802 | 0 | 6155 | 2
[10 empty] | 005-0169 | 0 | 18770 | 2
[10 empty] | 005-0188 | 0 | 2480 | 2
[10 empty] | 005-0204 | 0 | 14955 | 3
[10 empty] | 005-0220 | 0 | 13034 | 3
[10 empty] | 005-0233 | 0 | 15419 | 4
[10 empty] | 005-0249 | 0 | 12466 | 2
[10 empty] | 038-0131 | 0 | 15544 | 2
[10 empty] | 038-0147 | 0 | 11770 | 2
[10 empty] | 038-0161 | 0 | 18040 | 2
[10 empty] | 038-0179 | 0 | 9740 | 2
[10 empty] | 038-0189 | 0 | 6860 | 2
[10 empty] | 050-0017 | 0 | 15988 | 2
[10 empty] | 050-0033 | 0 | 16270 | 2
[10 empty] | 050-0049 | 0 | 17900 | 2
[10 empty] | 002-0808 | 0 | 8485 | 2
[10 empty] | 002-0808/08.51-I | 8485 | 9550 | 1
[10 empty] | 002-0808/08.51-D | 8485 | 9550 | 1
[10 empty] | 002-0825 | 0 | 16530 | 2
[10 empty] | 002-0842 | 0 | 16030 | 2
[10 empty] | 002-0873 | 0 | 9890 | 2
[10 empty] | 002-0883/00.34 | 338 | 5780 | 2
[10 empty] | 002-0905 | 0 | 15905 | 2
[10 empty] | 002-0921 | 0 | 10450 | 3
[10 empty] | 053-0000 | 0 | 17690 | 2
[10 empty] | 01S-0000 | 0 | 920 | 2
[10 empty] | 01S-0018 | 0 | 9993 | 3
[10 empty] | 01S-0028 | 0 | 15752 | 3
[10 empty] | 01S-0043 | 0 | 13605 | 3
[10 empty] | 01S-0057 | 0 | 15241 | 2
[10 empty] | 01S-0073 | 0 | 17073 | 2
[10 empty] | 006-0000 | 0 | 10103 | 4
[10 empty] | 006-0010 | 0 | 5285 | 2
[10 empty] | 006-0016 | 0 | 18916 | 2
[10 empty] | 006-0034 | 0 | 15842 | 2
[10 empty] | 006-0050 | 0 | 15005 | 2
[10 empty] | 006-0065 | 0 | 8221 | 3
[10 empty] | 063-0000 | 0 | 16719 | 2
[10 empty] | 063-0017 | 0 | 12128 | 2
[10 empty] | 063-0029 | 0 | 17231 | 2
[10 empty] | 063-0046 | 0 | 12902 | 2
[10 empty] | 063-0059 | 0 | 15213 | 2
[10 empty] | 063-0074 | 0 | 9575 | 2
[10 empty] | 006-0080 | 0 | 18310 | 3
[10 empty] | 006-0099 | 0 | 16012 | 3
[10 empty] | 006-0116-I | 0 | 803 | 1
[10 empty] | 006-0131 | 0 | 18170 | 2
[10 empty] | 006-0150 | 0 | 18503 | 3
[10 empty] | 006-0170 | 0 | 14330 | 2
[10 empty] | 006-0184 | 0 | 10983 | 3
[10 empty] | 006-0239 | 0 | 15338 | 2
[10 empty] | 006-0255 | 0 | 12696 | 2
[10 empty] | 060-0000 | 0 | 14510 | 3
[10 empty] | 060-0015 | 0 | 16280 | 3
[10 empty] | 060-0033 | 0 | 8692 | 2
[10 empty] | 060-0042 | 0 | 13129 | 3
[10 empty] | 060-0056 | 0 | 13876 | 3
[10 empty] | 060-0070 | 0 | 18671 | 2
[10 empty] | 060-0089 | 0 | 13750 | 2
[10 empty] | 060-0103 | 0 | 15800 | 2
[10 empty] | 063-0092 | 0 | 17519 | 2
[10 empty] | 063-0109 | 0 | 8093 | 2
[10 empty] | 065-0000 | 0 | 16310 | 2
[10 empty] | 065-0017 | 0 | 19697 | 3
[10 empty] | 065-0036 | 0 | 10215 | 2
[10 empty] | 006-0269 | 0 | 12910 | 2
[10 empty] | 006-0282 | 0 | 14778 | 2
[10 empty] | 006-0296 | 0 | 17116 | 2
[10 empty] | 006-0313 | 0 | 22185 | 2
[10 empty] | 006-0336 | 0 | 15041 | 2
[10 empty] | 006-0351 | 0 | 12026 | 2
[10 empty] | 006-0363 | 0 | 10937 | 2
[10 empty] | 006-0374 | 0 | 13304 | 2
[10 empty] | 006-0388 | 0 | 15451 | 2
[10 empty] | 006-0403 | 0 | 12933 | 2
[10 empty] | 006-0416 | 0 | 13645 | 2
[10 empty] | 006-0430/00.60-I | 602 | 1521 | 2
[10 empty] | 006-0430/00.60-D | 602 | 1521 | 2
[10 empty] | 006-0430/01.52 | 1521 | 14566 | 2
[10 empty] | 006-0489 | 0 | 11939 | 2
[10 empty] | 006-0501 | 0 | 18152 | 2
[10 empty] | 006-0519 | 0 | 21825 | 2
[10 empty] | 006-0541 | 0 | 10562 | 2
[10 empty] | 006-0551 | 0 | 18382 | 2
[10 empty] | 006-0570 | 0 | 13472 | 2
[10 empty] | 006-0584 | 0 | 12276 | 2
[10 empty] | 006-0596 | 0 | 13316 | 2
[10 empty] | 006-0610 | 0 | 16217 | 2
[10 empty] | 006-0626 | 0 | 12681 | 2
[10 empty] | 006-0639 | 0 | 19808 | 2
[10 empty] | 006-0659 | 0 | 11634 | 2
[10 empty] | 006-0670 | 0 | 13034 | 2
[10 empty] | 006-0683 | 0 | 11993 | 2
[10 empty] | 006-0695 | 0 | 13689 | 2
[10 empty] | 006-0709 | 0 | 14093 | 2
[10 empty] | 006-0723 | 0 | 16983 | 2
[10 empty] | 006-0740 | 0 | 9754 | 2
[10 empty] | 006-0750 | 0 | 16749 | 2
[10 empty] | 006-0767 | 0 | 15855 | 2
[10 empty] | 006-0783 | 0 | 16432 | 2
[10 empty] | 006-0800 | 0 | 14356 | 2
[10 empty] | 007-0131 | 0 | 21280 | 2
[10 empty] | 007-0152 | 0 | 16393 | 2
[10 empty] | 007-0169 | 0 | 16167 | 2
[10 empty] | 007-0185 | 0 | 11761 | 2
[10 empty] | 007-0196 | 0 | 15537 | 2
[10 empty] | 007-0212 | 0 | 12701 | 2
[10 empty] | 065-0047 | 0 | 6724 | 2
[10 empty] | 065-0054 | 0 | 18412 | 2
[10 empty] | 067-0046 | 0 | 5416 | 2
[10 empty] | 069-0000 | 0 | 17348 | 2
[10 empty] | 069-0017 | 0 | 15927 | 2
[10 empty] | 073-0151 | 0 | 6669 | 2
[10 empty] | 073-0159 | 0 | 14862 | 2
[10 empty] | 073-0174 | 0 | 17429 | 2
[10 empty] | 073-0191 | 0 | 15167 | 2
[10 empty] | 073-0206 | 0 | 19238 | 2
[10 empty] | 01S-0090 | 0 | 14076 | 2
[10 empty] | 01S-0104 | 0 | 13993 | 3
[10 empty] | 01S-0118 | 0 | 20041 | 3
[10 empty] | 01S-0138 | 0 | 16333 | 2
[10 empty] | 01S-0155 | 0 | 7937 | 2
[10 empty] | 01S-0163 | 0 | 16516 | 4
[10 empty] | 01S-0179 | 0 | 5286 | 2
[10 empty] | 01S-0195 | 0 | 19444 | 3
[10 empty] | 01S-0217 | 0 | 18617 | 2
[10 empty] | 01S-0235 | 0 | 11700 | 2
[10 empty] | 01S-0247 | 0 | 15279 | 3
[10 empty] | 01S-0262 | 0 | 11092 | 3
[10 empty] | 01S-0273 | 0 | 10786 | 2
[10 empty] | 01S-0284 | 0 | 19244 | 4
[10 empty] | 007-0000 | 0 | 15565 | 2
[10 empty] | 007-0016 | 0 | 11855 | 2
[10 empty] | 007-0028 | 0 | 16197 | 2
[10 empty] | 007-0044 | 0 | 14447 | 2
[10 empty] | 007-0058 | 0 | 9444 | 2
[10 empty] | 007-0078 | 0 | 19715 | 3
[10 empty] | 007-0098 | 0 | 16836 | 2
[10 empty] | 007-0115 | 0 | 16020 | 2
[10 empty] | 01S-0311 | 0 | 6355 | 2
[10 empty] | 01S-0317 | 0 | 2680 | 3
[10 empty] | 01S-0317/02.68 | 2680 | 5264 | 3
[10 empty] | 01S-0317/05.26-I | 5264 | 9921 | 2
[10 empty] | 74M-0000-I | 0 | 1750 | 2
[10 empty] | 01S-0317/05.26-D | 5264 | 9921 | 2
[10 empty] | 74M-0000-D | 0 | 1750 | 2
[10 empty] | 01S-0323-R1 | 0 | 272 | 1
[10 empty] | 01S-0324-R1 | 0 | 225 | 1
[10 empty] | 01S-0324-R4 | 0 | 93 | 1
[10 empty] | 01S-0326-R1 | 0 | 220 | 1
[10 empty] | 01S-0328-R1 | 0 | 452 | 1
[10 empty] | 01S-0326-R2 | 0 | 291 | 2
[10 empty] | 01S-0324-R3 | 0 | 334 | 1
[10 empty] | 01S-0324-R2 | 0 | 388 | 1
[10 empty] | 01S-0323-R2 | 0 | 245 | 1
[10 empty] | 076-0003/02.19-I | 2190 | 7782 | 2
[10 empty] | 076-0003/02.19-D | 2193 | 7798 | 2
[10 empty] | 01S-0347/00.45 | 446 | 3272 | 2
[10 empty] | 01S-0365/02.33 | 2330 | 15825 | 4
[10 empty] | 01S-0381 | 0 | 20570 | 4
[10 empty] | 073-0034 | 0 | 7040 | 2
[10 empty] | 073-0052 | 0 | 16249 | 2
[10 empty] | 073-0068 | 0 | 7521 | 2
[10 empty] | 073-0076 | 0 | 14570 | 2
[10 empty] | 073-0090 | 0 | 16227 | 2
[10 empty] | 073-0107 | 0 | 13623 | 2
[10 empty] | 073-0121 | 0 | 15372 | 2
[10 empty] | 073-0136 | 0 | 9208 | 2
[10 empty] | 074-0026 | 0 | 720 | 2
[10 empty] | 075-0000/00.36 | 360 | 8320 | 2
[10 empty] | 075-0014 | 0 | 9514 | 2
[10 empty] | 075-0035 | 0 | 17319 | 2
[10 empty] | 075-0052 | 0 | 8842 | 2
[10 empty] | 075-0061 | 0 | 17587 | 2
[10 empty] | 01S-0401 | 0 | 14674 | 4
[10 empty] | 01S-0416 | 0 | 14488 | 4
[10 empty] | 01S-0430 | 0 | 16505 | 4
[10 empty] | 01S-0447 | 0 | 15228 | 4
[10 empty] | 01S-0465 | 0 | 15930 | 4
[10 empty] | 01S-0481 | 0 | 19500 | 4
[10 empty] | 01S-0501 | 0 | 4526 | 4
[10 empty] | 01S-0516 | 0 | 3600 | 3
[10 empty] | 01S-0532 | 0 | 11890 | 2
[10 empty] | 01S-0544 | 0 | 16023 | 2
[10 empty] | 01S-0560 | 0 | 9960 | 2
[10 empty] | 008-0000 | 0 | 18332 | 2
[10 empty] | 008-0018 | 0 | 11515 | 2
[10 empty] | 008-0034 | 0 | 9540 | 2
[10 empty] | 008-0057 | 0 | 16225 | 2
[10 empty] | 008-0073 | 0 | 12023 | 2
[10 empty] | 008-0085 | 0 | 14274 | 2
[10 empty] | 008-0099 | 0 | 18560 | 2
[10 empty] | 008-0118 | 0 | 13682 | 2
[10 empty] | 008-0131 | 0 | 16690 | 2
[10 empty] | 008-0146 | 0 | 11780 | 2
[10 empty] | 077-0000 | 0 | 16945 | 2
[10 empty] | 077-0017 | 0 | 16840 | 2
[10 empty] | 079-0009 | 0 | 6426 | 2
[10 empty] | 079-0015 | 0 | 15428 | 2
[10 empty] | 079-0031 | 0 | 11240 | 2
[10 empty] | 079-0046 | 0 | 14975 | 2
[10 empty] | 080-0000 | 0 | 15840 | 2
[10 empty] | 080-0017 | 0 | 15945 | 2
[10 empty] | 080-0035 | 0 | 15570 | 2
[10 empty] | 080-0051 | 0 | 7207 | 2
[10 empty] | 082-0000 | 0 | 16825 | 2
[10 empty] | 082-0017 | 0 | 15230 | 2
[10 empty] | 082-0032 | 0 | 10255 | 2
[10 empty] | 082-0042 | 0 | 11160 | 2
[10 empty] | 01S-0569 | 0 | 13640 | 2
[10 empty] | 01S-0583 | 0 | 7120 | 4
[10 empty] | 01S-0583/07.12-I | 7120 | 8360 | 2
[10 empty] | 01S-0583/07.12-D | 7120 | 8360 | 2
[10 empty] | 01S-0583/08.36 | 8360 | 17450 | 3
[10 empty] | 01S-0601 | 0 | 16806 | 3
[10 empty] | 01S-0618 | 0 | 16348 | 3
[10 empty] | 01S-0635 | 0 | 16140 | 3
[10 empty] | 01S-0651 | 0 | 8940 | 3
[10 empty] | 01S-0666 | 0 | 1060 | 2
[10 empty] | 01S-0667 | 0 | 15540 | 4
[10 empty] | 01S-0683 | 0 | 16450 | 4
[10 empty] | 01S-0700 | 0 | 3300 | 4
[10 empty] | 01S-0704-I | 0 | 2310 | 2
[10 empty] | 01S-0706-I | 0 | 1677 | 4
[10 empty] | 01S-0706-D | 0 | 1676 | 4
[10 empty] | 01S-0707-I | 0 | 2090 | 2
[10 empty] | 01S-0712-I | 0 | 2616 | 2
[10 empty] | 01S-0720 | 0 | 8080 | 4
[10 empty] | 01S-0729 | 0 | 13400 | 3
[10 empty] | 01S-0746 | 0 | 16337 | 3
[10 empty] | 01S-0763 | 0 | 2648 | 2
[10 empty] | 01S-0765 | 0 | 8567 | 3
[10 empty] | 01S-0774 | 0 | 11970 | 3
[10 empty] | 01S-0786 | 0 | 480 | 2
[10 empty] | 01S-0787 | 0 | 4360 | 3
[10 empty] | 01S-0791 | 0 | 16319 | 3
[10 empty] | 01S-0807 | 0 | 10040 | 2
[10 empty] | 01S-0824 | 0 | 8820 | 2
[10 empty] | 01S-0833 | 0 | 7069 | 2
[10 empty] | 01S-0842 | 0 | 11476 | 2
[10 empty] | 01S-0854 | 0 | 4678 | 4
[10 empty] | 01S-0858/02.04 | 2040 | 12330 | 4
[10 empty] | 01S-0858-D | 0 | 2040 | 2
[10 empty] | 01S-0858-I | 0 | 2040 | 2
[10 empty] | 01S-0872 | 0 | 6037 | 2
[10 empty] | EDENDALE FROM FERRY RD WEST TO END CONSTRUCTION | 0 | 1185 | 2
[10 empty] | 01S-0900 | 0 | 14159 | 2
[10 empty] | 01S-0920-I | 0 | 1120 | 2
[10 empty] | 01S-0920/02.60-I | 2600 | 3670 | 2
[10 empty] | 01S-0920/02.60-D | 2600 | 3670 | 2
[10 empty] | 01S-0923/01.71 | 1710 | 2465 | 2
[10 empty] | 01S-0923-I | 0 | 1710 | 2
[10 empty] | 01S-0926 | 0 | 7427 | 2
[10 empty] | 01S-0933 | 0 | 19740 | 2
[10 empty] | 006-0814 | 0 | 13780 | 2
[10 empty] | 006-0828 | 0 | 19330 | 2
[10 empty] | 006-0847 | 0 | 18270 | 2
[10 empty] | 006-0866 | 0 | 14830 | 2
[10 empty] | 006-0881 | 0 | 11990 | 2
[10 empty] | 006-0893 | 0 | 8420 | 2
[10 empty] | 006-0901 | 0 | 6200 | 2
[10 empty] | 006-0918 | 0 | 20120 | 2
[10 empty] | 006-0938 | 0 | 3860 | 2
[10 empty] | 006-0942 | 0 | 14360 | 2
[10 empty] | 006-0956 | 0 | 21800 | 2
[10 empty] | 006-0978 | 0 | 4940 | 2
[10 empty] | 006-0983 | 0 | 8045 | 2
[10 empty] | 006-0996 | 0 | 15358 | 2
[10 empty] | 006-1011 | 0 | 13290 | 2
[10 empty] | 006-1024 | 0 | 12917 | 2
[10 empty] | 006-1046 | 0 | 15400 | 2
[10 empty] | 006-1061 | 0 | 17462 | 2
[10 empty] | 006-1079 | 0 | 14482 | 2
[10 empty] | 006-1093-C094 | 0 | 2500 | 2
[10 empty] | 006-1095 | 0 | 15590 | 2
[10 empty] | 006-1111 | 0 | 15936 | 2
[10 empty] | 006-1127 | 0 | 15760 | 2
[10 empty] | 006-1143-C096 | 0 | 1703 | 2
[10 empty] | 006-1145/00.64 | 645 | 12970 | 2
[10 empty] | 006-1157 | 0 | 7937 | 2
[10 empty] | 006-1168 | 0 | 2750 | 4
[10 empty] | 06A-0000 | 0 | 6889 | 2
[10 empty] | 008-0159 | 0 | 10010 | 2
[10 empty] | 008-0169 | 0 | 16600 | 2
[10 empty] | 008-0185 | 0 | 17330 | 2
[10 empty] | 008-0202 | 0 | 15176 | 2
[10 empty] | 008-0217 | 0 | 15090 | 2
[10 empty] | 008-0233 | 0 | 14050 | 2
[10 empty] | 008-0247 | 0 | 18690 | 2
[10 empty] | 008-0266 | 0 | 5570 | 2
[10 empty] | 008-0271 | 0 | 21250 | 2
[10 empty] | 008-0297 | 0 | 13250 | 2
[10 empty] | 008-0310 | 0 | 18056 | 3
[10 empty] | 008-0328 | 0 | 14800 | 3
[10 empty] | 008-0343 | 0 | 7030 | 3
[10 empty] | 008-0350 | 0 | 14770 | 3
[10 empty] | 008-0365 | 0 | 4850 | 2
[10 empty] | 008-0370 | 0 | 11330 | 2
[10 empty] | 008-0381 | 0 | 19500 | 2
[10 empty] | 008-0401 | 0 | 16500 | 2
[10 empty] | 008-0417 | 0 | 13180 | 2
[10 empty] | 008-0430 | 0 | 13970 | 2
[10 empty] | 008-0444 | 0 | 15200 | 3
[10 empty] | 08A-0000 | 0 | 11300 | 2
[10 empty] | 08A-0015 | 0 | 5890 | 2
[10 empty] | 08B-0000 | 0 | 2610 | 2
[10 empty] | 083-0000 | 0 | 15760 | 2
[10 empty] | 083-0016 | 0 | 6000 | 2
[10 empty] | 083-0034 | 0 | 14680 | 2
[10 empty] | 083-0049 | 0 | 8830 | 2
[10 empty] | 083-0058 | 0 | 11780 | 2
[10 empty] | 083-0070 | 0 | 15280 | 2
[10 empty] | 083-0085 | 0 | 10780 | 2
[10 empty] | 083-0096 | 0 | 13970 | 2
[10 empty] | 085-0000 | 0 | 16290 | 2
[10 empty] | 085-0016 | 0 | 14820 | 2
[10 empty] | 085-0031 | 0 | 17810 | 2
[10 empty] | 085-0049 | 0 | 1000 | 2
[10 empty] | 085-0062 | 0 | 17580 | 2
[10 empty] | 085-0079 | 0 | 12660 | 2
[10 empty] | 085-0092 | 0 | 12900 | 2
[10 empty] | 085-0105 | 0 | 15310 | 2
[10 empty] | 085-0120 | 0 | 14000 | 2
[10 empty] | 085-0134 | 0 | 14110 | 2
[10 empty] | 085-0148 | 0 | 16410 | 2
[10 empty] | 087-0000 | 0 | 14760 | 2
[10 empty] | 087-0015 | 0 | 17300 | 2
[10 empty] | 087-0033 | 0 | 15290 | 2
[10 empty] | 087-0048 | 0 | 17090 | 2
[10 empty] | 087-0065 | 0 | 15980 | 2
[10 empty] | 087-0082 | 0 | 13700 | 2
[10 empty] | 087-0096 | 0 | 9970 | 2
[10 empty] | 087-0110 | 0 | 5910 | 2
[10 empty] | 088-0000 | 0 | 8220 | 2
[10 empty] | 088-0008 | 0 | 4480 | 2
[10 empty] | 084-0000 | 0 | 1222 | 2
[10 empty] | 090-0000 | 0 | 17150 | 2
[10 empty] | 090-0017 | 0 | 17553 | 2
[10 empty] | 090-0035 | 0 | 11665 | 2
[10 empty] | 090-0051 | 0 | 8620 | 2
[10 empty] | 094-0000 | 0 | 15562 | 4
[10 empty] | 094-0016 | 0 | 2416 | 2
[10 empty] | 094-0030 | 0 | 13514 | 2
[10 empty] | 094-0043 | 0 | 17702 | 2
[10 empty] | 094-0061-C006 | 0 | 2770 | 1
[10 empty] | 094-0063 | 0 | 16795 | 2
[10 empty] | 094-0080 | 0 | 18786 | 2
[10 empty] | 094-0099 | 0 | 15310 | 2
[10 empty] | 094-0115 | 0 | 15591 | 2
[10 empty] | 094-0130 | 0 | 7475 | 2
[10 empty] | 094-0150 | 0 | 12754 | 2
[10 empty] | 094-0163 | 0 | 13399 | 2
[10 empty] | 094-0177 | 0 | 15239 | 2
[10 empty] | 094-0192 | 0 | 5286 | 2
[10 empty] | 094-0197 | 0 | 14303 | 2
[10 empty] | 094-0212 | 0 | 16899 | 2
[10 empty] | 094-0229 | 0 | 10866 | 2
[10 empty] | 094-0240 | 0 | 1275 | 2
[10 empty] | 094-0241 | 0 | 17320 | 2
[10 empty] | 096-0000 | 0 | 4891 | 2
[10 empty] | 096-0015 | 0 | 14391 | 2
[10 empty] | 096-0030 | 0 | 18659 | 2
[10 empty] | 096-0048-C006 | 0 | 1703 | 1
[10 empty] | 096-0050 | 0 | 15508 | 2
[10 empty] | 096-0066 | 0 | 18636 | 2
[10 empty] | 096-0084 | 0 | 7180 | 2
[10 empty] | 099-0000 | 0 | 523 | 2
[10 empty] | 099-0015 | 0 | 15477 | 2
[10 empty] | 099-0031 | 0 | 15363 | 2
[10 empty] | 099-0046 | 0 | 14109 | 2
[10 empty] | 099-0060 | 0 | 18156 | 2
[10 empty] | 01N-0794 | 0 | 20616 | 3
[10 empty] | 01N-0815 | 0 | 12984 | 3
[10 empty] | 01N-0828 | 0 | 14512 | 3
[10 empty] | 01N-0842 | 0 | 12494 | 3
[10 empty] | 01N-0855 | 0 | 9693 | 4
[10 empty] | 01N-0865 | 0 | 19914 | 3
[10 empty] | 01N-0885 | 0 | 15770 | 3
[10 empty] | 01N-0901 | 0 | 14085 | 3
[10 empty] | 01N-0914 | 0 | 10303 | 3
[10 empty] | 01N-0925-C003 | 0 | 1768 | 2
[10 empty] | 01N-0927-C003 | 0 | 4674 | 3
[10 empty] | 01N-0932 | 0 | 7543 | 3
[10 empty] | 01N-0939 | 0 | 15197 | 3
[10 empty] | 003-0140 | 0 | 17195 | 2
[10 empty] | 003-0171 | 0 | 5826 | 2
[10 empty] | 003-0176 | 0 | 12416 | 3
[10 empty] | 003-0189 | 0 | 13382 | 2
[10 empty] | 003-0203 | 0 | 15055 | 3
[10 empty] | 003-0218 | 0 | 9579 | 3
[10 empty] | 003-0229 | 0 | 4337 | 2
[10 empty] | 003-0229/04.34-I | 4337 | 8681 | 2
[10 empty] | 003-0229/04.34-D | 4337 | 8685 | 2
[10 empty] | 003-0229/08.68 | 8681 | 9321 | 4
[10 empty] | 003-0229/09.32-I | 9321 | 9946 | 2
[10 empty] | 003-0229/09.32-D | 9321 | 9943 | 2
[10 empty] | 003-0229/09.95 | 9946 | 10156 | 3
[10 empty] | 003-0229/10.16-I | 10156 | 10586 | 2
[10 empty] | 003-0229/10.16-D | 10156 | 10270 | 2
[10 empty] | 003-0229/10.26-D | 10270 | 10619 | 2
[10 empty] | 003-0240 | 0 | 17760 | 3
[10 empty] | 003-0258 | 0 | 10928 | 3
[10 empty] | 003-0279 | 0 | 7800 | 3
[10 empty] | 003-0310 | 0 | 11457 | 3
[10 empty] | 003-0321 | 0 | 16742 | 3
[10 empty] | 003-0338 | 0 | 14405 | 3
[10 empty] | 003-0352 | 0 | 18486 | 3
[10 empty] | 003-0384 | 0 | 18095 | 4
[10 empty] | 003-0402 | 0 | 12911 | 3
[10 empty] | 003-0403-R2 | 0 | 268 | 1
[10 empty] | 003-0432 | 0 | 11241 | 3
[10 empty] | 003-0444-C01N | 0 | 1768 | 1
[10 empty] | 003-0445-C01N | 0 | 4674 | 1
[10 empty] | 003-0450 | 0 | 18053 | 3
[10 empty] | 003-0458-R1 | 0 | 144 | 1
[10 empty] | 003-0468 | 0 | 2526 | 2
[10 empty] | 003-0471 | 0 | 3078 | 4
[10 empty] | 003-0474-I | 0 | 2975 | 2
[10 empty] | 003-0474-D | 0 | 2969 | 2
[10 empty] | 003-0474/02.96 | 2975 | 14831 | 3
[10 empty] | 003-0491 | 0 | 9098 | 2
[10 empty] | 004-0127 | 0 | 12952 | 2
[10 empty] | 004-0140 | 0 | 8131 | 2
[10 empty] | 004-0148 | 0 | 10295 | 2
[10 empty] | 004-0158 | 0 | 16582 | 2
[10 empty] | 004-0188 | 0 | 18231 | 3
[10 empty] | 004-0206 | 0 | 16192 | 2
[10 empty] | 004-0223 | 0 | 15482 | 2
[10 empty] | 004-0238-R1 | 0 | 316 | 2
[10 empty] | 03A-0000 | 0 | 15596 | 2
[10 empty] | 043-0000 | 0 | 14946 | 2
[10 empty] | 043-0015 | 0 | 17169 | 2
[10 empty] | 043-0032 | 0 | 17928 | 2
[10 empty] | 043-0051 | 0 | 5853 | 2
[10 empty] | 043-0065 | 0 | 15410 | 2
[10 empty] | 043-0080 | 0 | 16049 | 2
[10 empty] | 045-0000-I | 0 | 1828 | 2
[10 empty] | 045-0000-D | 0 | 1828 | 2
[10 empty] | 045-0000/01.83 | 1828 | 15339 | 3
[10 empty] | 045-0015 | 0 | 13310 | 3
[10 empty] | 045-0048 | 0 | 15903 | 2
[10 empty] | 045-0064 | 0 | 17059 | 2
[10 empty] | 045-0081 | 0 | 15925 | 2
[10 empty] | 045-0097 | 0 | 8094 | 3
[10 empty] | 049-0011 | 0 | 17960 | 2
[10 empty] | 049-0029 | 0 | 9046 | 2
[10 empty] | 049-0000 | 0 | 9171 | 2
[10 empty] | 054-0038 | 0 | 2703 | 2
[10 empty] | 054-0038/02.70-I | 2703 | 4288 | 2
[10 empty] | 054-0038/02.70-D | 2703 | 4288 | 2
[10 empty] | 054-0038/04.29 | 4288 | 17836 | 4
[10 empty] | 056-0000 | 0 | 10291 | 2
[10 empty] | 056-0022 | 0 | 1610 | 2
[10 empty] | 01N-0967/00.21 | 210 | 17413 | 3
[10 empty] | 01N-0985 | 0 | 11140 | 3
[10 empty] | 01N-0995 | 0 | 12791 | 3
[10 empty] | 01K-1012 | 0 | 8092 | 4
[10 empty] | 01K-1023 | 0 | 3601 | 4
[10 empty] | 059-0020-I | 0 | 6538 | 3
[10 empty] | 059-0020-D | 0 | 6538 | 3
[10 empty] | 01N-1060-R4 | 0 | 325 | 1
[10 empty] | 01N-1060-R2 | 0 | 429 | 2
[10 empty] | 01N-1060-R1 | 0 | 230 | 1
[10 empty] | 01N-1060-R3 | 0 | 775 | 3
[10 empty] | 01N-1064-R1 | 0 | 415 | 1
[10 empty] | 01N-1064-R2 | 0 | 375 | 1
[10 empty] | 01N-1066-R6 | 0 | 210 | 1
[10 empty] | 01N-1067-R3 | 0 | 554 | 2
[10 empty] | 01N-1060-I | 0 | 8310 | 3
[10 empty] | 01N-1060-D | 0 | 8265 | 4
[10 empty] | 01N-1068-I | 0 | 5718 | 4
[10 empty] | 01N-1068-D | 0 | 5735 | 4
[10 empty] | 01N-1070-R1 | 0 | 299 | 1
[10 empty] | 01N-1070-R2 | 0 | 385 | 1
[10 empty] | 002-0931 | 0 | 13599 | 4
[10 empty] | 002-0946 | 0 | 7686 | 4
[10 empty] | 002-0962-I | 0 | 12850 | 3
[10 empty] | 002-0962-D | 0 | 12860 | 2
[10 empty] | 002-0978-R2 | 0 | 863 | 2
[10 empty] | 002-0978-R1 | 0 | 385 | 3
[10 empty] | 002-0979-I | 0 | 0 | 2
[10 empty] | 002-0979-D | 0 | 0 | 2
[10 empty] | 01N-1068/05.72 | 5718 | 6180 | 3
[10 empty] | 01N-1071-R1 | 0 | 276 | 1
[10 empty] | 01N-1071-R2 | 0 | 450 | 1
[10 empty] | 01N-1072-R1 | 0 | 269 | 2
[10 empty] | 01N-1072-R4 | 0 | 296 | 1
[10 empty] | 01N-1072-R2 | 0 | 202 | 1
[10 empty] | 01N-1073-R1 | 0 | 664 | 3
[10 empty] | 01N-1072-R3 | 0 | 382 | 2
[10 empty] | 01N-1073-R2 | 0 | 185 | 1
[10 empty] | 01N-1075 | 0 | 130 | 3
[10 empty] | 057-0000 | 0 | 20590 | 3
[10 empty] | 003-0016 | 0 | 20147 | 4
[10 empty] | 003-0036 | 0 | 20056 | 4
[10 empty] | 003-0057 | 0 | 5730 | 2
[10 empty] | 003-0063 | 0 | 1918 | 3
[10 empty] | 030-0000 | 0 | 14611 | 2
[10 empty] | 003-0088 | 0 | 15657 | 3
[10 empty] | 003-0103 | 0 | 14376 | 3
[10 empty] | 003-0118 | 0 | 14163 | 3
[10 empty] | 003-0132 | 0 | 7945 | 2
[10 empty] | 033-0000 | 0 | 17374 | 2
[10 empty] | 033-0017 | 0 | 18455 | 3
[10 empty] | 002-0808/09.58 | 9550 | 16340 | 2
[10 empty] | 006-0430 | 0 | 602 | 2
[10 empty] | 006-0463 | 0 | 7879 | 2
[10 empty] | 067-0000 | 0 | 4560 | 2
[10 empty] | 067-0014 | 0 | 15269 | 2
[10 empty] | 067-0030 | 0 | 16328 | 2
[10 empty] | 007-0224 | 0 | 15068 | 2
[10 empty] | 007-0239 | 0 | 15225 | 2
[10 empty] | 007-0255 | 0 | 17916 | 2
[10 empty] | 074-0022 | 0 | 1529 | 3
[10 empty] | 074-0022/01.53 | 1529 | 3754 | 3
[10 empty] | 074-0024-R1 | 0 | 68 | 1
[10 empty] | 074-0024-R2 | 0 | 169 | 1
[10 empty] | 077-0033 | 0 | 9760 | 2
[10 empty] | 082-0053 | 0 | 17600 | 2
[10 empty] | 002-0032 | 0 | 2153 | 2
[10 empty] | 002-0034 | 0 | 3281 | 3
[10 empty] | 002-0037 | 0 | 10714 | 2
[10 empty] | 002-0048 | 0 | 12867 | 2
[10 empty] | 002-0061 | 0 | 11081 | 2
[10 empty] | 002-0072-C026 | 0 | 171 | 2
[10 empty] | 002-0073 | 0 | 20469 | 4
[10 empty] | 002-0093 | 0 | 7176 | 2
[10 empty] | 002-0100 | 0 | 14785 | 3
[10 empty] | 002-0116 | 0 | 14110 | 3
[10 empty] | 002-0130 | 0 | 610 | 2
[10 empty] | 002-0152-R3 | 0 | 193 | 1
[10 empty] | 29A-0000/06.91-D | 6906 | 7151 | 1
[10 empty] | 29A-0005-R1 | 0 | 203 | 1
[10 empty] | 29A-0005-R2 | 0 | 120 | 1
[10 empty] | 002-0185-I | 0 | 221 | 2
[10 empty] | 002-0209 | 0 | 14327 | 2
[10 empty] | 002-0258 | 0 | 12620 | 2
[10 empty] | 004-0000 | 0 | 15463 | 3
[10 empty] | 004-0015 | 0 | 19768 | 3
[10 empty] | 004-0045 | 0 | 15987 | 2
[10 empty] | 004-0061 | 0 | 8855 | 2
[10 empty] | 004-0070 | 0 | 7173 | 2
[10 empty] | 004-0077 | 0 | 16153 | 3
[10 empty] | 004-0094 | 0 | 19818 | 3
[10 empty] | 004-0114 | 0 | 13089 | 2
[10 empty] | 005-0000 | 0 | 5180 | 2
[10 empty] | 005-0005-C028 | 0 | 2481 | 2
[10 empty] | 005-0029 | 0 | 15988 | 3
[10 empty] | 005-0056 | 0 | 10491 | 3
[10 empty] | 005-0067 | 0 | 9832 | 4
[10 empty] | 005-0077 | 0 | 21924 | 3
[10 empty] | 005-0111 | 0 | 13709 | 3
[10 empty] | 005-0124-C01N | 0 | 7967 | 2
[10 empty] | 005-0150 | 0 | 20004 | 2
[10 empty] | 023-0000 | 0 | 1192 | 4
[10 empty] | 023-0003 | 0 | 6906 | 2
[10 empty] | 023-0015 | 0 | 16981 | 3
[10 empty] | 023-0032 | 0 | 10620 | 2
[10 empty] | 30A-0004 | 0 | 0 | 4
[10 empty] | 01N-0480-R1 | 0 | 554 | 1
[10 empty] | 01N-0480-R2 | 0 | 298 | 1
[10 empty] | 25A-0000 | 0 | 8095 | 2
[10 empty] | 25A-0008 | 0 | 13090 | 2
[10 empty] | 25A-0021 | 0 | 7040 | 2
[10 empty] | 026-0000-I | 0 | 1042 | 1
[10 empty] | 026-0000-D | 0 | 1042 | 1
[10 empty] | 026-0001 | 0 | 2174 | 3
[10 empty] | 026-0017 | 0 | 8951 | 2
[10 empty] | 026-0026 | 0 | 1135 | 2
[10 empty] | 026-0035 | 0 | 13349 | 3
[10 empty] | 026-0048 | 0 | 12341 | 2
[10 empty] | 026-0069-C002 | 0 | 171 | 2
[10 empty] | 026-0070 | 0 | 10268 | 2
[10 empty] | 026-0095 | 0 | 357 | 2
[10 empty] | 027-0000 | 0 | 15738 | 2
[10 empty] | 027-0016 | 0 | 5492 | 2
[10 empty] | 027-0021 | 0 | 5433 | 2
[10 empty] | 027-0027 | 0 | 18282 | 3
[10 empty] | 027-0046 | 0 | 20390 | 2
[10 empty] | 027-0067 | 0 | 7284 | 2
[10 empty] | 027-0083 | 0 | 1925 | 2
[10 empty] | 29A-0008/00.28 | 282 | 2060 | 4
[10 empty] | 029-0042 | 0 | 5713 | 3
[10 empty] | 029-0050 | 0 | 10317 | 2
[10 empty] | 029-0061 | 0 | 13240 | 2
[10 empty] | 030-0014 | 0 | 15679 | 2
[10 empty] | 030-0030 | 0 | 16366 | 2
[10 empty] | 030-0047 | 0 | 14061 | 2
[10 empty] | 030-0061 | 0 | 15605 | 2
[10 empty] | 030-0076 | 0 | 7589 | 2
[10 empty] | 030-0110 | 0 | 4451 | 2
[10 empty] | 030-0115 | 0 | 5041 | 2
[10 empty] | 030-0131 | 0 | 5841 | 2
[10 empty] | 030-0143-C005 | 0 | 1031 | 2
[10 empty] | 030-0147-I | 0 | 1108 | 2
[10 empty] | 030-0147-D | 0 | 1123 | 2
[10 empty] | 030-0158 | 0 | 11361 | 3
[10 empty] | 030-0170 | 0 | 17744 | 2
[10 empty] | 030-0187 | 0 | 199 | 2
[10 empty] | 034-0015 | 0 | 6259 | 2
[10 empty] | 041-0000 | 0 | 11282 | 2
[10 empty] | 041-0011 | 0 | 11440 | 2
[10 empty] | 041-0023 | 0 | 13821 | 2
[10 empty] | 041-0037 | 0 | 19271 | 2
[10 empty] | 041-0056 | 0 | 2733 | 2
[10 empty] | 043-0111 | 0 | 19054 | 2
[10 empty] | 047-0000 | 0 | 8835 | 2
[10 empty] | 047-0009 | 0 | 16970 | 2
[10 empty] | 047-0026 | 0 | 3319 | 2
[10 empty] | 048-0000 | 0 | 6820 | 2
[10 empty] | 079-0000 | 0 | 8970 | 2
[10 empty] | 01S-0704-D | 0 | 2320 | 2
[10 empty] | 01S-0707-D | 0 | 2090 | 2
[10 empty] | 01S-0712-D | 0 | 2616 | 2
[10 empty] | 01N-0486-D | 0 | 16298 | 2
[10 empty] | 01N-0504-I | 0 | 8907 | 2
[10 empty] | 01H-0519 | 0 | 7313 | 4
[10 empty] | 01N-0554 | 0 | 1200 | 4
[10 empty] | 01N-0554/01.20-I | 1200 | 1682 | 2
[10 empty] | 01N-0554/01.20-D | 1200 | 1679 | 2
[10 empty] | 01N-0556/00.05-I | 48 | 957 | 2
[10 empty] | 01N-0556/00.05-D | 48 | 963 | 2
[10 empty] | 01N-0574/02.93 | 2932 | 17650 | 3
[10 empty] | 01N-0591 | 0 | 1625 | 3
[10 empty] | 01N-0594/00.08 | 76 | 10677 | 3
[10 empty] | 01N-0605 | 0 | 1633 | 2
[10 empty] | 01N-0607 | 0 | 6462 | 2
[10 empty] | 01N-0625 | 0 | 11161 | 4
[10 empty] | 01N-0625/11.15-I | 11161 | 12021 | 2
[10 empty] | 01N-0625/11.15-D | 11161 | 12021 | 2
[10 empty] | 01N-0625/12.01 | 12021 | 12603 | 2
[10 empty] | 01N-0657-C030 | 0 | 5498 | 3
[10 empty] | 01N-0664 | 0 | 17042 | 3
[10 empty] | 01N-0680 | 0 | 14611 | 3
[10 empty] | 01N-0695-R1 | 0 | 183 | 1
[10 empty] | 01N-0726 | 0 | 17472 | 2
[10 empty] | 01N-0744 | 0 | 9508 | 2
[10 empty] | 01N-0753 | 0 | 9493 | 2
[10 empty] | 01N-0763 | 0 | 14832 | 3
[10 empty] | 01N-0777 | 0 | 16640 | 2
[10 empty] | 025-0000 | 0 | 12201 | 2
[10 empty] | 025-0012 | 0 | 10444 | 2
[10 empty] | 025-0024 | 0 | 17940 | 3
[10 empty] | 025-0042 | 0 | 16130 | 2
[10 empty] | 025-0058 | 0 | 14268 | 2
[10 empty] | 025-0072 | 0 | 11579 | 2
[10 empty] | 025-0084 | 0 | 14020 | 2
[10 empty] | 025-0099 | 0 | 13827 | 2
[10 empty] | 025-0113 | 0 | 13504 | 2
[10 empty] | 025-0127 | 0 | 12813 | 2
[10 empty] | 025-0143 | 0 | 12939 | 2
[10 empty] | 025-0156 | 0 | 15643 | 2
[10 empty] | 025-0172 | 0 | 13100 | 2
[10 empty] | 025-0188 | 0 | 16428 | 2
[10 empty] | 025-0206 | 0 | 11217 | 2
[10 empty] | 025-0226 | 0 | 16144 | 2
[10 empty] | 031-0000 | 0 | 13606 | 2
[10 empty] | 031-0014 | 0 | 17277 | 2
[10 empty] | 031-0031 | 0 | 16152 | 2
[10 empty] | 031-0047 | 0 | 9290 | 2
[10 empty] | 038-0000 | 0 | 17500 | 4
[10 empty] | 038-0017 | 0 | 19006 | 3
[10 empty] | 006-0116-D | 0 | 759 | 1
[10 empty] | 01N-0414/09.02 | 9020 | 10961 | 4
[10 empty] | 01N-0414/09.02-I | 9020 | 10961 | 3
[10 empty] | 01N-0414/09.02-D | 9020 | 10961 | 2
[10 empty] | 059-0024-R4 | 0 | 357 | 1
[10 empty] | 059-0024-R1 | 0 | 340 | 1
[10 empty] | 059-0024-R2 | 0 | 423 | 1
[10 empty] | 059-0024-R3 | 0 | 370 | 2
[10 empty] | 01N-0414/10.96-I | 10961 | 13566 | 6
[10 empty] | 01N-0414/10.96-D | 10961 | 13647 | 5
[10 empty] | 01S-0923-D | 0 | 1710 | 2
[10 empty] | 01S-0708-R1 | 0 | 140 | 1
[10 empty] | 01S-0713-R4 | 0 | 320 | 1
[10 empty] | 006-1168/02.75-I | 2750 | 7640 | 3
[10 empty] | 006-1168/02.75-D | 2750 | 7640 | 3
[10 empty] | 01S-0920-D | 0 | 1120 | 2
[10 empty] | 01S-0920/01.12 | 1120 | 2600 | 4
[10 empty] | 090-0035/11.66 | 11665 | 16020 | 2
[10 empty] | 002-0361 | 0 | 13739 | 3
[10 empty] | 01N-0461/12.99-I | 12989 | 16258 | 3
[10 empty] | 002-0751 | 0 | 7850 | 3
[10 empty] | 002-0858 | 0 | 13610 | 2
[10 empty] | 003-0158 | 0 | 12676 | 2
[10 empty] | 003-0371 | 0 | 12719 | 3
[10 empty] | 004-0035 | 0 | 9503 | 3
[10 empty] | 030-0131/06.10 | 5841 | 12191 | 2
[10 empty] | 035-0124 | 0 | 7534 | 2
[10 empty] | 047-0029 | 0 | 17063 | 2
[10 empty] | 01S-0185 | 0 | 9970 | 2
[10 empty] | 006-0196 | 0 | 13504 | 4
[10 empty] | 01S-0833/07.07 | 7069 | 10017 | 2
[10 empty] | 006-1024/12.95 | 12917 | 21578 | 2
[10 empty] | 083-0022 | 0 | 12408 | 2
[10 empty] | 043-0057 | 0 | 7926 | 2
[10 empty] | 01S-0900/14.18 | 14159 | 19453 | 2
[10 empty] | 01S-0651/09.00 | 8940 | 14720 | 2
[10 empty] | 006-0901/06.20 | 6200 | 16900 | 2
[10 empty] | 006-1157/07.94 | 7937 | 10445 | 3
[10 empty] | 01S-0729/13.40 | 13400 | 17670 | 2
[10 empty] | 01S-0872/06.04 | 6037 | 12826 | 2
[10 empty] | 096-0000/04.89 | 4891 | 15373 | 2
[10 empty] | 094-0016/02.42 | 2416 | 14460 | 2
[10 empty] | 087-0096/09.97 | 9970 | 14130 | 2
[10 empty] | 085-0049/01.00 | 1000 | 13250 | 2
[10 empty] | 08A-0000/11.30 | 11300 | 15125 | 2
[10 empty] | 099-0000/00.52 | 523 | 15346 | 2
[10 empty] | 005-0190 | 0 | 13254 | 3
[10 empty] | 002-0691/07.66 | 7660 | 16150 | 2
[10 empty] | 002-0626/11.31 | 11310 | 11693 | 2
[10 empty] | 002-0577/14.59 | 14590 | 15710 | 2
[10 empty] | 051-0002/08.35 | 8345 | 10655 | 2
[10 empty] | 045-0028 | 0 | 18924 | 2
[10 empty] | 043-0097 | 0 | 14125 | 2
[10 empty] | 01N-0954 | 0 | 11260 | 3
[10 empty] | 004-0176 | 0 | 11744 | 2
[10 empty] | 003-0415 | 0 | 17250 | 3
[10 empty] | 003-0269 | 0 | 10441 | 3
[10 empty] | 003-0287 | 0 | 11071 | 3
[10 empty] | 002-0883/05.78 | 5780 | 20340 | 3
[10 empty] | 002-0883/20.34 | 20340 | 21276 | 2
[10 empty] | 006-0073 | 0 | 5693 | 3
[10 empty] | 079-0042 | 0 | 4058 | 2
[10 empty] | 01S-0520 | 0 | 12417 | 4
[10 empty] | 01S-0462 | 0 | 3692 | 2
[10 empty] | 01S-0350/01.87 | 1866 | 2466 | 4
[10 empty] | 008-0034/09.54 | 9540 | 23101 | 2
[10 empty] | 075-0024 | 0 | 9542 | 2
[10 empty] | 073-0015 | 0 | 20666 | 2
[10 empty] | 01S-0327-D | 0 | 5678 | 2
[10 empty] | 01S-0327-I | 0 | 5769 | 2
[10 empty] | 01S-0303 | 0 | 6530 | 4
[10 empty] | 030-0120 | 0 | 10114 | 2
[10 empty] | 029-0021 | 0 | 20937 | 3
[10 empty] | 027-0085 | 0 | 8141 | 2
[10 empty] | 002-0146 | 0 | 1128 | 2
[10 empty] | 01N-0479-R1 | 0 | 280 | 1
[10 empty] | 01N-0479-R2 | 0 | 220 | 1
[10 empty] | 003-0005 | 0 | 4406 | 2
[10 empty] | 01N-0481-R1 | 0 | 276 | 1
[10 empty] | 034-0011 | 0 | 4477 | 2
[10 empty] | 01N-0448/05.06-I | 5055 | 14161 | 2
[10 empty] | 01N-0448/05.06-D | 5059 | 14170 | 3
[10 empty] | 020-0010-I | 0 | 2542 | 3
[10 empty] | 01N-0461/01.31-I | 1305 | 12989 | 3
[10 empty] | 01N-0461/01.31-D | 1306 | 12984 | 2
[10 empty] | 020-0010-D | 0 | 2543 | 3
[10 empty] | 016-0007/03.53-D | 3500 | 12907 | 5
[10 empty] | 025-0217 | 0 | 8019 | 2
[10 empty] | 026-0060 | 0 | 8933 | 2
[10 empty] | 026-0080 | 0 | 15503 | 2
[10 empty] | 020-0010/02.54-D | 2543 | 9675 | 3
[10 empty] | 020-0010/02.54-I | 2542 | 9662 | 2
[10 empty] | 020-0020-I | 0 | 4090 | 4
[10 empty] | 020-0020-D | 0 | 4172 | 3
[10 empty] | 020-0015-R2 | 0 | 208 | 1
[10 empty] | 020-0015-R1 | 0 | 395 | 2
[10 empty] | 01N-0431/11.16-I | 11155 | 16816 | 4
[10 empty] | 022-0000/03.71 | 3705 | 10098 | 3
[10 empty] | 01N-0477-I | 0 | 7800 | 2
[10 empty] | 002-0000 | 0 | 16488 | 3
[10 empty] | 01N-0431/11.17-D | 11168 | 16820 | 4
[10 empty] | 01N-0466-R2 | 0 | 257 | 1
[10 empty] | 01N-0466-R3 | 0 | 244 | 1
[10 empty] | 01N-0431-D | 0 | 11168 | 4
[10 empty] | 01N-0414-I | 0 | 9020 | 5
[10 empty] | 016-0003-R3 | 0 | 265 | 1
[10 empty] | 74M-0002-I | 0 | 4169 | 3
[10 empty] | 74M-0002-D | 0 | 4169 | 2
[10 empty] | 043-0130 | 0 | 20187 | 2
[10 empty] | 054-0000 | 0 | 1670 | 3
[10 empty] | 054-0001 | 0 | 16109 | 2
[10 empty] | 054-0017 | 0 | 20844 | 2
[10 empty] | 057-0021 | 0 | 4462 | 2
[10 empty] | 056-0011 | 0 | 10847 | 2
[10 empty] | 050-0002-I | 0 | 2290 | 2
[10 empty] | 050-0002-D | 0 | 2290 | 2
[10 empty] | 051-0002-I | 0 | 76 | 2
[10 empty] | 051-0002-D | 0 | 85 | 2
[10 empty] | 050-0000 | 0 | 3744 | 3
[10 empty] | 051-0000-D | 0 | 2421 | 2
[10 empty] | 051-0000-I | 0 | 2426 | 2
[10 empty] | 051-0002/00.08 | 76 | 8345 | 4
[10 empty] | 095-0000 | 0 | 20455 | 2
[10 empty] | 094-0138 | 0 | 11861 | 4
[10 empty] | 099-0078 | 0 | 14063 | 2
[10 empty] | 006-0471 | 0 | 13950 | 2
[10 empty] | 67A-0000 | 0 | 8937 | 2
[10 empty] | 077-0043 | 0 | 9970 | 2
[10 empty] | 077-0053 | 0 | 13964 | 2
[10 empty] | 077-0067 | 0 | 11486 | 2
[10 empty] | 077-0079 | 0 | 14897 | 2
[10 empty] | 078-0000 | 0 | 938 | 3
[10 empty] | 01S-0344-I | 0 | 2746 | 4
[10 empty] | 01S-0347-I | 0 | 446 | 2
[10 empty] | 01S-0347-D | 0 | 446 | 2
[10 empty] | 07A-0000 | 0 | 8600 | 3
[10 empty] | 071-0000 | 0 | 6380 | 2
[10 empty] | 073-0005 | 0 | 8778 | 4
[10 empty] | 076-0003/00.98-D | 983 | 2193 | 2
[10 empty] | 076-0003/00.98-I | 983 | 2190 | 2
[10 empty] | 076-0003 | 0 | 983 | 2
[10 empty] | 074-0021-R2 | 0 | 473 | 2
[10 empty] | 074-0021-R4 | 0 | 131 | 1
[10 empty] | 074-0019/02.08-D | 2080 | 2768 | 1
[10 empty] | 01N-0552 | 0 | 3656 | 5
[10 empty] | 01N-0553 | 0 | 530 | 4
[10 empty] | 01N-0553/00.53-I | 530 | 964 | 2
[10 empty] | 01N-0553/00.53-D | 530 | 952 | 2
[10 empty] | 003-0000 | 0 | 398 | 5
[10 empty] | 003-0000/00.45-I | 449 | 1374 | 2
[10 empty] | 003-0000-R1 | 0 | 656 | 2
[10 empty] | 003-0000-R2 | 0 | 646 | 2
[10 empty] | 032-0000 | 0 | 14985 | 2
[10 empty] | 032-0015 | 0 | 12763 | 2
[10 empty] | 032-0028-C030 | 0 | 1205 | 2
[10 empty] | 032-0029 | 0 | 16423 | 2
[10 empty] | 032-0045 | 0 | 11990 | 2
[10 empty] | 032-0057 | 0 | 11307 | 2
[10 empty] | 032-0069 | 0 | 12908 | 2
[10 empty] | 032-0082 | 0 | 14284 | 2
[10 empty] | 01N-0638 | 0 | 19194 | 4
[10 empty] | 005-0050-I | 0 | 884 | 3
[10 empty] | 005-0054-C030 | 0 | 1111 | 2
[10 empty] | 030-0147/01.11 | 1108 | 10296 | 2
[10 empty] | 30A-0000 | 0 | 1237 | 6
[10 empty] | 30A-0000/01.22-I | 1237 | 3577 | 2
[10 empty] | 30A-0000/01.22-D | 1237 | 3577 | 3
[10 empty] | 002-0223 | 0 | 8797 | 2
[10 empty] | 002-0242-C030 | 0 | 898 | 2
[10 empty] | 030-0205-C034 | 0 | 209 | 2
[10 empty] | 030-0218-C002 | 0 | 898 | 2
[10 empty] | 034-0010-C030 | 0 | 210 | 2
[10 empty] | 002-0243 | 0 | 12122 | 2
[10 empty] | 030-0206 | 0 | 12071 | 2
[10 empty] | 030-0219 | 0 | 10264 | 4
[10 empty] | 034-0000 | 0 | 10312 | 2
[10 empty] | 01S-0710-R2 | 0 | 130 | 1
[10 empty] | 01S-0710-R1 | 0 | 210 | 1
[10 empty] | 01S-0713-R1 | 0 | 392 | 1
[10 empty] | 01S-0713-R3 | 0 | 798 | 1
[10 empty] | 01N-0000 | 0 | 20070 | 2
[10 empty] | 01N-0020 | 0 | 23910 | 2
[10 empty] | 018-0007-I | 0 | 5320 | 2
[10 empty] | 016-0000/00.76-I | 758 | 9313 | 6
[10 empty] | 016-0000/00.76-D | 758 | 9314 | 5
[10 empty] | 01N-0303 | 0 | 15802 | 3
[10 empty] | 023-0000/01.30 | 1298 | 3063 | 2
[10 empty] | 030-0144 | 0 | 2741 | 3
[10 empty] | 003-0000/00.45-D | 449 | 1382 | 2
[10 empty] | 074-0021-R3 | 0 | 300 | 1
[10 empty] | 005-0124/07.93-I-C01N | 7967 | 8540 | 2
[10 empty] | 005-0124/07.93-D-C01N | 7967 | 8544 | 2
[10 empty] | 005-0124/08.57-C01N | 8540 | 8643 | 2
[10 empty] | 01S-0720-R1 | 0 | 865 | 1
[10 empty] | 01S-0720-R4 | 0 | 494 | 1
[10 empty] | 01S-0720-R2 | 0 | 280 | 1
[10 empty] | 01S-0720-R3 | 0 | 370 | 1
[10 empty] | 01N-0472-R1 | 0 | 220 | 1
[10 empty] | 01N-0472-R4 | 0 | 231 | 1
[10 empty] | 01N-0472-R2 | 0 | 171 | 1
[10 empty] | 01N-0472-R3 | 0 | 456 | 2
[10 empty] | 01N-0475-R4 | 0 | 148 | 1
[10 empty] | 01N-0475-R1 | 0 | 141 | 1
[10 empty] | 01N-0475-R2 | 0 | 73 | 1
[10 empty] | 01N-0475-R3 | 0 | 108 | 1
[10 empty] | 01N-0477-R1 | 0 | 198 | 1
[10 empty] | 01N-0477-R2 | 0 | 221 | 1
[10 empty] | 01N-0478-R3 | 0 | 849 | 2
[10 empty] | 01N-0478-R1 | 0 | 493 | 3
[10 empty] | 01N-0478-R4 | 0 | 402 | 1
[10 empty] | 01N-0478-R2 | 0 | 195 | 1
[10 empty] | 01S-0713-R2 | 0 | 255 | 1
[10 empty] | 01N-1063-R1 | 0 | 345 | 1
[10 empty] | 01N-1063-R2 | 0 | 405 | 1
[10 empty] | 01N-1063-R4 | 0 | 307 | 1
[10 empty] | 01N-1063-R3 | 0 | 450 | 2
[10 empty] | 059-0023-R1 | 0 | 458 | 1
[10 empty] | 059-0023-R2 | 0 | 491 | 1
[10 empty] | 002-0974-R2 | 0 | 154 | 1
[10 empty] | 002-0974-R1 | 0 | 156 | 1
[10 empty] | 01N-0414-R1 | 0 | 328 | 2
[10 empty] | 01N-0414-R4 | 0 | 352 | 2
[10 empty] | 01N-0414-R2 | 0 | 653 | 2
[10 empty] | 01N-0414-R3 | 0 | 723 | 2
[10 empty] | 018-0000-D | 0 | 6706 | 4
[10 empty] | 018-0000-I | 0 | 6706 | 4
[10 empty] | 010-0106 | 0 | 0 | 2
[10 empty] | 012-0223 | 0 | 0 | 2
[10 empty] | 014-0056 | 0 | 0 | 2
[10 empty] | 016-0107 | 0 | 0 | 2
[10 empty] | 023-0044 | 0 | 0 | 2
[10 empty] | 025-0242 | 0 | 0 | 2
[10 empty] | 026-0096 | 0 | 0 | 2
[10 empty] | 027-0094 | 0 | 0 | 2
[10 empty] | 029-0074 | 0 | 0 | 2
[10 empty] | 031-0056 | 0 | 0 | 2
[10 empty] | 032-0097 | 0 | 0 | 2
[10 empty] | 041-0059 | 0 | 0 | 2
[10 empty] | 047-0046 | 0 | 0 | 2
[10 empty] | 25A-0028 | 0 | 0 | 2
[10 empty] | 030-0229 | 0 | 0 | 2
[10 empty] | 033-0036 | 0 | 1 | 1
[10 empty] | 034-0025 | 0 | 0 | 2
[10 empty] | 035-0335 | 0 | 0 | 2
[10 empty] | 005-0262 | 0 | 0 | 2
[10 empty] | 038-0196 | 0 | 0 | 2
[10 empty] | 03A-0016 | 0 | 0 | 2
[10 empty] | 045-0105 | 0 | 0 | 2
[10 empty] | 003-0500 | 0 | 0 | 2
[10 empty] | 004-0239 | 0 | 0 | 2
[10 empty] | 043-0150 | 0 | 0 | 2
[10 empty] | 048-0007 | 0 | 1 | 2
[10 empty] | 049-0038 | 0 | 1 | 2
[10 empty] | 054-0055 | 0 | 0 | 2
[10 empty] | 056-0023 | 0 | 0 | 2
[10 empty] | 057-0065 | 0 | 1 | 2
[10 empty] | 053-0018 | 0 | 0 | 2
[10 empty] | 058-0015 | 0 | 0 | 2
[10 empty] | 060-0118 | 0 | 0 | 2
[10 empty] | 063-0117 | 0 | 0 | 2
[10 empty] | 074-0027 | 0 | 0 | 2
[10 empty] | 078-0001 | 0 | 0 | 2
[10 empty] | 079-0061 | 0 | 0 | 2
[10 empty] | 080-0059 | 0 | 0 | 2
[10 empty] | 082-0071 | 0 | 0 | 2
[10 empty] | 007-0273 | 0 | 0 | 3
[10 empty] | 067-0051 | 0 | 0 | 2
[10 empty] | 069-0033 | 0 | 0 | 2
[10 empty] | 073-0226 | 0 | 0 | 2
[10 empty] | 67A-0009 | 0 | 0 | 2
[10 empty] | 008-0460 | 0 | 0 | 2
[10 empty] | 06A-0007 | 0 | 0 | 2
[10 empty] | 083-0110 | 0 | 0 | 2
[10 empty] | 085-0164 | 0 | 0 | 2
[10 empty] | 087-0116 | 0 | 0 | 2
[10 empty] | 088-0013 | 0 | 0 | 2
[10 empty] | 084-0003 | 0 | 0 | 2
[10 empty] | 08A-0021 | 0 | 0 | 2
[10 empty] | 08B-0003 | 0 | 0 | 2
[10 empty] | 006-1175 | 0 | 0 | 2
[10 empty] | 01S-0953 | 0 | 0 | 2
[10 empty] | 090-0059 | 0 | 0 | 2
[10 empty] | 094-0258 | 0 | 0 | 2
[10 empty] | 095-0021 | 0 | 0 | 2
[10 empty] | 099-0092 | 0 | 0 | 2
[10 empty] | 01N-0557/02.52-I | 2520 | 17305 | 2
[10 empty] | 01N-0557/02.52-D | 2520 | 17305 | 2
[10 empty] | 01N-0561-R1 | 0 | 349 | 1
[10 empty] | 01N-0561-R2 | 0 | 343 | 1
[10 empty] | 01N-0561-R3 | 0 | 172 | 1
[10 empty] | 01N-0561-R4 | 0 | 244 | 2
[10 empty] | 01S-0501/04.53-I | 4526 | 4987 | 2
[10 empty] | 01S-0501/04.53-D | 4526 | 4987 | 2
[10 empty] | 01S-0506 | 0 | 800 | 4
[10 empty] | 01S-0506/00.80-I | 800 | 2038 | 1
[10 empty] | 01S-0506/00.80-D | 800 | 2038 | 1
[10 empty] | 01S-0506/02.04 | 2038 | 9101 | 4
[10 empty] | 20A-0000-I | 0 | 4156 | 3
[10 empty] | 20A-0000-D | 0 | 4156 | 2
[10 empty] | 20A-0001-R1 | 0 | 47 | 1
[10 empty] | 20A-0001-R2 | 0 | 169 | 1
[10 empty] | 020-0007-R3 | 0 | 241 | 3
[10 empty] | 020-0010-R4 | 0 | 735 | 2
[10 empty] | 020-0010-R3 | 0 | 231 | 2
[10 empty] | 020-0007-R1 | 0 | 240 | 3
[10 empty] | 020-0007-R2 | 0 | 242 | 2
[10 empty] | 020-0009-R1 | 0 | 606 | 1
[10 empty] | 020-0010-R1 | 0 | 385 | 1
[10 empty] | 020-0010-R2 | 0 | 394 | 1
[10 empty] | 020-0007-R4 | 0 | 142 | 2
[10 empty] | 050-0067 | 0 | 11942 | 2
[10 empty] | 050-0079 | 0 | 10521 | 2
[10 empty] | 050-0090 | 0 | 0 | 1
[10 empty] | 011-0000 | 0 | 14037 | 2
[10 empty] | 057-0026 | 0 | 9952 | 2
[10 empty] | 057-0050 | 0 | 14707 | 2
[10 empty] | 098-0000 | 0 | 21615 | 2
[10 empty] | 01N-0211 | 0 | 3492 | 2
[10 empty] | 003-0488 | 0 | 2723 | 2
[10 empty] | 098-0021 | 0 | 0 | 2
[10 empty] | 011-0014 | 0 | 15515 | 3
[10 empty] | 016-0000 | 0 | 758 | 4
[10 empty] | 075-0079 | 0 | 0 | 2
[10 empty] | 071-0006 | 0 | 0 | 2
[10 empty] | 096-0091 | 0 | 0 | 2
[10 empty] | 057-0036 | 0 | 13823 | 2
[10 empty] | 022-0013 | 0 | 0 | 2
[10 empty] | 077-0094 | 0 | 0 | 2
[10 empty] | 005-0045/01.95-I | 1946 | 5500 | 2
[10 empty] | 005-0045/01.95-D | 1946 | 5500 | 2
[10 empty] | 005-0045/05.50 | 5500 | 5676 | 4
[10 empty] | 025-0022 | 0 | 1150 | 2
[10 empty] | 002-0154-W-CO29 | 0 | 109 | 2
[10 empty] | 003-0065 | 0 | 11614 | 3
[10 empty] | 002-0232 | 0 | 10206 | 2
[10 empty] | 002-0271 | 0 | 12184 | 2
[10 empty] | 046-0000 | 0 | 19120 | 2
[10 empty] | 01N-0613 | 0 | 12339 | 2
[10 empty] | 01N-0477-D | 0 | 7848 | 2
[10 empty] | 01N-0557 | 0 | 2520 | 3
[10 empty] | 028-0000 | 0 | 5786 | 2
[10 empty] | 028-0009 | 0 | 8480 | 2
[10 empty] | 028-0017 | 0 | 7167 | 2
[10 empty] | 021-0000-W | 0 | 74 | 1
[10 empty] | 021-0000/00.04 | 38 | 106 | 2
[10 empty] | 021-0000/00.15 | 150 | 1775 | 2
[10 empty] | 021-0002 | 0 | 4932 | 2
[10 empty] | 047-0009/16.97 | 16970 | 17155 | 2
[10 empty] | 024-0000-I | 0 | 1079 | 1
[10 empty] | 024-0000-D | 0 | 1076 | 1
[10 empty] | 024-0000/01.08 | 1079 | 12965 | 2
[10 empty] | 037-0000 | 0 | 7307 | 2
[10 empty] | 034-0021 | 0 | 4155 | 2
[10 empty] | 005-0008 | 0 | 20108 | 3
[10 empty] | 029-0048 | 0 | 1419 | 2
[10 empty] | 030-0194 | 0 | 11466 | 2
[10 empty] | 003-0010 | 0 | 56 | 4
[10 empty] | 030-0084-C032 | 0 | 1198 | 2
[10 empty] | 027-0074 | 0 | 9586 | 2
[10 empty] | 021-0007 | 0 | 0 | 2
[10 empty] | 024-0013 | 0 | 0 | 2
[10 empty] | 028-0006-C005 | 0 | 2481 | 2
[10 empty] | 028-0024 | 0 | 0 | 2
[10 empty] | 037-0007 | 0 | 0 | 2
[10 empty] | 008-0030 | 0 | 4225 | 2
[10 empty] | 01S-0350 | 0 | 1866 | 4
[10 empty] | 007-0068 | 0 | 10160 | 2
[10 empty] | 073-0041 | 0 | 11537 | 2
[10 empty] | 075-0008 | 0 | 6157 | 2
[10 empty] | 018-0014 | 0 | 0 | 4
[10 empty] | 046-0020 | 0 | 0 | 2
[10 empty] | 01N-1076 | 0 | 2080 | 4
[10 empty] | 01N-1076/02.08-I | 2080 | 3078 | 2
[10 empty] | 01N-1076/02.08-D | 2080 | 3068 | 2
[10 empty] | 01N-1076/03.70 | 3698 | 4700 | 4
[10 empty] | 01N-1081 | 0 | 0 | 2
[10 empty] | 016-0047 | 0 | 21810 | 2
[10 empty] | 016-0069 | 0 | 13104 | 2
[10 empty] | 016-0082 | 0 | 9486 | 2
[10 empty] | 016-0092 | 0 | 14046 | 2
[10 empty] | 002-0651/05.23-C050-D | 5234 | 6445 | 2
[10 empty] | 002-0658-I | 0 | 713 | 2
[10 empty] | 050-0012 | 0 | 8985 | 2
[10 empty] | 01N-1066-R4 | 0 | 440 | 2
[10 empty] | 01N-1066-R5 | 0 | 725 | 1
[10 empty] | 01N-1066-R1 | 0 | 392 | 2
[10 empty] | 01N-1066-R3 | 0 | 625 | 1
[10 empty] | 01N-0474-R4 | 0 | 37 | 1
[10 empty] | 01N-0474-R2 | 0 | 33 | 1
[10 empty] | 01N-0474-R3 | 0 | 269 | 1
[10 empty] | 016-0008-R5 | 0 | 115 | 1
[10 empty] | 016-0008-R6 | 0 | 296 | 2
[10 empty] | 016-0008-R7 | 0 | 670 | 2
[10 empty] | 016-0008-R8 | 0 | 634 | 3
[10 empty] | 01N-0437-R3 | 0 | 380 | 2
[10 empty] | 01N-0437-R1 | 0 | 690 | 2
[10 empty] | 01N-0437-R2 | 0 | 178 | 1
[10 empty] | 01N-0474-R1 | 0 | 134 | 1
[10 empty] | 065-0072 | 0 | 0 | 2
[10 empty] | 093-0000 | 0 | 16325 | 2
[10 empty] | 093-0016 | 0 | 15040 | 2
[10 empty] | 093-0031 | 0 | 11800 | 2
[10 empty] | 093-0043 | 0 | 0 | 2
[10 empty] | 01H-0525 | 0 | 405 | 2
[10 empty] | 01B-0015 | 0 | 13918 | 2
[10 empty] | 01B-0029-C026 | 0 | 1147 | 2
[10 empty] | 01B-0030 | 0 | 13660 | 2
[10 empty] | 01B-0044 | 0 | 1 | 2
[10 empty] | 039-0017-C023 | 0 | 55 | 2
[10 empty] | 039-0018 | 0 | 15162 | 2
[10 empty] | 039-0033 | 0 | 9648 | 2
[10 empty] | 039-0043 | 0 | 15271 | 2
[10 empty] | 039-0058-C031 | 0 | 13609 | 2
[10 empty] | 039-0072 | 0 | 0 | 2
[10 empty] | 01S-0817 | 0 | 6220 | 2
[10 empty] | 01S-0870 | 0 | 1520 | 2
[10 empty] | 01N-0398-R5 | 0 | 223 | 1
[10 empty] | 01N-0398-R1 | 0 | 220 | 1
[10 empty] | 01N-0398-I | 0 | 11550 | 4
[10 empty] | 01N-0398-D | 0 | 11645 | 3
[10 empty] | 01N-0398-R3 | 0 | 328 | 2
[10 empty] | 01N-0410-R2 | 0 | 351 | 2
[10 empty] | 01N-0410-R1 | 0 | 449 | 1
[10 empty] | 01N-0412-R1 | 0 | 352 | 3
[10 empty] | 01N-0412-R2 | 0 | 281 | 2
[10 empty] | 01N-0398-R2 | 0 | 68 | 1
[10 empty] | 01N-0412-R3 | 0 | 260 | 5
[10 empty] | 01N-0412-R4 | 0 | 98 | 1
[10 empty] | 01N-0410-R3 | 0 | 337 | 2
[10 empty] | 01N-0398-R4 | 0 | 271 | 3
[10 empty] | 01N-0447-R1 | 0 | 342 | 3
[10 empty] | 01N-0447-R2 | 0 | 231 | 2
[10 empty] | 006-0121-R1 | 0 | 726 | 2
[10 empty] | 026-0006-C01B | 0 | 1147 | 2
[10 empty] | 026-0007 | 0 | 10348 | 2
[10 empty] | 01N-0410-R4 | 0 | 359 | 2
[10 empty] | 016-0007/03.53-I | 3517 | 12920 | 6
[10 empty] | 01N-0460-R1 | 0 | 271 | 1
[10 empty] | 01N-0460-R2 | 0 | 181 | 1
[10 empty] | 024-0008-R1 | 0 | 206 | 1
[10 empty] | 029-0049-R1 | 0 | 285 | 1
[10 empty] | 027-0082-C029 | 0 | 68 | 2
[10 empty] | 029-0060-C027 | 0 | 68 | 2
[10 empty] | 063-0084 | 0 | 7879 | 2
[10 empty] | 01N-1067-R2 | 0 | 120 | 1
[10 empty] | 01N-1067-R1 | 0 | 665 | 2
[10 empty] | 002-0150-R1 | 0 | 211 | 1
[10 empty] | 002-0153-R1 | 0 | 256 | 2
[10 empty] | 029-0014-I | 0 | 1467 | 1
[10 empty] | 029-0014-D | 0 | 1512 | 2
[10 empty] | 002-0152-R1 | 0 | 73 | 2
[10 empty] | 002-0152-R2 | 0 | 304 | 1
[10 empty] | 002-0153-R2 | 0 | 194 | 1
[10 empty] | 002-0149-R3 | 0 | 175 | 1
[10 empty] | 01S-0715-I | 0 | 5714 | 2
[10 empty] | 01S-0715-D | 0 | 5714 | 3
[10 empty] | 01S-0714-R1 | 0 | 195 | 2
[10 empty] | 01S-0714-R4 | 0 | 227 | 1
[10 empty] | 01S-0715-R2 | 0 | 345 | 1
[10 empty] | 01S-0715-R3 | 0 | 375 | 1
[10 empty] | 01S-0717-R1 | 0 | 429 | 1
[10 empty] | 01S-0717-R2 | 0 | 355 | 1
[10 empty] | 01S-0719-R1 | 0 | 158 | 1
[10 empty] | 01S-0719-R2 | 0 | 457 | 1
[10 empty] | 01N-0258/03.50 | 3502 | 4979 | 5
[10 empty] | 059-0000/12.79-I | 12795 | 17475 | 4
[10 empty] | 059-0000/12.79-D | 12795 | 17475 | 4
[10 empty] | 059-0014-R1 | 0 | 410 | 1
[10 empty] | 059-0016-R2 | 0 | 308 | 1
[10 empty] | 059-0016-R1 | 0 | 84 | 1
[10 empty] | 006-1145 | 0 | 181 | 2
[10 empty] | 006-1145/00.18-I | 181 | 645 | 1
[10 empty] | 006-1145/00.18-D | 181 | 645 | 1
[10 empty] | 01N-0398/11.53-I | 11550 | 15820 | 3
[10 empty] | 01N-0398/11.65-D | 11645 | 15825 | 4
[10 empty] | 002-0883-I | 0 | 235 | 2
[10 empty] | 002-0883-D | 0 | 230 | 2
[10 empty] | 002-0948-R1 | 0 | 200 | 2
[10 empty] | 002-0948-R2 | 0 | 208 | 1
[10 empty] | 002-0959-R1 | 0 | 362 | 1
[10 empty] | 002-0959-R2 | 0 | 384 | 1
[10 empty] | 059-0022-R1 | 0 | 285 | 2
[10 empty] | 059-0022-R2 | 0 | 255 | 1
[10 empty] | 01N-1066-R7 | 0 | 321 | 1
[10 empty] | 01N-1066-R2 | 0 | 170 | 1
[10 empty] | 002-0646-I | 0 | 765 | 2
[10 empty] | 086-0000 | 0 | 5285 | 2
[10 empty] | 086-0006 | NULL | NULL | NULL
[10 empty] | 097-0000 | 0 | 5106 | 2
[10 empty] | 097-0000/05.00 | 5106 | 10013 | 2
[10 empty] | 097-0000/10.00 | 10013 | 15518 | 2
[10 empty] | 097-0000/15.00 | 15518 | 19711 | 2
[10 empty] | 097-0020 | NULL | NULL | NULL
[10 empty] | 030-0085-C032 | 0 | 106 | 2
[10 empty] | 030-0086 | 0 | 19893 | 2
[10 empty] | 030-0105-C01N | 0 | 5573 | 2
[10 empty] | 032-0027-C030 | 0 | 105 | 2
[10 empty] | 01N-0663 | 0 | 86 | 2
[10 empty] | 030-0086-R1 | 0 | 81 | 2
[10 empty] | 006-0127-R2 | 0 | 90 | 2
[10 empty] | 006-0127-R1 | 0 | 90 | 2
[10 empty] | 073-0001 | 0 | 742 | 2
[10 empty] | 074-0009-R1 | 0 | 110 | 1
[10 empty] | 074-0009-W | 0 | 143 | 1
[10 empty] | 074-0009-R2 | 0 | 96 | 1
[10 empty] | 074-0009-R3 | 0 | 246 | 1
[10 empty] | 074-0007/02.98 | 2979 | 6034 | 4
[10 empty] | 074-0013-W | 0 | 145 | 2
[10 empty] | 074-0007/06.14 | 6142 | 6853 | 2
[10 empty] | 074-0014-W | 0 | 145 | 2
[10 empty] | 074-0007/06.92 | 6919 | 10391 | 2
[10 empty] | 074-0017-W | 0 | 145 | 2
[10 empty] | 074-0007/10.42 | 10420 | 14016 | 2
[10 empty] | 074-0019 | 0 | 424 | 2
[10 empty] | 074-0019-W | 0 | 202 | 1
[10 empty] | 074-0019/00.48 | 480 | 2080 | 2
[10 empty] | 74A-0000 | 0 | 2132 | 2
[10 empty] | 74A-0002 | NULL | NULL | NULL
[10 empty] | 076-0000-R1 | 0 | 312 | 1
[10 empty] | 074-0021-R1 | 0 | 119 | 1
[10 empty] | 076-0000 | 0 | 2518 | 2
[10 empty] | 074-0019/02.08-I | 2080 | 2768 | 2
[10 empty] | 002-0652-R1 | 0 | 433 | 2
[10 empty] | 002-0652-R2 | 0 | 397 | 2
[10 empty] | 044-0000 | 0 | 5002 | 5
[10 empty] | 016-0001-R1 | 0 | 50 | 2
[10 empty] | 016-0001-R2 | 0 | 105 | 1
[10 empty] | 016-0002-R1 | 0 | 376 | 1
[10 empty] | 016-0002-R2 | 0 | 343 | 2
[10 empty] | 20B-0000 | 0 | 2385 | 6
[10 empty] | 20B-0002 | 0 | 1 | 2
[10 empty] | 07A-0008 | 0 | 0 | 2
[10 empty] | 038-0036 | NULL | NULL | NULL
[10 empty] | 01N-0436-R3 | 0 | 460 | 2
[10 empty] | 006-0121-R2 | 0 | 713 | 2
[10 empty] | 006-0122-R1 | 0 | 148 | 1
[10 empty] | 006-0122-R2 | 0 | 120 | 1
[10 empty] | 006-0125-R1 | 0 | 306 | 1
[10 empty] | 006-0126-R2 | 0 | 77 | 1
[10 empty] | 006-0127-R3 | 0 | 72 | 1
[10 empty] | 006-0127-R4 | 0 | 96 | 1
[10 empty] | 062-0000 | 0 | 12749 | 2
[10 empty] | 062-0013 | 0 | 0 | 2
[10 empty] | 020-0005-R1 | 0 | 261 | 2
[10 empty] | 020-0005-R2 | 0 | 390 | 2
[10 empty] | 015-0111 | 0 | 8433 | 3
[10 empty] | 011-0030 | 0 | 0 | 2
[10 empty] | 015-0120 | 0 | 1 | 2
[10 empty] | 01N-0486-I | 0 | 16356 | 2
[10 empty] | 003-0076 | 0 | 11667 | 3
[10 empty] | 01N-0494-R2 | 0 | 236 | 1
[10 empty] | 01N-0494-R3 | 0 | 328 | 1
[10 empty] | 01N-0494-R4 | 0 | 258 | 1
[10 empty] | 01N-0494-R1 | 0 | 339 | 1
[10 empty] | 073-0001/00.73-I | 742 | 2380 | 2
[10 empty] | 073-0001/00.73-D | 742 | 2362 | 2
[10 empty] | 073-0001/02.38 | 2380 | 3963 | 3
[10 empty] | 01N-0510-R1 | 0 | 382 | 1
[10 empty] | 01N-0504-D | 0 | 8892 | 2
[10 empty] | 01H-0504/10.16 | 10157 | 15276 | 2
[10 empty] | 01N-0510-R2 | 0 | 327 | 1
[10 empty] | 01N-0510-R3 | 0 | 364 | 1
[10 empty] | 01N-0510-R4 | 0 | 292 | 1
[10 empty] | 01N-0044 | 0 | 20475 | 2
[10 empty] | 01N-0065 | 0 | 18468 | 2
[10 empty] | 01N-0083 | 0 | 19733 | 2
[10 empty] | 01N-0167 | 0 | 18134 | 2
[10 empty] | 036-0013 | 0 | 15895 | 2
[10 empty] | 036-0028 | 0 | 18577 | 2
[10 empty] | 036-0048 | 0 | 1 | 2
[10 empty] | 005-0050-D | 0 | 884 | 2
[10 empty] | 005-0050/0.88 | 884 | 3320 | 2
[10 empty] | 01N-0292 | 0 | 10608 | 3
[10 empty] | 010-0007 | 0 | 9151 | 3
[10 empty] | 005-0099 | 0 | 11912 | 2
[10 empty] | 002-0146/02.13-I | 2133 | 5137 | 3
[10 empty] | 002-0146/02.13-D | 2133 | 5162 | 2
[10 empty] | 002-0149-R1 | 0 | 185 | 1
[10 empty] | 002-0149-R2 | 0 | 203 | 1
[10 empty] | 002-0150-R2 | 0 | 291 | 1
[10 empty] | 002-0151-I-CO29 | 0 | 6396 | 5
[10 empty] | 002-0151/02.48-D-CO29 | 2484 | 6437 | 4
[10 empty] | 005-0045 | 0 | 1946 | 2
[10 empty] | 29A-0010-W | 0 | 116 | 2
[10 empty] | 29A-0011-W | 0 | 202 | 2
[10 empty] | 29A-0012-W | 0 | 110 | 2
[10 empty] | 029-0018-W | 0 | 206 | 2
[10 empty] | 006-0209 | 0 | 16077 | 2
[10 empty] | 006-0225 | 0 | 14410 | 2
[10 empty] | 29A-0000-D | 0 | 107 | 2
[10 empty] | 29A-0000-I | 0 | 111 | 2
[10 empty] | 29A-0001-W | 0 | 109 | 2
[10 empty] | 002-0163-W | 0 | 88 | 2
[10 empty] | 002-0161-W | 0 | 94 | 2
[10 empty] | 022-0001-R1 | 0 | 510 | 2
[10 empty] | 01K-1012/10.41 | 10409 | 11013 | 2
[10 empty] | 01K-1012/09.85-I | 9853 | 10409 | 1
[10 empty] | 01K-1012/09.85-D | 9853 | 10409 | 1
[10 empty] | 059-0000/17.47 | 17475 | 19220 | 4
[10 empty] | 059-0000/19.22-I | 19220 | 19695 | 2
[10 empty] | 059-0000/19.22-D | 19220 | 19685 | 2
[10 empty] | 002-0157/01.41 | 1410 | 3604 | 6
[10 empty] | 002-0159-R1 | 0 | 291 | 2
[10 empty] | 002-0159-R2 | 0 | 706 | 2
[10 empty] | 002-0159-R3 | 0 | 463 | 2
[10 empty] | 002-0159-R5 | 0 | 72 | 2
[10 empty] | 073-0145 | 0 | 5223 | 2
[10 empty] | 074-0007/02.15-D | 2152 | 2962 | 4
[10 empty] | 01N-0411-R1 | 0 | 132 | 1
[10 empty] | 01N-1075/00.13-I | 130 | 1690 | 4
[10 empty] | 01N-1075/00.13-D | 130 | 1795 | 4
[10 empty] | 01N-1030-R4 | 0 | 981 | 1
[10 empty] | 01N-1030-R1 | 0 | 292 | 1
[10 empty] | 01N-1030-R2 | 0 | 317 | 1
[10 empty] | 01N-1030-R3 | 0 | 327 | 1
[10 empty] | 016-0002-R5 | 0 | 437 | 3
[10 empty] | 01N-0410-R5 | 0 | 171 | 1
[10 empty] | 01N-0410-R6 | 0 | 115 | 1
[10 empty] | 01N-0472-R5 | 0 | 93 | 1
[10 empty] | 030-0187/00.20 | 199 | 7061 | 2
[10 empty] | 002-0157-I | 0 | 1410 | 4
[10 empty] | 002-0157-D | 0 | 1408 | 4
[10 empty] | 01N-0420-R1 | 0 | 302 | 1
[10 empty] | 01N-0420-R2 | 0 | 421 | 2
[10 empty] | 01N-0420-R3 | 0 | 340 | 2
[10 empty] | 01N-0420-R4 | 0 | 334 | 1
[10 empty] | 01N-0420-R5 | 0 | 215 | 1
[10 empty] | 01N-0429-R2 | 0 | 312 | 2
[10 empty] | 01N-0428-R1 | 0 | 2404 | 2
[10 empty] | 01N-0428-R2 | 0 | 620 | 2
[10 empty] | 01N-0427-R5 | 0 | 476 | 2
[10 empty] | 016-0003-R2 | 0 | 843 | 2
[10 empty] | 016-0003-R4 | 0 | 489 | 2
[10 empty] | 016-0002-R4 | 0 | 437 | 2
[10 empty] | 016-0004-R4 | 0 | 768 | 3
[10 empty] | 016-0003-R1 | 0 | 673 | 2
[10 empty] | 01N-0441-R3 | 0 | 278 | 2
[10 empty] | 01N-0441-R4 | 0 | 206 | 1
[10 empty] | 01N-0443-R1 | 0 | 270 | 2
[10 empty] | 01N-0443-R2 | 0 | 313 | 1
[10 empty] | 01N-0443-R3 | 0 | 394 | 2
[10 empty] | 01N-0443-R4 | 0 | 397 | 2
[10 empty] | 01N-0434-R5 | 0 | 85 | 1
[10 empty] | 018-0005-R1 | 0 | 313 | 2
[10 empty] | 018-0005-R2 | 0 | 281 | 2
[10 empty] | 018-0002-R1 | 0 | 312 | 3
[10 empty] | 018-0002-R2 | 0 | 444 | 2
[10 empty] | 018-0002-R3 | 0 | 242 | 3
[10 empty] | 018-0002-R4 | 0 | 230 | 1
[10 empty] | 018-0006-R1 | 0 | 239 | 1
[10 empty] | 018-0006-R2 | 0 | 307 | 2
[10 empty] | 01N-0414-R5 | 0 | 200 | 2
[10 empty] | 01N-0414/00.29 | 286 | 6186 | 2
[10 empty] | 01N-0420-R6 | 0 | 1593 | 1
[10 empty] | 002-0151-R3 | 0 | 98 | 1
[10 empty] | 29A-0000/06.91-I | 6906 | 7184 | 3
[10 empty] | 29A-0007-W | 0 | 269 | 2
[10 empty] | 29A-0008-I | 0 | 225 | 3
[10 empty] | 29A-0008-D | 0 | 214 | 2
[10 empty] | 01N-0402-R1 | 0 | 178 | 1
[10 empty] | 01N-0402-R2 | 0 | 329 | 1
[10 empty] | 002-0007-R1 | 0 | 291 | 1
[10 empty] | 002-0009-R1 | 0 | 411 | 1
[10 empty] | 002-0009-R2 | 0 | 531 | 1
[10 empty] | 01N-0547-W | 0 | 220 | 2
[10 empty] | 01N-0549-W | 0 | 161 | 2
[10 empty] | 01N-0483-R1 | 0 | 269 | 1
[10 empty] | 01N-0483-R2 | 0 | 339 | 1
[10 empty] | 01N-0483-R3 | 0 | 285 | 1
[10 empty] | 01N-0483-R4 | 0 | 250 | 1
[10 empty] | 01N-0491-R2 | 0 | 220 | 1
[10 empty] | 01N-0373/9.56-I | 9557 | 20922 | 2
[10 empty] | 01N-0373/9.56-D | 9557 | 20922 | 2
[10 empty] | 002-0654-R1 | 0 | 371 | 2
[10 empty] | 002-0654-R2 | 0 | 584 | 1
[10 empty] | 002-0654 R3 | 0 | 503 | 2
[10 empty] | 002-0654-R4 | 0 | 449 | 2
[10 empty] | 01N-0291-W | 0 | 208 | 1
[10 empty] | 059-0016-R3 | 0 | 240 | 1
[10 empty] | 059-0016-R4 | 0 | 112 | 1
[10 empty] | 01N-0381-R1 | 0 | 676 | 1
[10 empty] | 01N-0381-R2 | 0 | 933 | 1
[10 empty] | 01N-0389-R1 | 0 | 244 | 2
[10 empty] | 01N-0389-R2 | 0 | 238 | 2
[10 empty] | 01N-0389-R3 | 0 | 256 | 2
[10 empty] | 01N-0389-R4 | 0 | 290 | 2
[10 empty] | 020-0016-R1 | 0 | 331 | 1
[10 empty] | 020-0016-R2 | 0 | 261 | 1
[10 empty] | 020-0016-R3 | 0 | 306 | 1
[10 empty] | 020-0016-R4 | 0 | 320 | 1
[10 empty] | 020-0018-R1 | 0 | 256 | 1
[10 empty] | 020-0018-R2 | 0 | 206 | 1
[10 empty] | 020-0018-R3 | 0 | 308 | 1
[10 empty] | 020-0018-R4 | 0 | 365 | 1
[10 empty] | 002-0151-R1 | 0 | 1273 | 3
[10 empty] | 002-0155-R1 | 0 | 304 | 2
[10 empty] | 002-0155-R2 | 0 | 398 | 2
[10 empty] | 002-0155-R3 | 0 | 149 | 1
[10 empty] | 002-0155-R4 | 0 | 116 | 2
[10 empty] | 002-0155-R5 | 0 | 128 | 3
[10 empty] | 002-0155-R6 | 0 | 169 | 3
[10 empty] | 002-0155-R7 | 0 | 762 | 4
[10 empty] | 002-0151-R2 | 0 | 946 | 2
[10 empty] | 002-0972-R1 | 0 | 302 | 2
[10 empty] | 002-0972-R2 | 0 | 287 | 2
[10 empty] | 002-0972-R3 | 0 | 278 | 2
[10 empty] | 002-0972-R4 | 0 | 305 | 2
[10 empty] | 056-0014-R1 | 0 | 119 | 2
[10 empty] | 056-0014-R2 | 0 | 408 | 1
[10 empty] | 01N-0540/07.46 | 7460 | 9332 | 2
[10 empty] | 01N-0540/09.39 | 9393 | 10296 | 4
[10 empty] | 018-0007-D | 0 | 5320 | 2
[10 empty] | 002-0157/03.66 | 3664 | 4408 | 4
[10 empty] | 01N-0434-R6 | 0 | 46 | 2
[10 empty] | 059-0020-R1 | 0 | 217 | 1
[10 empty] | 01K-1022-R1 | 0 | 372 | 1
[10 empty] | 01K-1022-R2 | 0 | 116 | 1
[10 empty] | 003-0234-R1 | 0 | 566 | 2
[10 empty] | 003-0234-R2 | 0 | 307 | 2
[10 empty] | 003-0234-R3 | 0 | 311 | 2
[10 empty] | 003-0234-R4 | 0 | 364 | 2
[10 empty] | 023-0001-W | 0 | 158 | 2
[10 empty] | 023-0010-C039 | 0 | 55 | 4
[10 empty] | 023-0011 | 0 | 3891 | 2
[10 empty] | 002-0146/01.30-I | 1298 | 1694 | 2
[10 empty] | 002-0146/01.75 | 1746 | 2133 | 4
[10 empty] | 002-0146/01.30-D | 1298 | 1694 | 2
[10 empty] | 020-0001-R1 | 0 | 271 | 2
[10 empty] | 020-0001-R2 | 0 | 45 | 2
[10 empty] | 020-0001-R3 | 0 | 291 | 2
[10 empty] | 020-0001-R4 | 0 | 376 | 2
[10 empty] | 020-0001-R5 | 0 | 171 | 2
[10 empty] | 020-0003-R1 | 0 | 289 | 2
[10 empty] | 020-0003-R2 | 0 | 938 | 2
[10 empty] | 020-0003-R3 | 0 | 204 | 2
[10 empty] | 020-0003-R4 | 0 | 234 | 2
[10 empty] | 020-0005-R3 | 0 | 880 | 2
[10 empty] | 020-0005-R4 | 0 | 108 | 2
[10 empty] | 020-0000-I | 0 | 9684 | 2
[10 empty] | 020-0000-D | 0 | 9665 | 2
[10 empty] | 01N-0448-R1 | 0 | 337 | 2
[10 empty] | 01N-0448-R2 | 0 | 523 | 2
[10 empty] | 01N-0448-R3 | 0 | 418 | 2
[10 empty] | 01N-0448-R5 | 0 | 791 | 2
[10 empty] | 01N-0448-R6 | 0 | 686 | 2
[10 empty] | 01N-0448-R7 | 0 | 747 | 2
[10 empty] | 01N-0448-R8 | 0 | 359 | 2
[10 empty] | 036-0004 | 0 | 9191 | 2
[10 empty] | 036-0000-I | 0 | 324 | 3
[10 empty] | 036-0000-D | 0 | 301 | 3
[10 empty] | 029-0019-I | 0 | 140 | 2
[10 empty] | 016-0019-D | 0 | 168 | 3
[10 empty] | 018-0012-R2 | 0 | 1028 | 2
[10 empty] | 016-0019-R1 | 0 | 1926 | 2
[10 empty] | 016-0019-R2 | 0 | 217 | 2
[10 empty] | 016-0019-R3 | 0 | 68 | 2
[10 empty] | 016-0019-R4 | 0 | 244 | 2
[10 empty] | 016-0019-R5 | 0 | 447 | 2
[10 empty] | 016-0019-R6 | 0 | 505 | 2
[10 empty] | 018-0012-R1 | 0 | 277 | 2
[10 empty] | 018-0012-R3 | 0 | 331 | 2
[10 empty] | 018-0010-R1 | 0 | 225 | 2
[10 empty] | 018-0010-R2 | 0 | 208 | 2
[10 empty] | 018-0010-R3 | 0 | 456 | 2
[10 empty] | 018-0010-R4 | 0 | 234 | 2
[10 empty] | 018-0008-R1 | 0 | 303 | 2
[10 empty] | 018-0008-R2 | 0 | 271 | 2
[10 empty] | 01N-0422-R5 | 0 | 744 | 2
[10 empty] | 005-0240-R1 | 0 | 120 | 1
[10 empty] | 005-0240-R2 | 0 | 110 | 1
[10 empty] | 005-0240-R3 | 0 | 50 | 1
[10 empty] | 005-0240-R4 | 0 | 60 | 1
[10 empty] | 002-0962/12.85-I | 12850 | 16962 | 2
[10 empty] | 002-0962/12.86-D | 12860 | 16962 | 2
[10 empty] | 002-0946/07.69-I | 7686 | 8815 | 2
[10 empty] | 002-0946/08.82 | 8815 | 9220 | 2
[10 empty] | 002-0946/07.69-D | 7686 | 8815 | 1
[10 empty] | 002-0946/09.22-I | 9220 | 13006 | 2
[10 empty] | 002-0946/13.01-I | 13006 | 15805 | 2
[10 empty] | 002-0946/09.22-D | 9220 | 13024 | 2
[10 empty] | 002-0946/13.02-D | 13024 | 15800 | 2
[10 empty] | 002-0954-R1 | 0 | 155 | 1
[10 empty] | 002-0954-R2 | 0 | 184 | 1
[10 empty] | 002-0955-R1 | 0 | 148 | 1
[10 empty] | 002-0955-R2 | 0 | 305 | 1
[10 empty] | 020-0019-R1 | 0 | 316 | 4
[10 empty] | 020-0019-R4 | 0 | 496 | 3
[10 empty] | 01N-0458-R5 | 0 | 588 | 3
[10 empty] | 01N-0258 | 0 | 2900 | 2
[10 empty] | 01N-0258/02.90-I | 2900 | 3502 | 1
[10 empty] | 01N-0258/02.90-D | 2900 | 3500 | 1
[10 empty] | 025-0023-W | 0 | 128 | 2
[10 empty] | 002-0013-R1 | 0 | 490 | 1
[10 empty] | 01N-0540-I | 0 | 7372 | 2
[10 empty] | 01N-0540-D | 0 | 7387 | 2
[10 empty] | 01N-0539-R3 | 0 | 374 | 2
[10 empty] | 01N-0542-R1 | 0 | 390 | 2
[10 empty] | 01N-0542-R2 | 0 | 499 | 1
[10 empty] | 01N-0542-R3 | 0 | 377 | 2
[10 empty] | 01N-0542-R4 | 0 | 425 | 1
[10 empty] | 01N-0545-R1 | 0 | 306 | 2
[10 empty] | 01N-0545-R2 | 0 | 300 | 3
[10 empty] | 076-0009-R1 | 0 | 339 | 4
[10 empty] | 076-0008-R1 | 0 | 340 | 1
[10 empty] | 076-0008-R2 | 0 | 430 | 3
[10 empty] | 076-0009-R2 | 0 | 432 | 2
[10 empty] | 073-0000-I | 0 | 1337 | 2
[10 empty] | 073-0000-D | 0 | 1327 | 2
[10 empty] | 073-0000-R1 | 0 | 300 | 1
[10 empty] | 076-0010-R1 | 0 | 453 | 1
[10 empty] | 076-0010-R2 | 0 | 358 | 2
[10 empty] | 076-0011-R1 | 0 | 381 | 2
[10 empty] | 076-0011-R2 | 0 | 480 | 2
[10 empty] | 076-0011-I | 0 | 11976 | 2
[10 empty] | 076-0011-D | 0 | 11645 | 2
[10 empty] | 76H-0000/00.70 | 694 | 3092 | 4
[10 empty] | 075-0000-I | 0 | 360 | 2
[10 empty] | 075-0000-D | 0 | 370 | 2
[10 empty] | 01N-0426-R2 | 0 | 320 | 3
[10 empty] | 039-0000-I | 0 | 1077 | 1
[10 empty] | 039-0000-D | 0 | 1086 | 1
[10 empty] | 039-0004 | 0 | 3105 | 2
[10 empty] | 039-0002-W | 0 | 150 | 1
[10 empty] | 039-0000/01.19 | 1186 | 3110 | 2
[10 empty] | 039-0011 | 0 | 5666 | 2
[10 empty] | 059-0024-W | 0 | 233 | 2
[10 empty] | 006-0448 | 0 | 14113 | 2
[10 empty] | 01N-0488-R1 | 0 | 227 | 1
[10 empty] | 01N-0490-R1 | 0 | 285 | 1
[10 empty] | 01N-0491-R1 | 0 | 295 | 1
[10 empty] | 01H-0524-W | 0 | 111 | 2
[10 empty] | 01N-0539-R2 | 0 | 400 | 1
[10 empty] | 01N-0539-W | 0 | 486 | 2
[10 empty] | 01N-0528-R2 | 0 | 500 | 1
[10 empty] | 01N-0534-I | 0 | 4330 | 2
[10 empty] | 01N-0534-D | 0 | 4255 | 2
[10 empty] | 01N-0539-R4 | 0 | 379 | 1
[10 empty] | 01N-0539-R1 | 0 | 421 | 2
[10 empty] | 01N-0528-W | 0 | 618 | 1
[10 empty] | 000-0000 | 0 | 1 | 2
[10 empty] | 01B-0000/00.64 | 638 | 13676 | 2
[10 empty] | 003-0000/01.42 | 1417 | 2834 | 4
[10 empty] | 003-0002-W | 0 | 73 | 2
[10 empty] | 003-0001-W | 0 | 72 | 2
[10 empty] | 01N-0554/03.09-I | 3085 | 3367 | 2
[10 empty] | 01N-0555-W | 0 | 57 | 2
[10 empty] | 01N-0554/01.75-I | 1750 | 3049 | 2
[10 empty] | 01N-0554-W | 0 | 128 | 2
[10 empty] | 01N-0554/03.08-D | 3077 | 3349 | 2
[10 empty] | 01N-0554/01.75-D | 1747 | 3049 | 2
[10 empty] | 01N-0556-W | 0 | 98 | 2
[10 empty] | 01N-0593-R1 | 0 | 99 | 1
[10 empty] | 026-0026/01.17 | 1167 | 8715 | 2
[10 empty] | 026-0027-W | 0 | 51 | 1
[10 empty] | 021-0001-W | 0 | 80 | 1
[10 empty] | 027-0045-W | 0 | 131 | 1
[10 empty] | 027-0031-R1 | 0 | 250 | 1
[10 empty] | 027-0031-R2 | 0 | 250 | 1
[10 empty] | 027-0031-R3 | 0 | 250 | 1
[10 empty] | 027-0031-R4 | 0 | 250 | 1
[10 empty] | 01H-0525/00.86 | 858 | 2124 | 2
[10 empty] | 01H-0525/00.47-I | 470 | 858 | 1
[10 empty] | 01H-0525/00.47-D | 470 | 854 | 1
[10 empty] | 01H-0526-W | 0 | 127 | 1
[10 empty] | 016-0019/02.17 | 2170 | 10628 | 4
[10 empty] | 016-0021-W | 0 | 130 | 2
[10 empty] | 01N-0696-C005 | 0 | 9765 | 3
[10 empty] | 01N-0707 | 0 | 5233 | 3
[10 empty] | 01N-0701-R1 | 0 | 214 | 1
[10 empty] | 01N-0701-R2 | 0 | 443 | 1
[10 empty] | 01N-0701-R3 | 0 | 283 | 1
[10 empty] | 01N-0701-R4 | 0 | 456 | 1
[10 empty] | 01N-0703-R1 | 0 | 364 | 1
[10 empty] | 01N-0703-R2 | 0 | 564 | 1
[10 empty] | 01N-0703-R3 | 0 | 287 | 1
[10 empty] | 01N-0703-R4 | 0 | 546 | 1
[10 empty] | 01N-0706-W | 0 | 165 | 1
[10 empty] | 01N-0712-W | 0 | 165 | 1
[10 empty] | 01N-0695-W | 0 | 165 | 1
[10 empty] | 01N-0713 | 0 | 16337 | 3
[10 empty] | 01N-0712-R2 | 0 | 115 | 1
[10 empty] | 01N-0712-R1 | 0 | 130 | 1
[10 empty] | 005-0137 | 0 | 12080 | 2
[10 empty] | 01N-0706-R2 | 0 | 168 | 1
[10 empty] | 01N-0706-R1 | 0 | 165 | 1
[10 empty] | 002-0184-W | 0 | 220 | 2
[10 empty] | 01N-0695-R2 | 0 | 186 | 1
[10 empty] | 01N-0472-R6 | 0 | 886 | 1
[10 empty] | 016-0022-W | 0 | 221 | 2
[10 empty] | 01N-1030-W | 0 | 65 | 2
[10 empty] | 016-0019-I | 0 | 166 | 2
[10 empty] | 016-0019/00.17 | 168 | 2113 | 4
[10 empty] | 058-0009/00.82 | 822 | 841 | 2
[10 empty] | 058-0011-W | 0 | 164 | 2
[10 empty] | 059-0000/05.64-I | 5647 | 8989 | 1
[10 empty] | 059-0000/08.98 | 8989 | 12795 | 2
[10 empty] | 059-0000/05.64-D | 5647 | 8989 | 1
[10 empty] | 01K-1020-W | 0 | 162 | 2
[10 empty] | 01K-1012/08.15 | 8154 | 9853 | 2
[10 empty] | 035-0308/11.17 | 11170 | 13130 | 2
[10 empty] | 006-0116/05.62-D | 5623 | 5939 | 2
[10 empty] | 006-0116/06.00-D | 6000 | 11479 | 2
[10 empty] | 006-0116/00.81 | 803 | 5517 | 2
[10 empty] | 006-0121-W | 0 | 175 | 2
[10 empty] | 006-0116/05.62-I | 5621 | 11500 | 2
[10 empty] | 006-0116/11.50 | 11500 | 14551 | 5
[10 empty] | 006-0122-W | 0 | 95 | 2
[10 empty] | 006-0445 | 0 | 3437 | 2
[10 empty] | 002-0164-I | 0 | 13654 | 2
[10 empty] | 002-0164-D | 0 | 13644 | 2
[10 empty] | 002-0177-I | 0 | 7350 | 2
[10 empty] | 002-0177-D | 0 | 7356 | 2
[10 empty] | 002-0166-R1 | 0 | 258 | 1
[10 empty] | 002-0166-R2 | 0 | 238 | 1
[10 empty] | 002-0166-R3 | 0 | 278 | 1
[10 empty] | 002-0166-R4 | 0 | 249 | 1
[10 empty] | 002-0167-R1 | 0 | 222 | 1
[10 empty] | 002-0167-R2 | 0 | 340 | 1
[10 empty] | 002-0168-R1 | 0 | 222 | 1
[10 empty] | 002-0168-R2 | 0 | 348 | 1
[10 empty] | 002-0171-R1 | 0 | 321 | 1
[10 empty] | 002-0171-R2 | 0 | 284 | 1
[10 empty] | 002-0171-R3 | 0 | 488 | 1
[10 empty] | 002-0171-R4 | 0 | 394 | 1
[10 empty] | 002-0171-R5 | 0 | 179 | 1
[10 empty] | 002-0164-R1 | 0 | 184 | 1
[10 empty] | 01N-0389-R5 | 0 | 143 | 2
[10 empty] | 01N-0389-W1 | 0 | 95 | 2
[10 empty] | 01N-0389-W2 | 0 | 97 | 2
[10 empty] | 01N-0391-R1 | 0 | 420 | 2
[10 empty] | 01N-0391-R2 | 0 | 447 | 2
[10 empty] | TEL CYCLE TRACK #1 | 0 | 1120 | 1
[10 empty] | TEL CYCLE TRACK #2 | 0 | 5651 | 1
[10 empty] | 002-0184-R1 | 0 | 100 | 2
[10 empty] | 002-0184-R2 | 0 | 80 | 2
[10 empty] | 002-0033-W | 0 | 140 | 2
[10 empty] | 01N-0607-W | 0 | 197 | 1
[10 empty] | 002-0147-W | 0 | 92 | 2
[10 empty] | 002-0148-W | 0 | 88 | 2
[10 empty] | 002-0151-D-CO29 | 0 | 2416 | 2
[10 empty] | 002-0152-R4 | 0 | 183 | 1
[10 empty] | 002-0152-W | 0 | 56 | 1
[10 empty] | 002-0159-W | 0 | 82 | 2
[10 empty] | 002-0158-W | 0 | 103 | 2
[10 empty] | 29A-0000/00.19-I | 189 | 4314 | 2
[10 empty] | 29A-0000/00.16-D | 155 | 4332 | 2
[10 empty] | 29A-0009-W | 0 | 104 | 2
[10 empty] | 29A-0008/02.30 | 2304 | 3317 | 4
[10 empty] | 29A-0008/03.42 | 3418 | 4974 | 4
[10 empty] | 29A-0008/05.02 | 5022 | 6419 | 4
[10 empty] | 036-0000/00.43-I | 427 | 595 | 2
[10 empty] | 036-0001-W | 0 | 206 | 2
[10 empty] | 036-0000/02.18-I | 2183 | 2300 | 2
[10 empty] | 036-0002-W | 0 | 131 | 2
[10 empty] | 036-0000/04.38-I | 4382 | 4532 | 2
[10 empty] | 036-0003-W | 0 | 133 | 2
[10 empty] | 029-0014/01.47 | 1467 | 4883 | 3
[10 empty] | 029-0007-I-CO2 | 0 | 3953 | 4
[10 empty] | 029-0007/04.02-I-CO2 | 4021 | 6437 | 2
[10 empty] | 029-0011-W-CO2 | 0 | 109 | 2
[10 empty] | 029-0007-D-CO2 | 0 | 6396 | 5
[10 empty] | 002-0155-R8 | 0 | 206 | 1
[10 empty] | 002-0155-R9 | 0 | 154 | 6
[10 empty] | 29A-0013 | 0 | 1 | 2
[10 empty] | 015-0000 | 0 | 7430 | 2
[10 empty] | 015-0007-C012 | 0 | 1582 | 2
[10 empty] | 015-0009 | 0 | 17902 | 2
[10 empty] | 015-0027 | 0 | 16701 | 2
[10 empty] | 015-0044 | 0 | 9831 | 2
[10 empty] | 015-0054 | 0 | 15280 | 2
[10 empty] | 015-0069 | 0 | 11892 | 2
[10 empty] | 015-0080-C014 | 0 | 31 | 2
[10 empty] | 015-0081 | 0 | 10602 | 2
[10 empty] | 033-0035-R1 | 0 | 55 | 2
[10 empty] | 01N-0567-R1 | 0 | 1154 | 1
[10 empty] | 01N-0567-R2 | 0 | 893 | 1
[10 empty] | 01N-0571-R1 | 0 | 487 | 1
[10 empty] | 01N-0571-R2 | 0 | 625 | 1
[10 empty] | 01N-0571-R3 | 0 | 523 | 1
[10 empty] | 01N-0571-R4 | 0 | 649 | 1
[10 empty] | 01N-0576-R1 | 0 | 880 | 1
[10 empty] | 01N-0576-R2 | 0 | 566 | 1
[10 empty] | 01N-0574-I | 0 | 2932 | 2
[10 empty] | 01N-0574-D | 0 | 2932 | 2
[10 empty] | 01S-0000/01.15 | 1150 | 17652 | 3
[10 empty] | 01S-0001-W | 0 | 430 | 1
[10 empty] | 003-0065-W | 0 | 159 | 1
[10 empty] | 01S-0323-R3 | 0 | 410 | 1
[10 empty] | 01S-0323-R4 | 0 | 380 | 1
[10 empty] | 01N-1011-I | 0 | 19030 | 2
[10 empty] | 01N-1011-D | 0 | 19032 | 2
[10 empty] | 01N-1012-R1 | 0 | 391 | 2
[10 empty] | 01N-1012-R2 | 0 | 458 | 2
[10 empty] | 01N-1017-R1 | 0 | 394 | 2
[10 empty] | 01N-1017-R4 | 0 | 554 | 2
[10 empty] | 01N-1017-R2 | 0 | 540 | 2
[10 empty] | 01N-1017-R3 | 0 | 484 | 2
[10 empty] | 01N-1023-R1 | 0 | 440 | 2
[10 empty] | 01N-1023-R4 | 0 | 464 | 2
[10 empty] | 01N-1023-R3 | 0 | 402 | 2
[10 empty] | 01N-1023-R2 | 0 | 431 | 2
[10 empty] | 01N-1026-R1 | 0 | 389 | 2
[10 empty] | 01N-1026-R2 | 0 | 471 | 2
[10 empty] | 006-0991-W | 0 | 152 | 2
[10 empty] | 006-0993-W | 0 | 157 | 2
[10 empty] | 006-0994-W | 0 | 124 | 2
[10 empty] | 058-0000/02.88-I | 2870 | 3465 | 1
[10 empty] | 058-0000/03.47 | 3465 | 8979 | 2
[10 empty] | 058-0000/02.88-D | 2870 | 3465 | 1
[10 empty] | 038-0147/11.77 | 11770 | 13840 | 2
[10 empty] | 01S-0344-D | 0 | 2756 | 3
[10 empty] | 01S-0333/04.18-I | 4175 | 5590 | 2
[10 empty] | 01S-0333/04.18-D | 4175 | 5600 | 2
[10 empty] | 012-0010 | 0 | 6622 | 2
[10 empty] | 012-0009-C015 | 0 | 1577 | 2
[10 empty] | 014-0012 | 0 | 4260 | 2
[10 empty] | 014-0011-C015 | 0 | 32 | 2
[10 empty] | 01N-0272-C015 | 0 | 2269 | 2
[10 empty] | 006-0983/11.05 | 11052 | 11972 | 2
[10 empty] | 006-0983/10.64 | 10645 | 11015 | 2
[10 empty] | 006-0983/8.10 | 8105 | 10584 | 2
[10 empty] | M2PP CYCLEWAY | 0 | 16073 | 2
[10 empty] | 003-0009-W | 0 | 172 | 1
[10 empty] | 016-0008-R9 | 0 | 673 | 2
[10 empty] | 020-0019-R2 | 0 | 294 | 2
[10 empty] | 020-0019-R3 | 0 | 278 | 3
[10 empty] | 003-0298 | 0 | 11014 | 3
[10 empty] | 01S-0709-I | 0 | 1810 | 4
[10 empty] | 01S-0709-D | 0 | 1810 | 3
[10 empty] | 20A-0002-R1 | 0 | 369 | 2
[10 empty] | 20A-0002-R2 | 0 | 339 | 2
[10 empty] | 20A-0002-R3 | 0 | 405 | 2
[10 empty] | 20A-0002-R4 | 0 | 332 | 2
[10 empty] | 002-0962-R1 | 0 | 298 | 1
[10 empty] | 002-0962-R2 | 0 | 59 | 1
[10 empty] | 002-0962-R3 | 0 | 32 | 1
[10 empty] | 002-0962-R4 | 0 | 450 | 1
[10 empty] | 002-0962-R5 | 0 | 365 | 1
[10 empty] | 002-0962-R6 | 0 | 365 | 1
[10 empty] | 058-0000-I | 0 | 2000 | 2
[10 empty] | 058-0000-D | 0 | 2850 | 2
[10 empty] | 002-0962-W | 0 | 230 | 1
[10 empty] | 002-0159-R6 | 0 | 71 | 2
[10 empty] | 002-0159-R4 | 0 | 300 | 2
[10 empty] | SADDLE ROAD | 0 | 2070 | 3
[10 empty] | CAMBRIDGE AVE_A | 0 | 756 | 2
[10 empty] | MULGRAVE AVE_A | 166 | 429 | 3
[10 empty] | SADDLE RD_A | 0 | 1182 | 2
[10 empty] | SALISBURY ST_A | 0 | 1236 | 3
[10 empty] | OXFORD RD | 2577 | 3239 | 2
[10 empty] | SADDLE RD | 0 | 7775 | 3
[10 empty] | WOODLANDS RD | 0 | 1691 | 2
[10 empty] | MAKOMAKO RD | 0 | 10582 | 3
[10 empty] | MANGAHAO RD | 0 | 983 | 2
[10 empty] | PAHIATUA TRACK RD | 0 | 2630 | 3
[10 empty] | PAHIATUA-MANGAHAO RD | 0 | 5592 | 2
[10 empty] | PAHIATUA TRK | 0 | 8738 | 2
[10 empty] | 01S-0333-I | 0 | 1354 | 2
[10 empty] | 01S-0330-R1 | 0 | 690 | 2
[10 empty] | 01S-0330-R2 | 0 | 816 | 1
[10 empty] | 01S-0333-R1 | 0 | 345 | 1
[10 empty] | 01S-0333-R2 | 0 | 413 | 1
[10 empty] | 01S-0333-D | 0 | 1350 | 2
[10 empty] | JOHNS ROAD CUL DE SAC TO BE REVOKED | 1660 | 2360 | 2
[10 empty] | 01J-0000 | 0 | 1660 | 2
[10 empty] | 051-0013/05.24 | 5242 | 8137 | 2
[10 empty] | 051-0018-W | 0 | 203 | 1
[10 empty] | 01S-0333/01.41-I | 1408 | 4132 | 2
[10 empty] | 01S-0333/01.40-D | 1402 | 4129 | 2
[10 empty] | 01S-0335-R1 | 0 | 204 | 2
[10 empty] | 01S-0336-R1 | 0 | 323 | 2
[10 empty] | 01S-0336-R2 | 0 | 249 | 2
[10 empty] | 01S-0336-R3 | 0 | 276 | 2
[10 empty] | 01S-0334-W | 0 | 142 | 2
[10 empty] | 01S-0338-W | 0 | 143 | 2
[10 empty] | 01N-0502-R1 | 0 | 407 | 1
[10 empty] | 01N-0502-R2 | 0 | 436 | 1
[10 empty] | 01N-0502-R3 | 0 | 557 | 1
[10 empty] | 01N-0502-R4 | 0 | 505 | 1
[10 empty] | 01N-0504-R1 | 0 | 330 | 1
[10 empty] | 01N-0504-R2 | 0 | 820 | 2
[10 empty] | 01N-0504-R3 | 0 | 284 | 1
[10 empty] | 01N-0502-R5 | 0 | 279 | 2
[10 empty] | 01N-0504-R4 | 0 | 98 | 2
[10 empty] | 01N-0504-W | 0 | 105 | 1
[10 empty] | ABERFELDY STREET | 0 | 270 | 2
[10 empty] | 01S-0709-R1 | 0 | 75 | 2
[10 empty] | 01N-0594 | 0 | 76 | 2
[10 empty] | 029-0061/13.24 | 13240 | 13381 | 2
[10 empty] | 003-0010/0.06 | 56 | 5644 | 4
[10 empty] | 01S-0706-R1 | 0 | 52 | 3
[10 empty] | 005-0054-W | 0 | 171 | 1
[10 empty] | 01N-1047-I | 0 | 10513 | 3
[10 empty] | 01N-1047-D | 0 | 10543 | 3
[10 empty] | 01N-1032-R1 | 0 | 314 | 1
[10 empty] | 01N-1032-R2 | 0 | 420 | 2
[10 empty] | 01N-1032-R4 | 0 | 122 | 2
[10 empty] | 01N-1047-R1 | 0 | 380 | 1
[10 empty] | 01N-1047-R2 | 0 | 481 | 1
[10 empty] | 01N-1047-R3 | 0 | 427 | 1
[10 empty] | 01N-1047-R4 | 0 | 488 | 1
[10 empty] | 058-0009 | 0 | 164 | 2
[10 empty] | 058-0009/00.21-I | 214 | 305 | 1
[10 empty] | 058-0009/00.21-D | 214 | 304 | 1
[10 empty] | 058-0009/00.37-I | 377 | 772 | 1
[10 empty] | 058-0009/00.37-D | 377 | 772 | 2
[10 empty] | 058-0009-W | 0 | 142 | 1
[10 empty] | 058-0010-W | 0 | 141 | 2
[10 empty] | 01N-1050-R1 | 0 | 468 | 1
[10 empty] | 01N-1050-R2 | 0 | 384 | 1
[10 empty] | 01N-1050-R3 | 0 | 427 | 1
[10 empty] | 01N-1050-R4 | 0 | 489 | 1
[10 empty] | 01N-1056-R1 | 0 | 396 | 1
[10 empty] | 01N-1056-R2 | 0 | 347 | 1
[10 empty] | 01N-1056-R4 | 0 | 1043 | 2
[10 empty] | 01N-1056-R3 | 0 | 655 | 1
[10 empty] | 002-0646-W | 0 | 220 | 2
[10 empty] | 067-0005 | 0 | 9778 | 2
[10 empty] | BALLANCE VALLEY RD | 0 | 8865 | 2
[10 empty] | GORGE RD | 0 | 5325 | 2
[10 empty] | CYCLEWAY SH29A - OHAUITI RD TO POIKE RD | 0 | 2027 | 1
[10 empty] | CYCLEWAY - POIKE ROAD - SH29A INTERSECTION | 0 | 243 | 1
[10 empty] | 01S-0339-R2 | 0 | 141 | 1
[10 empty] | 01S-0339-R1 | 0 | 275 | 1
[10 empty] | 01S-0340-R2 | 0 | 343 | 1
[10 empty] | 01S-0340-R3 | 0 | 450 | 1
[10 empty] | 01S-0340-R4 | 0 | 413 | 1
[10 empty] | 01S-0341-R1 | 0 | 379 | 1
[10 empty] | 01S-0341-R2 | 0 | 361 | 1
[10 empty] | 01S-0341-R3 | 0 | 273 | 1
[10 empty] | 01S-0341-R4 | 0 | 260 | 1
[10 empty] | 01S-0339-W | 0 | 182 | 2
[10 empty] | 050-0003-R1 | 0 | 171 | 2
[10 empty] | 050-0003-R2 | 0 | 193 | 2
[10 empty] | 51A-0000 | 0 | 61 | 2
[10 empty] | 01S-0333/05.65-I | 5650 | 10580 | 2
[10 empty] | 01S-0333/05.65-D | 5650 | 10580 | 2
[10 empty] | 01N-1067-R4 | 0 | 230 | 1
[10 empty] | 01N-0263-R1 | 0 | 70 | 1
[10 empty] | 01N-0263-W | 0 | 115 | 2
[10 empty] | 01N-0513-I | 0 | 15303 | 2
[10 empty] | 01N-0513-D | 0 | 15300 | 2
[10 empty] | 01N-0528-I | 0 | 6041 | 2
[10 empty] | 01N-0528-D | 0 | 6046 | 2
[10 empty] | 01N-0514-R1 | 0 | 945 | 1
[10 empty] | 01N-0514-R2 | 0 | 647 | 1
[10 empty] | 01N-0528-R1 | 0 | 281 | 1
[10 empty] | 01N-0528-R4 | 0 | 336 | 1
[10 empty] | 002-0443/03.01 | 3010 | 18081 | 2
[10 empty] | 002-0446-W | 0 | 170 | 2
[10 empty] | 01N-1080-W | 0 | 268 | 2
[10 empty] | 01N-1079-W | 0 | 271 | 2
[10 empty] | 01N-1076/03.11-I | 3114 | 3543 | 2
[10 empty] | 01N-1076/3.21-D | 3210 | 3647 | 2
[10 empty] | 002-0883-W | 0 | 165 | 2
[10 empty] | 002-0658-W | 0 | 224 | 2
[10 empty] | 002-0144-W | 0 | 116 | 2
[10 empty] | 029-0018-R1 | 0 | 115 | 1
[10 empty] | 002-0130/00.61-I | 610 | 1517 | 2
[10 empty] | 002-0130/01.51 | 1517 | 13917 | 3
[10 empty] | 002-0130/00.61-D | 610 | 1517 | 1
[10 empty] | 002-0130/13.91-I | 13917 | 14193 | 1
[10 empty] | 002-0130/14.55 | 14546 | 16497 | 2
[10 empty] | 002-0130/13.91-D | 13917 | 14193 | 1
[10 empty] | 29A-0000/04.34 | 4314 | 6906 | 2
[10 empty] | EDENDALE START CONSTRUCTION TO FERRY ROAD | 11331 | 13248 | 2
[10 empty] | 01S-0886 | 0 | 545 | 2
[10 empty] | 01S-0886/00.67 | 665 | 14630 | 3
[10 empty] | 01S-0887-R1 | 0 | 90 | 2
[10 empty] | 01S-0887-R2 | 0 | 50 | 2
[10 empty] | 01S-0887-W | 0 | 181 | 2
[10 empty] | 029-0014/04.88-I | 4883 | 5196 | 2
[10 empty] | 029-0014/04.88-D | 4883 | 5196 | 2
[10 empty] | 01N-0528-R3 | 0 | 315 | 1
[10 empty] | 01N-0524-R1 | 0 | 228 | 1
[10 empty] | 0524-I-CYCLE TRAIL | 0 | 841 | 1
[10 empty] | 002-0670-W | 0 | 234 | 1
[10 empty] | 002-0130/14.25-I | 14252 | 14546 | 1
[10 empty] | 002-0130/14.25-D | 14252 | 14546 | 1
[10 empty] | 006-0993-R1 | 0 | 220 | 1
[10 empty] | 002-0678-W | 0 | 177 | 1
[10 empty] | 002-0146/01.13-I | 1128 | 1249 | 2
[10 empty] | 002-0146/01.13-D | 1128 | 1249 | 2
[10 empty] | 29A-0008/02.06-I | 2060 | 2240 | 2
[10 empty] | 29A-0008/02.06-D | 2060 | 2240 | 2
[10 empty] | 036-0000/00.59 | 595 | 1952 | 2
[10 empty] | 036-0000/00.43-D | 427 | 595 | 2
[10 empty] | 036-0000/01.95-I | 1952 | 2120 | 2
[10 empty] | 036-0000/01.95-D | 1952 | 2120 | 2
[10 empty] | 036-0000/04.38-D | 4382 | 4532 | 2
[10 empty] | 036-0000/02.30 | 2300 | 4311 | 2
[10 empty] | 036-0000/02.18-D | 2183 | 2300 | 2
[10 empty] | 033-0017/18.45-I | 18455 | 18665 | 2
[10 empty] | 033-0017/18.45-D | 18455 | 18655 | 2
[10 empty] | 002-0185/00.22 | 221 | 19951 | 2
[10 empty] | 002-0185-D | 0 | 221 | 2
[10 empty] | 029-0019/00.14 | 140 | 1727 | 3
[10 empty] | 029-0019-D | 0 | 140 | 2
[10 empty] | 002-0658/12.49 | 12490 | 16429 | 2
[10 empty] | 002-0678 | 0 | 12538 | 3
[10 empty] | 002-0638/05.13-I | 5131 | 9054 | 2
[10 empty] | 002-0638/05.13-D | 5131 | 9054 | 2
[10 empty] | 016-0031 | 0 | 5773 | 2
[10 empty] | 016-0030-W | 0 | 88 | 1
[10 empty] | 01P-0995/03.07-I | 3073 | 15300 | 2
[10 empty] | 01P-0995/03.07-D | 3073 | 15298 | 2
[10 empty] | 01P-0999-R1 | 0 | 410 | 1
[10 empty] | 01P-0999-R2 | 0 | 580 | 1
[10 empty] | 01P-1003-R1 | 0 | 445 | 1
[10 empty] | 01P-1003-R2 | 0 | 425 | 1
[10 empty] | 002-0707/07.42-I | 7421 | 10855 | 1
[10 empty] | 002-0707/10.85 | 10855 | 13114 | 2
[10 empty] | 002-0707/07.42-D | 7421 | 10855 | 2
[10 empty] | 002-0648-C050-W | 0 | 236 | 2
[10 empty] | 002-0651-C050-W | 0 | 176 | 2
[10 empty] | 002-0663-W | 0 | 204 | 2
[10 empty] | 002-0665-W | 0 | 204 | 2
[10 empty] | 002-0667-W | 0 | 207 | 2
[10 empty] | 002-0646/00.76 | 765 | 1404 | 2
[10 empty] | 002-0646/01.40-I | 1404 | 2340 | 2
[10 empty] | 002-0646-D | 0 | 765 | 1
[10 empty] | 002-0646/01.40-D | 1404 | 2340 | 1
[10 empty] | 002-0648-C050-D | 0 | 1565 | 2
[10 empty] | 002-0651/00.79-C050-D | 787 | 3396 | 1
[10 empty] | 002-0651/03.90-C050-D | 3900 | 4680 | 1
[10 empty] | 002-0658-D | 0 | 713 | 2
[10 empty] | 002-0658/00.98-D | 978 | 3183 | 1
[10 empty] | 002-0658/03.72-D | 3724 | 5085 | 2
[10 empty] | 002-0658/05.17-D | 5172 | 7437 | 2
[10 empty] | 002-0658/07.53-D | 7535 | 9253 | 2
[10 empty] | 002-0658/09.33-D | 9330 | 12364 | 2
[10 empty] | 074-0000-I | 0 | 6887 | 2
[10 empty] | 074-0000-D | 0 | 7072 | 2
[10 empty] | 074-0003-R1 | 0 | 398 | 1
[10 empty] | 074-0003-R2 | 0 | 406 | 2
[10 empty] | 074-0007-R1 | 0 | 460 | 1
[10 empty] | 074-0007-R2 | 0 | 429 | 1
[10 empty] | 074-0007-R3 | 0 | 333 | 1
[10 empty] | 002-0648-C050-I | 0 | 1565 | 2
[10 empty] | 002-0651 | 0 | 787 | 2
[10 empty] | 002-0651/00.79-C050-I | 787 | 3396 | 1
[10 empty] | 002-0651/03.40-C050 | 3396 | 3900 | 2
[10 empty] | 002-0651/03.90-C050-I | 3900 | 4680 | 2
[10 empty] | 002-0651/04.68-C050 | 4680 | 5234 | 2
[10 empty] | 002-0651/05.23-C050-I | 5234 | 6445 | 2
[10 empty] | 002-0658/00.71 | 713 | 978 | 2
[10 empty] | 002-0658/00.98-I | 978 | 3183 | 1
[10 empty] | 002-0658/03.18 | 3183 | 3724 | 2
[10 empty] | 002-0658/03.72-I | 3724 | 5085 | 1
[10 empty] | 002-0658/05.17-I | 5172 | 7437 | 2
[10 empty] | 002-0658/07.53-I | 7535 | 9253 | 1
[10 empty] | 002-0658/09.33-I | 9330 | 12364 | 2
[10 empty] | 084-0000/01.29 | 1285 | 2593 | 2
[10 empty] | 084-0001-W | 0 | 135 | 1
[10 empty] | 084-0003-W | 0 | 87 | 1
[10 empty] | 01N-0954/11.26-I | 11260 | 13052 | 1
[10 empty] | MASTERTON LEFTOVER 275 - 338 | 275 | 338 | 2
[10 empty] | 01N-0954/11.26-D | 11260 | 13052 | 1
[10 empty] | 01N-0967-I | 0 | 210 | 1
[10 empty] | 01N-0967-D | 0 | 210 | 1
[10 empty] | 76H-0000-W | 0 | 155 | 2
[10 empty] | 76H-0000-D | 0 | 696 | 2
[10 empty] | 76H-0000-I | 0 | 694 | 2
[10 empty] | 076-0015-R1 | 0 | 378 | 2
[10 empty] | 076-0015-R2 | 0 | 559 | 2
[10 empty] | 076-0017-R1 | 0 | 410 | 2
[10 empty] | 076-0017-R2 | 0 | 602 | 2
[10 empty] | 076-0017-R3 | 0 | 686 | 2
[10 empty] | 076-0017-R4 | 0 | 452 | 2
[10 empty] | 01S-0350/02.47-D | 2466 | 2556 | 2
[10 empty] | 01S-0350/02.47-I | 2466 | 2556 | 2
[10 empty] | 01S-0353-W | 0 | 180 | 2
[10 empty] | 01S-0350/02.63-D | 2630 | 3756 | 2
[10 empty] | 01S-0350/02.63-I | 2630 | 4094 | 2
[10 empty] | 01S-0350/03.76-D | 3756 | 7142 | 2
[10 empty] | 01S-0350/04.09-I | 4094 | 7156 | 2
[10 empty] | 01S-0363-R1 | 0 | 325 | 2
[10 empty] | 01S-0363-R2 | 0 | 307 | 2
[10 empty] | 01S-0365-D | 0 | 2330 | 2
[10 empty] | 01S-0365-I | 0 | 2330 | 2
[10 empty] | 01S-0365-R1 | 0 | 514 | 2
[10 empty] | 01S-0365-R2 | 0 | 590 | 2
[10 empty] | 01S-0365-R3 | 0 | 560 | 2
[10 empty] | 01S-0365-R4 | 0 | 557 | 2
[10 empty] | 74M-0002/04.17-I | 4169 | 4911 | 2
[10 empty] | 74M-0002/04.17-D | 4169 | 4915 | 2
[10 empty] | 074-0007-W1 | 0 | 190 | 2
[10 empty] | 074-0007-W2 | 0 | 177 | 2
[10 empty] | 074-0007-I | 0 | 83 | 2
[10 empty] | 074-0007-D | 0 | 83 | 2
[10 empty] | 074-0007/00.16-I | 164 | 2979 | 5
[10 empty] | 074-0007/00.13-D | 128 | 2101 | 2
[10 empty] | 01N-0486/16.30-D | 16298 | 17660 | 2
[10 empty] | 026-0001/2.24 | 2236 | 4618 | 2
[10 empty] | 026-0003-W | 0 | 152 | 1
[10 empty] | 01N-1032-W | 0 | 99 | 1
[10 empty] | 01N-1050-R5 | 0 | 75 | 2
[10 empty] | 01N-1049-W | 0 | 99 | 2
[10 empty] | 01N-1050-W | 0 | 116 | 2
[10 empty] | 01N-1050-R6 | 0 | 43 | 2
[10 empty] | 01N-1056-W | 0 | 99 | 2
[10 empty] | SHARED PATH TE AWA RIVER TRAIL | 0 | 1190 | 1
[10 empty] | SHARED PATH GREAT SOUTH RD NORTHWEST | 0 | 175 | 1
[10 empty] | SHARED PATH MANGAHARAKEKE DR OVERPASS | 0 | 155 | 1
[10 empty] | SHARED PATH MANGAHARAKEKE DR WESTERN | 0 | 745 | 1
[10 empty] | SHARED PATH TE RAPA RD SOUTHEAST | 0 | 115 | 1
[10 empty] | SHARED PATH TE RAPA WESTERN | 0 | 3330 | 1
[10 empty] | SHARED PATH TE RAPA EASTERN | 0 | 840 | 1
[10 empty] | SHARED PATH OAKLEA LANE | 0 | 290 | 1
[10 empty] | SHARED PATH PENCARROW ROAD | 0 | 105 | 1
[10 empty] | SHARED PATH STRAWBERRY FIELDS LANE | 0 | 895 | 1
[10 empty] | WEX-0528-I | 4884 | 18142 | 2
[10 empty] | WEX-0528-D | 5475 | 18149 | 2
[10 empty] | WEX-0546-I | 0 | 10788 | 2
[10 empty] | WEX-0546-D | 0 | 10795 | 2
[10 empty] | WEX-0536-R1 | 0 | 505 | 2
[10 empty] | WEX-0536-R2 | 0 | 926 | 2
[10 empty] | WEX-0539-R1 | 0 | 304 | 2
[10 empty] | WEX-0539-R2 | 0 | 483 | 2
[10 empty] | WEX-0539-R3 | 0 | 323 | 2
[10 empty] | WEX-0539-R4 | 0 | 451 | 2
[10 empty] | WEX-0548-R1 | 0 | 464 | 2
[10 empty] | WEX-0548-R2 | 0 | 436 | 2
[10 empty] | WEX-0548-R3 | 0 | 418 | 2
[10 empty] | WEX-0548-R4 | 0 | 455 | 2
[10 empty] | WEX-0552-R1 | 0 | 288 | 2
[10 empty] | WEX-0552-R2 | 0 | 422 | 2
[10 empty] | WEX-0552-R3 | 0 | 397 | 2
[10 empty] | WEX-0552-R4 | 0 | 510 | 2
[10 empty] | 003-0000/02.97 | 2966 | 5314 | 3
[10 empty] | 01N-0486/16.35-I | 16356 | 17738 | 2
[10 empty] | 003-0003-W | 0 | 200 | 2
[10 empty] | 023-0032/10.62 | 10620 | 11710 | 2
[10 empty] | 01N-0210-W | 0 | 84 | 1
[10 empty] | 010-0006-W | 0 | 172 | 2
[10 empty] | 010-0017/03.51 | 3512 | 16273 | 2
[10 empty] | 010-0020-W | 0 | 118 | 1
[10 empty] | HAYWARDS SB CYCLEWAY | 0 | 500 | 2
[10 empty] | 058-PCCREVOKE | 0 | 61 | 2
[10 empty] | 058-0012 | 0 | 5050 | 2
[10 empty] | 059-0000 | 0 | 140 | 2
[10 empty] | 059-0000/0.140 | 140 | 5647 | 2
[10 empty] | 01N-1058-I | 0 | 2578 | 2
[10 empty] | 01N-1058-D | 0 | 2578 | 2
[10 empty] | 01N-1030-I | 0 | 17281 | 3
[10 empty] | 01N-1030-D | 0 | 17277 | 3
[10 empty] | 01N-0995/12.79 | 12791 | 15441 | 2
[10 empty] | 01P-0995/12.79 | 12791 | 16065 | 3
[10 empty] | 058-0000/02.00-I | 2000 | 2870 | 2

## Roadname
Start here (1) | TOC and JM | Auckland_Harbour_Bridge | AUCK_ALLIANCE | BOP_EAST | BOP_WEST | CENTRAL_WAIKATO | COASTAL_OTAGO | EAST_WAIKATO | HAWKES_BAY | MANAWATU_WHANGANUI | MARLBOROUGH | MILFORD | NELSON_TASMAN | NORTH_CANTERBURY | NORTHLAND | OTAGO_CENTRAL | SOUTH_CANTERBURY | SOUTHLAND | TAIRAWHITI_ROADS_NORTHERN | TAIRAWHITI_ROADS_WESTERN | TARANAKI | TRANSMISSION_GULLY | WELLINGTON | WEST_COAST | WEST_WAIKATO | NULL
|  |  | 002 | 002 | 002 | 004 | 008 | 002 | 002 | 002 | 006 | 094 | 006 | 007 | 010 | 006 | 008 | 006 | 035 | 002 | 003 | 01N | 002 | 006 | 003 | 000
|  |  | 016 | 005 | 029 | 005 | 01S | 024 | 005 | 003 | 01S | 095 | 060 | 01J | 011 | 008 | 01S | 01S |  | 035 | 004 | 058 | 01K | 007 | 01B | 038
|  |  | 018 | 030 | 033 | 01N | 083 | 025 | 038 | 004 | 062 |  | 063 | 01S | 012 | 06A | 077 | 093 |  |  | 03A | 059 | 01N | 065 | 01H | 086
|  |  | 01N | 033 | 036 | 027 | 085 | 026 | 050 | 01N | 063 |  | 065 | 071 | 014 | 084 | 078 | 094 |  |  | 043 |  | 01P | 067 | 01N | 097
|  |  | 020 | 034 | 29A | 028 | 086 | 027 | 051 | 054 |  |  |  | 073 | 015 | 085 | 079 | 095 |  |  | 044 |  | 053 | 069 | 021 | 74A
|  |  | 022 | 035 | 99CYCLETRK | 030 | 087 | 029 | 51A | 056 |  |  |  | 074 | 016 | 08A | 080 | 096 |  |  | 045 |  | 058 | 073 | 023 | HAY
|  |  | 20A | 036 | 99HEWLETTS | 032 | 088 | 25A |  | 057 |  |  |  | 075 | 01N | 08B | 082 | 097 |  |  |  |  | 059 | 67A | 026
|  |  | 20B | 038 |  | 041 | 090 |  |  | 99BALLANCE VALLEY RD |  |  |  | 076 |  |  |  | 098 |  |  |  |  | 99M2PP CYCLEWAY |  | 029
|  |  |  | 30A |  | 046 | 99ABERFELDY |  |  | 99CAMBRIDGE AVE_A |  |  |  | 077 |  |  |  | 099 |  |  |  |  | 99MASTERTON |  | 030
[6 empty] | 047 |  |  |  | 99GORGE RD |  |  |  | 07A |  |  |  | 99EDENDALE | [6 empty] | 031
[6 empty] | 048 |  |  |  | 99MAKOMAKO RD |  |  |  | 74A | [10 empty] | 037
[6 empty] | 049 |  |  |  | 99MANGAHAO RD |  |  |  | 74M | [10 empty] | 039
[10 empty] | 99MULGRAVE AVE_A |  |  |  | 76H | [10 empty] | 052
[10 empty] | 99OXFORD RD |  |  |  | 99JOHNS RD | [10 empty] | 99SHARED PATH
[10 empty] | 99PAHIATUA TRACK RD | [14 empty] | 99WEX
99PAHIATUA-MANGAHAO RD
99PAHIATUA TRK
99SADDLE ROAD
99SADDLE RD_A
99SADDLE RD
99SALISBURY ST_A
99WOODLANDS RD
|  |  | 002AUCK_ALLIANCE | 002EAST_WAIKATO | 002BOP_WEST | 002BOP_EAST | 002TAIRAWHITI_ROADS_WESTERN | 002HAWKES_BAY | 002MANAWATU_WHANGANUI | 002WELLINGTON | 003WEST_WAIKATO | 003TARANAKI | 003MANAWATU_WHANGANUI | 004TARANAKI | 004CENTRAL_WAIKATO | 004MANAWATU_WHANGANUI | 005CENTRAL_WAIKATO | 005BOP_EAST | 005HAWKES_BAY | 006MARLBOROUGH | 006NELSON_TASMAN | 006WEST_COAST | 006OTAGO_CENTRAL | 006SOUTHLAND | 007NORTH_CANTERBURY | 007WEST_COAST | 008SOUTH_CANTERBURY | 008COASTAL_OTAGO | 008OTAGO_CENTRAL | 010NORTHLAND | 011NORTHLAND | 012NORTHLAND | 014NORTHLAND | 015NORTHLAND | 016AUCK_ALLIANCE | 016NORTHLAND | 018AUCK_ALLIANCE | 01BWEST_WAIKATO | 01HWEST_WAIKATO | 01JNORTH_CANTERBURY | 01KWELLINGTON | 01NNORTHLAND | 01NAUCK_ALLIANCE | 01NWEST_WAIKATO | 01NCENTRAL_WAIKATO | 01NMANAWATU-WHANGANUI | 01NWELLINGTON | 01PWELLINGTON | 01SMARLBOROUGH | 01SNORTH_CANTERBURY | 01SSOUTH_CANTERBURY | 01SCOASTAL_OTAGO | 01SSOUTHLAND | 020AUCK_ALLIANCE | 021WEST_WAIKATO | 022AUCK_ALLIANCE | 023WEST_WAIKATO | 024EAST_WAIKATO | 025EAST_WAIKATO | 026EAST_WAIKATO | 026WEST_WAIKATO | 027EAST_WAIKATO | 027CENTRAL_WAIKATO | 028CENTRAL_WAIKATO | 029BOP_WEST | 029EAST_WAIKATO | 029WEST_WAIKATO | 030WEST_WAIKATO | 030CENTRAL_WAIKATO | 030BOP_EAST | 031WEST_WAIKATO | 032CENTRAL_WAIKATO | 033BOP_EAST | 033BOP_WEST | 034BOP_EAST | 035BOP_EAST | 035TAIRAWHITI_ROADS_NORTHERN | 035TAIRAWHITI_ROADS_WESTERN | 036BOP_WEST | 036BOP_EAST | 037WEST_WAIKATO | 038BOP_EAST | 038HAWKES_BAY | 039WEST_WAIKATO | 03ATARANAKI | 041CENTRAL_WAIKATO | 043TARANAKI | 044TARANAKI | 045TARANAKI | 046CENTRAL_WAIKATO | 047CENTRAL_WAIKATO | 048CENTRAL_WAIKATO | 049CENTRAL_WAIKATO | 050HAWKES_BAY | 051HAWKES_BAY | 51AHAWKES_BAY | 052WEST_WAIKATO | 053WELLINGTON | 054MANAWATU_WHANGANUI | 056MANAWATU_WHANGANUI | 057MANAWATU_WHANGANUI | 058WELLINGTON | 059WELLINGTON | 060NELSON_TASMAN | 062MARLBOROUGH | 063MARLBOROUGH | 063NELSON_TASMAN | 065NELSON_TASMAN | 065WEST_COAST | 067WEST_COAST | 069WEST_COAST | 06AOTAGO_CENTRAL | 071NORTH_CANTERBURY | 073NORTH_CANTERBURY | 073WEST_COAST | 074NORTH_CANTERBURY | 075NORTH_CANTERBURY | 076NORTH_CANTERBURY | 077SOUTH_CANTERBURY | 077NORTH_CANTERBURY | 078SOUTH_CANTERBURY | 079SOUTH_CANTERBURY | 07ANORTH_CANTERBURY | 080SOUTH_CANTERBURY | 082SOUTH_CANTERBURY | 083COASTAL_OTAGO | 084OTAGO_CENTRAL | 085COASTAL_OTAGO | 085OTAGO_CENTRAL | 086COASTAL_OTAGO | 087COASTAL_OTAGO | 088COASTAL_OTAGO | 08AOTAGO_CENTRAL | 08BOTAGO_CENTRAL | 090COASTAL_OTAGO | 093SOUTHLAND | 094SOUTHLAND | 094MILFORD | 095SOUTHLAND | 095MILFORD | 096SOUTHLAND | 097SOUTHLAND | 098SOUTHLAND | 099SOUTHLAND | 20AAUCK_ALLIANCE | 20BAUCK_ALLIANCE | 25AEAST_WAIKATO | 29ABOP_WEST | 30ABOP_EAST | 67AWEST_COAST | 74ANORTH_CANTERBURY | 74MNORTH_CANTERBURY | 76HNORTH_CANTERBURY | 99TRANSMISSION_GULLY | 99ABERFELDYCOASTAL OTAGO | 99CAMBRIDGEMANAWATU_WHANGANUI | 99CYCLETRKBOP_WEST | 99HEWLETTSBOP_WEST | 99JOHNSRDNORTH_CANTERBURY | 99MAKOMAKOMANAWATU_WHANGANUI | 99MULGRAVEMANAWATU_WHANGANUI | 99OXFORDMANAWATU_WHANGANUI | 99PAHTRKMANAWATU_WHANGANUI | 99SADDLEMANAWATU_WHANGANUI | 99SALSBURYMANAWATU_WHANGANUI | 99WOODLANDSMANAWATU_WHANGANUI | 99EDENDALE_SOUTHLAND | 99SHAREDPATH_WEST_WAIKATO | 99WEX_WEST_WAIKATO | 99BALANCEMANAWATU_WHANGANUI | 99GORGEMANAWATU_WHANGANUI | 99M2PPCYCLEWELLINGTON | 99MASTERTONLEFTOVER_WELLINGTON
|  |  | 002-0000 | 002-0033-W | 002-0100 | 002-0209 | 002-0361 | 002-0483 | 002-0751 | 002-0858 | 003-0000 | 003-0088 | 003-0371 | 004-0000 | 004-0077 | 004-0140 | 005-0000 | 005-0029 | 005-0190 | 006-0000 | 006-0073 | 006-0269 | 006-0814 | 006-1024/12.95 | 007-0000 | 007-0131 | 008-0000 | 008-0159 | 008-0217 | 010-0000 | 011-0000 | 012-0000 | 014-0000 | 015-0000 | 016-0000 | 016-0019/00.17 | 018-0000-D | 01B-0000/00.64 | 01H-0504/10.16 | 01J-0000 | 01K-1012 | 01N-0000 | 01N-0373/9.56-D | 01N-0486/16.30-D | 01N-0594/00.08 | 01N-0828 | 01N-0985 | 01P-0995/03.07-D | 01S-0000 | 01S-0090 | 01S-0401 | 01S-0569 | 01S-0833/07.07 | 020-0000-D | 021-0000/00.04 | 022-0000 | 023-0000 | 024-0000/01.08 | 025-0000 | 026-0017 | 026-0000-D | 027-0000 | 027-0083 | 028-0000 | 029-0007/04.02-I-CO2 | 029-0042 | 029-0061/13.24 | 030-0000 | 030-0061 | 030-0110 | 031-0000 | 032-0000 | 033-0000 | 033-0017 | 034-0000 | 035-0000 | 035-0124 | 035-0308/11.17 | 036-0000/00.43-D | 036-0028 | 037-0000 | 038-0000 | 038-0131 | 039-0000/01.19 | 03A-0000 | 041-0000 | 043-0000 | 044-0000 | 045-0000/01.83 | 046-0000 | 047-0000 | 048-0000 | 049-0000 | 050-0000 | 051-0000-D | 51A-0000 | 0524-I-CYCLE TRAIL | 053-0000 | 054-0000 | 056-0000 | 057-0000 | 058-0000/02.00-I | 059-0000/0.140 | 060-0000 | 062-0000 | 063-0000 | 063-0084 | 065-0000 | 065-0047 | 067-0000 | 069-0000 | 06A-0000 | 071-0000 | 073-0000-D | 073-0145 | 074-0000-D | 075-0000/00.36 | 076-0000 | 077-0000 | 077-0053 | 078-0000 | 079-0000 | 07A-0000 | 080-0000 | 082-0000 | 083-0000 | 084-0000 | 085-0000 | 085-0062 | 086-0000 | 087-0000 | 088-0000 | 08A-0000 | 08B-0000 | 090-0000 | 093-0000 | 094-0000 | 094-0138 | 095-0000 | 095-0021 | 096-0000 | 097-0000 | 098-0000 | 099-0000 | 20A-0000-D | 20B-0000 | 25A-0000 | 29A-0000/00.16-D | 30A-0000 | 67A-0000 | 74A-0000 | 74M-0000-D | 76H-0000/00.70 | 01N-1030-R1 | ABERFELDY STREET | CAMBRIDGE AVE_A | TEL CYCLE TRACK #1 | CYCLEWAY SH29A - OHAUITI RD TO POIKE RD | JOHNS ROAD CUL DE SAC TO BE REVOKED | MAKOMAKO RD | MULGRAVE AVE_A | OXFORD RD | PAHIATUA TRACK RD | SADDLE RD | SALISBURY ST_A | WOODLANDS RD | EDENDALE FROM FERRY RD WEST TO END CONSTRUCTION | SHARED PATH TE AWA RIVER TRAIL | WEX-0528-I | BALLANCE VALLEY RD | GORGE RD | M2PP CYCLEWAY | MASTERTON LEFTOVER 275 - 338
|  |  | 002-0007-R1 | 002-0034 | 002-0116 | 002-0223 | 002-0375 | 002-0497 | 002-0758 | 002-0873 | 003-0000/00.45-D | 003-0103 | 003-0384 | 004-0015 | 004-0094 | 004-0148 | 005-0005-C028 | 005-0045 | 005-0204 | 006-0010 | 006-0080 | 006-0282 | 006-0828 | 006-1046 | 007-0016 | 007-0152 | 008-0018 | 008-0169 | 008-0233 | 010-0006-W | 011-0014 | 012-0009-C015 | 014-0011-C015 | 015-0007-C012 | 016-0000/00.76-D | 016-0019/02.17 | 018-0000-I | 01B-0015 | 01H-0519 |  | 01K-1012/08.15 | 01N-0020 | 01N-0373/9.56-I | 01N-0486/16.35-I | 01N-0605 | 01N-0842 | 01N-0995 | 01P-0995/03.07-I | 01S-0000/01.15 | 01S-0104 | 01S-0416 | 01S-0583 | 01S-0842 | 020-0000-I | 021-0000/00.15 | 022-0000/00.14-D | 023-0000/01.30 | 024-0000-D | 025-0012 | 026-0026 | 026-0000-I | 027-0016 | 027-0085 | 028-0006-C005 | 029-0007-D-CO2 | 029-0048 | 029-0074 | 030-0014 | 030-0076 | 030-0115 | 031-0014 | 032-0015 |  | 033-0017/18.45-D | 034-0010-C030 | 035-0011 | 035-0132 | 035-0321 | 036-0000/00.43-I | 036-0048 | 037-0007 | 038-0017 | 038-0147 | 039-0000-D | 03A-0016 | 041-0011 | 043-0015 |  | 045-0000-D | 046-0020 | 047-0009 | 048-0007 | 049-0011 | 050-0002-D | 051-0000-I |  |  | 053-0018 | 054-0001 | 056-0011 | 057-0021 | 058-0000/02.88-D | 059-0000/05.64-D | 060-0015 | 062-0013 | 063-0017 | 063-0092 | 065-0017 | 065-0054 | 067-0005 | 069-0017 | 06A-0007 | 071-0006 | 073-0000-I | 073-0151 | 074-0000-I | 075-0000-D | 076-0000-R1 | 077-0017 | 077-0067 | 078-0001 | 079-0009 | 07A-0008 | 080-0017 | 082-0017 | 083-0016 | 084-0000/01.29 | 085-0016 | 085-0079 |  | 087-0015 | 088-0008 | 08A-0000/11.30 | 08B-0003 | 090-0017 | 093-0016 | 094-0016 | 094-0150 |  |  | 096-0000/04.89 | 097-0000/05.00 | 098-0021 | 099-0000/00.52 | 20A-0000-I | 20B-0002 | 25A-0008 | 29A-0000/00.19-I | 30A-0000/01.22-D | 67A-0009 |  | 74M-0000-I | 76H-0000-D | 01N-1030-R2 |  |  | TEL CYCLE TRACK #2 | CYCLEWAY - POIKE ROAD - SH29A INTERSECTION |  | MANGAHAO RD |  |  | PAHIATUA TRK | SADDLE RD_A |  |  | EDENDALE START CONSTRUCTION TO FERRY ROAD | SHARED PATH GREAT SOUTH RD NORTHWEST | WEX-0528-D
|  |  | 002-0009-R1 | 002-0037 | 002-0130 | 002-0232 | 002-0390 | 002-0516 | 002-0772 | 002-0883/00.34 | 003-0000/00.45-I | 003-0118 | 003-0402 | 004-0035 | 004-0114 | 004-0158 | 005-0008 | 005-0045/01.95-D | 005-0220 | 006-0016 | 006-0099 | 006-0296 | 006-0847 | 006-1061 | 007-0028 | 007-0169 | 008-0030 | 008-0185 | 008-0247 | 010-0007 | 011-0030 | 012-0010 | 014-0012 | 015-0009 | 016-0000/00.76-I | 016-0021-W | 018-0002-R1 | 01B-0029-C026 | 01H-0524-W |  | 01K-1012/09.85-D | 01N-0044 | 01N-0381-R1 | 01N-0502-R5 | 01N-0607 | 01N-0855 | 01N-0995/12.79 | 01P-0995/12.79 | 01S-0001-W | 01S-0118 | 01S-0430 | 01S-0583/07.12-D | 01S-0854 | 020-0001-R1 | 021-0000-W | 022-0000/00.14-I | 023-0001-W | 024-0000-I | 025-0022 | 026-0026/01.17 | 026-0001 | 027-0021 | 027-0094 | 028-0009 | 029-0007-I-CO2 | 029-0049-R1 |  | 030-0030 | 030-0084-C032 | 030-0120 | 031-0031 | 032-0027-C030 |  | 033-0017/18.45-I | 034-0011 | 035-0021 | 035-0144 | 035-0327 | 036-0000/00.59 |  |  |  | 038-0147/11.77 | 039-0000-I |  | 041-0023 | 043-0032 |  | 045-0000-I |  | 047-0009/16.97 |  | 049-0029 | 050-0002-I | 051-0002/00.08 |  |  |  | 054-0017 | 056-0014-R1 | 057-0026 | 058-0000/02.88-I | 059-0000/05.64-I | 060-0033 |  | 063-0029 | 063-0109 | 065-0036 | 065-0072 | 067-0014 | 069-0033 |  |  | 073-0000-R1 | 073-0159 | 074-0003-R1 | 075-0000-I | 076-0003 | 077-0033 | 077-0079 |  | 079-0015 |  | 080-0035 | 082-0032 | 083-0022 | 084-0001-W | 085-0031 | 085-0092 |  | 087-0033 | 088-0013 | 08A-0015 |  | 090-0035 | 093-0031 | 094-0016/02.42 | 094-0163 |  |  | 096-0015 | 097-0000/10.00 |  | 099-0015 | 20A-0001-R1 |  | 25A-0021 | 29A-0000/04.34 | 30A-0000/01.22-I |  |  | 74M-0002/04.17-D | 76H-0000-I | 01N-1030-R3 | [8 empty] | PAHIATUA-MANGAHAO RD | SADDLE ROAD |  |  |  | SHARED PATH MANGAHARAKEKE DR OVERPASS | WEX-0546-I
|  |  | 002-0009-R2 | 002-0048 | 002-0130/00.61-D | 002-0242-C030 | 002-0406 | 002-0533 | 002-0788 | 002-0883/05.78 | 003-0000/01.42 | 003-0132 | 003-0403-R2 | 004-0045 | 004-0127 | 004-0176 | 005-0099 | 005-0045/01.95-I | 005-0233 | 006-0034 | 006-0116/00.81 | 006-0313 | 006-0866 | 006-1079 | 007-0044 | 007-0185 | 008-0034 | 008-0202 | 008-0266 | 010-0017 |  | 012-0017 | 014-0015 | 015-0027 | 016-0001-R1 | 016-0030-W | 018-0002-R2 | 01B-0030 | 01H-0525 |  | 01K-1012/09.85-I | 01N-0065 | 01N-0381-R2 | 01N-0504-D | 01N-0607-W | 01N-0865 | 01N-1011-D | 01P-0999-R1 | 01S-0018 | 01S-0138 | 01S-0447 | 01S-0583/07.12-I | 01S-0858/02.04 | 020-0001-R2 | 021-0001-W | 022-0000/00.61 | 023-0003 | 024-0008-R1 | 025-0023-W | 026-0027-W | 026-0001/2.24 | 027-0027 |  | 028-0017 | 029-0011-W-CO2 | 029-0050 |  | 030-0047 | 030-0085-C032 | 030-0131 | 031-0047 | 032-0028-C030 |  | 033-0035-R1 | 034-0015 | 035-0028 | 035-0159 | 035-0335 | 036-0000/01.95-D |  |  |  | 038-0161 | 039-0002-W |  | 041-0037 | 043-0051 |  | 045-0015 |  | 047-0026 |  | 049-0038 | 050-0003-R1 | 051-0002/08.35 |  |  |  | 054-0038 | 056-0014-R2 | 057-0036 | 058-0000/03.47 | 059-0000/08.98 | 060-0042 |  | 063-0046 | 063-0117 |  |  | 067-0030 |  |  |  | 073-0001 | 073-0174 | 074-0003-R2 | 075-0008 | 076-0003/00.98-D | 077-0043 | 077-0094 |  | 079-0031 |  | 080-0051 | 082-0042 | 083-0034 | 084-0003 | 085-0049 | 085-0105 |  | 087-0048 |  | 08A-0021 |  | 090-0035/11.66 | 093-0043 | 094-0030 | 094-0177 |  |  | 096-0030 | 097-0000/15.00 |  | 099-0031 | 20A-0001-R2 |  | 25A-0028 | 29A-0000/06.91-D | 30A-0004 |  |  | 74M-0002/04.17-I | 76H-0000-W | 01N-1030-W | [13 empty] | SHARED PATH MANGAHARAKEKE DR WESTERN | WEX-0546-D
|  |  | 002-0013-R1 | 002-0061 | 002-0130/00.61-I | 002-0243 | 002-0416 | 002-0544 | 002-0802 | 002-0883/20.34 | 003-0000/02.97 | 003-0140 | 003-0415 | 004-0061 |  | 004-0188 | 005-0111 | 005-0045/05.50 | 005-0240-R1 | 006-0050 | 006-0116/05.62-D | 006-0336 | 006-0881 | 006-1093-C094 | 007-0058 | 007-0196 | 008-0034/09.54 | 008-0401 | 008-0271 | 010-0017/03.51 |  | 012-0033 | 014-0030 | 015-0044 | 016-0001-R2 | 016-0031 | 018-0002-R3 | 01B-0044 | 01H-0525/00.47-D |  | 01K-1012/10.41 | 01N-0083 | 01N-0389-R1 | 01N-0504-I | 01N-0613 | 01N-0885 | 01N-1011-I | 01P-0999-R2 | 01S-0028 | 01S-0155 | 01S-0462 | 01S-0583/08.36 | 01S-0858-D | 020-0001-R3 | 021-0002 | 022-0000/03.71 | 023-0010-C039 | 024-0013 | 025-0024 | 026-0035 | 026-0003-W | 027-0031-R1 |  | 028-0024 | 029-0014/01.47 | 029-0060-C027 |  |  | 030-0086 | 030-0131/06.10 | 031-0056 | 032-0029 |  | 033-0036 | 034-0021 | 035-0041 | 035-0172 |  | 036-0000/01.95-I |  |  |  | 038-0179 | 039-0004 |  | 041-0056 | 043-0057 |  | 045-0028 |  | 047-0029 |  |  | 050-0003-R2 | 051-0002-D |  |  |  | 054-0038/02.70-D | 056-0022 | 057-0050 | 058-0000-D | 059-0000/12.79-D | 060-0056 |  | 063-0059 |  |  |  | 067-0046 |  |  |  | 073-0001/00.73-D | 073-0191 | 074-0007/00.13-D | 075-0014 | 076-0003/00.98-I |  |  |  | 079-0042 |  | 080-0059 | 082-0053 | 083-0049 | 084-0003-W | 085-0049/01.00 | 085-0120 |  | 087-0065 |  |  |  | 090-0051 |  | 094-0043 | 094-0192 |  |  | 096-0048-C006 |  |  | 099-0046 | 20A-0002-R1 |  |  | 29A-0000/06.91-I |  |  |  | 74M-0002-D |  | 058-0009/00.82 | [13 empty] | SHARED PATH TE RAPA RD SOUTHEAST | WEX-0536-R1
|  |  | 002-0018 | 002-0072-C026 | 002-0130/01.51 | 002-0258 | 002-0429 | 002-0562 | 002-0808 | 002-0883-D | 003-0000-R1 | 003-0158 | 003-0432 | 004-0070 |  | 004-0206 | 005-0124/07.93-D-C01N | 005-0050/0.88 | 005-0240-R2 | 006-0065 | 006-0116/05.62-I | 006-0351 | 006-0893 | 006-1095 | 007-0068 | 007-0212 | 008-0057 | 008-0417 | 008-0297 | 010-0020-W |  | 012-0046 | 014-0044 | 015-0054 | 016-0002-R1 | 016-0037 | 018-0002-R4 |  | 01H-0525/00.47-I |  | 01K-1020-W | 01N-0104 | 01N-0389-R2 | 01N-0504-R1 | 01N-0625 | 01N-0901 | 01N-1012-R1 | 01P-1003-R1 | 01S-0043 | 01S-0163 | 01S-0465 | 01S-0601 | 01S-0858-I | 020-0001-R4 | 021-0007 | 022-0000/10.10 | 023-0011 |  | 025-0042 | 026-0048 | 026-0006-C01B | 027-0031-R2 |  |  | 029-0014/04.88-D | 029-0061 |  |  | 030-0086-R1 | 030-0143-C005 |  | 032-0045 |  |  | 034-0025 | 035-0049 | 035-0180 |  | 036-0000/02.18-D |  |  |  | 038-0189 | 039-0011 |  | 041-0059 | 043-0065 |  | 045-0048 |  | 047-0046 |  |  | 050-0012 | 051-0002-I |  |  |  | 054-0038/02.70-I | 056-0023 | 057-0065 | 058-0000-I | 059-0000/12.79-I | 060-0070 |  | 063-0074 |  |  |  | 067-0051 |  |  |  | 073-0001/00.73-I | 073-0206 | 074-0007/00.16-I | 075-0024 | 076-0003/02.19-D |  |  |  | 079-0046 |  |  | 082-0071 | 083-0058 |  |  | 085-0134 |  | 087-0082 |  |  |  | 090-0059 |  | 094-0061-C006 | 094-0197 |  |  | 096-0050 |  |  | 099-0060 | 20A-0002-R2 |  |  | 29A-0000-D |  |  |  | 74M-0002-I |  | 058-0011-W | [13 empty] | SHARED PATH TE RAPA WESTERN | WEX-0536-R2
|  |  | 002-0032 | 002-0073 | 002-0130/13.91-D | 002-0271 | 002-0443 | 002-0577 | 002-0808/08.51-D | 002-0883-I | 003-0000-R2 | 003-0171 | 003-0444-C01N | 004-0239 |  | 004-0223 | 005-0124/07.93-I-C01N | 005-0050-D | 005-0240-R3 |  | 006-0116/06.00-D | 006-0363 | 006-0901 | 006-1111 | 007-0078 | 007-0224 | 008-0073 | 008-0430 | 008-0310 | 010-0033 |  | 012-0061 | 014-0056 | 015-0069 | 016-0002-R2 | 016-0047 | 018-0005-R1 |  | 01H-0525/00.86 |  | 01K-1022-R1 | 01N-0119 | 01N-0389-R3 | 01N-0504-R2 | 01N-0625/11.15-D | 01N-0914 | 01N-1012-R2 | 01P-1003-R2 | 01S-0057 | 01S-0179 | 01S-0481 | 01S-0618 | 01S-0870 | 020-0001-R5 |  | 022-0001-R1 | 023-0015 |  | 025-0058 | 026-0060 | 026-0007 | 027-0031-R3 |  |  | 029-0014/04.88-I |  |  |  | 030-0105-C01N | 030-0144 |  | 032-0057 |  |  |  | 035-0065 | 035-0190 |  | 036-0000/02.18-I |  |  |  | 038-0196 | 039-0017-C023 |  |  | 043-0080 |  | 045-0064 |  |  |  |  | 050-0017 | 051-0013 |  |  |  | 054-0038/04.29 |  |  | 058-0012 | 059-0000/17.47 | 060-0089 | [9 empty] | 073-0001/02.38 | 073-0226 | 074-0007/02.15-D | 075-0035 | 076-0003/02.19-I |  |  |  | 079-0061 |  |  |  | 083-0070 |  |  | 085-0148 |  | 087-0096 | [5 empty] | 094-0063 | 094-0212 |  |  | 096-0066 |  |  | 099-0078 | 20A-0002-R3 |  |  | 29A-0000-I | [5 empty] | 01N-1047-I | [13 empty] | SHARED PATH TE RAPA EASTERN | WEX-0539-R1
|  |  |  | 002-0093 | 002-0130/13.91-I | 002-0283 | 002-0443/03.01 | 002-0577/14.59 | 002-0808/08.51-I | 002-0883-W | 003-0001-W | 003-0176 | 003-0445-C01N |  |  | 004-0238-R1 | 005-0124/08.57-C01N | 005-0050-I | 005-0240-R4 |  | 006-0116/11.50 | 006-0374 | 006-0901/06.20 | 006-1127 | 007-0098 | 007-0239 | 008-0085 | 008-0444 | 008-0328 | 010-0048 |  | 012-0074 |  | 015-0080-C014 | 016-0002-R3 | 016-0069 | 018-0005-R2 |  | 01H-0526-W |  | 01K-1022-R2 | 01N-0134 | 01N-0389-R4 | 01N-0504-R3 | 01N-0625/11.15-I | 01N-0925-C003 | 01N-1017-R1 |  | 01S-0073 | 01S-0185 | 01S-0501 | 01S-0635 | 01S-0872 | 020-0003-R1 |  | 022-0013 | 023-0032 |  | 025-0072 | 026-0069-C002 |  | 027-0031-R4 |  |  | 029-0014-D |  |  |  |  | 030-0147/01.11 |  | 032-0069 |  |  |  | 035-0079 | 035-0200 |  | 036-0000/02.30 |  |  |  |  | 039-0018 |  |  | 043-0097 |  | 045-0081 |  |  |  |  | 050-0033 | 051-0013/05.24 |  |  |  | 054-0055 |  |  | 058-0015 | 059-0000/19.22-D | 060-0103 | [9 empty] | 073-0005 |  | 074-0007/02.98 | 075-0052 | 076-0008-R1 | [7 empty] | 083-0085 |  |  | 085-0164 |  | 087-0096/09.97 | [5 empty] | 094-0080 | 094-0229 |  |  | 096-0084 |  |  | 099-0092 | 20A-0002-R4 |  |  | 29A-0001-W | [5 empty] | 01N-1047-D | [13 empty] | SHARED PATH OAKLEA LANE | WEX-0539-R2
[5 empty] | 002-0130/14.25-D | 002-0294 | 002-0446-W | 002-0592 | 002-0808/09.58 | 002-0905 | 003-0002-W | 003-0189 | 003-0450 |  |  |  | 005-0124-C01N | 005-0054-C030 | 005-0249 |  | 006-0116-D | 006-0388 | 006-0918 | 006-1143-C096 | 007-0115 | 007-0255 | 008-0099 | 008-0460 | 008-0343 | 010-0063 |  | 012-0089 |  | 015-0081 | 016-0002-R4 | 016-0082 | 018-0006-R1 |  |  |  | 01K-1023 | 01N-0149 | 01N-0389-R5 | 01N-0504-R4 | 01N-0625/12.01 | 01N-0927-C003 | 01N-1017-R2 |  |  | 01S-0195 | 01S-0501/04.53-D | 01S-0651 | 01S-0872/06.04 | 020-0003-R2 |  |  | 023-0032/10.62 |  | 025-0084 | 026-0070 |  | 027-0045-W |  |  | 029-0014-I |  |  |  |  | 030-0147-D |  | 032-0082 |  |  |  | 035-0094 | 035-0213 |  | 036-0000/04.38-D |  |  |  |  | 039-0033 |  |  | 043-0111 |  | 045-0097 |  |  |  |  | 050-0049 | 051-0018-W | [7 empty] | 059-0000/19.22-I | 060-0118 | [9 empty] | 073-0015 |  | 074-0007/06.14 | 075-0061 | 076-0008-R2 | [7 empty] | 083-0096 |  |  |  |  | 087-0110 | [5 empty] | 094-0099 | 094-0240 |  |  | 096-0091 | [6 empty] | 29A-0005-R1 | [5 empty] | 01N-1032-R1 | [13 empty] | SHARED PATH PENCARROW ROAD | WEX-0539-R3
[5 empty] | 002-0130/14.25-I | 002-0304 | 002-0461 | 002-0608 | 002-0825 | 002-0921 | 003-0003-W | 003-0203 | 003-0458-R1 |  |  |  | 005-0137 | 005-0054-W | 005-0262 |  | 006-0116-I | 006-0403 | 006-0938 | 006-1145 |  | 007-0273 | 008-0118 |  | 008-0350 | 010-0079 |  | 012-0106 |  | 015-0111 | 016-0002-R5 | 016-0092 | 018-0006-R2 |  |  |  |  | 01N-0167 | 01N-0389-W1 | 01N-0504-W | 01N-0638 | 01N-0932 | 01N-1017-R3 |  |  | 01S-0217 | 01S-0501/04.53-I | 01S-0651/09.00 | 01S-0886 | 020-0003-R3 |  |  | 023-0044 |  | 025-0099 | 026-0080 |  | 027-0046 |  |  | 029-0018-R1 |  |  |  |  | 030-0147-I |  | 032-0097 |  |  |  | 035-0106 | 035-0225 |  | 036-0000/04.38-I |  |  |  |  | 039-0043 |  |  | 043-0130 |  | 045-0105 |  |  |  |  | 050-0067 | [8 empty] | 059-0014-R1 | [10 empty] | 073-0034 |  | 074-0007/06.92 | 075-0079 | 076-0009-R1 | [7 empty] | 083-0110 |  |  |  |  | 087-0116 | [5 empty] | 094-0115 | 094-0241 | [9 empty] | 29A-0005-R2 | [5 empty] | 01N-1032-R2 | [13 empty] | SHARED PATH STRAWBERRY FIELDS LANE | WEX-0539-R4
[5 empty] | 002-0130/14.55 | 002-0318 | 002-0474 | 002-0626 | 002-0842 | 002-0931 | 003-0005 | 003-0218 | 003-0468 |  |  |  | 005-0150 | 005-0056 |  |  | 006-0121-R1 | 006-0416 | 006-0942 | 006-1145/00.18-D |  |  | 008-0131 |  | 008-0365 | 010-0095 |  | 012-0122 |  | 015-0120 | 016-0003-R1 | 016-0107 | 018-0007-D |  |  |  |  | 01N-0185 | 01N-0389-W2 | 01N-0510-R1 | 01N-0657-C030 | 01N-0939 | 01N-1017-R4 |  |  | 01S-0235 | 01S-0506 | 01S-0666 | 01S-0886/00.67 | 020-0003-R4 |  |  |  |  | 025-0113 | 026-0095 |  | 027-0067 |  |  | 029-0018-W |  |  |  |  | 030-0158 | [5 empty] | 035-0116 | 035-0238 |  | 036-0000-D |  |  |  |  | 039-0058-C031 |  |  | 043-0150 | [6 empty] | 050-0079 | [8 empty] | 059-0016-R1 | [10 empty] | 073-0041 |  | 074-0007/10.42 |  | 076-0009-R2 | [18 empty] | 094-0130 | 094-0258 | [9 empty] | 29A-0007-W | [5 empty] | 01N-1032-R4 | [14 empty] | WEX-0548-R1
[5 empty] | 002-0144-W | 002-0334 |  | 002-0626/11.31 |  | 002-0946 | 003-0009-W | 003-0229 | 003-0471 |  |  |  | 005-0169 | 005-0067 |  |  | 006-0121-R2 | 006-0430 | 006-0956 | 006-1145/00.18-I |  |  | 008-0146 |  | 008-0370 | 010-0106 |  | 012-0132 |  |  | 016-0003-R2 |  | 018-0007-I |  |  |  |  | 01N-0190 | 01N-0391-R1 | 01N-0510-R2 | 01N-0663 | 01N-0954 | 01N-1023-R1 |  |  | 01S-0247 | 01S-0506/00.80-D | 01S-0667 | 01S-0887-R1 | 020-0005-R1 |  |  |  |  | 025-0127 | 026-0096 |  | 027-0074 |  |  | 029-0019/00.14 |  |  |  |  | 030-0170 | [6 empty] | 035-0250 |  | 036-0000-I |  |  |  |  | 039-0072 | [9 empty] | 050-0090 | [8 empty] | 059-0016-R2 | [10 empty] | 073-0052 |  | 074-0007-D |  | 076-0010-R1 | [29 empty] | 29A-0008/00.28 | [5 empty] | 01N-1047-R1 | [14 empty] | WEX-0548-R2
[5 empty] | 002-0146 | 002-0345 |  | 002-0638 |  | 002-0946/07.69-D | 003-0010 | 003-0229/04.34-D | 003-0474/02.96 |  |  |  | 005-0188 | 005-0077 |  |  | 006-0121-W | 006-0430/00.60-D | 006-0978 | 006-1145/00.64 |  |  |  |  | 008-0381 |  |  | 012-0153 |  |  | 016-0003-R3 |  | 018-0008-R1 |  |  |  |  | 01N-0198 | 01N-0391-R2 | 01N-0510-R3 | 01N-0664 | 01N-0954/11.26-D | 01N-1023-R2 |  |  | 01S-0262 | 01S-0506/00.80-I | 01S-0683 | 01S-0887-R2 | 020-0005-R2 |  |  |  |  | 025-0143 |  |  | 027-0082-C029 |  |  | 029-0019-D |  |  |  |  | 030-0187 | [6 empty] | 035-0263 |  | 036-0001-W | [23 empty] | 059-0016-R3 | [10 empty] | 073-0068 |  | 074-0007-I |  | 076-0010-R2 | [29 empty] | 29A-0008/02.06-D | [5 empty] | 01N-1047-R2 | [14 empty] | WEX-0548-R3
[5 empty] | 002-0146/01.13-D |  |  | 002-0638/05.13-D |  | 002-0946/07.69-I | 003-0010/0.06 | 003-0229/04.34-I | 003-0474-D | [7 empty] | 006-0122-R1 | 006-0430/00.60-I | 006-0983 | 006-1157 | [7 empty] | 012-0169 |  |  | 016-0003-R4 |  | 018-0008-R2 |  |  |  |  | 01N-0210-W | 01N-0398/11.53-I | 01N-0510-R4 | 01N-0680 | 01N-0954/11.26-I | 01N-1023-R3 |  |  | 01S-0273 | 01S-0506/02.04 | 01S-0700 | 01S-0887-W | 020-0005-R3 |  |  |  |  | 025-0156 | [5 empty] | 029-0019-I |  |  |  |  | 030-0187/00.20 | [6 empty] | 035-0274 |  | 036-0002-W | [23 empty] | 059-0016-R4 | [10 empty] | 073-0076 |  | 074-0007-R1 |  | 076-0011-D | [29 empty] | 29A-0008/02.06-I | [5 empty] | 01N-1047-R3 | [14 empty] | WEX-0548-R4
[5 empty] | 002-0146/01.13-I |  |  | 002-0638/05.13-I |  | 002-0946/08.82 | 003-0016 | 003-0229/08.68 | 003-0474-I | [7 empty] | 006-0122-R2 | 006-0430/01.52 | 006-0983/10.64 | 006-1157/07.94 | [7 empty] | 012-0185 |  |  | 016-0004-R1 |  | 018-0010-R1 |  |  |  |  | 01N-0211 | 01N-0398/11.65-D | 01N-0513-D | 01N-0695-R1 | 01N-0967/00.21 | 01N-1023-R4 |  |  | 01S-0284 | 01S-0516 | 01S-0704-D | 01S-0900 | 020-0005-R4 |  |  |  |  | 025-0172 | [5 empty] | 029-0021 |  |  |  |  | 030-0194 | [6 empty] | 035-0289 |  | 036-0003-W | [23 empty] | 059-0020-D | [10 empty] | 073-0090 |  | 074-0007-R2 |  | 076-0011-I | [29 empty] | 29A-0008/02.30 | [5 empty] | 01N-1047-R4 | [14 empty] | WEX-0552-R1
[5 empty] | 002-0146/01.30-D |  |  | 002-0646/00.76 |  | 002-0946/09.22-D | 003-0036 | 003-0229/09.32-D | 003-0488 | [7 empty] | 006-0122-W | 006-0445 | 006-0983/11.05 | 006-1168 | [7 empty] | 012-0202 |  |  | 016-0004-R2 |  | 018-0010-R2 |  |  |  |  | 01N-0215 | 01N-0398-D | 01N-0513-I | 01N-0695-R2 | 01N-0967-D | 01N-1026-R1 |  |  | 01S-0303 | 01S-0520 | 01S-0704-I | 01S-0900/14.18 | 020-0007-R1 |  |  |  |  | 025-0188 | [10 empty] | 030-0205-C034 | [6 empty] | 035-0300 |  | 036-0004 | [23 empty] | 059-0020-I | [10 empty] | 073-0107 |  | 074-0007-R3 |  | 076-0011-R1 | [29 empty] | 29A-0008/03.42 | [5 empty] | 058-0009 | [14 empty] | WEX-0552-R2
[5 empty] | 002-0146/01.30-I |  |  | 002-0646/01.40-D |  | 002-0946/09.22-I | 003-0057 | 003-0229/09.32-I | 003-0491 | [7 empty] | 006-0125-R1 | 006-0448 | 006-0983/8.10 | 006-1168/02.75-D | [7 empty] | 012-0223 |  |  | 016-0004-R3 |  | 018-0010-R3 |  |  |  |  | 01N-0233 | 01N-0398-I | 01N-0514-R1 | 01N-0695-W | 01N-0967-I | 01N-1026-R2 |  |  | 01S-0311 | 01S-0532 | 01S-0706-D | 01S-0920/01.12 | 020-0007-R2 |  |  |  |  | 025-0206 | [10 empty] | 030-0206 | [6 empty] | 035-0308 |  | 036-0013 | [23 empty] | 059-0020-R1 | [10 empty] | 073-0121 |  | 074-0007-W1 |  | 076-0011-R2 | [29 empty] | 29A-0008/05.02 | [5 empty] | 058-0009/00.21-I | [14 empty] | WEX-0552-R3
[5 empty] | 002-0146/01.75 |  |  | 002-0646/01.40-I |  | 002-0946/13.01-I | 003-0063 | 003-0229/09.95 | 003-0500 | [7 empty] | 006-0126-R2 | 006-0463 | 006-0991-W | 006-1168/02.75-I | [10 empty] | 016-0004-R4 |  | 018-0010-R4 |  |  |  |  | 01N-0245 | 01N-0398-R1 | 01N-0514-R2 | 01N-0696-C005 |  | 01N-1030-R4 |  |  | 01S-0317 | 01S-0544 | 01S-0706-I | 01S-0920/02.60-D | 020-0007-R3 |  |  |  |  | 025-0217 | [10 empty] | 030-0218-C002 | [32 empty] | 059-0022-R1 | [10 empty] | 073-0136 |  | 074-0007-W2 |  | 076-0015-R1 | [29 empty] | 29A-0008-D | [5 empty] | 058-0009/00.21-D | [14 empty] | WEX-0552-R4
[5 empty] | 002-0146/02.13-D |  |  | 002-0646-D |  | 002-0946/13.02-D | 003-0065 | 003-0229/10.16-D | [8 empty] | 006-0127-R1 | 006-0471 | 006-0993-R1 | 006-1175 | [10 empty] | 016-0006-R1 |  | 018-0012-R1 |  |  |  |  | 01N-0258 | 01N-0398-R2 | 01N-0524-R1 | 01N-0701-R1 |  | 01N-1058-D |  |  | 01S-0317/02.68 | 01S-0560 | 01S-0706-R1 | 01S-0920/02.60-I | 020-0007-R4 |  |  |  |  | 025-0226 | [10 empty] | 030-0219 | [32 empty] | 059-0022-R2 | [12 empty] | 074-0009-R1 |  | 076-0015-R2 | [29 empty] | 29A-0008-I | [5 empty] | 058-0009/00.37-I
[5 empty] | 002-0146/02.13-I |  |  | 002-0646-I |  | 002-0948-R1 | 003-0065-W | 003-0229/10.16-I | [8 empty] | 006-0127-R2 | 006-0489 | 006-0993-W | [11 empty] | 016-0006-R2 |  | 018-0012-R2 |  |  |  |  | 01N-0258/02.90-D | 01N-0398-R3 | 01N-0528-D | 01N-0701-R2 |  | 01N-1058-I |  |  | 01S-0317/05.26-D |  | 01S-0707-D | 01S-0920-D | 020-0009-R1 |  |  |  |  | 025-0242 | [10 empty] | 030-0229 | [32 empty] | 059-0023-R1 | [12 empty] | 074-0009-R2 |  | 076-0017-R1 | [29 empty] | 29A-0009-W | [5 empty] | 058-0009/00.37-D
[5 empty] | 002-0147-W |  |  | 002-0646-W |  | 002-0948-R2 | 003-0076 | 003-0229/10.26-D | [8 empty] | 006-0127-R3 | 006-0501 | 006-0994-W | [11 empty] | 016-0006-R3 |  | 018-0012-R3 |  |  |  |  | 01N-0258/02.90-I | 01N-0398-R4 | 01N-0528-I | 01N-0701-R3 |  | 01N-1060-D |  |  | 01S-0317/05.26-I |  | 01S-0707-I | 01S-0920-I | 020-0010/02.54-D | [48 empty] | 059-0023-R2 | [12 empty] | 074-0009-R3 |  | 076-0017-R2 | [29 empty] | 29A-0010-W | [5 empty] | 058-0009-W
[5 empty] | 002-0148-W |  |  | 002-0648-C050-D |  | 002-0954-R1 |  | 003-0234-R1 | [8 empty] | 006-0127-R4 | 006-0519 | 006-0996 | [11 empty] | 016-0006-R4 |  | 018-0014 |  |  |  |  | 01N-0258/03.50 | 01N-0398-R5 | 01N-0528-R1 | 01N-0701-R4 |  | 01N-1060-I |  |  | 01S-0323-R1 |  | 01S-0708-R1 | 01S-0923/01.71 | 020-0010/02.54-I | [48 empty] | 059-0024-R1 | [12 empty] | 074-0009-W |  | 076-0017-R3 | [29 empty] | 29A-0011-W | [5 empty] | 058-0010-W
[5 empty] | 002-0149-R1 |  |  | 002-0648-C050-I |  | 002-0954-R2 |  | 003-0234-R2 | [8 empty] | 006-0131 | 006-0541 | 006-1011 | [11 empty] | 016-0007/03.53-D | [6 empty] | 01N-0258/05.04-D | 01N-0402-R1 | 01N-0528-R2 | 01N-0703-R1 |  | 01N-1060-R1 |  |  | 01S-0323-R2 |  | 01S-0709-D | 01S-0923-D | 020-0010-D | [48 empty] | 059-0024-R2 | [12 empty] | 074-0013-W |  | 076-0017-R4 | [29 empty] | 29A-0012-W | [5 empty] | 01N-1050-R1
[5 empty] | 002-0149-R2 |  |  | 002-0648-C050-W |  | 002-0955-R1 |  | 003-0234-R3 | [8 empty] | 006-0150 | 006-0551 | 006-1024 | [11 empty] | 016-0007/03.53-I | [6 empty] | 01N-0258/05.04-I | 01N-0402-R2 | 01N-0528-R3 | 01N-0703-R2 |  | 01N-1060-R2 |  |  | 01S-0323-R3 |  | 01S-0709-I | 01S-0923-I | 020-0010-I | [48 empty] | 059-0024-R3 | [12 empty] | 074-0014-W | [31 empty] | 29A-0013 | [5 empty] | 01N-1050-R2
[5 empty] | 002-0149-R3 |  |  | 002-0651 |  | 002-0955-R2 |  | 003-0234-R4 | [8 empty] | 006-0170 | 006-0570 | [12 empty] | 016-0007-D | [6 empty] | 01N-0258/06.40 | 01N-0410-R1 | 01N-0528-R4 | 01N-0703-R3 |  | 01N-1060-R3 |  |  | 01S-0323-R4 |  | 01S-0709-R1 | 01S-0926 | 020-0010-R1 | [48 empty] | 059-0024-R4 | [12 empty] | 074-0017-W | [37 empty] | 01N-1050-R3
[5 empty] | 002-0150-R1 |  |  | 002-0651/00.79-C050-D |  | 002-0959-R1 |  | 003-0240 | [8 empty] | 006-0184 | 006-0584 | [12 empty] | 016-0007-I | [6 empty] | 01N-0258/07.25-D | 01N-0410-R2 | 01N-0528-W | 01N-0703-R4 |  | 01N-1060-R4 |  |  | 01S-0324-R1 |  | 01S-0710-R1 | 01S-0933 | 020-0010-R2 | [48 empty] | 059-0024-W | [12 empty] | 074-0019 | [37 empty] | 01N-1050-R4
[5 empty] | 002-0150-R2 |  |  | 002-0651/00.79-C050-I |  | 002-0959-R2 |  | 003-0258 | [8 empty] | 006-0196 | 006-0596 | [12 empty] | 016-0008-R1 | [6 empty] | 01N-0258/07.25-I | 01N-0410-R3 | 01N-0534-D | 01N-0706-R1 |  | 01N-1063-R1 |  |  | 01S-0324-R2 |  | 01S-0710-R2 | 01S-0953 | 020-0010-R3 | [61 empty] | 074-0019/00.48 | [37 empty] | 01N-1056-R1
[5 empty] | 002-0151/02.48-D-CO29 |  |  | 002-0651/03.40-C050 |  | 002-0962/12.85-I |  | 003-0269 | [8 empty] | 006-0209 | 006-0610 | [12 empty] | 016-0008-R2 | [6 empty] | 01N-0263-R1 | 01N-0410-R4 | 01N-0534-I | 01N-0706-R2 |  | 01N-1063-R2 |  |  | 01S-0324-R3 |  | 01S-0712-D |  | 020-0010-R4 | [61 empty] | 074-0019/02.08-D | [37 empty] | 01N-1056-R2
[5 empty] | 002-0151-D-CO29 |  |  | 002-0651/03.90-C050-D |  | 002-0962/12.86-D |  | 003-0279 | [8 empty] | 006-0225 | 006-0626 | [12 empty] | 016-0008-R3 | [6 empty] | 01N-0263-W | 01N-0410-R5 | 01N-0539-R1 | 01N-0706-W |  | 01N-1063-R3 |  |  | 01S-0324-R4 |  | 01S-0712-I |  | 020-0012-R1 | [61 empty] | 074-0019/02.08-I | [37 empty] | 01N-1056-R4
[5 empty] | 002-0151-I-CO29 |  |  | 002-0651/03.90-C050-I |  | 002-0962-D |  | 003-0287 | [8 empty] | 006-0239 | 006-0639 | [12 empty] | 016-0008-R4 | [6 empty] | 01N-0266 | 01N-0410-R6 | 01N-0539-R2 | 01N-0707 |  | 01N-1063-R4 |  |  | 01S-0326-R1 |  | 01S-0713-R1 |  | 020-0012-R2 | [61 empty] | 074-0019-W | [37 empty] | 01N-1056-R3
[5 empty] | 002-0151-R1 |  |  | 002-0651/04.68-C050 |  | 002-0962-I |  | 003-0298 | [8 empty] | 006-0255 | 006-0659 | [12 empty] | 016-0008-R5 | [6 empty] | 01N-0272-C015 | 01N-0411-R1 | 01N-0539-R3 | 01N-0712-R1 |  | 01N-1064-R1 |  |  | 01S-0326-R2 |  | 01S-0713-R2 |  | 020-0013-R1 | [61 empty] | 074-0021-R1 | [37 empty] | 01N-1032-W
[5 empty] | 002-0151-R2 |  |  | 002-0651/05.23-C050-D |  | 002-0962-R1 |  | 003-0310 | [9 empty] | 006-0670 | [12 empty] | 016-0008-R6 | [6 empty] | 01N-0273 | 01N-0412-R1 | 01N-0539-R4 | 01N-0712-R2 |  | 01N-1064-R2 |  |  | 01S-0327-D |  | 01S-0713-R3 |  | 020-0013-R2 | [61 empty] | 074-0021-R2 | [37 empty] | 01N-1050-R5
[5 empty] | 002-0151-R3 |  |  | 002-0651/05.23-C050-I |  | 002-0962-R2 |  | 003-0321 | [9 empty] | 006-0683 | [12 empty] | 016-0008-R7 | [6 empty] | 01N-0291-W | 01N-0412-R2 | 01N-0539-W | 01N-0712-W |  | 01N-1066-R1 |  |  | 01S-0327-I |  | 01S-0713-R4 |  | 020-0013-R3 | [61 empty] | 074-0021-R3 | [37 empty] | 01N-1049-W
[5 empty] | 002-0152-R1 |  |  | 002-0651-C050-W |  | 002-0962-R3 |  | 003-0338 | [9 empty] | 006-0695 | [12 empty] | 016-0008-R8 | [6 empty] | 01N-0292 | 01N-0412-R3 | 01N-0540/07.46 | 01N-0713 |  | 01N-1066-R2 |  |  | 01S-0328-R1 |  | 01S-0714-R1 |  | 020-0013-R4 | [61 empty] | 074-0021-R4 | [37 empty] | 01N-1050-W
[5 empty] | 002-0152-R2 |  |  | 002-0652-R1 |  | 002-0962-R4 |  | 003-0352 | [9 empty] | 006-0709 | [12 empty] | 016-0008-R9 | [6 empty] | 01N-0303 | 01N-0412-R4 | 01N-0540/09.39 | 01N-0726 |  | 01N-1066-R3 |  |  | 01S-0330-R1 |  | 01S-0714-R4 |  | 020-0015-R1 | [61 empty] | 074-0022 | [37 empty] | 01N-1050-R6
[5 empty] | 002-0152-R3 |  |  | 002-0652-R2 |  | 002-0962-R5 | [11 empty] | 006-0723 | [12 empty] | 016-0011-R1 | [6 empty] | 01N-0319 | 01N-0414/00.29 | 01N-0540-D | 01N-0744 |  | 01N-1066-R4 |  |  | 01S-0330-R2 |  | 01S-0715-D |  | 020-0015-R2 | [61 empty] | 074-0022/01.53 | [37 empty] | 01N-1056-W
[5 empty] | 002-0152-R4 |  |  | 002-0654 R3 |  | 002-0962-R6 | [11 empty] | 006-0740 | [12 empty] | 016-0011-R2 | [6 empty] | 01N-0336 | 01N-0414/09.02 | 01N-0540-I | 01N-0753 |  | 01N-1066-R5 |  |  | 01S-0333/01.40-D |  | 01S-0715-I |  | 020-0016-R1 | [61 empty] | 074-0024-R1 | [37 empty] | 058-PCCREVOKE
[5 empty] | 002-0152-W |  |  | 002-0654-R1 |  | 002-0962-W | [11 empty] | 006-0750 | [12 empty] | 016-0012-R1 | [6 empty] | 01N-0346 | 01N-0414/09.02-D | 01N-0542-R1 | 01N-0763 |  | 01N-1066-R6 |  |  | 01S-0333/01.41-I |  | 01S-0715-R2 |  | 020-0016-R2 | [61 empty] | 074-0024-R2 | [37 empty] | 059-0000
[5 empty] | 002-0153-R1 |  |  | 002-0654-R2 |  | 002-0972-R1 | [11 empty] | 006-0767 | [12 empty] | 016-0012-R2 | [6 empty] | 01N-0363 | 01N-0414/09.02-I | 01N-0542-R2 | 01N-0777 |  | 01N-1066-R7 |  |  | 01S-0333/04.18-D |  | 01S-0715-R3 |  | 020-0016-R3 | [61 empty] | 074-0026 | [37 empty] | 01N-1030-I
[5 empty] | 002-0153-R2 |  |  | 002-0654-R4 |  | 002-0972-R2 | [11 empty] | 006-0783 | [12 empty] | 016-0014-R1 | [6 empty] | 01N-0373 | 01N-0414/10.96-D | 01N-0542-R3 | 01N-0794 |  | 01N-1067-R1 |  |  | 01S-0333/04.18-I |  | 01S-0717-R1 |  | 020-0016-R4 | [61 empty] | 074-0027 | [37 empty] | 01N-1030-D
[5 empty] | 002-0154-W-CO29 |  |  | 002-0658/00.71 |  | 002-0972-R3 | [11 empty] | 006-0800 | [12 empty] | 016-0014-R2 | [7 empty] | 01N-0414/10.96-I | 01N-0542-R4 | 01N-0815 |  | 01N-1067-R2 |  |  | 01S-0333/05.65-D |  | 01S-0717-R2 |  | 020-0018-R1
[5 empty] | 002-0155-R1 |  |  | 002-0658/00.98-D |  | 002-0972-R4 | [24 empty] | 016-0014-R3 | [7 empty] | 01N-0414-D | 01N-0545-R1 |  |  | 01N-1067-R3 |  |  | 01S-0333/05.65-I |  | 01S-0719-R1 |  | 020-0018-R2
[5 empty] | 002-0155-R2 |  |  | 002-0658/00.98-I |  | 002-0974-R1 | [24 empty] | 016-0014-R4 | [7 empty] | 01N-0414-I | 01N-0545-R2 |  |  | 01N-1067-R4 |  |  | 01S-0333-D |  | 01S-0719-R2 |  | 020-0018-R3
[5 empty] | 002-0155-R3 |  |  | 002-0658/03.18 |  | 002-0974-R2 | [24 empty] | 016-0014-R5 | [7 empty] | 01N-0414-R1 | 01N-0547-W |  |  | 01N-1068/05.72 |  |  | 01S-0333-I |  | 01S-0720 |  | 020-0018-R4
[5 empty] | 002-0155-R4 |  |  | 002-0658/03.72-D |  | 002-0978-R1 | [24 empty] | 016-0016-R1 | [7 empty] | 01N-0414-R2 | 01N-0549-W |  |  | 01N-1068-D |  |  | 01S-0333-R1 |  | 01S-0720-R1 |  | 020-0019-R1
[5 empty] | 002-0155-R5 |  |  | 002-0658/03.72-I |  | 002-0978-R2 | [24 empty] | 016-0016-R2 | [7 empty] | 01N-0414-R3 | 01N-0552 |  |  | 01N-1068-I |  |  | 01S-0333-R2 |  | 01S-0720-R2 |  | 020-0019-R2
[5 empty] | 002-0155-R6 |  |  | 002-0658/05.17-D |  | 002-0979-D | [24 empty] | 016-0016-R3 | [7 empty] | 01N-0414-R4 | 01N-0553 |  |  | 01N-1070-R1 |  |  | 01S-0334-W |  | 01S-0720-R3 |  | 020-0019-R3
[5 empty] | 002-0155-R7 |  |  | 002-0658/05.17-I |  | 002-0979-I | [24 empty] | 016-0016-R4 | [7 empty] | 01N-0414-R5 | 01N-0553/00.53-D |  |  | 01N-1070-R2 |  |  | 01S-0335-R1 |  | 01S-0720-R4 |  | 020-0019-R4
[5 empty] | 002-0155-R8 |  |  | 002-0658/07.53-D | [26 empty] | 016-0018-R1 | [7 empty] | 01N-0417-R1 | 01N-0553/00.53-I |  |  | 01N-1071-R1 |  |  | 01S-0336-R1 |  | 01S-0729 |  | 020-0020-D
[5 empty] | 002-0155-R9 |  |  | 002-0658/07.53-I | [26 empty] | 016-0018-R2 | [7 empty] | 01N-0417-R2 | 01N-0554 |  |  | 01N-1071-R2 |  |  | 01S-0336-R2 |  | 01S-0729/13.40 |  | 020-0020-I
[5 empty] | 002-0157/01.41 |  |  | 002-0658/09.33-D | [26 empty] | 016-0019-D | [7 empty] | 01N-0417-R3 | 01N-0554/01.20-D |  |  | 01N-1072-R1 |  |  | 01S-0336-R3 |  | 01S-0746
[5 empty] | 002-0157/03.66 |  |  | 002-0658/09.33-I | [26 empty] | 016-0019-I | [7 empty] | 01N-0417-R4 | 01N-0554/01.20-I |  |  | 01N-1072-R2 |  |  | 01S-0338-W |  | 01S-0763
[5 empty] | 002-0157-D |  |  | 002-0658/12.49 | [26 empty] | 016-0019-R1 | [7 empty] | 01N-0419-R1 | 01N-0554/01.75-D |  |  | 01N-1072-R3 |  |  | 01S-0339-R1 |  | 01S-0765
[5 empty] | 002-0157-I |  |  | 002-0658-D | [26 empty] | 016-0019-R2 | [7 empty] | 01N-0419-R2 | 01N-0554/01.75-I |  |  | 01N-1072-R4 |  |  | 01S-0339-R2 |  | 01S-0774
[5 empty] | 002-0158-W |  |  | 002-0658-I | [26 empty] | 016-0019-R3 | [7 empty] | 01N-0419-R3 | 01N-0554/03.08-D |  |  | 01N-1073-R1 |  |  | 01S-0339-W |  | 01S-0786
[5 empty] | 002-0159-R1 |  |  | 002-0658-W | [26 empty] | 016-0019-R4 | [7 empty] | 01N-0419-R4 | 01N-0554/03.09-I |  |  | 01N-1073-R2 |  |  | 01S-0340-R2 |  | 01S-0787
[5 empty] | 002-0159-R2 |  |  | 002-0663-W | [26 empty] | 016-0019-R5 | [7 empty] | 01N-0420-R1 | 01N-0554-W |  |  | 01N-1075 |  |  | 01S-0340-R3 |  | 01S-0791
[5 empty] | 002-0159-R3 |  |  | 002-0665-W | [26 empty] | 016-0019-R6 | [7 empty] | 01N-0420-R2 | 01N-0555-W |  |  | 01N-1075/00.13-D |  |  | 01S-0340-R4 |  | 01S-0807
[5 empty] | 002-0159-R4 |  |  | 002-0667-W | [26 empty] | 016-0022-W | [7 empty] | 01N-0420-R3 | 01N-0556/00.05-D |  |  | 01N-1075/00.13-I |  |  | 01S-0341-R1 |  | 01S-0817
[5 empty] | 002-0159-R5 |  |  | 002-0670-W | [34 empty] | 01N-0420-R4 | 01N-0556/00.05-I |  |  | 01N-1076 |  |  | 01S-0341-R2 |  | 01S-0824
[5 empty] | 002-0159-R6 |  |  | 002-0678 | [34 empty] | 01N-0420-R5 | 01N-0556-W |  |  | 01N-1076/02.08-D |  |  | 01S-0341-R3 |  | 01S-0833
[5 empty] | 002-0159-W |  |  | 002-0678-W | [34 empty] | 01N-0420-R6 | 01N-0557 |  |  | 01N-1076/02.08-I |  |  | 01S-0341-R4
[5 empty] | 002-0161-W |  |  | 002-0691 | [34 empty] | 01N-0420-R7 | 01N-0557/02.52-D |  |  | 01N-1076/03.11-I |  |  | 01S-0344-D
[5 empty] | 002-0163-W |  |  | 002-0691/07.66 | [34 empty] | 01N-0422-R1 | 01N-0557/02.52-I |  |  | 01N-1076/03.70 |  |  | 01S-0344-I
[5 empty] | 002-0164-D |  |  | 002-0707 | [34 empty] | 01N-0422-R2 | 01N-0561-R1 |  |  | 01N-1076/3.21-D |  |  | 01S-0347/00.45
[5 empty] | 002-0164-I |  |  | 002-0707/07.42-D | [34 empty] | 01N-0422-R3 | 01N-0561-R2 |  |  | 01N-1079-W |  |  | 01S-0347-D
[5 empty] | 002-0164-R1 |  |  | 002-0707/07.42-I | [34 empty] | 01N-0422-R4 | 01N-0561-R3 |  |  | 01N-1080-W |  |  | 01S-0347-I
[5 empty] | 002-0166-R1 |  |  | 002-0707/10.85 | [34 empty] | 01N-0422-R5 | 01N-0561-R4 |  |  | 01N-1081 |  |  | 01S-0350
[5 empty] | 002-0166-R2 |  |  | 002-0721 | [34 empty] | 01N-0423-R1 | 01N-0567-R1 | [5 empty] | 01S-0350/01.87
[5 empty] | 002-0166-R3 |  |  | 002-0729 | [34 empty] | 01N-0425-R1 | 01N-0567-R2 | [5 empty] | 01S-0350/02.47-D
[5 empty] | 002-0166-R4 |  |  | 002-0743 | [34 empty] | 01N-0425-R2 | 01N-0571-R1 | [5 empty] | 01S-0350/02.47-I
[5 empty] | 002-0167-R1 | [37 empty] | 01N-0426-R1 | 01N-0571-R2 | [5 empty] | 01S-0350/02.63-D
[5 empty] | 002-0167-R2 | [37 empty] | 01N-0426-R2 | 01N-0571-R3 | [5 empty] | 01S-0350/02.63-I
[5 empty] | 002-0168-R1 | [37 empty] | 01N-0426-R3 | 01N-0571-R4 | [5 empty] | 01S-0350/03.76-D
[5 empty] | 002-0168-R2 | [37 empty] | 01N-0427-D | 01N-0574/02.93 | [5 empty] | 01S-0350/04.09-I
[5 empty] | 002-0171-R1 | [37 empty] | 01N-0427-I | 01N-0574-D | [5 empty] | 01S-0353-W
[5 empty] | 002-0171-R2 | [37 empty] | 01N-0427-R1 | 01N-0574-I | [5 empty] | 01S-0363-R1
[5 empty] | 002-0171-R3 | [37 empty] | 01N-0427-R2 | 01N-0576-R1 | [5 empty] | 01S-0363-R2
[5 empty] | 002-0171-R4 | [37 empty] | 01N-0427-R3 | 01N-0576-R2 | [5 empty] | 01S-0365/02.33
[5 empty] | 002-0171-R5 | [37 empty] | 01N-0427-R4 | 01N-0591 | [5 empty] | 01S-0365-D
[5 empty] | 002-0177-D | [37 empty] | 01N-0427-R5 | 01N-0593-R1 | [5 empty] | 01S-0365-I
[5 empty] | 002-0177-I | [37 empty] | 01N-0428-R1 | 01N-0594 | [5 empty] | 01S-0365-R1
[5 empty] | 002-0184-R1 | [37 empty] | 01N-0428-R2 | [6 empty] | 01S-0365-R2
[5 empty] | 002-0184-R2 | [37 empty] | 01N-0428-R3 | [6 empty] | 01S-0365-R3
[5 empty] | 002-0184-W | [37 empty] | 01N-0428-R4 | [6 empty] | 01S-0365-R4
[5 empty] | 002-0185/00.22 | [37 empty] | 01N-0429-R1 | [6 empty] | 01S-0381
[5 empty] | 002-0185-D | [37 empty] | 01N-0429-R2
[5 empty] | 002-0185-I | [37 empty] | 01N-0429-R5
01N-0430-R1
01N-0430-R2
01N-0431/11.16-I
01N-0431/11.17-D
01N-0431-D
01N-0431-I
01N-0431-R1
01N-0431-R2
01N-0432-R1
01N-0433-R1
01N-0433-R2
01N-0434-R1
01N-0434-R2
01N-0434-R3
01N-0434-R4
01N-0434-R5
01N-0434-R6
01N-0434-W
01N-0435-R1
01N-0435-R2
01N-0436-R1
01N-0436-R2
01N-0436-R3
01N-0436-R4
01N-0436-R5
01N-0436-R6
01N-0436-W
01N-0437-R1
01N-0437-R2
01N-0437-R3
01N-0438-R1
01N-0438-R2
01N-0438-R3
01N-0438-R4
01N-0441-R1
01N-0441-R2
01N-0441-R3
01N-0441-R4
01N-0443-R1
01N-0443-R2
01N-0443-R3
01N-0443-R4
01N-0444-R1
01N-0444-R2
01N-0444-R3
01N-0444-R4
01N-0447-R1
01N-0447-R2
01N-0448/05.06-D
01N-0448/05.06-I
01N-0448-D
01N-0448-I
01N-0448-R1
01N-0448-R2
01N-0448-R3
01N-0448-R4
01N-0448-R5
01N-0448-R6
01N-0448-R7
01N-0448-R8
01N-0451-R1
01N-0451-R2
01N-0454-R1
01N-0454-R2
01N-0454-R3
01N-0454-R4
01N-0458-R1
01N-0458-R2
01N-0458-R3
01N-0458-R4
01N-0458-R5
01N-0460-R1
01N-0460-R2
01N-0461/01.31-D
01N-0461/01.31-I
01N-0461/12.98-D
01N-0461/12.99-I
01N-0461-D
01N-0461-I
01N-0462-R1
01N-0462-R2
01N-0462-R3
01N-0462-R4
01N-0466-R1
01N-0466-R2
01N-0466-R3
01N-0466-R4
01N-0472-R1
01N-0472-R2
01N-0472-R3
01N-0472-R4
01N-0472-R5
01N-0472-R6
01N-0474-R1
01N-0474-R2
01N-0474-R3
01N-0474-R4
01N-0475-R1
01N-0475-R2
01N-0475-R3
01N-0475-R4
01N-0477-D
01N-0477-I
01N-0477-R1
01N-0477-R2
01N-0478-R1
01N-0478-R2
01N-0478-R3
01N-0478-R4
01N-0479-R1
01N-0479-R2
01N-0480-R1
01N-0480-R2
01N-0481-R1
01N-0483-R1
01N-0483-R2
01N-0483-R3
01N-0483-R4
01N-0486-D
01N-0486-I
01N-0488-R1
01N-0490-R1
01N-0491-R1
01N-0491-R2
01N-0494-R1
01N-0494-R2
01N-0494-R3
01N-0494-R4
01N-0502-R1
01N-0502-R2
01N-0502-R3
01N-0502-R4

## EXAMPLE Change Form
Change Management Record - 21/22 Annual Plan (ALL FIELDS ARE TO BE COMPLETED)
| Network |  |  | SAP Project Type |  |  |  |  | SAP Project Name |  | Year | Change No
|  |  |  | Select Project Name (2) |  |  |  |  | Project Name + Network (3) |  | 21/22 | yyyymm_001
Documenting the changes made from a baseline which is the current version of the annual plan on the server So, the changes include any changes made as a result of the initial moderation feedback and changes made by the initial moderation work | [10 empty] | Sign off as per the delegations in change management process
Telling us what has been changed and why | [6 empty] | By how much | Residual Risk and Management Plan
WBS | Work Category | Nature of change | What have you changed and why including link to revised programmes |  |  |  | Funding change +/- ($k) | Risk/Opportunity | The consequences of the changes on Annual Plan, Programme and/or Waka Kotahi, and how these have been considered/managed |  | SUBMITTED by | NM Approved (Y/N)
60100595 | WC111 | Cost Change >30% | Additional cost to complete that exceeds allocation |  |  |  |  | High risk impact | funding this expenditure will need to come from other projects within TAC
60029445 | WC215 | Lane Change | from x to y, see programme tab |  |  |  |  | Moderate risk impact | Removed from 21.22 which could require additional maintenance
60034133 | WC212 CS | Length Change >30% | reduced length of Chipseal, see programme tab |  |  |  |  | Opportunity | Changed year to align with Council development
60029273 |  | Rework | [5 empty] | Shared Risk | Shared risk profile on rework
|  | Site completed in Previous Year | [5 empty] | Other (MUST specify)
Site carried Over from Previous Year
Other (MUST specify)
|  | WBS / Project Correction from Allocation | Change of WBS allocation
[5 empty] | Total Requested | 0
[5 empty] | Total Approved | 0
Senior Network Managers Endorsment
|  |  | Name |  |  | Date
Senior Network Managers Recomendations:
Approvals (see change management process for for futher details) DO NOT TYPE OVER GREEN CELLS | [9 empty] | Comments
Required |  | Principal Asset Integrator |  |  |  | Date
Required |  | Principal Structural Engineer |  |  |  | Date
Not Required |  | System Manager |  |  |  | Date
|  | Endorsed by APMT |  |  |  | Date
Approval Comments:
Updates | [9 empty] | Comments
|  | Achievement tracker |  |  |  | Date
|  | Allocations |  |  |  | Date
Comments:
Note on K2: #N/A means lookup has not found a valid code - try a different SAP Project Name
Note on P3: NAMING CONVENTION yyyymm_001 include year and month then _ with a sequential number for ease of tracking
Note on H22: This is the sum approved by two TAs (or equivalent)

## EXAMPLE Change to Prog
DO NOT enter in these cells
Line item no# | Tracker ID | Select Network first then State Highway to populate the RoadName lookup |  | Start | End | Length | No. of lanes | Lane Name | Lane km | Current / Proposed Treatment | What is the nature of the change? | Description/ Explanation/ Justification on Performance Impacts | Funding change +/- ($k) | Work Category | Intended month of completion. | Approval as per Instructions
[16 empty] | Justified change to baseline? | Line approved (Y/N)
|  | State Highway | Road Name
1 |  | 002AUCK_ALLIANCE | 002-0000 |  |  | 0 |  | All | 0 |  | Lane Change |  |  | WC124
2 |  | 018AUCK_ALLIANCE | 018-0002-R1 |  |  | 0 |  | L2 | 0 |  | Length Change >30% |  |  | WC212 TAC
3 |  | 004WEST_WAIKATO_SOUTH | 004-0000 |  |  | 0 |  | R2 | 0 |  | Rework |  |  | WC212 SCRIM
4 |  | 099SOUTHLAND | 099-0031 |  |  | 0 |  | Left Lanes | 0 |  | Site Deferred (MUST indicate to what year) |  |  | WC212 CS | March
5 | [5 empty] | 0 |  |  | 0
6 | [5 empty] | 0 |  |  | 0
7 | [5 empty] | 0 |  |  | 0
8 | [5 empty] | 0 |  |  | 0
9 | [5 empty] | 0 |  |  | 0
10 | [5 empty] | 0 |  |  | 0
[12 empty] | Total Requested | 0
[12 empty] | Total Approved | 0