# SH73 Waimakariri Bluffs and Paddy’s Bend - Business Case

# Part of Enhanced Network Resilience –Canterbury, Year 1 Implementation

| RTC Region: Region 11 (North Canterbury) | Submitted by: Maintenance Contract Manager Barry Stratton Phone: 03 964 2812 | Date: 2 May 2016 |
| --- | --- | --- |
| NOC Region: North Canterbury |  |  |

### Part A – Project Overview

#### Previous Application

Has this project/work been applied for previously - under either Preventive Maintenance or Resilience Improvements?

Yes ☐				No ☒

If yes, has significant change occurred since the last application (detail what has changed)? NA

#### Problem Definition

Rockfall has repeatedly affected the SH73 corridor between Mt White and Bealey resulting in high maintenance and operations costs, outages and puts road users at a safety risk. These outages cause social and economic impacts, and potential safety/personal security issues including damage to vehicles; punctures, door/panel/roof, windows and windscreens.

#### Problem Background

Waimakariri Bluffs and Paddy’s Bend are the two most significant rockfall sites on State Highway 73 (SH73) between Christchurch and Arthur’s Pass, based upon the current NZTA rockfall hazard rating system. Several studies have indicated that based upon BCRs the current strategy of clearing up of rockfall debris is sub-optimal for maintenance costs, traffic disruption and Life Safety risk.

Previous reports include:

- Transfund New Zealand reports 134 and 135, 1999

- SH73 Route Security Strategic Study, 2007

- SH73 Waimakariri Bluffs and Paddy’s Bend - Rockfall Risk Assessment and Mitigation Effectiveness Study, OPUS 2015

#### Benefits of fixing the problem

Improved resilience of SH73 addressing rock fall/slips risk leading to reduction in maintenance activity, Life Safety risk levels and improved route resilience to outage from small to moderate rockslides.

#### Site Description

There are a series of unstable rock slopes above and below SH73, starting from around 8km east of Bealey Settlement.

| SH: 73, 8km east of Bealey settlement | ONRC Classification: Regional | AADT (2014): 1316 |
| --- | --- | --- |
| RS: 121 |  |  |
| RP Start: 2.650 |  |  |
| RP Finish: 6.500 |  |  |

NZTM

X 1564982.2, Y 5672158.6

X 1564982.2, Y 5672158.6

#### Baseline Rockfall and crash information

|  | Paddy’s Bend (RP121/6.215) | Waimakariri Bluffs (RP121/4.920) |
| --- | --- | --- |
| ## Length of site (m) | Approximately 100 m | Approx. 250 -400 m |
| ## Height of site (m) | 80 – 90 m | 20 – 45 m |
| ## Rockfall History/Likelihood of rocks landing on road ## (e.g. few, occasional, often or constant falls throughout year). | Constant falls throughout the year: continued detritus accumulation; individual rockfall <1500mm greywacke monthly and rockslides 5-25,000 m3 (24hr closure in 2012). | Constant falls throughout the year: continued detritus accumulation; individual rockfall <900mm greywacke monthly and rockslides 5-25,000 m3. |
| ## 5 year History of rockfall and related crashes | Fatal / Serious = none. (9 in 15 years) Minor = approximately one vehicle / boulder interaction every other week. | Fatal / Serious = none. (9 in 15 years) Minor = approximately one vehicle / boulder interaction every other week. |
| ## Average Recurrance Interval (ARI) for fatality | 29-52 years, Reduces by factor of 10 with intervention (325 to 591 years) | 41-75 years, Reduces by factor of 10 with intervention |
| ## Likely Mitigation ## (e.g. scaling, fencing, bolting etc.) | Localised source removal followed by installation of a 2,000kJ 4 – 5 m high attenuator | Scaling and Mesh and bolt/ throated drape |
| ## RHRS Score (Highest in region 11) | 632 @2015 | 563 |
| ## Cost Estimate ($k) | $630k – $800k NPV $0.7m to $0.9m | $485k – $670k NPV $0.5m to $0.7m |

Sourced from:

SH73 Waimakariri Bluffs and Paddy’s Bend – Rockfall Risk Assessment and Mitigation Effectiveness Study, OPUS, June 2015.

#### Project Objectives

Reduce the number and impacts of small to moderate rockslides on this section of SH73 to improve route resilience, reduce maintenance activity and reduce Life Safety risk levels.

| Project Objectives |  |
| --- | --- |
| Objective One | Reduction in maintenance activity |
| Objective Two | Reduction in Life Safely risk levels |
| Objective Three | Provide improvements in Route Resilience from outage due to`` small to moderate rockslides |

#### Has the activity been included in the current RLTP and NLTP?

Yes, Enhanced Network Resilience – Canterbury is included in the current RLTP and NLTP (2015-18).

The programme is a three year programme, with this business case being for the first year top priority activity.

See SAP # 107972014 and TIO 107972014, with supporting documentation:

Resilience Strategic Case v2 Final.DOC

13 Canterbury 15_16 Enhanced Network Resilience.XLS

#### Primary Outcome (TIO)

#### Secure and resilient network

Other outcomes:

- Journey time reliability

- Efficient freight supply chains

- Reduced deaths and serious injuries

- Reduced environmental impacts

#### Project Options Development

A number of options were considered as reported by OPUS in the report: “SH73 RP121/2.65-6.50 Waimakariri Bluffs and Paddy’s Bend, Rockfall Risk Assessment and Mitigation Effectiveness Study”. The assessment quantified the rockfall, causes, consequences, risk and effectiveness of mitigation at the two sites. These sites have the highest Rockfall Hazard Rating in Region 11.

SH73 is a “regional” state highway that provides direct connection between Canterbury and the West Coast, particularly for connection to the national and regional support services in Christchurch. The SH73 Route Security Study (2007) considered the option of closing the route but this would be unacceptable to the public. Alternative alignments are unaffordable and have significant environmental impacts with the adjacent Waimakariri River.

The options considered have therefore focused on how to reduce the rockfall risk on the existing SH73 corridor.

Following the Canterbury earthquake sequence (2010 / 2011) significant development and research

into the appropriate choice and design of rockfall protection systems has been made. As a result of

this the Christchurch City Council (CCC) produced a Rockfall Protection System (RPS) guideline17.

Within this guideline there are references to two methodologies used to appropriately size rockfall

protection systems18,19. These two methods, plus a general simplified method developed as part of

the Port Hills Geotechnical Group (PHGG) have been used to provide preliminary barrier designs.

Due to the need to regularly remove accumulations of debris from within any rockfall barrier and

minimise the requirement for replacement parts (i.e. brake elements), an attenuator system is

considered to be the most appropriate at Paddy’s Bend. Boulders reaching the attenuator will ultimately be guided down to highway level behind the attenuator drape. At highway level a low height wall (or small catch ditch) will be required to ensure the boulders remain outside the trafficked highway surface.

Mitigation requirements at Waimakariri Bluffs are significantly different to those required at

Paddy’s Bend with the site lending itself to an ‘at source treatment’, typically anchored mesh with

localised spot bolting or a throated drape system.

| Alternative Project Options | Description of Activity | Cost (Capital and maintenance) | Assessment of Options, ALARP Appropriate mitigation expenditure ratio |
| --- | --- | --- | --- |
| Do Nothing Option | Leave as is, ongoing rockfall and maintenance operations | NPV $0.85m | The problem will get worse/road failure will occur |
| Prelim. Option 1 | Monitoring/warning system | Low | Minimal crash reduction, indicative BCR 1.8 |
| Prelim. Option 2 (explore further) | Wire mesh rockfall catchfence | Moderate | Good crash reduction, indicative BCR 11 |
| Prelim. Option 3 | Scaling, bolting and gabion wall rockfall catchfence | Moderate | Good crash reduction, higher cost, indicative BCR 6.1 |
| Prelim. Option 4 | Scaling, bolting and wire mesh netting | High | Good crash reduction, high cost, indicative BCR 4.3 |
| Prelim. Option 5 | Rock fall shed | High | High cost, indicative BCR 1.2 |
| Paddys Option 1 Attenuator | 1,000 kJ, 4-5m high attenuator fence | $0.4m to $0.54m: NPV $1.1m to $1.5m | 1.0:0.4 |
| Paddys Option 2 Attenuator (Preferred) | 2,000 kJ, 4-5m high attenuator fence | $0.63m to $0.80m: NPV $0.95m to $1.5m | 1.0:0.6, improved level of mitigation at appropriate cost |
| Paddys Option 3 | Drill and blast benching (entire crest) | $1.43m to $2.31m | 1.0:1.3, High cost rejected |
| Waimak Bluffs (Preferred) | Mesh & bolt / throated drape rockfall mitigation system | $0.48m to $0.67m | 1.0:1.5 |

#### Project Description and costs

Paddys Bend: rock scaling with design and installation of a 2,000 kJ, 4 – 5 m high attenuator, Expected cost $875,000 ($0.7m to $0.90m, NPV including maintenance $1.1m to $1.7m)

Waimakariri Bluffs: rock scaling with mesh & bolt / throated drape rockfall mitigation system, Expected cost $485,000 (NPV $0.48m to $0.67m)

Total Expected cost for Enhance Network Resilience Year 1:

$1.36m ($1.11m to $1.47m)

#### Benefits of solution

| Benefit | Measure |  |  |  |
| --- | --- | --- | --- | --- |
| Reduction in maintenance activity | Do Minimum capital and maintenance cost, whole of life NPV $0.85m for unplanned maintenance activity | Option capital and maintenance cost, whole of life NPV $0.95m, including planned maintenance activity $0.25m | Improved option for lower cost planned maintenance activity |  |
| Life Safety risk levels (reduced) | Do minimum risk of fatal crashes, NPV $1.3m | Option risk of fatal crashes, NPV $0.15m, significant reduction | ARIfatality from unacceptable to acceptable | AIFR (PMAR), Tolerable (ALARP) 7.4*10-5 down to 6.9 *10-6 (1 in 13514 year return down to 1 in 144,928) |
| Improved route resilience | Societal risk: Do Minimum: unacceptable small or large rockslide buries coach or large boulder impacts coach | Societal risk reduced | Reduced risk profile by 25 to 50% |  |

#### Resilience Information

## Do - Nothing Option

| Description of the failure mode if nothing done: Rockfall |  |  |
| --- | --- | --- |
| Cost of reinstatement + Annual Maintenance | (A) | $75k |
| Probability of occurrence in next 12 months Certain = 0.8 Probable = 0.5 Possible = 0.2 | (B) | 0.8 |
| National Cost | (C) = A x B | $60k |

## Resilience Options

| Options Considered | Capital Cost | Life | Any Additional Abnormal Maintenance Costs | Agency Costs 25 yr NPV (D) | Maintenance Priority Index C/D |
| --- | --- | --- | --- | --- | --- |
| (Examples) - Attenuator | $700k | 40 | $250k | $950k | 0.06 |

## Safety Consequences

Describe safety consequences of doing nothing: Rockfall related fatality within the next 30 years.

Probability of occurrence: 0.033

| Describe route security consequences of doing nothing: |  |  |
| --- | --- | --- |
| Probability of occurrence | (B) (See B in 8.1) | 0.8 |
| Probable length of full road closure (Days) | (X) | 0.25 |
| Detour length (Km) | (Y) | 100 |
| ADT | (Z) | 1269 |
| Security Factor | Multiply B, X, Y& Z | 25380 |

### Part B – Project Assessment

#### Risk Assessment

The risk assessment has reviewed existing rockfall and crash records, interviewed key personnel, undertaken quantitative rockfall risk assessment and considered the return period of fatality, the annual individual fatality risk, and the societal risk. This has identified that incidents have happened in the past leading to a 24 hour closure (25,000 m3 of rockfall) and are likely to occur in the future. The risk is therefore considered as High to Extreme.

##### Risk assessment procedure

Descriptor; Consequence; Insignificant; Minor; Moderate; Major; Critical. Probability; Description; Minor delays during clean-up and/or insignificant risk to users; Reduced capacity and/or low risk to users; Reduced to half the capacity for more than 24 hours and/or unacceptable risk to users; Route closed for more than 24 hours and/or major risk to users; Sever the route and/or extreme risk to users. Almost Certain; Expected to occur in most circumstances; High; High; Extreme; Extreme; Extreme. Likely; Will probably occur in most circumstances; Low; High; High; Extreme; Extreme. Possible; Might occur at sometime; Negligible; Low; High; Extreme; Extreme. Unlikely; Could occur at sometime; Negligible; Negligible; Low; High; Extreme.

#### Strategic Fit and Effectiveness Profile (MM)

STRATEGIC FIT

| Explanation | Rating |
| --- | --- |
| Safety Reduces risk of death and injury to road users Reduces risk of damage to vehicles Resilience Reduces likelihood of outage due to rockfall Reduces ongoing maintenance activity and costs | MEDIUM MEDIUM OVERALL RATING: MEDIUM |

EFFECTIVENESS

| Component | Explanation | Rating |
| --- | --- | --- |
| Outcomes focussed | - Clearly defined benefits - ONRC= regional, target for resilience is: - route is always available except during major-extreme weather or emergency events and viable alternatives nearly always exist - Rapid clearance of incidents affecting road users. - Road users may be advised in advance of issues | HIGH |
| Integrated | Resilience is the key problem that leads to safety risks. Intervention reduces risk of both. | MEDIUM* |
| Correctly scoped | A range of options have been considered and appropriate ALARP solution chosen. | MEDIUM* |
| Affordable | Enhanced Network Resilience included in NLTP as three year programme. Paddys’s Bend and Waimak Bluffs are year one of this programme. The options chosen are at appropriate level of investment and offer reduced whole of life maintenance costs. | MEDIUM* |
| Timely | There are ongoing rockfall events with risk to road users and high ongoing maintenance cost. Reducing the risk and likelihood is timely for intervention. | HIGH |
| Confidence | The problem has been well researched and is able to be implemented. | HIGH* |
| Overall | Assessment based on lowest rating of all components | MEDIUM* |

#### Efficiency Profile - Present Value Calculations

The early development work used Transfund Research Report 134 and Economic Evaluation Manual (EEM) procedures with assumed risk reduction of 25 to 40%. This identified high benefits cost ratio (up to BCR =13) for the installation of rockfall mitigation measures. This analysis was then updated using the latest EEM to assess 10% discount over 25 years, and 6% over 40 years, and a lower risk profile, that reduced the BCR by around 14%.

The economic analysis was then updated for Paddy’s Bend using the latest project capital and maintenance costs, and resultant costs of crashes.  This identified NPV of fatal accidents reduce from $1.3m for the Do Minimum to $0.15 million for the option. Fatal crashes represent around 32% of the total crash savings, and hence total NPV crash benefits are around $5.55m.

The NPV cost (maintenance and capital) for the option is $1.69m, as opposed to $0.85m for the Do Minimum. The NPV net cost is therefore $0.84, giving an overall BCR of 6.6. Sensitivity testing using the 95%ile cost gives a BCR of 4.9.

Refer: SH73 Waimak Bluff and Paddys Bend ENResilience EEM_Summary.xlsx

#### Supporting Documents

SH73 Waimakariri Bluffs and Paddy’s Bend – Rockfall Risk Assessment and Mitigation Effectiveness Study, June 2015, OPUS

## SH73 Waimak Bluff and Paddys Bend ENResilience EEM_Summary.xlsx

## Recommendation endorsed by: ________________________________________

Network Manager/Maintenance Contract Manager

## Recommendation endorsed by: ________________________________________

Principal Asset Manager Integrator (local)

National office use only:

Application assessed by: ___________________________________________

Application Rank/Score:

Appendix 1: Supporting Information