## EXAMPLE
Template example (adapted from Waka Kotahi Z/44 Risk management practice guide)
Note: The environmental risks detailed in this register are subject to variations dependent on the project/contract. These are not to be used as standard risks.
Risk identifier | Date raised (dd/mm/yy) | Activity | Sub activity (if relevant) | Details of activities | Environmental topic | Environmental risk description (impact or opportunity) | Risk owner | Uncontrolled (current) risk |  |  | Environmental management reference and tools | Mitigation measure (controls/treatments) | Controlled (residual) risk
|  | Activity |  |  |  |  | Risk owner | Likelihood | Consequence | Risk level |  |  | Likelihood | Consequence | Residual risk level
1 | 2022-07-20 | Earthworks and excavations | Cut and fill/stockpilling | Any works involving land disturbing activities. | Air quality | Dust causing a nuisance to staff, road users and neighbouring properties [refer to Sensitive Sites]. | Environmental manager | Possible | Insignificant | Low | EP6 - Dust control | Identify work tasks that may result in dust. Have a dust management plan. | Unlikely | Insignificant | Low
2 | 2022-07-20 | Earthworks and excavations | Stormwater drain excavations | Any works involving land disturbing activities. | Ecology | Erosion of soils and generation of sediment may impact upon slope stability, visual quality and affect ecological communities. | Environmental manager | Likely | Minor | Medium | EP7 - Erosion and sediment control | Erosion prevention procedures including minimising earth disturbed and stabilising disturbed surfaces. | Unlikely | Minor | Low
3 | 2022-07-20 | Earthworks and excavations | Eathworks within 10m of stream | Any works involving land disturbing activities. | Freshwater quality | Sediment entering streams and other water bodies can affect water quality and impact upon aquatic ecosystems [refer to Sensitive Sites]. | Environmental manager | likely | Moderate | High | EP7 - Erosion and sediment control | Protect water bodies and stormwater systems potentially affected by the activity. | Unlikely | Moderate | Medium
4 | 2022-07-20 | Earthworks and excavations | Heavy machineary use requiring compactor | Any works involving land disturbing activities. | Noise and vibration | Noise nuisance may affect neighbouring land occupiers [refer to Sensitive Sites]. | Environmental manager | likely | Insignificant | Low | EP10 - Noise | Keep noise levels to the acceptable standard as set in NZS 6803:1999 and given in EP 10. Notify residents. | Unlikely | Insignificant | Low
5 | 2022-07-20 | Earthworks and excavations | Cut and fill | Any works involving land disturbing activities. | Historic heritage | Known cultural or heritage assets not recognised. Damage to undiscovered archaeological sites [refer to Sensitive Sites]. | Environmental manager | Possible | Severe | High | EP 3 - Archaeology, EMP, Appendix 3 | Identify where known culture and heritage assets are. Archaeologist to assess network for likely risk of undiscovered items. Knowledge of what to do in the event of discovering an unknown site. | Unlikely | Severe | Medium
6 | 2022-07-20 | Earthworks and excavations | Cut and fill | Any works involving land disturbing activities. | Human health | Exposure of contaminated land may impact human health and water quality of runoff. [refer to Sensitive Sites] | Environmental manager | Almost certain | Moderate | High | EP 5 - Contaminated land | Map known contaminated land sites. Procedure on how to identify contaminated land. | Unlikely | Moderate | Medium
7 | 2022-07-20 | Infrastructure mangement | Road sweeping | Sweeping roads using sweeper trucks. | Freshwater quality | Sweepings entering the stormwater system. | Environmental manager | likely | Minor | Medium | EP 16 - Road sweepings | Maintain sweeper trucks and operate as per EP16. | Unlikely | Minor | Low
8 | 2022-07-20 | Infrastructure mangement | Road sweeping | Sweeping roads using sweeper trucks. | Freshwater quality | Inappropriate disposal of sweepings. | Environmental manager | Almost certain | Minor | Medium | EP 23 - Waste management | Dispose of waste at approved landfills. | Rare | Minor | Low
9 | 2022-07-20 | Earthworks and excavations | Cut and fill/stockpilling | Any activity requiring stockpiling of materials. | Air quality | Unmaintained and insecure stockpile leading to sediment-laden runoff off entering the environment. | Environmental manager | Almost certain | Insignificant | Low | EP 18 - Stockpiling | Careful positioning of stockpile. Use of sediment treatment devices and runoff diversions (eg bunds). | Unlikely | Insignificant | Low
10 | 2022-07-20 | Earthworks and excavations | Cut and fill | Any activity requiring stockpiling of materials. | Flora, fauna and habitats | Unmaintained open areas leading to establishment and spread of pest plants. | Environmental manager | Possible | Minor | Medium | Pest management plan | Control pest plants before seeding. Ensure material from stockpiles is not contaminated when spread in areas. | Unlikely | Minor | Low
11 | 2022-07-20 | Storange and use of hazardous substance | Solvents use | Storage of substances classified as hazardous both at the depot and onsite. | Hazardous substances | Contamination of land or water from leaks or spills. | Environmental manager | Possible | Severe | High | EP 9 - Storage of hazardous substances | Storage facilities that comply with HSNO Act 1996. Procedures for storage and handling. Spill response procedures and equipment fully stocked and available. | Unlikely | Severe | Medium

## RISK TEMPLATE
Risk identifier | Date raised (dd/mm/yy) | Activity | Sub activity (if relevant) | Details of activities | Environmental topic | Environmental risk description (impact or opportunity) | Risk owner | Uncontrolled (current) risk |  |  | Environmental management reference and tools | Mitigation measure (controls/treatments) | Controlled (residual) risk
|  | Activity |  |  |  |  | Risk owner | Likelihood | Consequence | Risk level |  |  | Likelihood | Consequence | Residual risk level

## RISK MATRICES
RISK MATRICES
Adapted from Waka Kotahi Z/44 Risk management practice guide
Likelihood score and rating
Likelihood rating | Description
Almost certain | Is expected to occur in most circumstances (>85% chance of occuring)
Likely | Will probably occur in most circumstances (55% to 85% chance of occuring)
Possible | Could occur (30% to 55% chance of occuring)
Unlikely | Could occur but not expected (5% to 30% chance of occuring)
Rare | Occurs but only in exceptonal cicumstances (<5% chance of occuring)
Consequence score and rating
Consequence rating | Description – impact | Description – opportunity
Extreme | Permanent pollution damage or other environmental damage | Demonstrate environmental innovation likely to lead to changes in international standards
Severe | Significant and widespread pollution or other environmental damage, with long-term effects | Demonstrate environmental innovation likely to lead to changes in national standards
Moderate | Pollution or other environmental damage at a localised level, with medium-term effects | Demonstrate a number of enhancements to environmental best practice
Minor | Minimum pollution or other environmental damage. Short-term effects only | Demonstrate industry leading application of environmental best practice
Insignificant | Small scale pollution or other environmental damage is localised with no resultant effects. Contained locally | Demonstrates compliance with environmental practice
Likelihood and consequence are used to determine the overall risk level
| Insignificant | Minor | Moderate | Severe | Extreme
Almost certain | Low | Medium | High | Critical | Critical
Likely | Low | Medium | High | Critical | Critical
Possible | Low | Medium | Medium | High | Critical
Unlikely | Low | Low | Medium | Medium | High
Rare | Low | Low | Low | Low | High

## data lists
| Insignificant | Minor | Moderate | Severe | Extreme | Risk status
Almost certain | Low | Medium | High | Critical | Critical | Draft
Likely | Low | Medium | High | Critical | Critical | Live-Treat
Possible | Low | Medium | Medium | High | Critical | Live-Parked
Unlikely | Low | Low | Medium | Medium | High | Impacted
Rare | Low | Low | Low | Low | High | Closed
Rejected
| Low | Medium | High | Critical