## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Group Phase | Latest Phase profile | Priority | Request Decision | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR
2016-04-27 | April 2016 Review | New approval | Investment management (incl. Transport Planning) | Activity management planning improvement | BOP Highway & Network Operations | Activity Management Plan Bay of Plenty 15/18 | Programme business case |  | HM_ | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 526500 | 526500
2016-04-22 | April 2016 Review | New approval | Investment management (incl. Transport Planning) | Activity management planning improvement | Kapiti Coast District Council | Activity Management Plan Review | Programme business case |  | HH_ | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 286263 | 137426
2016-04-19 | April 2016 Review | New approval | Investment management (incl. Transport Planning) | Activity management planning improvement | Wairoa District Council | Bridge Asset Management Plan | Study |  | MH_ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 50000 | 34000
2016-04-22 | April 2016 Review | New approval | External funding | Cycling facilities | Hutt City Council | The Beltway Investigation Design Delivery | Implementation | UCF ADMIN (BELTWAY) | HH6.5 | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1303000 | 1303000 |  | 6.5 | 6.5 | 6.5
2016-04-22 | April 2016 Review | New approval | Walking and cycling improvements | Cycling facilities | Hutt City Council | The Beltway Investigation Design Delivery | Indicative Business Case |  | HH6.5 | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 100000 | 51000 |  | 6.5 | 6.5 | 6.5
2016-04-22 | April 2016 Review | New approval | Walking and cycling improvements | Cycling facilities | Kapiti Coast District Council | Urban Cycleway Fund programe | Construction | Construction of UCF projects (NLTF funding) | HH10.6 | 1 | Approved with conditions | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Investment Transport online or by request | 3232196 | 1559748 | Council agrees to share phase outputs as soon as they are available and this is shared with the Agency prior to claiming expenditure for the subsequent phase of each project (e.g. The Agency holds IBC and DBC information for any project progressing to construction). | 10.6 | 0 | 10.6
2016-04-22 | April 2016 Review | New approval | Walking and cycling improvements | Cycling facilities | Kapiti Coast District Council | Urban Cycleway Fund programe | Detailed Business Case | Design (UCF Programme) | HH10.6 | 1 | Approved with conditions | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Investment Transport online or by request | 198214 | 94403 | Council agrees to share phase outputs as soon as they are available and this is shared with the Agency prior to claiming expenditure for the subsequent phase of each project (e.g. The Agency holds IBC detail for any project progressing to specimen design). | 10.6 | 0 | 10.6
2016-04-22 | April 2016 Review | New approval | External funding | Cycling facilities | Kapiti Coast District Council | Urban Cycleway Fund programe | Implementation | UCF Funding (as per MOU) | HH10.6 | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1575000 | 1575000 |  | 10.6 | 0 | 10.6
2016-04-22 | April 2016 Review | New approval | Walking and cycling improvements | Cycling facilities | Kapiti Coast District Council | Urban Cycleway Fund programe | Indicative Business Case | Feasibility (UCF projects) | HH10.6 | 1 | Approved with conditions precedent | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Investment Transport online or by request | 34335 | 16137 | Council agrees to share phase outputs as soon as they are available and this is shared with the Agency prior to claiming expenditure for the subsequent phase of each project (Agency receives the outputs of each project IBC before committing to design or construction of that project). | 10.6 | 0 | 10.6
2016-04-29 | April 2016 Review | New approval | Walking and cycling improvements | Cycling facilities | Rotorua Lakes Council | Rotorua Urban Cycleways | Implementation | NLTF and local share | HH4.9 | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 4020000 | 2105200 |  | 4.9 | 4.9 | 4.9
2016-04-29 | April 2016 Review | New approval | External funding | Cycling facilities | Rotorua Lakes Council | Rotorua Urban Cycleways | Implementation | UCP | HH4.9 | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1500000 | 1500000 |  | 4.9 | 4.9 | 4.9
2016-04-11 | April 2016 Review | New approval | State highway maintenance | Emergency works | Otago Highway & Network Operations | (E) SH6 Pipson Creek Flood 18 Feb16 | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 126360 | 126360
2016-04-18 | April 2016 Review | New approval | State highway maintenance | Emergency works | Waikato Highway & Network Operations | SH 4 Mansonâ€™s Tomo | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 89505 | 89505
2016-04-04 | April 2016 Review | New approval | Local road maintenance | Emergency works | Westland District Council | Jackson Bay Road. Rain fall event damage. 24 January 2016 | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 150000 | 150000
2016-04-14 | April 2016 Review | New approval | Local road improvements | New roads | Tauranga City Council | Grenada Street Connection | Construction | Construction | HM9 | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1300000 | 539085 |  |  | 9 | 9
2016-04-22 | April 2016 Review | New approval | Investment management (incl. Transport Planning) | Programme Business Case Development | Hutt City Council | The Beltway | Programme business case |  | HH_ | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1 | 1
2016-04-11 | April 2016 Review | New approval | Public transport | Public transport improvements, major renewals and minor improvements | Auckland Transport | Station Lvl of Servic Impr. - Morningside Lvl Crossing Impr. | Implementation | Morningside Level Crossing Improvements | HM31.7 | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1333229 | 679947 |  |  | 31.7 | 31.7
2016-04-22 | April 2016 Review | New approval | Local road improvements | Resilience improvements | Hutt City Council | Bridge Corrosion Protection | Construction |  | HHM | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1100999 | 561509
2016-04-07 | April 2016 Review | New approval | State highway improvements | Road improvements | Auckland Highway & Network Operations | Auck Accelerated Prog: Southern Corridor Improvements | Repayment | Repayment | HH13 | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 241324627 | 241324627 |  | 13 | 0 | 6
2016-04-07 | April 2016 Review | New approval | State highway improvements | Road improvements | Auckland Highway & Network Operations | SH20A to Airport | Repayment | Repayment | HM1.7 | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 128716511 | 128716511 |  | 1.7 | 3.1 | 3.1
2016-04-04 | April 2016 Review | New approval | Local road improvements | Road improvements | Christchurch City Council | PT Infrastructure Investment Indicative business case | Indicative Business Case | PT Infrastructure Investment Indicative business c | HM*1.7 | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 51125 | 24540 |  | 1.7 | 1.7 | 1.7
2016-04-14 | April 2016 Review | New approval | External funding | Road improvements | Taranaki Highway & Network Operations | SH3 Mt Messenger Bypass | Detailed Business Case | Detailed Business Case | HM1.1 | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 2872800 | 2872800 |  |  | 1.1 | 1.1
2016-04-06 | April 2016 Review | New approval | Regional Improvements | Road improvements | Waikato Highway & Network Operations | SH3 (Ohaupo to Te Awamutu), NSRRP | Implementation | SH3 (Ohaupo to Te Awamutu), NSRRP | HH2.2 | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 6617700 | 6617700 |  |  | 2.2 | 2.2
2016-04-04 | April 2016 Review | New approval | State highway improvements | Road improvements | Waikato Highway & Network Operations | SH37 (SH3 to Waitomo), NSRRP | Implementation | SH37 (SH3 to Waitomo), NSRRP | HMH | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1846800 | 1846800 |  |  | 66 | 66
2016-04-19 | April 2016 Review | New approval | Local road improvements | Road improvements | Wairoa District Council | Blacks Beach Lifeline Resilience | Construction | 15/16 Construction | MM1 | 7 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 200000 | 136000 |  |  | 1 | 1.4
2016-04-22 | April 2016 Review | Cash flow adjustment | Local road maintenance | Drainage renewals | Hutt City Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | MMH | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0
2016-04-20 | April 2016 Review | Cash flow adjustment | Local road maintenance | Emergency works | Ashburton District Council | Emergency Works after 10 Sept 2013 wind events. | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -125 | -61
2016-04-26 | April 2016 Review | Cash flow adjustment | State highway maintenance | Emergency works | BOP Highway & Network Operations | EW Waioeka Gorge Slip March 2012 | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 351883 | 0
2016-04-22 | April 2016 Review | Cash flow adjustment | State highway maintenance | Emergency works | BOP Highway & Network Operations | Heavy rain events 11th & 12th October 2011 BoP east | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -10 | -10
2016-04-29 | April 2016 Review | Cash flow adjustment | Local road maintenance | Emergency works | Far North District Council | Emergency Wks Repair July/Aug 2014 Stg 1 permanent repairs | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0
2016-04-29 | April 2016 Review | Cash flow adjustment | Local road maintenance | Emergency works | Far North District Council | Emergency Works - Mangakahia Road - April 2015 | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0
2016-04-29 | April 2016 Review | Cash flow adjustment | Local road maintenance | Emergency works | Far North District Council | Emergency Works Jul/Aug 2014 event-Stage 2 permanent repairs | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0
2016-04-29 | April 2016 Review | Cash flow adjustment | Local road maintenance | Emergency works | Far North District Council | Emergency Works Jul/Aug 2014 event-Stage 3 permanent repairs | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0
2016-04-29 | April 2016 Review | Cash flow adjustment | Local road maintenance | Emergency works | Far North District Council | Emergency Works Repairs September 2013 event | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0
2016-04-29 | April 2016 Review | Cash flow adjustment | State highway maintenance | Emergency works | Nelson Highway & Network Operations | Emergency Works Nelson December Storm Events 11/12 | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0
2016-04-29 | April 2016 Review | Cash flow adjustment | Local road maintenance | Emergency works | South Taranaki District Council | Emergency Events 13/14 | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -19 | -10
2016-04-29 | April 2016 Review | Cash flow adjustment | Local road maintenance | Emergency works | South Taranaki District Council | Emergency Works June 2015 | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0
2016-04-29 | April 2016 Review | Cash flow adjustment | Local road maintenance | Emergency works | Tararua District Council | Emerency Works August 2014 | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0
2016-04-29 | April 2016 Review | Cash flow adjustment | Local road maintenance | Emergency works | Tararua District Council | Emerency Works August 2014 | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0
2016-04-29 | April 2016 Review | Cash flow adjustment | Local road maintenance | Emergency works | Tararua District Council | Emergency Works Event 23 September 2015 | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0
2016-04-22 | April 2016 Review | Cash flow adjustment | State highway maintenance | Emergency works | Waikato Highway & Network Operations | (E) 13/007/03 SH3 Mangaotaki Rest Area Slump | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -1 | -1
2016-04-06 | April 2016 Review | Cash flow adjustment | State highway maintenance | Emergency works | Waikato Highway & Network Operations | EW EW Drought Damage SH25 &26 12/13 13-003/3 | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 18 | 18
2016-04-29 | April 2016 Review | Cash flow adjustment | Local road maintenance | Emergency works | Wanganui District Council | 2015 June 20 E/works | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0
2016-04-29 | April 2016 Review | Cash flow adjustment | Local road maintenance | Emergency works | Wanganui District Council | E/Works 2013/14 | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0
2016-04-18 | April 2016 Review | Cash flow adjustment | External funding | New roads | Canterbury Highway & Network Operations | Mingha Bluff to Rough Creek | Construction | Construction | MML | 7 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  |  | 1.1 | 1.1
2016-04-22 | April 2016 Review | Cash flow adjustment | Investment management (incl. Transport Planning) | Regional land transport planning management | Nelson City Council | Regional Land Transport Programme | Programme Business Case |  | HH_ | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 75
2016-04-18 | April 2016 Review | Cash flow adjustment | State highway improvements | Replacement of bridges and other structures | Canterbury Highway & Network Operations | Seismic Retrofit - Canterbury | Construction | Construction | HMH | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -29 | -29 |  |  | 99 | 99
2016-04-18 | April 2016 Review | Cash flow adjustment | Regional Improvements | Replacement of bridges and other structures | Manawatu/Wanganui Highway & Network Operations | Whirokino Trestle and Manawatu River Bridge Replacement | Implementation | Construction | HH99 | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  | 99 | 1.5 | 1.5
2016-04-18 | April 2016 Review | Cash flow adjustment | State highway improvements | Replacement of bridges and other structures | Waikato Highway & Network Operations | Atiamuri Bridge Replacement | Construction |  | HH | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  |  | 0
2016-04-04 | April 2016 Review | Cash flow adjustment | Local road improvements | Road improvements | Christchurch City Council | Annex/Birmingham/Wrights Route Upgrade | Design | Design phase | MM*7 | 7 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 1 |  | 7 | 17 | 17
2016-04-01 | April 2016 Review | Cash flow adjustment | Regional Improvements | Road improvements | Gisborne Highway & Network Operations | Eastland Port Access | Detailed Business Case | Detailed Business Case | MM0 | 7 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  | 0 | 0 | 1.3
2016-04-22 | April 2016 Review | Cash flow adjustment | Local road maintenance | Sealed road pavement rehabilitation | Hutt City Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | MMH | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0
2016-04-22 | April 2016 Review | Cash flow adjustment | Local road maintenance | Sealed road pavement rehabilitation | Nelson City Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HMH | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 326000 | 153220
2016-04-22 | April 2016 Review | Cash flow adjustment | Local road maintenance | Sealed road resurfacing | Hutt City Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | MMH | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | -1
2016-04-22 | April 2016 Review | Cash flow adjustment | Local road maintenance | Sealed road resurfacing | Nelson City Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HMH | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -326000 | -153220
2016-04-22 | April 2016 Review | Cash flow adjustment | Local road maintenance | Structures component replacements | Nelson City Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HMH | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 740
2016-04-22 | April 2016 Review | Cash flow adjustment | Local road maintenance | Structures maintenance | Hutt City Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | MMH | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0
2016-04-22 | April 2016 Review | Cash flow adjustment | Local road maintenance | Traffic services renewals | Nelson City Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HMH | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -1541 | -740
2016-04-04 | April 2016 Review | Cost / Scope adjustment | Local road improvements | Advance property purchase | Christchurch City Council | Wigram Magdala Link | Property | Wigram Magdala Grade Separated Link | HM4 | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -142914 | -75744 |  | 4 | 4.7 | 4.7
2016-04-06 | April 2016 Review | Cost / Scope adjustment | Local road maintenance | Cycle path maintenance | Manawatu District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HMH | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -5000 | -2700
2016-04-18 | April 2016 Review | Cost / Scope adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Nelson St Cycleway | Construction | UCP Nelson St Cycleway - Phase 1 CON (NLTF) | HH2.4 | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 207547 | 110000 |  |  | 2.4 | 2.4
2016-04-20 | April 2016 Review | Cost / Scope adjustment | External funding | Cycling facilities | Auckland Transport | Nelson St Cycleway | Construction | UCP Nelson St Cycleway - Phase 1 CON (UCF) | HH2.4 | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 99653 | 99653 |  |  | 2.4 | 2.4
2016-04-20 | April 2016 Review | Cost / Scope adjustment | External funding | Cycling facilities | Auckland Transport | Nelson St Cycleway | Design | UCP Nelson St Cycleway - Phase 1 +2 DES (UCF) | HH2.4 | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 136784 | 136784 |  |  | 2.4 | 2.4
2016-04-18 | April 2016 Review | Cost / Scope adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Nelson St Cycleway | Design | UCP Nelson St Cycleway - Phase 1+2 DES (NLTF) | HH2.4 | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 255091 | 135198 |  |  | 2.4 | 2.4
2016-04-05 | April 2016 Review | Cost / Scope adjustment | Walking and cycling improvements | Cycling facilities | Hastings District Council | Model Communities 2012-15 - Collectors | Construction | Model Communities: HDC Cycling Infrastructure | HM2.1 | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 767836 | 468380 |  |  | 2.1 | 2.1
2016-04-19 | April 2016 Review | Cost / Scope adjustment | External funding | Cycling facilities | Hastings District Council | Model Communities 2015-18 Walking and Cycling | Construction | UCF Urban Cycle Fund | MH0 | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1149999 | 1149999 |  |  | 0 | 3.9
2016-04-19 | April 2016 Review | Cost / Scope adjustment | Walking and cycling improvements | Cycling facilities | Hastings District Council | Model Communities 2015-18 Walking and Cycling | Construction | Urban Cycleway Fund | MH0 | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -1149999 | -1149999 |  |  | 0 | 3.9
2016-04-19 | April 2016 Review | Cost / Scope adjustment | External funding | Cycling facilities | Napier City Council | Cycle Strategy Implementation | Construction | UCF Funded | MM*5.1 | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1721604 | 1721604 |  |  | 5.1 | 5.1
2016-04-19 | April 2016 Review | Cost / Scope adjustment | Walking and cycling improvements | Cycling facilities | Napier City Council | Cycle Strategy Implementation | Construction | UCF Funding | MM*5.1 | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -1709904 | -1709904 |  |  | 5.1 | 5.1
2016-04-06 | April 2016 Review | Cost / Scope adjustment | Local road maintenance | Drainage renewals | Manawatu District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HMH | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 351430 | 189772
2016-04-22 | April 2016 Review | Cost / Scope adjustment | State highway maintenance | Emergency works | BOP Highway & Network Operations | EW Heavy Rainfall 21.4.13 SH2 Papamoa | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1644 | 1644
2016-04-22 | April 2016 Review | Cost / Scope adjustment | State highway maintenance | Emergency works | BOP Highway & Network Operations | Heavy Rain & High Wind Event - Sept 2013 | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 3765 | 3765
2016-04-29 | April 2016 Review | Cost / Scope adjustment | State highway maintenance | Emergency works | Canterbury Highway & Network Operations | EW Heavy Rainfall June/July 2013 | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 39487 | 261739
2016-04-20 | April 2016 Review | Cost / Scope adjustment | Local road maintenance | Emergency works | Christchurch City Council | EW - Ferrymead Bridge - EQ Reinstatement - NLTP Funding | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -750000 | -680600
2016-04-05 | April 2016 Review | Cost / Scope adjustment | Local road maintenance | Emergency works | Manawatu District Council | June 2015 Flood Event | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 3914873 | 2687006
2016-04-29 | April 2016 Review | Cost / Scope adjustment | State highway maintenance | Emergency works | Manawatu/Wanganui Highway & Network Operations | E/W Manawatu/Whanganui 14/15 Region 8 | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -147645 | -147645
2016-04-29 | April 2016 Review | Cost / Scope adjustment | State highway maintenance | Emergency works | Manawatu/Wanganui Highway & Network Operations | EW West Wanganui 10/11 Region 8 (Wanganui) | Construction | Emergency Work | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 25927 | 25927
2016-04-29 | April 2016 Review | Cost / Scope adjustment | State highway maintenance | Emergency works | Nelson Highway & Network Operations | Emergency Works Nelson December Storm Events 11/12 | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1161882 | 1161882
2016-04-22 | April 2016 Review | Cost / Scope adjustment | State highway maintenance | Emergency works | Nelson Highway & Network Operations | Minor E/W Nelson | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 3571 | 3571
2016-04-29 | April 2016 Review | Cost / Scope adjustment | State highway maintenance | Emergency works | Northland Highway & Network Operations | EW Various Sites Nthland Storm Event | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -277981 | -277981
2016-04-22 | April 2016 Review | Cost / Scope adjustment | State highway maintenance | Emergency works | Southland Highway & Network Operations | (E) Southland SH94 Red Rockfall | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 2223 | 2223
2016-04-22 | April 2016 Review | Cost / Scope adjustment | State highway maintenance | Emergency works | Tasman Highway & Network Operations | Emergency Works Tasman HNO 2011/12 | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 3872 | 3872
2016-04-06 | April 2016 Review | Cost / Scope adjustment | State highway maintenance | Emergency works | Waikato Highway & Network Operations | (E) 13/006/03 SH3 Meads North Slump | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 6300 | 6300
2016-04-22 | April 2016 Review | Cost / Scope adjustment | State highway maintenance | Emergency works | Waikato Highway & Network Operations | EW East Waikato Storm Event 13-009/3 | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 6525 | 129640
2016-04-21 | April 2016 Review | Cost / Scope adjustment | State highway maintenance | Emergency works | Waikato Highway & Network Operations | EW SH23 RP32-10.25 East of Greenslade Road | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 643 | 12766
2016-04-21 | April 2016 Review | Cost / Scope adjustment | State highway maintenance | Emergency works | Waikato Highway & Network Operations | EW SH25 Slip 6 Dec 2013 | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 4240 | 4240
2016-04-06 | April 2016 Review | Cost / Scope adjustment | State highway maintenance | Emergency works | Waikato Highway & Network Operations | EW SH25 Slip 6 Dec 2013 | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 80000
2016-04-21 | April 2016 Review | Cost / Scope adjustment | State highway maintenance | Emergency works | Waikato Highway & Network Operations | EW WW 12/012/03 SH1 Fergusson Gully RP574/11.05 | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 18551 | 368571
2016-04-29 | April 2016 Review | Cost / Scope adjustment | Local road maintenance | Emergency works | Wanganui District Council | 2015 June 20 E/works | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | -1149238
2016-04-22 | April 2016 Review | Cost / Scope adjustment | State highway maintenance | Emergency works | West Coast Highway & Network Operations | (E) West Coast Rockfall August 13 | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 37940 | 37940
2016-04-22 | April 2016 Review | Cost / Scope adjustment | State highway maintenance | Emergency works | West Coast Highway & Network Operations | EW West Coast March 2015 | Construction |  | ___ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 930 | 930
2016-04-06 | April 2016 Review | Cost / Scope adjustment | Local road maintenance | Environmental maintenance | Manawatu District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HMH | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 367472 | 198435
2016-04-06 | April 2016 Review | Cost / Scope adjustment | Local road maintenance | Level crossing warning devices | Manawatu District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HMH | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -27675 | -14945
2016-04-18 | April 2016 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | BOP Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | HHM | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -277020 | -277020
2016-04-27 | April 2016 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | BOP Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | HHM | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1804734 | 1804734
2016-04-18 | April 2016 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | Canterbury Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | MHH | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 277020 | 277020
2016-04-12 | April 2016 Review | Cost / Scope adjustment | Local road improvements | Minor improvements | Hamilton City Council | Minor improvements 2015-18 | Local Roads |  | MHH | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -643018 | -327939
2016-04-05 | April 2016 Review | Cost / Scope adjustment | Local road improvements | Minor improvements | Manawatu District Council | Minor improvements 2015-18 | Local Roads |  | MMH | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | -2781
2016-04-22 | April 2016 Review | Cost / Scope adjustment | Local road improvements | Minor improvements | Nelson City Council | Minor improvements 2015-18 | Local Roads |  | MHH | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 1410
2016-04-06 | April 2016 Review | Cost / Scope adjustment | Local road maintenance | Network and asset management | Manawatu District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HMH | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 217545 | 117474
2016-04-12 | April 2016 Review | Cost / Scope adjustment | Local road maintenance | Network and asset management | Waikato Regional Council | Road Safety Promotion 2015-18 | Implementation |  | HMM | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -40000 | -20800
2016-04-04 | April 2016 Review | Cost / Scope adjustment | Local road improvements | New roads | Christchurch City Council | Wigram Magdala Link | Construction | Wigram Magdala Grade Separated Link | HM4 | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -2604933 | -1406664 |  | 4 | 4.7 | 4.7
2016-04-18 | April 2016 Review | Cost / Scope adjustment | State highway improvements | New roads | Gisborne Highway & Network Operations | Gisborne Stock Effluent Facility | Construction | Gisborne Stock Effluent Facility | MMH | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -50174 | -50174 |  |  |  | 4.4
2016-04-18 | April 2016 Review | Cost / Scope adjustment | State highway improvements | New roads | Gisborne Highway & Network Operations | HPMV SH35 Gisborne Route 1- Tolaga Bay/Matawhero to Port | Construction | SH35 HPMV Gisborne Route 1 Construction Phase | MMH | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -91301 | -91301 |  |  | 4.8 | 4.8
2016-04-18 | April 2016 Review | Cost / Scope adjustment | State highway improvements | New roads | Gisborne Highway & Network Operations | HPMV SH35 Gisborne Route 1- Tolaga Bay/Matawhero to Port | Design | SH35 HPMV Gisborne Route 1 Design Phase | MMH | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -45805 | -45805 |  |  | 4.8 | 4.8
2016-04-18 | April 2016 Review | Cost / Scope adjustment | State highway improvements | New roads | Gisborne Highway & Network Operations | HPMV SH35 Gisborne Route 1- Tolaga Bay/Matawhero to Port | Design | SH35 HPMV Gisborne Route 1 Design Phase | MMH | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -91301 | -91301 |  |  | 4.8 | 4.8
2016-04-18 | April 2016 Review | Cost / Scope adjustment | State highway improvements | New roads | Gisborne Highway & Network Operations | HPMV SH35 Gisborne Route 1- Tolaga Bay/Matawhero to Port | Investigation | Investigation | MMH | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -56686 | -56686 |  |  | 4.8 | 4.8
2016-04-05 | April 2016 Review | Cost / Scope adjustment | Public transport | Public transport improvements, major renewals and minor improvements | Horizons Manawatu | Minor improvements 2015-18 | PT Improvements |  | MHM | 5 | Approved with conditions | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Investment Transport online or by request | 0 | 150 | The trial services will need to achieve an appropriate level of effectiveness by achieving an agreed Farebox Recovery Rate. If this is met the service may then be put forward for inclusion within the PT base programme. The trial services will need to achieve an appropriate level of effectiveness by achieving an agreed Farebox Recovery Rate. If this is met the service may then be put forward for inclusion within the PT base programme.
2016-04-12 | April 2016 Review | Cost / Scope adjustment | Investment management (incl. Transport Planning) | Regional land transport planning management | Waikato Regional Council | Regional Land Transport Planning Management 2015-18 | Programme Business Case |  | HH_ | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -113 | -2009
2016-04-18 | April 2016 Review | Cost / Scope adjustment | External funding | Replacement of bridges and other structures | Gisborne Highway & Network Operations | SH2 Motu Bridge Replacement | Detailed Business Case | Detailed Business Case | LM*L* | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -30676 | -30676 |  | 1 | 1 | 1
2016-04-12 | April 2016 Review | Cost / Scope adjustment | Local road improvements | Replacement of bridges and other structures | Opotiki District Council | Pakihi Bridge Replacement | Construction | Pakihi Bridge Construction | MM22.4 | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 308050 | 184830 |  | 22.4 | 11.9 | 11.9
2016-04-18 | April 2016 Review | Cost / Scope adjustment | State highway improvements | Replacement of bridges and other structures | Wellington Highway & Network Operations | Mt Victoria Tunnel - Safety Improvements | Construction |  | HM99 | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -318994 | -318994 |  |  | 99 | 99
2016-04-18 | April 2016 Review | Cost / Scope adjustment | State highway improvements | Road improvements | Auckland Highway & Network Operations | Papakura I/C Upgrade | Construction |  | MMM | 6 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -294395 | -294395 |  |  | 1 | 0
2016-04-18 | April 2016 Review | Cost / Scope adjustment | State highway improvements | Road improvements | Canterbury Highway & Network Operations | North Ashburton Safety Works | Construction | North Ashburton Safety Works | HMH | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -55928 | -55928 |  |  |  | 10.5
2016-04-18 | April 2016 Review | Cost / Scope adjustment | State highway improvements | Road improvements | Canterbury Highway & Network Operations | North Ashburton Safety Works | Design | North Ashburton Safety Works | HMH | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 14167 | 14167 |  |  |  | 10.5
2016-04-04 | April 2016 Review | Cost / Scope adjustment | Local road improvements | Road improvements | Christchurch City Council | Intersection Improvement: Marshland/Lower Styx/Hawkins | Design | Design intersection and bridge works | HH2.5 | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 55000 | 29700 |  | 2.5 | 0 | 2.5
2016-04-04 | April 2016 Review | Cost / Scope adjustment | Local road improvements | Road improvements | DOC (Mt Cook) | Tasman Valley Road realignment and sealing | Construction | Tasman valley road re-alignment and sealing | MMH | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -391219 | -391219 |  |  |  | 4.2
2016-04-20 | April 2016 Review | Cost / Scope adjustment | Local road improvements | Road improvements | Grey District Council | [64.324.59.1] Taylorville-Blackball Rd strengthening | Construction | Rock to Ruby Strengthening | MM6.7 | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 250000 | 175000 |  | 6.7 | 0 | 6.7
2016-04-14 | April 2016 Review | Cost / Scope adjustment | State highway improvements | Road improvements | Marlborough Highway & Network Operations | SH1 SH62 Spring Creek Intersection RAB | Design | SH1 SH62 Spring Creek Intersection RAB | MM*2 | 7 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 18214 | 18214 |  |  | 2 | 2
2016-04-06 | April 2016 Review | Cost / Scope adjustment | Local road maintenance | Routine drainage maintenance | Manawatu District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HMH | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 114392 | 61772
2016-04-06 | April 2016 Review | Cost / Scope adjustment | Local road maintenance | Sealed pavement maintenance | Manawatu District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HMH | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -360742 | -194801
2016-04-06 | April 2016 Review | Cost / Scope adjustment | Local road maintenance | Sealed road pavement rehabilitation | Manawatu District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HMH | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -363242 | -202500
2016-04-12 | April 2016 Review | Cost / Scope adjustment | Local road maintenance | Sealed road pavement rehabilitation | Rotorua Lakes Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | MMH | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -350000 | -178500
2016-04-06 | April 2016 Review | Cost / Scope adjustment | Local road maintenance | Sealed road resurfacing | Manawatu District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HMH | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -131625 | -71078
2016-04-12 | April 2016 Review | Cost / Scope adjustment | Local road maintenance | Sealed road resurfacing | Rotorua Lakes Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | MMH | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -281000 | -143310
2016-04-06 | April 2016 Review | Cost / Scope adjustment | Local road maintenance | Structures maintenance | Manawatu District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HMH | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -93750 | -50625
2016-04-06 | April 2016 Review | Cost / Scope adjustment | Local road maintenance | Traffic services maintenance | Manawatu District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HMH | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -90777 | -49020
2016-04-06 | April 2016 Review | Cost / Scope adjustment | Local road maintenance | Traffic services renewals | Manawatu District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HMH | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 179937 | 97166
2016-04-12 | April 2016 Review | Cost / Scope adjustment | Investment management (incl. Transport Planning) | Transport model development | Waikato Regional Council | Waikato Regional Transport Model 2014/15 Upgrade | Study |  | MM_ | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -4027 | -2400
2016-04-06 | April 2016 Review | Cost / Scope adjustment | Local road maintenance | Unsealed pavement maintenance | Manawatu District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HMH | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -121465 | -65591
2016-04-06 | April 2016 Review | Cost / Scope adjustment | Local road maintenance | Unsealed road metalling | Manawatu District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | HMH | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -36500 | -19710
2016-04-13 | April 2016 Review | Cost / Scope adjustment | Walking and cycling improvements | Walking facilities | Christchurch City Council | Major Cycleway: Papanui Parallel (Grassmere Rte to City) UCF | Construction | Grassmere Link (Grants to Tomes) NZTA/Local | HM3.2 | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 39972 | 21585 |  | 3.2 | 9.8 | 9.8
2016-04-22 | April 2016 Review | Support for programme business case |  |  | Hutt City Council | The Beltway | Support for PBC |  | HH_ | 0 | Supported | This is not a funding decision | 0
2016-04-22 | April 2016 Review | Support for programme business case |  |  | Kapiti Coast District Council | KÄpiti Strategic Cycle Network | Support for PBC |  | HH5+ | 0 | Supported | This is not a funding decision | 0