## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Phase Label | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Decision Status | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR
2018-10-25 | October 2018 Review | New approval | Investment management (incl. Transport Planning) | Activity management planning improvement | Auckland Transport | Asset Management Planning - 2018-21 | Programme business case |  | H__ | HH_ | N | 3 | Approved | Approved by Senior Manager System Planning | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 2183436 | 1113552
2018-10-26 | October 2018 Review | New approval | Investment management (incl. Transport Planning) | Activity management planning improvement | Manawatu District Council | Investment Management | Programme business case |  | H__ | MM_ | N | 3 | Approved | Approved by Senior Manager System Planning | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 300000 | 159000
2018-10-26 | October 2018 Review | New approval | Investment management (incl. Transport Planning) | Activity management planning improvement | Palmerston North City Council | PNCC Network Operating Plan | Programme business case |  | M__ | HH_ | N | 4 | Approved | Approved by Senior Manager System Planning | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 110000 | 56100
2018-10-26 | October 2018 Review | New approval | Investment management (incl. Transport Planning) | Activity management planning improvement | Rangitikei District Council | Activity Management Planning | Programme business case |  | HM*_ | MM_ | N | 3 | Approved | Approved by Senior Manager System Planning | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 300000 | 189000
2018-10-26 | October 2018 Review | New approval | Walking and cycling improvements | Cycling facilities | Auckland Transport | Auckland Cycle Network - City Centre Network | Implementation | UCP - ACN CCN - Tamaki Drive (Seg 2-5) IMP (NLTF) | HHH | HHH | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 14400000 | 7344000 |  | 5.1 | 0 | 6.8
2018-10-08 | October 2018 Review | New approval | Walking and cycling improvements | Cycling facilities | Auckland Transport | Cycling Investment - Central Isthmus & Sandringham | Detailed Business Case | Cycling Investment - Central & Sandringham - DBC | H_L | H_M | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 4920000 | 2509200 |  | 1.9 | 0 | 1.9
2018-10-08 | October 2018 Review | New approval | Walking and cycling improvements | Cycling facilities | Auckland Transport | Cycling Investment - City Centre and Fringe | Detailed Business Case | Cycling Investment - City Centre and Fringe - DBC | H_L | H_M | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 3740000 | 1907400 |  | 1.9 | 0 | 1.9
2018-10-08 | October 2018 Review | New approval | Walking and cycling improvements | Cycling facilities | Auckland Transport | Cycling Investment - Henderson | Detailed Business Case | Cycling Investment - Henderson - DBC | H_L | H_M | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 2550000 | 1300500 |  | 1.9 | 0 | 1.9
2018-10-24 | October 2018 Review | New approval | Local road maintenance | Emergency works | Auckland Transport | E/W Rural South - 2-5 June 2018 Storm Event | Construction |  | ___ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (SD&D) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1281290 | 653458
2018-10-30 | October 2018 Review | New approval | Local road maintenance | Emergency works | Central Hawkes Bay District Council | EW September week of 2nd 2018 | Construction |  | ___ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (SD&D) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 4400000 | 3520000
2018-10-30 | October 2018 Review | New approval | Local road maintenance | Emergency works | Central Hawkes Bay District Council | EW September week of 2nd 2018 | Construction |  | ___ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (SD&D) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 196764 | 118058
2018-10-24 | October 2018 Review | New approval | Local road maintenance | Emergency works | Far North District Council | EW June 2018 | Construction |  | ___ |  | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1625203 | 1072634
2018-10-15 | October 2018 Review | New approval | Local road maintenance | Emergency works | Hurunui District Council | June 2018 Event | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager Systems Management | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 640000 | 326400
2018-10-05 | October 2018 Review | New approval | State highway maintenance | Emergency works | NZTA (BOP) | EW BOPE Heavy Rain Event 12-13 May 2018 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager Systems Management | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 300142 | 300142
2018-10-05 | October 2018 Review | New approval | State highway maintenance | Emergency works | NZTA (BOP) | EW BOPE Heavy Rain Event 4-8 August 2018 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager Systems Management | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 195360 | 195360
2018-10-11 | October 2018 Review | New approval | State highway maintenance | Emergency works | NZTA (Hawkes Bay) | EW June 2018 Storm Event | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager Systems Management | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 345380 | 345380
2018-10-10 | October 2018 Review | New approval | State highway maintenance | Emergency works | NZTA (Manawatu/Whanganui) | Manawatu gorge Slip 25 April 2017 | Construction |  | ___ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (SD&D) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1 | 1
2018-10-23 | October 2018 Review | New approval | Local road maintenance | Emergency works | Rangitikei District Council | Emergency Works September 2018 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager Systems Management | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 685000 | 568550
2018-10-02 | October 2018 Review | New approval | Local road maintenance | Emergency works | Rangitikei District Council | Emergency works June 2018 Rangitane & Kawhatau bridges | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager Systems Management | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 243000 | 201690
2018-10-02 | October 2018 Review | New approval | Local road maintenance | Emergency works | Rangitikei District Council | Emergency works May 2018 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager Systems Management | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 907000 | 752810
2018-10-02 | October 2018 Review | New approval | Local road maintenance | Emergency works | Rotorua Lakes Council | Storm Event April 2018 | Construction |  | ___ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (SD&D) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 999411 | 549676
2018-10-11 | October 2018 Review | New approval | Investment management (incl. Transport Planning) | Programme Business Case Development | NZTA (Auckland) | Auckland Transport System Optimisation PBC | Programme business case |  | H_H | VH_ | N | 3 | Approved | Approved by Senior Manager System Planning | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 810500 | 810500
2018-10-24 | October 2018 Review | New approval | Investment management (incl. Transport Planning) | Programme Business Case Development | NZTA (Manawatu/Whanganui) | Accessing Central New Zealand Business Case | Programme business case |  | HM*_ | HM*_ | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 400000 | 400000
2018-10-17 | October 2018 Review | New approval | Investment management (incl. Transport Planning) | Programme Business Case Development | NZTA (Otago) | Dunedin City and Hospital | Programme business case |  | H__ | H__ | N | 3 | Approved | Approved by Senior Manager System Planning | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 400000 | 200000
2018-10-05 | October 2018 Review | New approval | Investment management (incl. Transport Planning) | Programme Business Case Development | Queenstown-Lakes District Council | Queenstown Integrated Transport PBC (Frankton Masterplan) | Programme business case |  | H__ | V__ | N | 3 | Approved | Approved by Senior Manager System Planning | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 559900 | 285549
2018-10-05 | October 2018 Review | New approval | Investment management (incl. Transport Planning) | Programme Business Case Development | Queenstown-Lakes District Council | Wanaka Masterplan PBC | Programme business case |  | M__ | HH_ | N | 4 | Approved | Approved by Senior Manager System Planning | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 565000 | 288150
2018-10-15 | October 2018 Review | New approval | State highway improvements | Property purchase (State highways) | NZTA (Canterbury) | Mingha Bluff to Rough Creek | Property | Property | MML | MML | N | 6 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 256500 | 256500 |  | 1.1 | 1.1 | 1.1
2018-10-24 | October 2018 Review | New approval | Rapid Transit | Rapid Transit Infrastructure | NZTA (Auckland) | City Centre to Mangere Light Rail | Detailed Business Case | Business case RT improvements | HML | HML | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 14000000 | 14000000 |  | 2 | 1 | 1
2018-10-25 | October 2018 Review | New approval | Investment management (incl. Transport Planning) | Regional land transport planning management | Auckland Transport | Regional Land Transport Planning Management 2018-21 | Programme Business Case |  | H__ | H__ | N | 3 | Approved | Approved by Senior Manager System Planning | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 3033785 | 1547231
2018-10-19 | October 2018 Review | New approval | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH30 Kopaki Bridge Replacement | Detailed Business Case | SSBC | H_PV_EoL | HHPV_EoL | N | 2 | Approved | Approved by Senior Manager System Planning | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 268402 | 268402 |  |  | 99 | 99
2018-10-11 | October 2018 Review | New approval | Local road improvements | Road improvements | Auckland Transport | Streetlighting Upgrade LED | Implementation | Streetlighting Update V Lights - IMP | M_H | HHL | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 46698070 | 33342422 |  | 5 | 2.1 | 2.1
2018-10-29 | October 2018 Review | New approval | Local road improvements | Road improvements | Hamilton City Council | 2018-28 Rototuna Growth - Thomas /Gordonton Rd Intersection | Implementation | Construction - Thomas/Gordonton | VH_ | VMVH | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 2754000 | 2079270 |  | 2 | 0 | 2
2018-10-29 | October 2018 Review | New approval | Local road improvements | Road improvements | Hamilton City Council | 2018-28 Rototuna Growth - Thomas /Gordonton Rd Intersection | Pre-implementation* | Investigation - Thomas/Gordonton | VH_ | VMVH | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 440000 | 332200 |  | 2 | 0 | 2
2018-10-25 | October 2018 Review | New approval | State highway improvements | Road improvements | NZTA (Taranaki) | SH3 Awakino Gorge to Mt Messenger Corridor | Implementation | Const: Mt Messenger to Awakino Gorge Corridor | MML | HHL | N | 6 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 5521993 | 5521993 |  | 1.5 | 1.5 | 1.5
2018-10-25 | October 2018 Review | New approval | State highway improvements | Road improvements | NZTA (Taranaki) | SH3 Awakino Gorge to Mt Messenger Corridor | Pre-implementation* | Pre Imp- Mt Messenger to Awakino Gorge Corridor | MML | HHL | N | 6 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 756458 | 756458 |  | 1.5 | 1.5 | 1.5
2018-10-23 | October 2018 Review | New approval | Promotion of road safety and demand management | Travel demand management | Dunedin City Council | Travel Demand Management 2018 - 21 | Implementation | Travel Demand Management | HHM | VH_ | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 660000 | 363000 |  | 1 | 1 | 1
2018-10-11 | October 2018 Review | New approval | Promotion of road safety and demand management | Travel demand management | Greater Wellington | Demand Management | Implementation | Demand management programme | M_VH | HHVH | N | 2 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 2352859 | 1199958 |  | 17.1 | 0 | 17.1
2018-10-11 | October 2018 Review | New approval | Promotion of road safety and demand management | Travel demand management | Nelson City Council | Travel Demand Management | Implementation | Travel Demand Management | MML* | HHH | N | 6 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 769235 | 392309 |  | 1 | 0 | 0
2018-10-11 | October 2018 Review | Cash flow adjustment | Local road maintenance | Environmental maintenance | Chatham Islands Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | Local Roads |  | MM |  | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0
2018-10-05 | October 2018 Review | Cash flow adjustment | Local road maintenance | Minor events | Nelson City Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | Local Roads |  | MM |  | N | 5 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 3 | 3
2018-10-15 | October 2018 Review | Cash flow adjustment | Local road maintenance | Network and asset management | NZ Transport Agency | National Speed Limit Register | Pre-implementation* | Build register framework | VHPV_EoL | VH_ | N | 2 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 1 | 99
2018-10-05 | October 2018 Review | Cash flow adjustment | Local road maintenance | Network and asset management | Nelson City Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | Local Roads |  | MM |  | N | 5 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -3 | -1
2018-10-30 | October 2018 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Auckland) | SH 1 Waitemata Harbour Crossing | Investigation |  | HHL | HHL | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 0.5 | 0.4 | 0.6
2018-10-11 | October 2018 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Auckland) | SH1 Puhoi to Warkworth RoNS Detailed Design and Construction | Construction | Construction - other than the PPP component | HML | HML | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1.1 | 1.1 | 1.1
2018-10-30 | October 2018 Review | Cash flow adjustment | Regional Improvements | New roads | NZTA (Hawkes Bay) | Prebensen Hyderabad Intersection upgrade | Construction | Implementation | MMH | MMH | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 14.6 | 14.6
2018-10-31 | October 2018 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Wellington) | Wellington RoNS (5) - Transmission Gully | Design |  | HHL | HHL | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 1.4 | 1.4
2018-10-12 | October 2018 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Wellington) | Wellington RoNS (7) - SH1 Peka Peka to Otaki Expressway | Construction |  | HHL | MHM | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1.4 | 0.6 | 0.6
2018-10-18 | October 2018 Review | Cash flow adjustment | State highway improvements | New traffic management facilities | NZTA (Wellington) | Weigh Right MacKay's | Implementation | Construction/Implementation (C) | HHH | MHPV_EoL | N | 1 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -1 | -1 |  |  | 14 | 14
2018-10-05 | October 2018 Review | Cash flow adjustment | Promotion of road safety and demand management | Promotion, education and advertising | Kaipara District Council | Road Safety Promotion 2018-21 | Implementation |  | HM | HH | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0
2018-10-15 | October 2018 Review | Cash flow adjustment | Promotion of road safety and demand management | Promotion, education and advertising | Whakatane District Council | Road Safety Promotion 2018-21 | Implementation |  | HM | HM | N | 4 | Approved | Approved by Senior Investment Advisor | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0
2018-10-05 | October 2018 Review | Cash flow adjustment | Promotion of road safety and demand management | Promotion, education and advertising | Whangarei District Council | Road Safety Promotion 2018-21 | Implementation |  | HM | HH | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0
2018-10-05 | October 2018 Review | Cash flow adjustment | Promotion of road safety and demand management | Promotion, education and advertising | Whangarei District Council | Road Safety Promotion 2018-21 | Implementation |  | MM | MH | N | 5 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0
2018-10-15 | October 2018 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Auckland) | SH 1 Waitemata Harbour Crossing | Property |  | HHL | HHL | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -1 | -1 |  | 0.5 | 0.4 | 0.6
2018-10-17 | October 2018 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (BOP) | Tauranga Northern Link | Property | Property | HHL | HHM | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 2 |  | 2
2018-10-17 | October 2018 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (BOP) | W2T Omokoroa to Te Puna (Transformed) | Property |  | HHL | HML | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1.2 | 1.3 | 1.3
2018-10-11 | October 2018 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Hawkes Bay) | Prebensen Hyderabad Intersection upgrade | Property |  | MMH | MMH | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 14.6 | 14.6
2018-10-17 | October 2018 Review | Cash flow adjustment | Regional Improvements | Property purchase (State highways) | NZTA (Hawkes Bay) | SH2 Watchman Rd, HB Airport Intersection | Property | Property Purchase | HML | HMM | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 2.2 | 2.2
2018-10-11 | October 2018 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Manawatu/Whanganui) | Rangitikei Line Tremaine Ave Intersection Improvement | Property |  | MHH | MMH | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 13.8 | 13.8
2018-10-17 | October 2018 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Waikato) | Atiamuri Bridge Replacement | Property |  | HHPV_EoL | HHH | N | 2 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 0 | 0 | 1
2018-10-17 | October 2018 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Waikato) | SH1 (Cambridge to Piarere) Long Term Improvements | Property | Property Phase C2P | HHL | HHL | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 0 | 0.9
2018-10-17 | October 2018 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Waikato) | SH1 South-East Hamilton Improvements | Property | SH1 Cobham/Cambridge Improvements Property | HMM | MMM | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 5.9 | 5.9
2018-10-17 | October 2018 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Waikato) | SH3 Awakino Tunnel Bypass | Property |  | HLL | MML | N | 0 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -1 | -1 |  | 2.5 | 2.5 | 2.5
2018-10-18 | October 2018 Review | Cash flow adjustment | Regional Improvements | Replacement of bridges and other structures | NZTA (West Coast) | HPMV T2 West Coast connections | Implementation | Implementation | HML | HML | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1.6 | 1.6 | 1.6
2018-10-15 | October 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Auckland) | East West Link -part of Auckland Accelerated Programme(AAP) | Implementation | Construction | HHL | HHL | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 1.9 | 1.9
2018-10-17 | October 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Auckland) | East West Link -part of Auckland Accelerated Programme(AAP) | Pre-implementation* | Design | HHL | HHL | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 1.9 | 1.9
2018-10-15 | October 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Auckland) | East West Link -part of Auckland Accelerated Programme(AAP) | Property | Property | HHL | HHL | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 1.9 | 1.9
2018-10-30 | October 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (BOP) | SH30A Urban Revitalisation, Connect Rotorua | Pre-implementation* | Pre imp | MHL | MHL | N | 6 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1.1 | 0 | 1.1
2018-10-17 | October 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (BOP) | Tauranga Northern Link | Pre-implementation* | Pre-implementation - W2T - 1 - TNL | HHL | HHM | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 2 |  | 2
2018-10-17 | October 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (BOP) | W2T Katikati Urban (previously called Katikati bypass) | Investigation |  | M_L | MML | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 0 | 2.5
2018-10-17 | October 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (BOP) | W2T Omokoroa to Te Puna (Transformed) | Detailed Business Case | Omokoroa to Te Puna | HHL | HML | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1 | 1 |  | 1.2 | 1.3 | 1.3
2018-10-11 | October 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Manawatu/Whanganui) | Otamaraho Curve P/L Extension | Construction | Otamaraho Curve P/L Extension | HMM | HMH | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 2.2 | 2.2
2018-10-11 | October 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Manawatu/Whanganui) | Papatawa Realignment | Construction |  | MMM | MMM | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 2.6 | 3.1
2018-10-11 | October 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Manawatu/Whanganui) | Rangitikei Line Tremaine Ave Intersection Improvement | Construction | Rangitikei Line Tremaine Ave Intersection Improvem | MHH | MMH | N | 2 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 13.8 | 13.8
2018-10-11 | October 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Manawatu/Whanganui) | Shannon North S/W | Construction | Shannon North S/W | MMH | HLH | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 0 | 5.8
2018-10-11 | October 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Northland) | SH1 Corridor Improvements - Whangarei | Construction |  | HMM | HMM | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 2.3 | 0 | 2.3
2018-10-17 | October 2018 Review | Cash flow adjustment | Regional Improvements | Road improvements | NZTA (Northland) | SH10 Kaeo Bridge upgrade | Implementation | Construction | HM_ | MML | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1 | 1 |  | 0.6 | 0.6 | 0.6
2018-10-17 | October 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Northland) | SH12 Matakohe Bridges | Property |  | HML | MML | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1.1 | 1.3 | 1.3
2018-10-17 | October 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | SH25 Coromandel Motorcycle Demonstration Project - stage 2 | Construction | Construction | HHH | HHM | N | 1 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 7.3 | 7.2 | 7.2
2018-10-18 | October 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | SH3 Awakino Tunnel Bypass | Construction | Construction - NLTF funding | HLL | MML | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -1 | -1 |  | 2.5 | 2.5 | 2.5
2018-10-30 | October 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Wellington) | SH58 Safety Improvements | Implementation | Implementation | HMM | HML | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 2.5 | 1.3 | 1.3
2018-10-11 | October 2018 Review | Cash flow adjustment | Local road maintenance | Sealed pavement maintenance | Chatham Islands Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | Local Roads |  | MM |  | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0
2018-10-11 | October 2018 Review | Cash flow adjustment | Local road maintenance | Unsealed pavement maintenance | Chatham Islands Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | Local Roads |  | MM |  | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0
2018-10-15 | October 2018 Review | Cost Decrease | Public transport | Bus services | NZ Transport Agency | PTOM implementation - Provision for NZTA representative | Implementation | Implementation | HMM | HMM | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -386804 | -386804 |  |  | 0 | 0
2018-10-05 | October 2018 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Auckland Transport | 2012-15 Glen Innes to Tamaki Drive Cycleway | Design | UCP Glen Innes-Tamaki Dr C/way - DES (UCF & NLTF) | HHL | HHL | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 3950714 | 2093878 |  | 2.3 | 0 | 0.8
2018-10-11 | October 2018 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | NZTA (Gisborne) | Walking and Cycling connectivity | Pre-implementation* | Pre Implementation | HML | HML | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -179550 | -179550 |  |  | 0 | 5.7
2018-10-11 | October 2018 Review | Cost Decrease | Local road maintenance | Emergency works | Ashburton District Council | Rain event July 2017 | Construction |  | ___ |  | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -16791 | -8563
2018-10-30 | October 2018 Review | Cost Decrease | Local road maintenance | Emergency works | Central Hawkes Bay District Council | EW September week of 2nd 2018 | Construction |  | ___ |  | N |  | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -4400000 | -3520000
2018-10-30 | October 2018 Review | Cost Increase | Local road maintenance | Emergency works | Manawatu District Council | Emergency works June 2018 Storm | Construction |  | ___ |  | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 88308 | 46804
2018-10-30 | October 2018 Review | Cost Decrease | Local road maintenance | Emergency works | Manawatu District Council | Emergency works June 2018 Storm | Construction |  | ___ |  | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -88308 | -64465
2018-10-11 | October 2018 Review | Cost Decrease | Local road maintenance | Emergency works | Manawatu District Council | June 2015 Flood Event | Construction |  | ___ |  | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -88308 | -46803
2018-10-26 | October 2018 Review | Cost Increase | External funding | Emergency works | NZTA (Canterbury) | Kaikoura Nov 2016 EQ: Reinstatement SH1 | Construction |  | ___ |  | N |  | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 5323028 | 5323028
2018-10-11 | October 2018 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Hawkes Bay) | EW June 2018 Storm Event | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager Systems Management | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 105992 | 105992
2018-10-18 | October 2018 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Manawatu/Whanganui) | Manawatu gorge Slip 25 April 2017 | Construction |  | ___ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (SD&D) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 7277956 | 7277956
2018-10-17 | October 2018 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Waikato) | (EW) Thames Coast Storm Event - Jan 2018 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager Systems Management | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 472500 | 472500
2018-10-11 | October 2018 Review | Cost Decrease | Local road maintenance | Emergency works | Palmerston North City Council | Storm Event 20/21 June 2015 Recovery Works | Construction |  | ___ |  | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -102332 | -52189
2018-10-15 | October 2018 Review | Cost Decrease | Local road improvements | Low cost / low risk improvements | Manawatu District Council | Low cost / low risk improvements 2018-21 | Local Roads |  | __ |  | N | 0 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -624755 | -331121
2018-10-15 | October 2018 Review | Cost Decrease | Local road improvements | Low cost / low risk improvements | Rangitikei District Council | Low cost / low risk improvements 2018-21 | Local Roads |  | __ |  | N | 0 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -197000 | -124110
2018-10-11 | October 2018 Review | Cost Increase | State highway improvements | New roads | NZTA (Canterbury) | Broughs Road Extension | Construction | Construction | HHM | MHM | N | 2 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1974419 | 1974419 |  | 3.6 | 0 | 3.6
2018-10-05 | October 2018 Review | Cost Increase | State highway improvements | New roads | NZTA (Taranaki) | SH3 Mt Messenger Bypass | Construction | Construction | HML | HML | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 3933803 | 3933803 |  | 1.1 | 0.5 | 0.5
2018-10-05 | October 2018 Review | Cost Decrease | External funding | New roads | NZTA (Taranaki) | SH3 Mt Messenger Bypass | Implementation | ARSHP | HML | HML | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -4188454 | -4188454 |  | 1.1 | 0.5 | 0.5
2018-10-11 | October 2018 Review | Cost Decrease | Local road improvements | New traffic management facilities | Ashburton District Council | Rakaia Pedestrian Level Crossing Improvements | Construction | Construction | HML* | HMH | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -8801 | -8801 |  | 99 | 0 | 0
2018-10-18 | October 2018 Review | Cost Increase | State highway improvements | New traffic management facilities | NZTA (Canterbury) | Lyttelton Tunnel Safety Retrofit (Deluge) System | Implementation | Construction | HHPV_EoL | HHVH | N | 2 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 79300 | 257439 |  | 0 | 0 | 99
2018-10-30 | October 2018 Review | Cost Increase | Local road improvements | New traffic management facilities | Waitaki District Council | Waitaki Avenue level crossing upgrade | Construction | Construction | HHH | HHH | N | 1 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 61453 |  | 17.9 | 17.9 | 17.9
2018-10-18 | October 2018 Review | Cost Decrease | Investment management (incl. Transport Planning) | Programme Business Case Development | NZTA (Waikato) | North Waikato Integrated Growth Management PBC | Programme business case |  | HH_ | HH_ | N | 1 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -137087 | -52087
2018-10-25 | October 2018 Review | Cost Increase | Investment management (incl. Transport Planning) | Programme Business Case Development | NZTA (Wellington) | Resilience Wellington - Programme Business Case | Programme business case |  | HM*_ | HM_ | N | 2 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 152339 | 152339
2018-10-25 | October 2018 Review | Cost Increase | Investment management (incl. Transport Planning) | Programme Business Case Development | NZTA (Wellington) | Wellington Port Access Programme Business case | Programme business case |  | HH_ | HML | N | 1 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 310000 | 310000
2018-10-18 | October 2018 Review | Cost Increase | Promotion of road safety and demand management | Promotion, education and advertising | Hawkes Bay Regional Council | Road Safety Promotion 2018-21 | Implementation |  | HM | HH | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 96621
2018-10-15 | October 2018 Review | Cost Decrease | Promotion of road safety and demand management | Promotion, education and advertising | NZ Transport Agency | National Road Safety Advertising &Education Programme2018-21 | Implementation |  | MM | HM | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -600000 | -600000
2018-10-05 | October 2018 Review | Cost Increase | External funding | Property purchase (State highways) | NZTA (Marlborough) | New ÅŒpaoa River Bridge | Property |  | MM_ | MML* | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 5158639 | 5158639 |  | 1.4 | 0 | 1.4
2018-10-05 | October 2018 Review | Cost Decrease | State highway improvements | Property purchase (State highways) | NZTA (Marlborough) | New ÅŒpaoa River Bridge | Property | Property - NLTF Funding | MM_ | MML* | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -5158639 | -5158639 |  | 1.4 | 0 | 1.4
2018-10-05 | October 2018 Review | Cost Decrease | State highway improvements | Property purchase (State highways) | NZTA (Taranaki) | Normanby Overbridge Realignment | Property | 2649 | LMH | HMH | N | 6 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -64967 | -64967 |  | 4.1 | 4.1 | 4.1
2018-10-24 | October 2018 Review | Cost Increase | Public transport | Public transport infrastructure and major renewals | Auckland Transport | Auckland Metro Train Capacity | Implementation | Auckland Metro Train Capacity - Imp | HHM | HHM | N | 2 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 21667072 | 11050207 |  | 2.8 | 2.8 | 2.8
2018-10-29 | October 2018 Review | Cost Increase | Public transport | Public transport infrastructure and major renewals | Auckland Transport | NCI - Rosedale Station and Assoc. Local Road Improvements | Implementation | NCI - Rosedale LR Components - IMP | HHL | HML | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 4291420 | 2188624 |  | 1.1 | 0 | 1.1
2018-10-29 | October 2018 Review | Cost Increase | Public transport | Public transport infrastructure and major renewals | Auckland Transport | NCI - Rosedale Station and Assoc. Local Road Improvements | Implementation | NCI - Rosedale PT Components - IMP | HHL | HML | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 15960700 | 8139957 |  | 1.1 | 0 | 1.1
2018-10-11 | October 2018 Review | Cost Decrease | Public transport | Public transport infrastructure and major renewals | NZTA (Auckland) | City Centre to Mangere Light Rail | Detailed Business Case | Business Case PT improvements | HML | HML | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -35864 | -35864 |  | 2 | 1 | 1
2018-10-05 | October 2018 Review | Cost Increase | External funding | Replacement of bridges and other structures | NZTA (Otago) | Kawarau Falls Bridge | Construction | Kawarau Falls Construction | HML | HML | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 6776394 | 6776394 |  | 1.5 | 1.5 | 1.5
2018-10-05 | October 2018 Review | Cost Decrease | State highway improvements | Replacement of bridges and other structures | NZTA (Otago) | Kawarau Falls Bridge | Implementation | Kawarau Bridge Falls - NLTF Funding | HML | HML | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -6776394 | -6776394 |  | 1.5 | 1.5 | 1.5
2018-10-18 | October 2018 Review | Cost Decrease | Regional Improvements | Replacement of bridges and other structures | NZTA (Waikato) | HPMV T2 SH27 from Morrinsville to Tirau | Pre-implementation* |  | HM*L* | HML | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -70957 | -70957 |  |  | 2.2 | 2.2
2018-10-11 | October 2018 Review | Cost Decrease | Local road improvements | Replacement of bridges and other structures | Nelson City Council | Oldham Bridge Replacement | Construction | Design and Construction | MMH | MM_ | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -18556 | -9464 |  | 99 | 1 | 1
2018-10-30 | October 2018 Review | Cost Increase | State highway improvements | Resilience improvements | NZTA (Hawkes Bay) | SH2 Raupunga Bluff Enhanced Resilience | Implementation |  | HHH | MMH | N | 1 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1052513 | 1052513
2018-10-29 | October 2018 Review | Cost Increase | Local road improvements | Road improvements | Horowhenua District Council | LED Street Lights Renewals | Construction | LED Renewals | MHH | MHH | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 45118 | 38350 |  |  | 5 | 5
2018-10-15 | October 2018 Review | Cost Decrease | Local road improvements | Road improvements | Kawerau District Council | Street Light Upgrade LEDs | Construction | Installation of LEDs | HHH | MMH | N | 1 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -25982 | -25826 |  |  | 5 | 5
2018-10-15 | October 2018 Review | Cost Decrease | Local road improvements | Road improvements | Matamata-Piako District Council | LED project | Construction | construction | MHH | MHH | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -327660 | -278511 |  |  | 5 | 5
2018-10-11 | October 2018 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (BOP) | Bethlehem to Route J - Four laning (SH2) | Design |  | MMH | HMM | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -203148 | -203148 |  |  | 4.4 | 1
2018-10-18 | October 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Canterbury) | Marshland to Burwood Median Barrier | Implementation | Implementation/Construction | HMM | HMM | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 768957 | 768957 |  |  | 3.6 | 3.6
2018-10-11 | October 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Gisborne) | HPMV T2 GIS HNO Napier Port to Gis | Pre-implementation* | Pre Imp | HMM | HHVH | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 178041 | 178041 |  | 2.3 | 0 | 19.2
2018-10-11 | October 2018 Review | Cost Decrease | Regional Improvements | Road improvements | NZTA (Gisborne) | HPMV T2 Gis HNO Te Araroa to Tologa | Pre-implementation* | Pre Implementation | MHM | MMM | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -178041 | -178041 |  |  | 1.8 | 1.8
2018-10-17 | October 2018 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Hawkes Bay) | Corkscrew Gully Northbound & Southbound Passing Lanes | Design | Corkscrew Gully Northbound Passing Lane | LLL* | MLL* | N | 11 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -23829 | -23829 |  |  | 3.5 | 3.5
2018-10-31 | October 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Hawkes Bay) | HPMV T2 HB HNO Napier Port to Gisborne | Pre-implementation* | HPMV T2 HB HNO Napier Port to Gisborne | MMVH | HHVH | N | 0 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 32790 | 32790 |  | 15 | 0 | 19.2
2018-10-15 | October 2018 Review | Cost Decrease | External funding | Road improvements | NZTA (Hawkes Bay) | Napier Port Access | Detailed Business Case | Napier Port Access | MML* | HMM | N | 8 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -180018 | -180018 |  |  | 3.9 | 3.9
2018-10-05 | October 2018 Review | Cost Increase | External funding | Road improvements | NZTA (Taranaki) | Normanby Overbridge Realignment | Construction | Implementation | LMH | HMH | N | 7 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 64967 | 64967 |  | 4.1 | 4.1 | 4.1
2018-10-18 | October 2018 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Waikato) | SH25 Coromandel Motorcycle Demonstration Project - stage 2 | Design | Design | HHH | HHM | N | 1 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -9647 | -9647 |  | 7.3 | 7.2 | 7.2
2018-10-05 | October 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Waikato) | SH3 Awakino Tunnel Bypass | Construction | Construction - NLTF funding | HLL | MML | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 7811546 | 7811546 |  | 2.5 | 2.5 | 2.5
2018-10-05 | October 2018 Review | Cost Decrease | External funding | Road improvements | NZTA (Waikato) | SH3 Awakino Tunnel Bypass | Implementation | Construction implementation | HLL | MML | N | 0 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -7811546 | -7811546 |  | 2.5 | 2.5 | 2.5