## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Phase Label | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Decision Status | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR
2019-11-11 | November 2019 Review | New approval | Public transport | Bus services | NZ Transport Agency | Nationally held contingency | Implementation | PT Service Programme | H_L | H_L | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 20000000 | 20000000 |  | 1 | 1 | 1
2019-11-27 | November 2019 Review | New approval | Walking and cycling improvements | Cycling facilities | Auckland Transport | Airport Access - Short-term Improvements | Pre-implementation* | Airport Access - Mangere Cycling Improvement - PRE | HML | HML | N | 5 | Approved with conditions precedent | Approved with conditions precedent by NZTA Board/Board Committee | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Transport Investment Online or by request | 792750 | 404303 | That the NZTA Team Leader â€“ Walking and Cycling â€“ Transport Services endorses the preferred option and scope. | 1.4 | 1.4 | 1.4
2019-11-29 | November 2019 Review | New approval | External funding | Cycling facilities | Auckland Transport | Auckland Cycle Network - Links to Public Transport | Implementation | UCP - ACN Links to PT - NL to Avondale - IMP (UCF) | HHM | MHM | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 4706176 | 4706176 |  | 4.1 | 0 | 4.1
2019-11-26 | November 2019 Review | New approval | Walking and cycling improvements | Cycling facilities | Tauranga City Council | Ngatai Road Improvements | Construction | Design and Commence Construction | H_L* | V_M | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1300000 | 663000 |  | 1 | 3.7 | 3.7
2019-11-11 | November 2019 Review | New approval | Local road maintenance | Emergency works | Far North District Council | EW August 2019 | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 876000 | 578160
2019-11-04 | November 2019 Review | New approval | State highway maintenance | Emergency works | NZTA (Taranaki) | EW SH43 Tahora Saddle | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 792000 | 792000
2019-11-28 | November 2019 Review | New approval | State highway maintenance | Emergency works | NZTA (Waikato) | EW East Waikato Storm Event Sep 2019 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager System Management (Transport Services) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1474176 | 1474176
2019-11-05 | November 2019 Review | New approval | State highway maintenance | Emergency works | NZTA (Waikato) | EW-Willows Hill SH30 | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 205209 | 205209
2019-11-08 | November 2019 Review | New approval | State highway improvements | Property purchase (State highways) | NZTA (Northland) | SH1 Loop Road North to Smeatons Hill Safety Improvement | Property | Property Acquisition | HML | HML | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 2462400 | 2462400 |  | 1.2 | 0 | 1.2
2019-11-11 | November 2019 Review | New approval | State highway improvements | Property purchase (State highways) | NZTA (Otago) | Beaumont bridge replacement | Property | Beaumont Bridge Property | HHPV_EoL | MHPV_EoL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1128600 | 1128600 |  |  | 0 | 12
2019-11-18 | November 2019 Review | New approval | Regional Improvements | Property purchase (State highways) | NZTA (Taranaki) | Waitara to Bell Block Route Imp: SH3/3A to Waitara | Property | Property | MM*L | HML | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 3078000 | 3078000 |  | 1.5 | 1.1 | 1.1
2019-11-11 | November 2019 Review | New approval | Public transport | Public transport information supply, operations and maintenance | NZ Transport Agency | Nationally held contingency | Implementation | RITS | H_L | H_L | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 941226 | 611799 |  | 1 | 1 | 1
2019-11-27 | November 2019 Review | New approval | Rapid Transit | Rapid Transit Infrastructure | NZTA (Auckland) | Supporting Growth Route Protection Programme | Detailed Business Case | DBC RTN | HMM | HML | N | 4 | Approved with conditions | Approved with conditions by Chief Financial Officer (CFO) | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Transport Investment Online or by request | 14300000 | 14300000 | Condition subsequent: Provide the CFO with a complete summary of the expected costs for the SGA including associated direct costs for alliance partners and the costs of follow-on phases, indicating which costs are effectively committed as each funding approval stage is reached. | 1.6 | 1.6 | 1.6
2019-11-15 | November 2019 Review | New approval | State highway improvements | Replacement of bridges and other structures | NZTA (Otago) | Beaumont bridge replacement | Implementation | Beaumont Construction | HHPV_EoL | MHPV_EoL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 20025468 | 20025468 |  |  | 0 | 12
2019-11-22 | November 2019 Review | New approval | Local road improvements | Road improvements | Auckland Transport | Transport Network for Growth - Combined | Detailed Business Case | TNFG - Combined - DBC and Pre-lodgement | H_M | H_M | N | 4 | Approved with conditions | Approved with conditions by Chief Financial Officer (CFO) | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Transport Investment Online or by request | 53323000 | 27194730 | Provide the CFO with a complete summary of the expected costs for the SGA including associated direct costs for alliance partners and the costs of follow-on phases, indicating which costs are effectively committed as each funding approval stage is reached. | 3.3 | 4.8 | 4.8
2019-11-11 | November 2019 Review | New approval | Local road improvements | Road improvements | Christchurch City Council | AAC Hereford Street (Manchester-Cambridge) | Implementation |  | H_L | HHM | N | 5 | Approved with conditions | Approved with conditions by Chief Financial Officer (CFO) | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Transport Investment Online or by request | 4310522 | 2198366 | condition subsequent - Performance measures are to be established and agreed with the NZ Transport Agency Investment Advisor | 1.8 | 0 | 2.1
2019-11-27 | November 2019 Review | New approval | External funding | Road improvements | Kaipara District Council | PGF Program Support | Detailed Business Case | Program Support | V_H | V_VH | N | 1 | Approved | Approved by Minister of Regional Development | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1300000 | 1300000 |  | 3 | 1 | 1
2019-11-12 | November 2019 Review | New approval | State highway improvements | Road improvements | NZTA (Canterbury) | SH1 Ashley to Belfast - (SH71 to Tram Rd) | Implementation | SSI | H_L | H_L | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 2420006 | 2420006 |  | 1 | 0 | 1.6
2019-11-12 | November 2019 Review | New approval | State highway improvements | Road improvements | NZTA (Canterbury) | SH1 Ashley to Belfast SSI (William St to SH71) | Implementation | SSI | M_L | H_M | N | 6 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 3693600 | 3693600 |  | 1 | 0 | 1.6
2019-11-27 | November 2019 Review | New approval | State highway improvements | Road improvements | NZTA (Gisborne) | Gisborne SH Speed Management Guide Implementation | Implementation | Gisborne SH Speed Management Implementation | VM*L* | VHL | N | 1 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 502141 | 502141 |  | 1 | 0 | 4.6
2019-11-27 | November 2019 Review | New approval | State highway improvements | Road improvements | NZTA (Gisborne) | Gisborne SH Speed Management Guide Implementation | Pre-implementation* | Gisborne SH Speed Management Pre-Implementation | VM*L* | VHL | N | 1 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1333585 | 1333585 |  | 1 | 0 | 4.6
2019-11-05 | November 2019 Review | New approval | Regional Improvements | Road improvements | NZTA (Manawatu/Whanganui) | Pahiatua Track shoulder improvements | Implementation | Pre-imp + Imp | H_L | H_L | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 2154600 | 2154600 |  | 1 | 0 | 1
2019-11-27 | November 2019 Review | New approval | State highway improvements | Road improvements | NZTA (Nelson) | Nelson SH Speed Management Guide Implementation | Implementation | Nelson SH Speed Management Implementation | V_L | V_L | N | 1 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 200856 | 200856 |  | 2.8 | 0 | 4.6
2019-11-27 | November 2019 Review | New approval | State highway improvements | Road improvements | NZTA (Nelson) | Nelson SH Speed Management Guide Implementation | Pre-implementation* | Nelson SH Speed Management Pre-Implementation | V_L | V_L | N | 1 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1057717 | 1057717 |  | 2.8 | 0 | 4.6
2019-11-15 | November 2019 Review | New approval | State highway improvements | Road improvements | NZTA (Waikato) | Te Rapa Section | Construction | Te Rapa Pavement Repairs | HHL | HML | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 28215000 | 28215000 |  | 1.4 | 0 | 1.4
2019-11-06 | November 2019 Review | New approval | State highway improvements | Road improvements | NZTA (Wellington) | Asset Management Data Standard (DEfT) | Detailed Business Case | Detailed Business Case | M_M | V_M | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1689769 | 1689769 |  | 4.8 | 0 | 3.8
2019-11-15 | November 2019 Review | New approval | Local road improvements | Road improvements | Porirua City Council | Access Kenepuru Corridor SSBC | Single-Stage Business Case | SSBC | H_L | H_L* | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 60000 | 33600 |  | 1.7 | 0 | 0
2019-11-20 | November 2019 Review | New approval | Investment management (incl. Transport Planning) | Transport model development | Greater Wellington | Transport Analytics (across Wellington Region) | Programme business case |  | HML | HM_ | N | 3 | Approved | Approved by Senior Manager System Planning (Transport Services) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 756000 | 385560
2019-11-01 | November 2019 Review | New approval | Investment management (incl. Transport Planning) | Transport model development | NZTA (Hawkes Bay) | Hawke's Bay Transport Study | Programme business case |  | H_L* | H_L* | N | 3 | Approved | Approved by Senior Manager System Planning (Transport Services) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 100035 | 100035
2019-11-18 | November 2019 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | 2012-15 Glen Innes to Tamaki Drive Cycleway | Design | UCP Glen Innes-Tamaki Dr C/way - DES (UCF & NLTF) | HHL | HHL | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 0.9 | 0 | 0.8
2019-11-19 | November 2019 Review | Cash flow adjustment | External funding | Cycling facilities | Auckland Transport | Auckland Cycle Network - City Centre Network | Implementation | UCP - ACN CCN - Westhaven to CBD (UCF) | HHH | HHH | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 5.1 | 0 | 6.8
2019-11-18 | November 2019 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Auckland Cycle Network - City Centre Network | Implementation | UCP - ACN CCN - Westhaven to CBD (NLTF) | HHH | HHH | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 1 |  | 5.1 | 0 | 6.8
2019-11-18 | November 2019 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Auckland Cycle Network - City Centre Network | Implementation | UCP - ACN CCN - K' Road (NLTF) | HHH | HHH | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 1 |  | 5.1 | 0 | 6.8
2019-11-19 | November 2019 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Auckland Cycle Network - Western Connections to City | Implementation | UCP - ACN Western Connections to City - IMP (NLTF) | MHH | MHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 1 |  | 10.6 | 0 | 4.5
2019-11-21 | November 2019 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Auckland Cycle Network - Western Connections to City | Implementation | UCP - ACN Western Connections to City - IMP (NLTF) | MHH | MHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | -1 |  | 10.6 | 0 | 4.5
2019-11-18 | November 2019 Review | Cash flow adjustment | Local road maintenance | Emergency works | Auckland Transport | E/W Rural South Auckland 24 December 2018 Storm Event | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0
2019-11-18 | November 2019 Review | Cash flow adjustment | Local road maintenance | Environmental maintenance | Clutha District Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | SPR |  | MH |  | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -1059 | -1006
2019-11-18 | November 2019 Review | Cash flow adjustment | Local road improvements | Low cost / low risk improvements | Ashburton District Council | Low cost / low risk improvements 2018-21 | Local Roads |  | __ |  | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0
2019-11-08 | November 2019 Review | Cash flow adjustment | Local road improvements | Low cost / low risk improvements | Clutha District Council | Low cost / low risk improvements 2018-21 | Local Roads |  | __ |  | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | -1
2019-11-27 | November 2019 Review | Cash flow adjustment | State highway improvements | Low cost / low risk improvements | NZTA (Gisborne) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0
2019-11-18 | November 2019 Review | Cash flow adjustment | Local road maintenance | Network and asset management | Clutha District Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | SPR |  | MH |  | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 8396 | 7976
2019-11-08 | November 2019 Review | Cash flow adjustment | Promotion of road safety and demand management | Promotion, education and advertising | Clutha District Council | Road Safety Promotion 2018-21 | Implementation |  | HM | HH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0
2019-11-21 | November 2019 Review | Cash flow adjustment | Regional Improvements | Property purchase (State highways) | NZTA (Taranaki) | Waitara to Bell Block Route Imp: SH3/3A to Waitara | Property | Property | MM*L | HML | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1.5 | 1.1 | 1.1
2019-11-18 | November 2019 Review | Cash flow adjustment | Public transport | Public transport infrastructure and major renewals | Auckland Transport | AMETI - Eastern Busway 1 (Previously part of AMETI Stage 2A) | Property | Eastern Busway 1 (Panmure-Pakuranga) | VHL | HHL | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 1 |  | 1.4 | 0 | 1.1
2019-11-18 | November 2019 Review | Cash flow adjustment | Public transport | Public transport infrastructure and major renewals | Auckland Transport | Airport Access - Short-term Improvements | Detailed Business Case | Airport Access - Short Term Improvements - SSBC | HML | HML | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 1 |  | 1.4 | 1.4 | 1.4
2019-11-18 | November 2019 Review | Cash flow adjustment | Public transport | Public transport infrastructure and major renewals | Auckland Transport | ICP - Ellerslie Pakuranga Highway | Detailed Business Case | ICP-Ellerslie Pakuranga-SSBC | H_L | H_L | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 1 |  | 2.5 | 0 | 2.5
2019-11-18 | November 2019 Review | Cash flow adjustment | Public transport | Public transport infrastructure and major renewals | Auckland Transport | ICP - Gt North Rd - New Lynn to City | Detailed Business Case | ICP-Gt North Rd-New Lynn to City-SSBC | H_L | H_L | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1.3 | 0 | 1.3
2019-11-18 | November 2019 Review | Cash flow adjustment | Public transport | Public transport infrastructure and major renewals | Auckland Transport | ICP - Gt North Rd â€“ New Lynn to Henderson | Detailed Business Case | ICP-Gt North Rd-New Lynn to Henderson-SSBC | H_L | H_L | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 1 |  | 1.2 | 0 | 1.2
2019-11-18 | November 2019 Review | Cash flow adjustment | Public transport | Public transport infrastructure and major renewals | Auckland Transport | ICP - Gt South Rd â€“ Manurewa to Papakura | Detailed Business Case | ICP - Manurewa to Papakura - SSBC | H_L | H_L | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 0.2 | 0 | 2.1
2019-11-18 | November 2019 Review | Cash flow adjustment | Public transport | Public transport infrastructure and major renewals | Auckland Transport | ICP - Gt South Rd â€“ Newmarket to Manurewa | Detailed Business Case | ICP - Newmarket to Manurewa - SSBC | H_L | H_L | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 2.5 | 0 | 2.5
2019-11-18 | November 2019 Review | Cash flow adjustment | Public transport | Public transport infrastructure and major renewals | Auckland Transport | ICP - Manukau Road | Detailed Business Case | ICP - Manukau Road - SSBC | H_L | H_L | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 2.7 | 0 | 2.7
2019-11-18 | November 2019 Review | Cash flow adjustment | Public transport | Public transport infrastructure and major renewals | Auckland Transport | ICP - Mt Eden Road | Detailed Business Case | ICP-Mt.Eden-SSBC | H_M | H_L | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 4.1 | 0 | 4.1
2019-11-18 | November 2019 Review | Cash flow adjustment | Public transport | Public transport infrastructure and major renewals | Auckland Transport | ICP - New North Road | Detailed Business Case | ICP - New North Road - SSBC | H_M | H_L | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 4.2 | 0 | 4.2
2019-11-18 | November 2019 Review | Cash flow adjustment | Public transport | Public transport infrastructure and major renewals | Auckland Transport | ICP - Parnell Road | Detailed Business Case | ICP-Parnell Road-SSBC | H_M | H_L | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 1 |  | 3.9 | 0 | 3.9
2019-11-18 | November 2019 Review | Cash flow adjustment | Public transport | Public transport infrastructure and major renewals | Auckland Transport | ICP - Ponsonby Road | Detailed Business Case | ICP_Ponsonby Road-SSBC | H_M | H_L | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 1 |  | 3 | 0 | 3
2019-11-18 | November 2019 Review | Cash flow adjustment | Public transport | Public transport infrastructure and major renewals | Auckland Transport | ICP - Remuera Road | Detailed Business Case | ICP-Remuera Road-SSBC | H_L | H_L | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1.5 | 0 | 1.5
2019-11-18 | November 2019 Review | Cash flow adjustment | Public transport | Public transport infrastructure and major renewals | Auckland Transport | ICP - Sandringham Road | Detailed Business Case | ICP - Sandringham - SSBC | H_M | H_L | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 3.1 | 0 | 3.1
2019-11-19 | November 2019 Review | Cash flow adjustment | Local road improvements | Road improvements | Auckland Transport | Auckland Smarter Transport Pricing | Detailed Business Case | Detailed Business Case | H__ | HH_ | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 1 |  |  | 0 | 1
2019-11-18 | November 2019 Review | Cash flow adjustment | Local road improvements | Road improvements | Auckland Transport | East West Connections | Implementation | Early Works (ii) FN32 (Road Components) | H_L | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1.5 | 1.5 | 1.5
2019-11-18 | November 2019 Review | Cash flow adjustment | Local road improvements | Road improvements | Auckland Transport | Lake Road Corridor Improvements | Detailed Business Case | Lake Rd Corridor improvements (IBC) | M_L | H_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1.1 | 0 | 1.1
2019-11-18 | November 2019 Review | Cash flow adjustment | Local road improvements | Road improvements | Auckland Transport | Murphys Road Culvert Improvements | Construction | Murphys Rd Culvert Improvements - Construction | H_L | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1.5 | 1 | 1
2019-11-18 | November 2019 Review | Cash flow adjustment | Local road improvements | Road improvements | Auckland Transport | RSP - DairyFlat / CR Highways Intersection Improvement | Implementation | RSP-Dairyflat-CR highways Intersectns Imprvemt-IMP | V_VH | V_VH | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -1 | -1 |  | 11.3 | 11.3 | 11.3
2019-11-19 | November 2019 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | SH1 Wex Long Swamp Section | Construction | implementation of Construction | HHL | MHL | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 1.3 | 1.3
2019-11-18 | November 2019 Review | Cash flow adjustment | Local road maintenance | Routine drainage maintenance | Clutha District Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | SPR |  | MH |  | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -300 | -285
2019-11-18 | November 2019 Review | Cash flow adjustment | Local road maintenance | Sealed pavement maintenance | Clutha District Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | SPR |  | MH |  | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -26228 | -24917
2019-11-18 | November 2019 Review | Cash flow adjustment | Local road maintenance | Sealed road resurfacing | Clutha District Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | SPR |  | MH |  | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 19375 | 18407
2019-11-18 | November 2019 Review | Cash flow adjustment | Local road maintenance | Structures maintenance | Clutha District Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | SPR |  | MH |  | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -72 | -68
2019-11-18 | November 2019 Review | Cash flow adjustment | Local road maintenance | Traffic services maintenance | Clutha District Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | SPR |  | MH |  | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -163 | -155
2019-11-18 | November 2019 Review | Cash flow adjustment | Local road maintenance | Traffic services renewals | Clutha District Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | SPR |  | MH |  | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 50 | 48
2019-11-14 | November 2019 Review | Cost Decrease | Public transport | Bus services | Auckland Transport | Public Transport Programme 2018-21 | Operations |  | HM | HM | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -2606452 | -1329291
2019-11-11 | November 2019 Review | Cost Increase | Public transport | Bus services | Bay of Plenty Regional Council | Public Transport Programme 2018-21 | Operations |  | HM | MM | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 311519 | 158874
2019-11-11 | November 2019 Review | Cost Increase | Public transport | Bus services | Hawkes Bay Regional Council | Public Transport Programme 2018-21 | Operations |  | MM | MM | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 75000 | 38250
2019-11-11 | November 2019 Review | Cost Increase | Public transport | Bus services | Nelson City Council | Public Transport Programme 2018-21 | Operations |  | MH | MH | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 27500 | 14025
2019-11-29 | November 2019 Review | Cost Decrease | External funding | Cycling facilities | Auckland Transport | 2012-15 Glen Innes to Tamaki Drive Cycleway | Construction | UCP Glen Innes-Tamaki Dr C/way-Sec 3 CON (UCF) | HHL | HHL | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -325579 | -325579 |  | 0.9 | 0 | 0.8
2019-11-29 | November 2019 Review | Cost Decrease | External funding | Cycling facilities | Auckland Transport | Auckland Cycle Network - City Centre Network | Implementation | UCP - ACN CCN - Westhaven to CBD (UCF) | HHH | HHH | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -1241445 | -1241445 |  | 5.1 | 0 | 6.8
2019-11-29 | November 2019 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Auckland Transport | Auckland Cycle Network - City Centre Network | Implementation | UCP - ACN CCN - Westhaven to CBD (NLTF) | HHH | HHH | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1241445 | 633136 |  | 5.1 | 0 | 6.8
2019-11-29 | November 2019 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Auckland Transport | Auckland Cycle Network - Links to Public Transport | Implementation | UCP - ACN Links to PT - NL to Avondale - IMP(NLTF) | HHM | MHM | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -4706176 | -2400150 |  | 4.1 | 0 | 4.1
2019-11-12 | November 2019 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Queenstown-Lakes District Council | Wakatipu Active Travel Network | Pre-implementation* | pre-implementation | H_L | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 2150438 | 1096724 |  | 2.6 | 2.6 | 2.6
2019-11-05 | November 2019 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Wellington City Council | Wellington Cycle Network - Eastern Package | Implementation | Evans Bay - UCP Implementation - NLTF | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 4720000 | 2407200 |  | 2.5 | 0 | 2.5
2019-11-08 | November 2019 Review | Cost Decrease | Local road maintenance | Emergency works | Dunedin City Council | E/W Rain event November 2018 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | -14000
2019-11-01 | November 2019 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (Waikato) | EW East Waikato Storm Event Dec 2018 | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (Transport Services) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -106 | -106
2019-11-22 | November 2019 Review | Cost Decrease | Local road improvements | New roads | Auckland Transport | Transport Network for Growth - North | Detailed Business Case | North DBC | H_M | HMM | N |  | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -23565157 | -12018230 |  | 3.2 | 3.2 | 3.2
2019-11-22 | November 2019 Review | Cost Decrease | Local road improvements | New roads | Auckland Transport | Transport Network for Growth - Warkworth | Detailed Business Case | Warkworth DBC | H_L | HML | N |  | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -451727 | -230381 |  | 1.1 | 1.1 | 1.1
2019-11-29 | November 2019 Review | Cost Increase | State highway improvements | New roads | NZTA (Waikato) | SH1 Wex Ngaruawahia Section | Construction |  | HML | HML | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 125489 | 125489 |  |  | 0 | 1
2019-11-12 | November 2019 Review | Cost Increase | State highway improvements | New roads | NZTA (Waikato) | SH1 Wex Ngaruawahia Section | Construction |  | HML | HML | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 29408022 | 29408022 |  |  | 0 | 1
2019-11-18 | November 2019 Review | Cost Decrease | Local road improvements | New traffic management facilities | Christchurch City Council | AAC TP30k: Slow Core | Construction |  | HHL | HHH | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -120126 | -61264 |  | 2.2 | 22.8 | 22.8
2019-11-14 | November 2019 Review | Cost Increase | Public transport | Passenger ferry services | Auckland Transport | Public Transport Programme 2018-21 | Operations |  | HM | HM | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 13275169 | 6770336
2019-11-14 | November 2019 Review | Cost Increase | Public transport | Passenger rail services | Auckland Transport | Public Transport Programme 2018-21 | Operations |  | HM | HM | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 34119289 | 17513894
2019-11-18 | November 2019 Review | Cost Increase | Investment management (incl. Transport Planning) | Programme Business Case Development | NZ Transport Agency | Transport Planning activities - Internal Costs | Programme business case |  | HH_ | HH_ | N | 1 | Approved | Approved by Senior Manager System Planning (Transport Services) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1775713 | 1775713
2019-11-18 | November 2019 Review | Cost Decrease | Promotion of road safety and demand management | Promotion, education and advertising | Bay of Plenty Regional Council | BOPRC Road Safety 2018-2021 | Implementation |  | HM | HM | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -179205 | -91395
2019-11-27 | November 2019 Review | Cost Decrease | Promotion of road safety and demand management | Promotion, education and advertising | NZTA (Marlborough) | Road Safety Promotion 2018-21 | Implementation |  | MM | MH | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -478 | -478
2019-11-27 | November 2019 Review | Cost Increase | Promotion of road safety and demand management | Promotion, education and advertising | NZTA (Wellington) | Road Safety Promotion 2018-21 | Implementation |  | HM | HM | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 23665 | 23665
2019-11-18 | November 2019 Review | Cost Decrease | Promotion of road safety and demand management | Promotion, education and advertising | Selwyn District Council | Road Safety Promotion 2018-21 | Implementation |  | HM | HH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -10000 | -5100
2019-11-18 | November 2019 Review | Cost Decrease | Promotion of road safety and demand management | Promotion, education and advertising | Selwyn District Council | Road Safety Promotion 2018-21 | Implementation |  | HM | HM | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -10500 | -5355
2019-11-18 | November 2019 Review | Cost Increase | Promotion of road safety and demand management | Promotion, education and advertising | Selwyn District Council | Road Safety Promotion 2018-21 | Implementation |  | HM | HH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 20500 | 10455
2019-11-21 | November 2019 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (BOP) | TEL Tauranga Eastern Link | Property |  | HHL | HHL | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 205200 | 205200 |  | 1 | 2 | 2
2019-11-27 | November 2019 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Canterbury) | Broughs Road Extension | Property | Property | HHM | MHM | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 607581 | 607581 |  | 3.6 | 0 | 3.6
2019-11-27 | November 2019 Review | Cost Decrease | State highway improvements | Property purchase (State highways) | NZTA (Canterbury) | Broughs Road Extension | Property | Property | HHM | MHM | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -452865 | -452865 |  | 3.6 | 0 | 3.6
2019-11-07 | November 2019 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Wellington) | Wellington RoNS (2)-Wellington Inner-City (Tunnel to Tunnel) | Property |  | HHL | HHL | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 280181 | 280181 |  |  | 1.4 | 1.4
2019-11-04 | November 2019 Review | Cost Increase | Local road improvements | Property purchase (local roads) | Auckland Transport | LRGF - Gills to Oteha Valley Connection | Property | Gills to Oteha Valley Connection - Property | MHH | MLH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 842560 | 429706 |  | 8.6 | 0 | 8.6
2019-11-14 | November 2019 Review | Cost Increase | Public transport | Public transport facilities operations and maintenance | Auckland Transport | Public Transport Programme 2018-21 | Operations |  | HM | HM | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 5426918 | 2767729
2019-11-14 | November 2019 Review | Cost Decrease | Public transport | Public transport information supply, operations and maintenance | Auckland Transport | Public Transport Programme 2018-21 | Operations |  | HM | HM | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -5323407 | -2714938
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport information supply, operations and maintenance | Bay of Plenty Regional Council | Public Transport Programme 2018-21 | Operations |  | HM | MM | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 876773 | 447154
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport information supply, operations and maintenance | Bay of Plenty Regional Council | Regional Consortium Ticketing Solution | Implementation | Implementation - RITS Shared Operational Cost | HML | HML | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 266578 | 135955 |  | 1.2 | 1.2 | 1.2
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport information supply, operations and maintenance | Bay of Plenty Regional Council | Regional Consortium Ticketing Solution | Implementation | RITS Supplier direct cost (INIT only) | HML | HML | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 37167 | 24160 |  | 1.2 | 1.2 | 1.2
2019-11-11 | November 2019 Review | Cost Decrease | Public transport | Public transport information supply, operations and maintenance | Hawkes Bay Regional Council | National Ticketing Programme | Implementation | NTP - Stabilisation of existing ticketing system | MMH | HHL* | N | 4 | Declined | Declined by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have not been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -45944 | -23432 |  | 99 | 0 | 0
2019-11-18 | November 2019 Review | Cost Decrease | Public transport | Public transport information supply, operations and maintenance | Hawkes Bay Regional Council | National Ticketing Programme | Implementation | NTP - Stabilisation of existing ticketing system | MMH | HHL* | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -38340 | -19553 |  | 99 | 0 | 0
2019-11-25 | November 2019 Review | Cost Increase | Public transport | Public transport information supply, operations and maintenance | Hawkes Bay Regional Council | Public Transport Programme 2018-21 | Operations |  | MM | MM | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 90000 | 45900
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport information supply, operations and maintenance | Hawkes Bay Regional Council | Regional Consortium Interim Ticketing Solution | Implementation | RITS Supplier direct cost (INIT only) | HML | HML | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 116382 | 75650 |  | 1.2 | 1.2 | 1.2
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport information supply, operations and maintenance | Hawkes Bay Regional Council | Regional Consortium Interim Ticketing Solution | Implementation | RITS Shared Operational Cost | HML | HML | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 69394 | 35390 |  | 1.2 | 1.2 | 1.2
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport information supply, operations and maintenance | Horizons Manawatu | Public Transport Programme 2018-21 | Operations |  | MM | MM | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 190000 | 96900
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport information supply, operations and maintenance | Horizons Manawatu | Regional Consortium Interim Ticketing Solution | Implementation | RITS Supplier direct cost (INIT only) | HML | HML | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 9662 | 6282 |  | 1.2 | 1.2 | 1.2
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport information supply, operations and maintenance | Horizons Manawatu | Regional Consortium Interim Ticketing Solution | Implementation | RITS Shared Operational Cost | HML | HML | N | 5 | Approved with conditions | Approved with conditions by Chief Financial Officer (CFO) | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Transport Investment Online or by request | 68888 | 35133 | Condition subsequent â€“ it should be made clear to the RITS participants that no further NLTF funding is available for the project | 1.2 | 1.2 | 1.2
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport information supply, operations and maintenance | Invercargill City Council | Public Transport Programme 2018-21 | Operations |  | HL | MM | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 25000 | 14000
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport information supply, operations and maintenance | Invercargill City Council | Regional Consortium Interim Ticketing Solution | Implementation | RITS Shared Operational Cost | HML | HML | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 31951 | 16141 |  | 1.2 | 1.2 | 1.2
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport information supply, operations and maintenance | Invercargill City Council | Regional Consortium Interim Ticketing Solution | Implementation | RITS Supplier direct cost (INIT only) | HML | HML | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 4461 | 2900 |  | 1.2 | 1.2 | 1.2
2019-11-18 | November 2019 Review | Cost Decrease | Public transport | Public transport information supply, operations and maintenance | Nelson City Council | National Ticketing Programme | Implementation | NTP - Stablisation of existing ticketing system | MMH | HHL* | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -95431 | -48669 |  | 99 | 0 | 0
2019-11-25 | November 2019 Review | Cost Increase | Public transport | Public transport information supply, operations and maintenance | Nelson City Council | Public Transport Programme 2018-21 | Operations |  | MH | MH | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 144051 | 73466
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport information supply, operations and maintenance | Nelson City Council | Regional Consortium Interim Ticketing Solution | Implementation | RITS Supplier direct cost (INIT only) | HML | HML | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 4461 | 2902 |  | 1.2 | 1.2 | 1.2
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport information supply, operations and maintenance | Nelson City Council | Regional Consortium Interim Ticketing Solution | Implementation | RITS Shared Operational Cost | HML | HML | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 31983 | 16311 |  | 1.2 | 1.2 | 1.2
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport information supply, operations and maintenance | Northland Regional Council | Public Transport Programme 2018-21 | Operations |  | MM | MM | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 40000 | 21600
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport information supply, operations and maintenance | Northland Regional Council | Regional Consortium Interim Ticketing Solution | Implementation | RITS Supplier direct cost (INIT only) | HML | HML | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 4461 | 2900 |  | 1.2 | 1.2 | 1.2
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport information supply, operations and maintenance | Northland Regional Council | Regional Consortium Interim Ticketing Solution | Implementation | RITS Shared Operational Cost | HML | HML | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 32015 | 17290 |  | 1.2 | 1.2 | 1.2
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport information supply, operations and maintenance | Otago Regional Council | Regional Consortium Interim Ticketing Solution | Implementation | RITS Supplier direct cost (INIT only) | HML | HML | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 37166 | 24159 |  | 1.2 | 1.2 | 1.2
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport information supply, operations and maintenance | Otago Regional Council | Regional Consortium Interim Ticketing Solution | Implementation | RITS Shared Operational Cost | HML | HML | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 266357 | 135842 |  | 1.2 | 1.2 | 1.2
2019-11-11 | November 2019 Review | Cost Decrease | Public transport | Public transport information supply, operations and maintenance | Taranaki Regional Council | National Ticketing Programme | Implementation | NTP - Stablisation of existing ticketing system | MMPV_EoL | HHH | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -78048 | -39804 |  | 99 | 0 | 0
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport information supply, operations and maintenance | Taranaki Regional Council | Regional Consortium Interim Ticketing Solution | Implementation | RITS Shared Operational Cost | HML | HM_ | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 31631 | 16133 |  | 1.2 | 1.2 | 1.2
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport information supply, operations and maintenance | Waikato Regional Council | Public Transport Programme 2018-21 | Operations |  | MM | MM | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 926102 | 472312
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport information supply, operations and maintenance | Waikato Regional Council | Regional Consortium Interim Ticketing Solution | Implementation | RITS Supplier direct cost (INIT only) | HML | HML | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 37166 | 24159 |  | 1.2 | 1.2 | 1.2
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport information supply, operations and maintenance | Waikato Regional Council | Regional Consortium Interim Ticketing Solution | Implementation | RITS Shared Operational Cost | HML | HML | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 266768 | 136052 |  | 1.2 | 1.2 | 1.2
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport infrastructure and major renewals | Bay of Plenty Regional Council | Regional Consortium Ticketing Solution | Implementation | RITS Implementation | HML | HML | N | 4 | Approved with conditions | Approved with conditions by Chief Financial Officer (CFO) | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Transport Investment Online or by request | 1081059 | 702689 | Condition subsequent â€“ it should be made clear to the RITS participants that no further NLTF funding is available for the project | 1.2 | 1.2 | 1.2
2019-11-18 | November 2019 Review | Cost Decrease | Public transport | Public transport infrastructure and major renewals | Hamilton City Council | The Base Station (Start Up Rail Service) | Pre-implementation* | Rotokauri PT Hub + Park and Ride | H_L | H_L | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -3139925 | -2370643 |  | 0.5 | 0.5 | 0.5
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport infrastructure and major renewals | Hawkes Bay Regional Council | Regional Consortium Interim Ticketing Solution | Implementation | RITS Implementation | HML | HML | N | 4 | Approved with conditions | Approved with conditions by Chief Financial Officer (CFO) | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Transport Investment Online or by request | 260256 | 169167 | Condition subsequent â€“ it should be made clear to the RITS participants that no further NLTF funding is available for the project | 1.2 | 1.2 | 1.2
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport infrastructure and major renewals | Horizons Manawatu | Regional Consortium Interim Ticketing Solution | Implementation | RITS Implementation | HML | HML | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 386978 | 251536 |  | 1.2 | 1.2 | 1.2
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport infrastructure and major renewals | Invercargill City Council | Regional Consortium Interim Ticketing Solution | Implementation | RITS Implementation | HML | HML | N | 4 | Approved with conditions | Approved with conditions by Chief Financial Officer (CFO) | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Transport Investment Online or by request | 299701 | 194806 | Condition subsequent â€“ it should be made clear to the RITS participants that no further NLTF funding is available for the project | 1.2 | 1.2 | 1.2
2019-11-11 | November 2019 Review | Cost Decrease | Public transport | Public transport infrastructure and major renewals | Nelson City Council | National Ticketing Programme | Implementation | NTP - Stabilisation of existing ticketing system | MMH | HHL* | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -9205 | -5983 |  | 99 | 0 | 0
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport infrastructure and major renewals | Nelson City Council | Regional Consortium Interim Ticketing Solution | Implementation | RITS Implementation | HML | HML | N | 4 | Approved with conditions | Approved with conditions by Chief Financial Officer (CFO) | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Transport Investment Online or by request | 131394 | 85406 | Condition subsequent â€“ it should be made clear to the RITS participants that no further NLTF funding is available for the project | 1.2 | 1.2 | 1.2
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport infrastructure and major renewals | Northland Regional Council | Regional Consortium Interim Ticketing Solution | Implementation | RITS Implentation | HML | HML | N | 4 | Approved with conditions | Approved with conditions by Chief Financial Officer (CFO) | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Transport Investment Online or by request | 123161 | 80054 | Condition subsequent â€“ it should be made clear to the RITS participants that no further NLTF funding is available for the project | 1.2 | 1.2 | 1.2
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport infrastructure and major renewals | Otago Regional Council | Regional Consortium Interim Ticketing Solution | Implementation | RITS Implementation | HML | HML | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1136321 | 738608 |  | 1.2 | 1.2 | 1.2
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport infrastructure and major renewals | Taranaki Regional Council | Regional Consortium Interim Ticketing Solution | Implementation | RITS Implementation | HML | HM_ | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 219434 | 142632 |  | 1.2 | 1.2 | 1.2
2019-11-12 | November 2019 Review | Cost Increase | Public transport | Public transport infrastructure and major renewals | Waikato Regional Council | Regional Consortium Interim Ticketing Solution | Implementation | RITS Implementation | HML | HML | N | 4 | Approved with conditions | Approved with conditions by Chief Financial Officer (CFO) | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Transport Investment Online or by request | 1033324 | 671661 | Condition subsequent â€“ it should be made clear to the RITS participants that no further NLTF funding is available for the project | 1.2 | 1.2 | 1.2
2019-11-22 | November 2019 Review | Cost Decrease | Local road improvements | Road improvements | Auckland Transport | Transport Network for Growth - North West | Detailed Business Case | North West DBC | H_M | HMM | N |  | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -6304416 | -3215252 |  | 3.5 | 3.5 | 3.5
2019-11-22 | November 2019 Review | Cost Decrease | Local road improvements | Road improvements | Auckland Transport | Transport Network for Growth - South | Detailed Business Case | South DBC | H_M | HMM | N |  | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -13902215 | -7090130 |  | 3.7 | 3.7 | 3.7
2019-11-06 | November 2019 Review | Cost Decrease | Local road improvements | Road improvements | NZ Transport Agency | Digital Engineering for Transport | Detailed Business Case | DEfT IBC | M_M | VMM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -2700000 | -2700000 |  | 4.8 | 0 | 3.8
2019-11-01 | November 2019 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (BOP) | SH29 Eastern Kaimai Safe System Corridor | Construction | SH29 Eastern Kaimai Safe System Corridor | HMH | HMH | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -1708 | -1708 |  |  |  | 5.2
2019-11-18 | November 2019 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (BOP) | SH30 Eastern Corridor, Connect Rotorua | Detailed Business Case | SH30 Eastern Corridor Connect Rotorua | MHM | MMM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 346357 | 346357 |  | 3 | 2.7 | 2.7
2019-11-21 | November 2019 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (BOP) | SH30 Eastern Corridor, Connect Rotorua | Implementation | SH30 Eastern Corridor Connect Rotorua | MHM | MMM | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 6287439 | 6287439 |  | 3 | 2.7 | 2.7
2019-11-18 | November 2019 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (BOP) | SH30 Eastern Corridor, Connect Rotorua | Pre-implementation* | Preimp | MHM | MMM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -346356 | -346356 |  | 3 | 2.7 | 2.7
2019-11-21 | November 2019 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (Marlborough) | SH1 SH62 Spring Creek Intersection RAB | Construction |  | MM*L* | HML | N | 7 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 86317 | 86317 |  |  | 1.5 | 1.5
2019-11-08 | November 2019 Review | Cost Decrease | Regional Improvements | Road improvements | NZTA (Northland) | SH1 Loop Road North to Smeatons Hill Safety Improvement | Implementation | Implementation | HML | HML | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -2462400 | -2462400 |  | 1.2 | 0 | 1.2
2019-11-18 | November 2019 Review | Cost Decrease | Regional Improvements | Road improvements | NZTA (Otago) | SH1 Oamaru to Dunedin safety improvements | Detailed Business Case | Detailed Business Case | HML | HML | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -463737 | -463737 |  | 2 | 2.2 | 2.2
2019-11-08 | November 2019 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (Otago) | SH1 Oamaru to Dunedin safety improvements | Detailed Business Case | Detailed Business Case | HML | HML | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 463737 | 463737 |  | 2 | 2.2 | 2.2
2019-11-21 | November 2019 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Southland) | SH1S Bluff Highway/Elles Road I/S Improvement | Pre-implementation* | Pre-Implementation | MML* | HHL | N | 6 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 26000 | 26000 |  | 1.2 | 2.4 | 2.4
2019-11-14 | November 2019 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Taranaki) | Normanby Overbridge Realignment | Implementation | Implementation - NLTF funding | LMH | HMH | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1250000 | 1250000 |  | 4.1 | 4.1 | 4.1
2019-11-18 | November 2019 Review | Cost Decrease | Regional Improvements | Road improvements | NZTA (Taranaki) | Waitara to Bell Block Route Imp: SH3/3A to Waitara | Pre-implementation* | Pre-implementation | MM*L | HML | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -3078000 | -3078000 |  | 1.5 | 1.1 | 1.1
2019-11-05 | November 2019 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Tasman) | SH6 Clover Road intersection | Construction | Construction | HHH | HHH | N | 1 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 375971 | 375971 |  | 5 | 5 | 5
2019-11-01 | November 2019 Review | Cost Decrease | Regional Improvements | Road improvements | NZTA (Waikato) | SH1 (Cambridge to Piarere) ST Improvements, NSRRP | Detailed Business Case | Short Term Safety | HM*M | HHL | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -235624 | -235624 |  | 4.6 | 1.2 | 1.2
2019-11-06 | November 2019 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Wellington) | Asset Management Data Standard (DEfT) | Detailed Business Case | Detailed Business Case | M_M | V_M | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1103809 | 1103809 |  | 4.8 | 0 | 3.8
2019-11-07 | November 2019 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (West Coast) | Kaikoura Nov 2016 EQ: Lewis Pass Altern Upg Route - W-Coast | Implementation | Implementation | HML | HML | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -196534 | -196534 |  | 1.4 | 1.4 | 1.4
2019-11-08 | November 2019 Review | Cost Decrease | Local road improvements | Road improvements | Nelson City Council | LED Streetlight Upgrade | Construction | Construction | MHH | HH_ | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -348544 | -296262 |  | 5 | 5 | 5
2019-11-14 | November 2019 Review | Cost Increase | Public transport | Total mobility operations | Auckland Transport | Public Transport Programme 2018-21 | Operations |  | HM | HM | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 104732 | 62840
2019-11-14 | November 2019 Review | Cost Increase | Public transport | Total mobility wheelchair hoist use payments | Auckland Transport | Public Transport Programme 2018-21 | Operations |  | HM | HM | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 3751 | 3751