## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Phase Label | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Decision Status | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR | Your Phase reference | TIO Phase id | SAP item id | TIO Request id
2023-09-26 | September 2023 Review | New approval | External funding | Cycling facilities | Rotorua Lakes Council | CERF-TC Malfroy Rd Shared Path 0-0.81 | Implementation | Complementary Activities | HHH | VHHL | N | 4 | Approved | Approved by Minister for Crown Appropriation | Per CERF funding | 185000 | 185000 |  |  |  | 0 | Complementary Activities | 284260 |  | 122915
2023-09-06 | September 2023 Review | New approval | External funding | Cycling facilities | Waikato District Council | CERF-TC-RÄhui PÅkeka ¦ Huntly Connections Project | Pre-implementation* | RÄhui PÅkeka ¦ Huntly Connections Project | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | Change to existing phase approval - was previously allocated to the incorrect funding source. | 375000 | 375000 |  |  | 0 | 0 | Initial Project Scoping and Consultation | 284658 |  | 125317
2023-09-04 | September 2023 Review | New approval | Local road maintenance | Emergency works | Buller District Council | Buller District Flood Event - July 2021 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds to move from normal FAR to higher FAR. Adjust emergency works funding (Higher FAR). | 238557 | 219472 |  |  |  |  | Buller Flood Event WC141 reinstatement - (Normal FAR+20%) (Normal FAR+20%) | 288966 |  | 125707
2023-09-04 | September 2023 Review | New approval | Local road maintenance | Emergency works | Carterton District Council | Emergency Works Te Wharau Storm Event October 2022 | Construction | Permanent remedials | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds to move from normal FAR to higher FAR. Adjust emergency works funding (Higher FAR). | 414911 | 294587 |  |  |  |  | Permanent remedials (Normal FAR+20%) | 288969 |  | 125712
2023-09-04 | September 2023 Review | New approval | Local road maintenance | Emergency works | Carterton District Council | Storm event August 2022 | Construction | Network reinstatement (Normal FAR+20%) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds to move from normal FAR to higher FAR. Adjust emergency works funding (Higher FAR). | 103861 | 73741 |  |  |  |  | (Normal FAR+20%) (Normal FAR+20%) | 288968 |  | 125711
2023-09-04 | September 2023 Review | New approval | Local road maintenance | Emergency works | DOC (Southland) | EWâ€“DOC(Southland) June 2023 event Wilmot Pass | Construction | Immediate response & Road reinstatement | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds to move from normal FAR to higher FAR. Adjust emergency works funding (Higher FAR). | 31427 | 22313 |  |  |  |  | (Normal FAR+20%) | 288967 |  | 125709
2023-09-07 | September 2023 Review | New approval | Local road maintenance | Emergency works | Far North District Council | EW - Far North DC August 2022 | Construction | I & D of all sites & Practitioner Solutions Const. | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds to move from normal FAR to higher FAR. Adjust emergency works funding (Higher FAR). | 2644713 | 2353795 |  |  |  |  | Phase 2 (Normal FAR+20%) | 288986 |  | 125758
2023-09-07 | September 2023 Review | New approval | Local road maintenance | Emergency works | Far North District Council | EW Far North DC May 2023 | Construction | Phase 2 - Minor Remedial Works - EW May 2023 | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds to move from normal FAR to higher FAR. Adjust emergency works funding (Higher FAR). | 3832431 | 3410864 |  |  |  |  | Phase 2 - Minor Remedial Works - EW May 2023 (Normal FAR+20%) | 288987 |  | 125759
2023-09-04 | September 2023 Review | New approval | Local road maintenance | Emergency works | Rotorua Lakes Council | EW - Rotorua LC Storm Damage July 2022 | Construction | Phase 2 - Construction (Normal FAR+20%) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds to move from normal FAR to higher FAR. Adjust emergency works funding (Higher FAR). | 47426 | 36044 |  |  |  |  | (Normal FAR+20%) (Normal FAR+20%) | 288971 |  | 125717
2023-09-04 | September 2023 Review | New approval | Local road maintenance | Emergency works | South Wairarapa District Council | Storm event August 2022 | Construction | Network reinstatement (Normal FAR+20%) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds to move from normal FAR to higher FAR. Adjust emergency works funding (Higher FAR). | 427538 | 303552 |  |  |  |  | (Normal FAR+20%) (Normal FAR+20%) | 288972 |  | 125719
2023-09-04 | September 2023 Review | New approval | Local road maintenance | Emergency works | Taupo District Council | EW - Taupo DC Omori Road slip October 22 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds to move from normal FAR to higher FAR. Adjust emergency works funding (Higher FAR). | 163364 | 115988 |  |  |  |  | (Normal FAR+20%) | 288970 |  | 125715
2023-09-27 | September 2023 Review | New approval | Local road maintenance | Emergency works | Waitomo District Council | EW - Waitomo DC Winter 2022 Events | Construction | Construction & MSQA Of Permanent Construction Site | ___ |  | N |  | Approved | Approved by National Manager, Programmes and Standards (Transport Services) | Please refer Value, Outcomes and Scope Committee funding request paper link: https://infohub.nzta.govt.nz/otcs/cs.dll/link/59222104 | 3993145 | 3793488 | [5 empty] | 283094 |  | 121163
2023-09-21 | September 2023 Review | New approval | Investment management (incl. Transport Planning) | Management of the funding allocation system | NZ Transport Agency | Strategic Resilience Programme | Implementation | 60071774 | HHM | VHHH | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | This funding enables the Resilience Programme to develop nationally consistent policies, frameworks and processes to optimise resilience outcomes for Waka Kotahi and the wider NLTP | 500000 | 500000 |  |  |  | 4 | 60071774 | 288964 |  | 125932
2023-09-20 | September 2023 Review | New approval | External funding | New activities influencing users of the transport system | Dunedin City Council | CERF-TC-South Dunedin Schools | Implementation | Active Travel package | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | Part of the Budget 2022 Cabinet approved initiatives with funding under the Climate Emergency response Fund (CERF) programme. CERF-TC projects do not follow the same NLTF business case assessment pathway. The business case assessment has been replaced with a bespoke application, assessment, monitoring process as detailed in Transport Choices Funding Agreement Guidance Notes. | 781327 | 722994 |  |  |  | 0 | Active Travel Package | 284108 |  | 125559
2023-09-21 | September 2023 Review | New approval | External funding | New activities influencing users of the transport system | Invercargill City Council | CERF-TC ICC and SDC - Cycling End User facilities | Pre-implementation* | Stage 1 - Pre-Implementation Project | HHH | HHM | N | 4 | Approved | Approved by Minister for Crown Appropriation | 2022 cabinet approved budget where Transport Choice (CERF initiatives) for the Govt's Emission Reduction Plan. TC is directed towards activities, infrastructure and services that reduce reliance on cars and support uptake of active and shared modes of transport. | 180000 | 97500 |  |  |  | 0 |  | 288978 |  | 125723
2023-09-14 | September 2023 Review | New approval | External funding | New activities influencing users of the transport system | Matamata-Piako District Council | CERF-TC MPDC Transport Choices Projects | Implementation | Complementary Measures: MV pump track / parking | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | Per CERF funding | 140000 | 140000 |  |  |  | 0 |  | 284170 |  | 123275
2023-09-19 | September 2023 Review | New approval | External funding | New activities influencing users of the transport system | Porirua City Council | CERF-TC - Papakowhai Shared Path | Implementation | Project early implementation | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | Recommend funding of $7,420,000 Early Implementation as it aligns with the Crown-funded CERF TC PBC and approval has been confirmed by CERF-TC programme team | 7420000 | 7420000 |  |  | 0 | 0 | Implementation - Papakowhai Shared Path | 284226 |  | 125652
2023-09-20 | September 2023 Review | New approval | External funding | New activities influencing users of the transport system | Queenstown-Lakes District Council | CERF-TC - Arthur's Point to Queenstown - Route C5 | Implementation | Arthurs Point to Queenstown Route | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | Part of the Budget 2022 Cabinet approved initiatives with funding under the Climate Emergency response Fund (CERF) programme. CERF-TC projects do not follow the same NLTF business case assessment pathway. The business case assessment has been replaced with a bespoke application, assessment, monitoring process as detailed in Transport Choices Funding Agreement Guidance Notes. | 7065985 | 7065985 |  |  |  | 0 |  | 284493 |  | 125403
2023-09-13 | September 2023 Review | New approval | External funding | Operations & maintenance of real-time and ticketing systems | Auckland Transport | Community Connect - Auckland Trial | Implementation | Community Connect - Admin | MHL | MHL | N | 7 | Approved | Approved by Minister for Crown Appropriation | Crown funded. | 3744000 | 3744000 |  |  |  |  | 525.289 | 289019 |  | 125795
2023-09-13 | September 2023 Review | New approval | External funding | Operations & maintenance of real-time and ticketing systems | Bay of Plenty Regional Council | CERF-CC Community Connect Scheme | Implementation | Community Connect - Admin | MHL | MHL | N | 7 | Approved | Approved by Minister for Crown Appropriation | Crown funded | 105000 | 105000 | [5 empty] | 289020 |  | 125796
2023-09-13 | September 2023 Review | New approval | External funding | Operations & maintenance of real-time and ticketing systems | Environment Canterbury | CERF-CC Community Connect Scheme | Implementation | Community Connect - Admin | MHL | MHL | N | 7 | Approved | Approved by Minister for Crown Appropriation | Crown funded. | 403000 | 403000 | [5 empty] | 289021 |  | 125798
2023-09-13 | September 2023 Review | New approval | External funding | Operations & maintenance of real-time and ticketing systems | Gisborne District Council | CERF-CC Community Connect Scheme | Implementation | Community Connect - Admin | MHL | MHL | N | 7 | Approved | Approved by Minister for Crown Appropriation | Crown funded | 4000 | 4000 | [5 empty] | 289025 |  | 125807
2023-09-13 | September 2023 Review | New approval | External funding | Operations & maintenance of real-time and ticketing systems | Greater Wellington | CERF-CC Community Connect Scheme | Implementation | Community Connect - Admin | MLL | MHL | N | 10 | Approved | Approved by Minister for Crown Appropriation | Crown funded | 1713000 | 1713000 | [5 empty] | 289022 |  | 125801
2023-09-13 | September 2023 Review | New approval | External funding | Operations & maintenance of real-time and ticketing systems | Hawkes Bay Regional Council | CERF-CC Community Connect Scheme | Implementation | Community Connect - Admin | MHL | MHL | N | 7 | Approved | Approved by Minister for Crown Appropriation | Crown funded | 21000 | 21000 | [5 empty] | 289026 |  | 125809
2023-09-13 | September 2023 Review | New approval | External funding | Operations & maintenance of real-time and ticketing systems | Horizons Manawatu | CERF-CC Community Connect Scheme | Implementation | Community Connect - Admin | MHL | MHL | N | 7 | Approved | Approved by Minister for Crown Appropriation | Crown funded | 42000 | 42000 | [5 empty] | 289027 |  | 125811
2023-09-13 | September 2023 Review | New approval | External funding | Operations & maintenance of real-time and ticketing systems | Northland Regional Council | CERF-CC Community Connect Scheme | Implementation | Community Connect - Admin | MHL | MHL | N | 7 | Approved | Approved by Minister for Crown Appropriation | Crown funded. | 8000 | 8000 | [5 empty] | 289031 |  | 125816
2023-09-26 | September 2023 Review | New approval | External funding | Operations & maintenance of real-time and ticketing systems | Otago Regional Council | CERF-CC Community Connect Scheme | Implementation | Community Connect - Admin | MHL | MHL | N | 7 | Approved | Approved by Minister for Crown Appropriation | Crown funded. | 125000 | 125000 | [5 empty] | 289023 |  | 125805
2023-09-13 | September 2023 Review | New approval | External funding | Operations & maintenance of real-time and ticketing systems | Taranaki Regional Council | CERF-CC Community Connect Scheme | Implementation | Community Connect - Admin | MHL | MHL | N | 7 | Approved | Approved by Minister for Crown Appropriation | Crown funded | 26000 | 26000 | [5 empty] | 289032 |  | 125818
2023-09-20 | September 2023 Review | New approval | External funding | Operations & maintenance of real-time and ticketing systems | Waikato Regional Council | CERF-CC Community Connect Scheme | Implementation | Community Connect Rail Concessions | MHL | MHL | N | 7 | Approved | Approved by Minister for Crown Appropriation | Crown funded | 21000 | 21000 | [5 empty] | 288518 |  | 125572
2023-09-20 | September 2023 Review | New approval | External funding | Operations & maintenance of real-time and ticketing systems | Waikato Regional Council | CERF-CC Community Connect Scheme | Implementation | Community Connect - Admin | MHL | MHL | N | 7 | Approved | Approved by Minister for Crown Appropriation | Crown funded | 156000 | 156000 | [5 empty] | 289033 |  | 125820
2023-09-11 | September 2023 Review | New approval | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | Dunedin City Council | SFDT - Park and Ride Facilities - Mosgiel and Burnside | Implementation | Park and Ride Mosgiel - Stage One | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Increase public transport patronage through reducing the barriers to uptake and improving the attractiveness of travelling by bus, with a 5% increase in mode share of journeys to work / education made by this mode; and Enable the delivery to start on an important element of the Shaping Future Dunedin Transport programme. | 8088000 | 4124880 |  |  | 2.2 | 1.6 |  | 276616 |  | 125463
2023-09-11 | September 2023 Review | New approval | External funding | Passenger services - bus | Greater Wellington | CERF-Bus Driver Ts & Cs | Implementation | CERF driver uplift - wrong funding source | VHHL | VHHL | N | 2 | Approved | Approved by Minister for Crown Appropriation | Crown funded. | 16894073 | 8615976 |  |  |  | 1 |  | 284583 |  | 125784
2023-09-12 | September 2023 Review | New approval | External funding | Passenger services - bus | Greater Wellington | CERF-Bus Driver Ts & Cs | Implementation | CERF - Driver Wage Uplift | VHHL | VHHL | N | 2 | Approved | Approved by Minister for Crown Appropriation | Crown funded | 16894073 | 8615976 |  |  |  | 1 |  | 289017 |  | 125793
2023-09-12 | September 2023 Review | New approval | External funding | Passenger services - bus | Marlborough District Council | CERF-Bus Driver Ts & Cs | Implementation | CERF - Driver Wage Uplift - wrong funding source | VHHL | VHHL | N | 2 | Approved | Approved by Minister for Crown Appropriation | Crown funded | 38639 | 19705 | [5 empty] | 289016 |  | 125785
2023-09-12 | September 2023 Review | New approval | External funding | Passenger services - bus | Marlborough District Council | CERF-Bus Driver Ts & Cs | Implementation | CERF - Driver Wage Uplift | VHHL | VHHL | N | 2 | Approved | Approved by Minister for Crown Appropriation | Crown funded | 38639 | 19705 | [5 empty] | 289018 |  | 125794
2023-09-26 | September 2023 Review | New approval | External funding | Passenger services - bus | Otago Regional Council | CERF-CC Community Connect Scheme | Implementation | Community Connect Bus Concessions | MHL | MHL | N | 7 | Approved | Approved by Minister for Crown Appropriation | Crown funded. | 1447000 | 1447000 | [5 empty] | 288522 |  | 125575
2023-09-20 | September 2023 Review | New approval | External funding | Passenger services - bus | Waikato Regional Council | CERF-CC Community Connect Scheme | Implementation | Community Connect Bus Concessions | MHL | MHL | N | 7 | Approved | Approved by Minister for Crown Appropriation | Crown funded. | 1930000 | 1930000 | [5 empty] | 288517 |  | 125571
2023-09-26 | September 2023 Review | New approval | External funding | Passenger services - ferry | Otago Regional Council | CERF-CC Community Connect Scheme | Implementation | Community Connect Ferry Concessions | MHL | MHL | N | 7 | Approved | Approved by Minister for Crown Appropriation | Crown funded. | 112000 | 112000 | [5 empty] | 288523 |  | 125576
2023-09-28 | September 2023 Review | New approval | Local road improvements | Road improvements | Auckland Transport | TNFG - South - Pukekohe | Pre-implementation* | TNFG - South - Pukekohe | HHVL | HHL | N | 9 | Approved with conditions | Approved with conditions by Chief Financial Officer (CFO) | This decision has involved consideration of how any identified greenhouse gas emissions impacts of the activity proposed for investment supports the GPS climate change strategic priority (including impacts on relevant transport emission reduction targets and consistency with the ERP) and how the proposal is consistent with the GPS as a whole. Please note decision subsequent. | 7058930 | 3600054 | November 2023 funding decisions paper was approved having a BCR < 1. The update should also reflect the overall programme BCR (as per project team's update). that an update is provided to a future Investment & Delivery Committee recapping on the Supporting Growth Alliance Programme as a whole (costs to date, future commitments, expected funding) and looking at "lessons learned" |  |  |  | 324.2777 | 277748 |  | 125276
2023-09-27 | September 2023 Review | New approval | Road to Zero | Road improvements | NZTA (BOP) | SH33 (Te Ngae Junction to Paengaroa), NSRRP | Pre-implementation* |  | H_H | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $220k from NZTA National | 239800 | 239800 |  |  | 1.2 | 1.2 |  | 278522 | 60062267 | 125949
2023-09-22 | September 2023 Review | New approval | State highway improvements | Road improvements | NZTA (Manawatu/Whanganui) | SH1 Utiku Slip Resilience Improvements | Indicative Business Case |  | VHHL | VHHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | Point of Entry has been prepared in response to identified imminent risk of landslips closing SH1 through the central North Island. Overall the activity shows a strong alignment with GPS Strategic Priorities and the expected outcome is considered aligned with climate change. | 900000 | 900000 | [5 empty] | 288940 | 60071715 | 125704
2023-09-04 | September 2023 Review | New approval | Road to Zero | Road improvements | NZTA (Marlborough) | SH6 Blenheim to Woodbourne Safety Improvements | Implementation |  | VHML | VHHL | N | 3 | Approved | Approved by Chief Financial Officer (CFO) | The activity is aligned with GPS is part of Road to Zero Strategy and Speed and Infrastructure Delivery Programme. | 17698739 | 17698739 |  |  | 0 | 1.6 |  | 278197 | 60044735 | 125697
2023-09-27 | September 2023 Review | New approval | Road to Zero | Road improvements | NZTA (Waikato) | SH1 ETA Corridor Improvements | Pre-implementation* |  | VHML | VHML | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $360k from NZTA National | 392400 | 392400 |  |  | 2.6 | 2.6 |  | 288438 | 60071441 | 125950
2023-09-06 | September 2023 Review | New approval | Road to Zero | Road improvements | NZTA (Wellington) | SH2 Remutaka | Implementation | SH2 Twin Lakes Rd to SH2 Twin Bdg - Stg 1a | HHL | VHHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The key benefit is to address safety. â€¢ We note that the BCR for stage 1 Remutaka Hill is 6.78. â€¢ The requirements of section 20 of the Land Transport Management Act 2003 have been met. â€¢ The decision is neutral in relation to the climate change strategic priority set out in the GPS (including impacts on relevant transport emission reduction targets and consistency with the ERP) and the proposal is consistent with the GPS. | 4283700 | 4283700 |  |  | 2.1 | 2.1 | 79 | 277277 | 60060936 | 125528
2023-09-15 | September 2023 Review | Cash flow adjustment | Local road maintenance | Bridge and structures renewals | Buller District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | SPR |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Approved transfer of unspent wc216 allocation to 214. | -560000 | -560000 | [5 empty] | 272240 |  | 125726
2023-09-01 | September 2023 Review | Cash flow adjustment | Local road maintenance | Cycle path maintenance | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The proposed cash flow changes are in line with the target quantities Auckland Transport programmed to deliver this 2023/24 FY that are also based on priority asset needs. | -393924 | -200901 | [5 empty] | 272189 |  | 125552
2023-09-01 | September 2023 Review | Cash flow adjustment | Local road maintenance | Cycle path renewal | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The proposed cash flow changes are in line with the target quantities Auckland Transport programmed to deliver this 2023/24 FY that are also based on priority asset needs. | -101788 | -51911 | [5 empty] | 272205 |  | 125552
2023-09-01 | September 2023 Review | Cash flow adjustment | Local road maintenance | Drainage renewals | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The proposed cash flow changes are in line with the target quantities Auckland Transport programmed to deliver this 2023/24 FY that are also based on priority asset needs. | -6552854 | -3341956 | [5 empty] | 272199 |  | 125552
2023-09-01 | September 2023 Review | Cash flow adjustment | Local road maintenance | Drainage renewals | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Redistributing carry forwards from WC111 to WC's 211, 212, 213, 214, 215, 216, 222, 225 | 90679 | 62569 | [5 empty] | 272533 |  | 125498
2023-09-15 | September 2023 Review | Cash flow adjustment | Local road maintenance | Drainage renewals | Hurunui District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | SPR |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reallocation of funds to cover changes to work programme namely, resealing, drainage renewals and increases to winter maintenance. | 65000 | 65000 | [5 empty] | 272784 |  | 125554
2023-09-01 | September 2023 Review | Cash flow adjustment | State highway maintenance | Emergency works | NZTA (BOP) | EW BOPE RW July HR from 20220708 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Project Close | 0 | 0 | [5 empty] | 282157 | 60067964 | 125614
2023-09-01 | September 2023 Review | Cash flow adjustment | Local road maintenance | Environmental maintenance | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The proposed cash flow changes are in line with the target quantities Auckland Transport programmed to deliver this 2023/24 FY that are also based on priority asset needs. | 2770345 | 1412876 | [5 empty] | 272192 |  | 125552
2023-09-01 | September 2023 Review | Cash flow adjustment | Local road maintenance | Footpath maintenance | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The proposed cash flow changes are in line with the target quantities Auckland Transport programmed to deliver this 2023/24 FY that are also based on priority asset needs. | -4037535 | -2059143 | [5 empty] | 272190 |  | 125552
2023-09-01 | September 2023 Review | Cash flow adjustment | Local road maintenance | Footpath renewal | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The proposed cash flow changes are in line with the target quantities Auckland Transport programmed to deliver this 2023/24 FY that are also based on priority asset needs. | -265506 | -135408 | [5 empty] | 272206 |  | 125552
2023-09-01 | September 2023 Review | Cash flow adjustment | Local road maintenance | Footpath renewal | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Redistributing carry forwards from WC111 to WC's 211, 212, 213, 214, 215, 216, 222, 225 | 560646 | 386846 | [5 empty] | 272540 |  | 125498
2023-09-01 | September 2023 Review | Cash flow adjustment | Local road maintenance | Network and asset management | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The proposed cash flow changes are in line with the target quantities Auckland Transport programmed to deliver this 2023/24 FY that are also based on priority asset needs. | 6544218 | 3337551 | [5 empty] | 272196 |  | 125552
2023-09-01 | September 2023 Review | Cash flow adjustment | Local road maintenance | Network operations | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The proposed cash flow changes are in line with the target quantities Auckland Transport programmed to deliver this 2023/24 FY that are also based on priority asset needs. | -5814968 | -2965633 | [5 empty] | 272194 |  | 125552
2023-09-01 | September 2023 Review | Cash flow adjustment | Local road maintenance | Network service maintenance | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The proposed cash flow changes are in line with the target quantities Auckland Transport programmed to deliver this 2023/24 FY that are also based on priority asset needs. | -2280644 | -1163129 | [5 empty] | 272193 |  | 125552
2023-09-15 | September 2023 Review | Cash flow adjustment | Local road improvements | New roads | Auckland Transport | Matakana Link Road â€“ Repayment | Repayment | MLR - Balancing | H_H | M_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This request is balancing the repayment to align with the current surplus & CSA submitted for approval. | 0 | 0 |  |  | 0 | 7.7 | 323.2673 | 267305 |  | 125752
2023-09-15 | September 2023 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Canterbury) | CHCH Southern Motorway HJR to Rolleston (Stage 2 & 3) | Construction | Implementation | H_M | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | To move $983,901 from CY to Y1. | 0 | 0 |  |  | 2.4 | 1.5 | 60215381 | 200236 | 60215381 | 125769
2023-09-01 | September 2023 Review | Cash flow adjustment | External funding | New roads | NZTA (Nelson) | Nelson Future Access | Detailed Business Case | DBC - Nelson Future Access | VHHL | VHHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Remove spend from this phase as there is no ARSHP funds- transfer to Phase id 284618 (NLTF funding). | 0 | 0 |  |  | 2.2 | 2.2 | 60032525 | 234004 | 60032525 | 125499
2023-09-18 | September 2023 Review | Cash flow adjustment | External funding | Passenger services - bus | Greater Wellington | CERF-Bus Driver Ts & Cs | Implementation | CERF - Driver Wage Uplift | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is over 3 years. | 0 | 1 |  |  |  | 1 |  | 289017 |  | 125880
2023-09-18 | September 2023 Review | Cash flow adjustment | External funding | Passenger services - bus | Marlborough District Council | CERF-Bus Driver Ts & Cs | Implementation | CERF - Driver Wage Uplift | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is over 3 years. | 0 | 0 | [5 empty] | 289018 |  | 125881
2023-09-15 | September 2023 Review | Cash flow adjustment | Public transport services | Passenger services - ferry | Auckland Transport | Government reduced public transport fares scheme (Crown) | Implementation | Ferry Service - Reduced Fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | 0 | 0 |  |  |  |  | 512.2812 | 281218 |  | 125871
2023-09-15 | September 2023 Review | Cash flow adjustment | Public transport services | Passenger services - rail | Auckland Transport | Government reduced public transport fares scheme (Crown) | Implementation | Rail services - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | 0 | 0 |  |  |  |  | 515.2812 | 281219 |  | 125872
2023-09-11 | September 2023 Review | Cash flow adjustment | Investment management (incl. Transport Planning) | Programme Business Case Development | NZ Transport Agency | Innovation Programme | Programme business case |  | HHL | VHHM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | New projected cashflow. Moving $3M from Yr 23/24 to 24/25 | 0 | 0 |  |  |  |  | 60069122 | 277975 |  | 125787
2023-09-01 | September 2023 Review | Cash flow adjustment | Road to Zero | Property purchase (State highways) | NZTA (BOP) | W2T Waihi to Omokoroa (Safer Corridor) | Property | Property RTZ 331 | VHHL | HHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move funds to future years | 1 | 1 |  |  | 0 | 1 |  | 280900 | 60062262 | 125684
2023-09-15 | September 2023 Review | Cash flow adjustment | Public transport services | Public transport operations and management | Auckland Transport | Government reduced public transport fares scheme (Crown) | Implementation | PT Ops and Man - Reduced Fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | 0 | 0 |  |  |  |  | 524.2812 | 281221 |  | 125874
2023-09-08 | September 2023 Review | Cash flow adjustment | Rail network | Rail network and asset management | KiwiRail | Rail Network Investment Programme 2021-24 Freight & Tourism | Implementation | First RNIP Period | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Updated to reflect ACM's reconciliation of Crown and NLTF spend and remaining budget. | 0 | 0 |  |  | 1 | 1 | National Freight and Tourism Network | 281083 |  | 125768
2023-09-01 | September 2023 Review | Cash flow adjustment | Public transport infrastructure | Rapid Transit Infrastructure | NZTA (Canterbury) | PT Futures MRT | Indicative Business Case |  | VHLL | HHL | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Forecast has been revised to push $790,820 from 2023/24 into the next financial year 2024/25 | 0 | 0 |  |  | 1 | 1 |  | 268114 | 60054249 | 125682
2023-09-01 | September 2023 Review | Cash flow adjustment | State highway improvements | Replacement of bridges and other structures | NZTA (Canterbury) | Seismic Retrofit - Canterbury | Construction | Construction | H_H | H_H | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  | 99 | 99 | 60218483 | 215198 | 60218483 | 125616
2023-09-01 | September 2023 Review | Cash flow adjustment | State highway improvements | Resilience improvements | NZTA (Otago) | SH6 Cromwell to Frankton Resilience | Single-Stage Business Case |  | HHL | HMM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Pushed $325,000 from 2023/4 into the next financial year 2024/5. | 0 | 0 | [5 empty] | 277398 | 60069352 | 125678
2023-09-01 | September 2023 Review | Cash flow adjustment | State highway improvements | Resilience improvements | NZTA (Otago) | SH6 OTA Haast to Hawea RESIL IMPR | Single-Stage Business Case |  | HHL | HMM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | updated the forecast and pushed $160,500 from 2023/4 into the next financial year 2024/5. | 0 | 0 | [5 empty] | 277408 | 60069350 | 125676
2023-09-04 | September 2023 Review | Cash flow adjustment | State highway improvements | Resilience improvements | NZTA (Southland) | SH94 Milford Road to Te Anau Downs | Single-Stage Business Case |  | HHL | HMM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | pushed $632,400 from 2023/4 into the next financial year 2024/5. | 0 | 0 |  |  |  | 2.4 |  | 277422 | 60069346 | 125674
2023-09-01 | September 2023 Review | Cash flow adjustment | State highway improvements | Resilience improvements | NZTA (Tasman) | SH60 Takaka Hill Resilience Improvements | Single-Stage Business Case |  | HHL | HMM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | updated the forecast and pushed $138,000 from 2023/4 into the next financial year 2024/5. | 0 | 0 | [5 empty] | 277442 | 60069349 | 125675
2023-09-01 | September 2023 Review | Cash flow adjustment | State highway improvements | Resilience improvements | NZTA (West Coast) | SH6 WTCT Haast to Hawea RESIL IMPR | Single-Stage Business Case |  | HHL | HHM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | pushed $160,500 from 2023/4 into the next financial year 2024/5. | 0 | 0 | [5 empty] | 277534 | 60069351 | 125677
2023-09-06 | September 2023 Review | Cash flow adjustment | External funding | Road improvements | NZTA (Auckland) | NZUP SH22 Paeraataa Roundabout (funded by KiwiRail) | Pre-implementation* | Totally funded by KiwiRail | MMM | MMM | N | 8 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | To align SAP and TIO for this fully funded Kiwi Rail Project. 4% admin charged to Kiwi Rail. | 0 | 0 |  |  | 3.9 | 2.8 |  | 282213 | 60068075 | 125743
2023-09-01 | September 2023 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Auckland) | SH16 Brigham Creek to Waimauku Safety Enhancements | Implementation |  | HML | HML | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow allocation of $5,386,420 from FY27 to Current FY | -1 | -1 |  |  | 0 | 1.1 | 60040043 | 261620 | 60040043 | 125654
2023-09-01 | September 2023 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (BOP) | SH2: Baypark to Bayfair Link Upgrade (was MGI) | Construction | Implementation | H_H | H_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move $200,000 from 2023/24 contingencies into 2024/25 contingencies | 0 | 0 |  |  | 2.5 | 2.5 | 60209881 | 194043 | 60209881 | 125655
2023-09-15 | September 2023 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (BOP) | W2T Waihi to Omokoroa (Safer Corridor) | Implementation |  | VHHL | HHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move 6.5m from CY to Y2 because of WBOPDC contributions | 0 | 0 |  |  | 0 | 1 |  | 278524 | 60062260 | 125696
2023-09-01 | September 2023 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Waikato) | SH1 Cambridge to Piarere online safety improvements | Implementation | Stg 1 and 2 | VHML | VHLL | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | pls transfer from CY ($3,458,999) to Y1$3,358,999 and Y2$100,000 due to project phasing and resequencing | 0 | 0 |  |  | 0 | 1.6 |  | 278490 | 60062182 | 125653
2023-09-01 | September 2023 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Waikato) | SH29 Piarere to SH28 | Pre-implementation* | SH29 Piarere to SH28 | VHHM | VHHL | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | pls move $457,072 from CY to Y1 due to rephasing/slow down of project. | -1 | -1 |  |  | 2.1 | 2.1 | 38 | 277244 | 60060852 | 125619
2023-09-01 | September 2023 Review | Cash flow adjustment | Regional Improvements | Road improvements | NZTA (West Coast) | SH6 High St/Marlborough St intersection | Implementation | Construction/implementation | M_M | M_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project close | 0 | 0 |  |  | 3.4 | 3.4 | 60036929 | 240407 | 60036929 | 125618
2023-09-01 | September 2023 Review | Cash flow adjustment | Regional Improvements | Road improvements | NZTA (West Coast) | SH6 Inangahua Junction to SH67 Slow Vehicle Bays | Implementation | Construction | M_M | M_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  | 3 | 3 | 60031580 | 231956 | 60031580 | 125680
2023-09-01 | September 2023 Review | Cash flow adjustment | Regional Improvements | Road improvements | NZTA (West Coast) | SH7 Springs Junction to Reefton Slow Vehicle Bays | Implementation | Construction | M_M | M_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  | 3 | 3 | 60031583 | 231960 | 60031583 | 125681
2023-09-01 | September 2023 Review | Cash flow adjustment | Local road maintenance | Routine drainage maintenance | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The proposed cash flow changes are in line with the target quantities Auckland Transport programmed to deliver this 2023/24 FY that are also based on priority asset needs. | -135367 | -69037 | [5 empty] | 272187 |  | 125552
2023-09-01 | September 2023 Review | Cash flow adjustment | Local road maintenance | Sealed pavement maintenance | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The proposed cash flow changes are in line with the target quantities Auckland Transport programmed to deliver this 2023/24 FY that are also based on priority asset needs. | -8858605 | -4517888 | [5 empty] | 272185 |  | 125552
2023-09-15 | September 2023 Review | Cash flow adjustment | Local road maintenance | Sealed pavement maintenance | Buller District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | SPR |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Approved transfer of unspent wc216 allocation to 214. | -280000 | -280000 | [5 empty] | 272223 |  | 125726
2023-09-01 | September 2023 Review | Cash flow adjustment | Local road maintenance | Sealed pavement maintenance | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Redistributing carry forwards from WC111 to WC's 211, 212, 213, 214, 215, 216, 222, 225 | -4894584 | -3377263 | [5 empty] | 272519 |  | 125498
2023-09-15 | September 2023 Review | Cash flow adjustment | Local road maintenance | Sealed pavement maintenance | Hurunui District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | SPR |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reallocation of funds to cover changes to work programme namely, resealing, drainage renewals and increases to winter maintenance. | -280024 | -280024 | [5 empty] | 272770 |  | 125554
2023-09-01 | September 2023 Review | Cash flow adjustment | Local road maintenance | Sealed road pavement rehabilitation | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The proposed cash flow changes are in line with the target quantities Auckland Transport programmed to deliver this 2023/24 FY that are also based on priority asset needs. | -19213193 | -9798728 | [5 empty] | 272200 |  | 125552
2023-09-15 | September 2023 Review | Cash flow adjustment | Local road maintenance | Sealed road pavement rehabilitation | Buller District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | SPR |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Approved transfer of unspent wc216 allocation to 214. | 840000 | 840000 | [5 empty] | 272238 |  | 125726
2023-09-01 | September 2023 Review | Cash flow adjustment | Local road maintenance | Sealed road pavement rehabilitation | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Redistributing carry forwards from WC111 to WC's 211, 212, 213, 214, 215, 216, 222, 225 | 355905 | 245574 | [5 empty] | 272534 |  | 125498
2023-09-01 | September 2023 Review | Cash flow adjustment | Local road maintenance | Sealed road resurfacing | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The proposed cash flow changes are in line with the target quantities Auckland Transport programmed to deliver this 2023/24 FY that are also based on priority asset needs. | 34915847 | 17807082 | [5 empty] | 272198 |  | 125552
2023-09-01 | September 2023 Review | Cash flow adjustment | Local road maintenance | Sealed road resurfacing | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Redistributing carry forwards from WC111 to WC's 211, 212, 213, 214, 215, 216, 222, 225 | 161356 | 111336 | [5 empty] | 272532 |  | 125498
2023-09-15 | September 2023 Review | Cash flow adjustment | Local road maintenance | Sealed road resurfacing | Hurunui District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | SPR |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reallocation of funds to cover changes to work programme namely, resealing, drainage renewals and increases to winter maintenance. | 231024 | 231024 | [5 empty] | 272783 |  | 125554
2023-09-01 | September 2023 Review | Cash flow adjustment | Local road maintenance | Structures component replacements | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The proposed cash flow changes are in line with the target quantities Auckland Transport programmed to deliver this 2023/24 FY that are also based on priority asset needs. | -3257431 | -1661290 | [5 empty] | 272201 |  | 125552
2023-09-01 | September 2023 Review | Cash flow adjustment | Local road maintenance | Structures component replacements | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Redistributing carry forwards from WC111 to WC's 211, 212, 213, 214, 215, 216, 222, 225 | 763640 | 526912 | [5 empty] | 272535 |  | 125498
2023-09-15 | September 2023 Review | Cash flow adjustment | Local road maintenance | Structures component replacements | Hurunui District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | SPR |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reallocation of funds to cover changes to work programme namely, resealing, drainage renewals and increases to winter maintenance. | -16000 | -16000 | [5 empty] | 272786 |  | 125554
2023-09-01 | September 2023 Review | Cash flow adjustment | Local road maintenance | Structures maintenance | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The proposed cash flow changes are in line with the target quantities Auckland Transport programmed to deliver this 2023/24 FY that are also based on priority asset needs. | -591517 | -301673 | [5 empty] | 272188 |  | 125552
2023-09-15 | September 2023 Review | Cash flow adjustment | Public transport services | Total mobility operations | Auckland Transport | Government reduced public transport fares scheme (Crown) | Implementation | Total Mobility - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | 0 | 0 |  |  |  |  | 517.2812 | 281220 |  | 125873
2023-09-01 | September 2023 Review | Cash flow adjustment | Local road maintenance | Traffic services renewals | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The proposed cash flow changes are in line with the target quantities Auckland Transport programmed to deliver this 2023/24 FY that are also based on priority asset needs. | 699797 | 356896 | [5 empty] | 272204 |  | 125552
2023-09-01 | September 2023 Review | Cash flow adjustment | Local road maintenance | Traffic services renewals | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Redistributing carry forwards from WC111 to WC's 211, 212, 213, 214, 215, 216, 222, 225 | 127976 | 88303 | [5 empty] | 272538 |  | 125498
2023-09-01 | September 2023 Review | Cash flow adjustment | Local road maintenance | Unsealed pavement maintenance | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The proposed cash flow changes are in line with the target quantities Auckland Transport programmed to deliver this 2023/24 FY that are also based on priority asset needs. | 4187759 | 2135757 | [5 empty] | 272186 |  | 125552
2023-09-01 | September 2023 Review | Cash flow adjustment | Local road maintenance | Unsealed road metalling | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The proposed cash flow changes are in line with the target quantities Auckland Transport programmed to deliver this 2023/24 FY that are also based on priority asset needs. | 2385366 | 1216537 | [5 empty] | 272197 |  | 125552
2023-09-01 | September 2023 Review | Cash flow adjustment | Local road maintenance | Unsealed road metalling | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Redistributing carry forwards from WC111 to WC's 211, 212, 213, 214, 215, 216, 222, 225 | 2834382 | 1955724 | [5 empty] | 272531 |  | 125498
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Bridge and structures renewals | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Request to increase the following WC's to a total of $3,285,480 is requested under the following WC's below: WC111 - request increase of $200,000 WC112 - request increase of $224,846 WC113 - request increase of $92,705 WC114 - request increase of $515,620 WC121 - request increase of $221,268 WC122 - request increase of $115,551 WC125 - request increase of $6,400 WC151 - request increase of $400,000 WC215 - request increase of $206,823 WC216 - request increase of $1,302,267 ZERO IMPACT ON BOTTOM LINE | 1302267 | 898564 | [5 empty] | 272536 |  | 125756
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Bridge and structures renewals | Kapiti Coast District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Our contract unit rates have increased by 25-30% since the start of LTP cycle. The escalation sits above 20%, with a further 5-10% felt due to increased operational cost (examples include the increased traffic management and HSE compliance costs, higher dumping costs, longer carts for aggregates). | 208454 | 106312 | [5 empty] | 272947 |  | 125506
2023-09-27 | September 2023 Review | Cost Decrease | Local road maintenance | Bridge and structures renewals | Masterton District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Seeking small increase. Seeking additional local share and we may look to revise program if affordable. Council has local share for this request. | -32068 | -17958 | [5 empty] | 273107 |  | 125493
2023-09-28 | September 2023 Review | Cost Decrease | Local road maintenance | Bridge and structures renewals | Tauranga City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCC's MOR bid reduced by $10m at the start of the 21/24 NLTP. Inflation and historic under investment in the maintenance of the Transport Network have resulted n a perfect storm in which TCC find themselves. The commissioners have committed to additional funds for 2023/24 and beyond to close the gap. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58849106 | -86548 | -44140 | [5 empty] | 274344 |  | 125744
2023-09-28 | September 2023 Review | Cost Decrease | Local road maintenance | Bridge and structures renewals | Thames-Coromandel District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCDC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance rate increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in this district during 2022/23 have resulted in increased quantities of maintenance works required to maintain service levels. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58899309 | -307389 | -156768 | [5 empty] | 274369 |  | 125825
2023-09-27 | September 2023 Review | Cost Decrease | Local road maintenance | Cycle path maintenance | Kapiti Coast District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Our contract unit rates have increased by 25-30% since the start of LTP cycle. The escalation sits above 20%, with a further 5-10% felt due to increased operational cost (examples include the increased traffic management and HSE compliance costs, higher dumping costs, longer carts for aggregates). | -10000 | -5100 | [5 empty] | 272934 |  | 125506
2023-09-27 | September 2023 Review | Cost Decrease | Local road maintenance | Cycle path maintenance | Masterton District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Seeking small increase. Seeking additional local share and we may look to revise program if affordable. Council has local share for this request. | -170 | -95 | [5 empty] | 273094 |  | 125493
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Cycle path maintenance | Tauranga City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCC's MOR bid reduced by $10m at the start of the 21/24 NLTP. Inflation and historic under investment in the maintenance of the Transport Network have resulted n a perfect storm in which TCC find themselves. The commissioners have committed to additional funds for 2023/24 and beyond to close the gap. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58849106 | 28579 | 14576 | [5 empty] | 274331 |  | 125744
2023-09-28 | September 2023 Review | Cost Decrease | Local road maintenance | Cycle path maintenance | Waipa District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Reduced NLTF for the 21/24 NLTP through moderation. Increases 111 sealed pavement maintenance by $600,000 to address priority pavement repairs after a very wet past 12 months and deteriorating road surface conditions. Increases 215 Structure component renewal by $1,800,000 for additional repairs to historic Victoria Bridge in Cambridge where a major repair and repaint contract is underway. Total increase sought $2,400,000. It is confirmed that Council has the local $$ share and has contracted resources engaged to complete this additional work. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58844596 | -75000 | -38250 | [5 empty] | 274519 |  | 125766
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Cycle path maintenance | Whakatane District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | WhakatÄne DC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance cost increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in the Bay of Plenty have resulted in increased minor event response costs and larger pavement and surfacing maintenance work programmes due to saturated pavements. WhakatÄne DC has budgeted for their local share of funding to support this NLTF increase request and has supplier capacity to deliver these additional works. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58867310 | 1000 | 630 | [5 empty] | 274800 |  | 125746
2023-09-27 | September 2023 Review | Cost Decrease | Local road maintenance | Cycle path renewal | Kapiti Coast District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Our contract unit rates have increased by 25-30% since the start of LTP cycle. The escalation sits above 20%, with a further 5-10% felt due to increased operational cost (examples include the increased traffic management and HSE compliance costs, higher dumping costs, longer carts for aggregates). | -319982 | -163191 | [5 empty] | 272950 |  | 125506
2023-09-28 | September 2023 Review | Cost Decrease | Local road maintenance | Cycle path renewal | Tauranga City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCC's MOR bid reduced by $10m at the start of the 21/24 NLTP. Inflation and historic under investment in the maintenance of the Transport Network have resulted n a perfect storm in which TCC find themselves. The commissioners have committed to additional funds for 2023/24 and beyond to close the gap. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58849106 | -100000 | -51000 | [5 empty] | 274347 |  | 125744
2023-09-22 | September 2023 Review | Cost Increase | External funding | Cycling facilities | Tauranga City Council | CERF - Te Papa Spatial Plan (TPSP) | Pre-implementation* |  | HHH | HHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | FAR was incorrectly set to 0% instead of 100%. This review item is to correct this. - Simon Fendall. | 0 | 399780 |  |  | 1 | 0 |  | 284173 |  | 125942
2023-09-01 | September 2023 Review | Cost Increase | Local road maintenance | Drainage renewals | Horowhenua District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | WC discussion undertaken to consolidate spending and programme capabilities resulting in change request. | 190000 | 114000 | [5 empty] | 272759 |  | 125670
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Drainage renewals | Kapiti Coast District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Our contract unit rates have increased by 25-30% since the start of LTP cycle. The escalation sits above 20%, with a further 5-10% felt due to increased operational cost (examples include the increased traffic management and HSE compliance costs, higher dumping costs, longer carts for aggregates). | 119042 | 60711 | [5 empty] | 272944 |  | 125506
2023-09-27 | September 2023 Review | Cost Decrease | Local road maintenance | Drainage renewals | Masterton District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Seeking small increase. Seeking additional local share and we may look to revise program if affordable. Council has local share for this request. | -290 | -162 | [5 empty] | 273104 |  | 125493
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Drainage renewals | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Additional MOR funding requested in the 2023/24 financial year. Reduced NLTF for the 21/24 NLTP through moderation. Increase in costs from year 2 in the 21/24 NLTP due to contract retender. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58846793 | 445200 | 284928 | [5 empty] | 274026 |  | 125748
2023-09-28 | September 2023 Review | Cost Decrease | Local road maintenance | Drainage renewals | Tauranga City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCC's MOR bid reduced by $10m at the start of the 21/24 NLTP. Inflation and historic under investment in the maintenance of the Transport Network have resulted n a perfect storm in which TCC find themselves. The commissioners have committed to additional funds for 2023/24 and beyond to close the gap. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58849106 | -25423 | -12966 | [5 empty] | 274341 |  | 125744
2023-09-28 | September 2023 Review | Cost Decrease | Local road maintenance | Drainage renewals | Thames-Coromandel District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCDC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance rate increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in this district during 2022/23 have resulted in increased quantities of maintenance works required to maintain service levels. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58899309 | -95456 | -48683 | [5 empty] | 274366 |  | 125825
2023-09-28 | September 2023 Review | Cost Decrease | Local road maintenance | Drainage renewals | Waipa District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Reduced NLTF for the 21/24 NLTP through moderation. Increases 111 sealed pavement maintenance by $600,000 to address priority pavement repairs after a very wet past 12 months and deteriorating road surface conditions. Increases 215 Structure component renewal by $1,800,000 for additional repairs to historic Victoria Bridge in Cambridge where a major repair and repaint contract is underway. Total increase sought $2,400,000. It is confirmed that Council has the local $$ share and has contracted resources engaged to complete this additional work. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58844596 | -139500 | -71145 | [5 empty] | 274529 |  | 125766
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Drainage renewals | Whakatane District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | WhakatÄne DC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance cost increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in the Bay of Plenty have resulted in increased minor event response costs and larger pavement and surfacing maintenance work programmes due to saturated pavements. WhakatÄne DC has budgeted for their local share of funding to support this NLTF increase request and has supplier capacity to deliver these additional works. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58867310 | 220000 | 138600 | [5 empty] | 274810 |  | 125746
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Drainage renewals | Whangarei District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | WhangÄrei DC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance cost increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap caused by escalation, Cyclone Gabrielle & other weather events in the district have resulted in increased pavement and surfacing maintenance work programmes due to saturated pavements. WhangÄrei DC have advised that local share is available to support this NLTF increase request and has supplier capacity to deliver these additional works. | 4200000 | 2226000 | [5 empty] | 274860 |  | 125545
2023-09-04 | September 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Buller District Council | Buller District Flood Event - July 2021 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -238557 | -171762 |  |  |  |  | Buller Flood Event WC141 reinstatement - (Normal FAR+20%) | 282264 |  | 125708
2023-09-04 | September 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Carterton District Council | Emergency Works Te Wharau Storm Event October 2022 | Construction | Permanent remedials | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -414911 | -211605 |  |  |  |  | Permanent remedials | 283237 |  | 125713
2023-09-04 | September 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Carterton District Council | Storm event August 2022 | Construction | Network reinstatement (Normal FAR+20%) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -103861 | -52969 |  |  |  |  | (Normal FAR+20%) | 283097 |  | 125714
2023-09-04 | September 2023 Review | Cost Decrease | Local road maintenance | Emergency works | DOC (Southland) | EWâ€“DOC(Southland) June 2023 event Wilmot Pass | Construction | Immediate response & Road reinstatement | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -31427 | -16027 | [5 empty] | 284567 |  | 125710
2023-09-07 | September 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Far North District Council | EW - Far North DC August 2022 | Construction | I & D of all sites & Practitioner Solutions Const. | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -2644713 | -1824852 |  |  |  |  | Phase 2 | 283199 |  | 125761
2023-09-07 | September 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Far North District Council | EW Far North DC May 2023 | Construction | Phase 2 - Minor Remedial Works - EW May 2023 | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -3832431 | -2644377 |  |  |  |  | Phase 2 - Minor Remedial Works - EW May 2023 | 284262 |  | 125760
2023-09-15 | September 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Hurunui District Council | EW - Canterbury Floods May 2021 Hurunui | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Council has surplused unwanted funds. | -4407 | -2292 |  |  |  |  | Initial response and reinstatement May ( | 279835 |  | 125790
2023-09-15 | September 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Hurunui District Council | EW Flooding - December 2021 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Automatic reconciliation of approved costs with claimed costs for 2023/24 as activity is claiming complete | -215133 | -111869 | [5 empty] | 281285 |  | 125789
2023-09-22 | September 2023 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Waikato) | EW East Waikato Slip Hvy Rain 20200531 | Construction |  | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | Recover final spend $3k from surplus | 3370 | 3370 | [5 empty] | 270844 | 60057372 | 125359
2023-09-04 | September 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Rotorua Lakes Council | EW - Rotorua LC Storm Damage July 2022 | Construction | Phase 2 - Construction (Normal FAR+20%) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -47426 | -26559 |  |  |  |  | (Normal FAR+20%) | 283356 |  | 125718
2023-09-04 | September 2023 Review | Cost Decrease | Local road maintenance | Emergency works | South Wairarapa District Council | Storm event August 2022 | Construction | Network reinstatement (Normal FAR+20%) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -427538 | -218044 |  |  |  |  | (Normal FAR+20%) | 283096 |  | 125720
2023-09-04 | September 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Taupo District Council | EW - Taupo DC Omori Road slip October 22 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -163364 | -83315 | [5 empty] | 284155 |  | 125716
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Environmental maintenance | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Request to increase the following WC's to a total of $3,285,480 is requested under the following WC's below: WC111 - request increase of $200,000 WC112 - request increase of $224,846 WC113 - request increase of $92,705 WC114 - request increase of $515,620 WC121 - request increase of $221,268 WC122 - request increase of $115,551 WC125 - request increase of $6,400 WC151 - request increase of $400,000 WC215 - request increase of $206,823 WC216 - request increase of $1,302,267 ZERO IMPACT ON BOTTOM LINE | 221268 | 152675 | [5 empty] | 272526 |  | 125756
2023-09-01 | September 2023 Review | Cost Increase | Local road maintenance | Environmental maintenance | Horowhenua District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | WC discussion undertaken to consolidate spending and programme capabilities resulting in change request. | 31820 | 19092 | [5 empty] | 272752 |  | 125670
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Environmental maintenance | Kapiti Coast District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Our contract unit rates have increased by 25-30% since the start of LTP cycle. The escalation sits above 20%, with a further 5-10% felt due to increased operational cost (examples include the increased traffic management and HSE compliance costs, higher dumping costs, longer carts for aggregates). | 141599 | 72215 | [5 empty] | 272937 |  | 125506
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Environmental maintenance | Masterton District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Seeking small increase. Seeking additional local share and we may look to revise program if affordable. Council has local share for this request. | 174791 | 97883 | [5 empty] | 273097 |  | 125493
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Environmental maintenance | Rotorua Lakes Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Additional MOR funding requested in the 2023/24 financial year. Reduced NLTF for the 21/24 NLTP through moderation. Cost fluctuations running at 18% has reduced our resealing programme in year 1 and 2 and current funding levels will halve our normal resurfacing for 2023-24. Environmental maintenance costs had increased significantly under new contract arrangement. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58885222 | 420471 | 235464 | [5 empty] | 273896 |  | 125755
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Environmental maintenance | South Taranaki District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | After in depth discussions with STDC the local share for these WC has been guaranteed and the physical resources to undertake the increase in WC214 and WC212 is available. The AWPT have had the designs undertaken and NPV have been requested. Logging and weather events in the district have been continuous and the effect has been a reduced LOS and a loss in resilience. Ecxtra funding will allow the network to "recover" and increase the safety, improve efficiency of freight and improve resilience on the rural parts. | 300000 | 189000 | [5 empty] | 273994 |  | 125621
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Environmental maintenance | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Additional MOR funding requested in the 2023/24 financial year. Reduced NLTF for the 21/24 NLTP through moderation. Increase in costs from year 2 in the 21/24 NLTP due to contract retender. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58846793 | 158189 | 101241 | [5 empty] | 274019 |  | 125748
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Environmental maintenance | Tauranga City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCC's MOR bid reduced by $10m at the start of the 21/24 NLTP. Inflation and historic under investment in the maintenance of the Transport Network have resulted n a perfect storm in which TCC find themselves. The commissioners have committed to additional funds for 2023/24 and beyond to close the gap. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58849106 | 233053 | 118857 | [5 empty] | 274334 |  | 125744
2023-09-28 | September 2023 Review | Cost Decrease | Local road maintenance | Environmental maintenance | Thames-Coromandel District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCDC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance rate increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in this district during 2022/23 have resulted in increased quantities of maintenance works required to maintain service levels. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58899309 | -59210 | -30197 | [5 empty] | 274359 |  | 125825
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Environmental maintenance | Waipa District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Reduced NLTF for the 21/24 NLTP through moderation. Increases 111 sealed pavement maintenance by $600,000 to address priority pavement repairs after a very wet past 12 months and deteriorating road surface conditions. Increases 215 Structure component renewal by $1,800,000 for additional repairs to historic Victoria Bridge in Cambridge where a major repair and repaint contract is underway. Total increase sought $2,400,000. It is confirmed that Council has the local $$ share and has contracted resources engaged to complete this additional work. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58844596 | 8000 | 4080 | [5 empty] | 274522 |  | 125766
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Environmental maintenance | Whakatane District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | WhakatÄne DC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance cost increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in the Bay of Plenty have resulted in increased minor event response costs and larger pavement and surfacing maintenance work programmes due to saturated pavements. WhakatÄne DC has budgeted for their local share of funding to support this NLTF increase request and has supplier capacity to deliver these additional works. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58867310 | 253000 | 159390 | [5 empty] | 274803 |  | 125746
2023-09-27 | September 2023 Review | Cost Decrease | Local road maintenance | Environmental renewals | Kapiti Coast District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Our contract unit rates have increased by 25-30% since the start of LTP cycle. The escalation sits above 20%, with a further 5-10% felt due to increased operational cost (examples include the increased traffic management and HSE compliance costs, higher dumping costs, longer carts for aggregates). | -14000 | -7140 | [5 empty] | 272948 |  | 125506
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Footpath maintenance | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Request to increase the following WC's to a total of $3,285,480 is requested under the following WC's below: WC111 - request increase of $200,000 WC112 - request increase of $224,846 WC113 - request increase of $92,705 WC114 - request increase of $515,620 WC121 - request increase of $221,268 WC122 - request increase of $115,551 WC125 - request increase of $6,400 WC151 - request increase of $400,000 WC215 - request increase of $206,823 WC216 - request increase of $1,302,267 ZERO IMPACT ON BOTTOM LINE | 6400 | 4416 | [5 empty] | 272524 |  | 125756
2023-09-27 | September 2023 Review | Cost Decrease | Local road maintenance | Footpath maintenance | Masterton District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Seeking small increase. Seeking additional local share and we may look to revise program if affordable. Council has local share for this request. | -810 | -454 | [5 empty] | 273095 |  | 125493
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Footpath maintenance | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Additional MOR funding requested in the 2023/24 financial year. Reduced NLTF for the 21/24 NLTP through moderation. Increase in costs from year 2 in the 21/24 NLTP due to contract retender. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58846793 | 393750 | 252000 | [5 empty] | 274017 |  | 125748
2023-09-28 | September 2023 Review | Cost Decrease | Local road maintenance | Footpath maintenance | Tauranga City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCC's MOR bid reduced by $10m at the start of the 21/24 NLTP. Inflation and historic under investment in the maintenance of the Transport Network have resulted n a perfect storm in which TCC find themselves. The commissioners have committed to additional funds for 2023/24 and beyond to close the gap. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58849106 | -110000 | -56100 | [5 empty] | 274332 |  | 125744
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Footpath maintenance | Thames-Coromandel District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCDC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance rate increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in this district during 2022/23 have resulted in increased quantities of maintenance works required to maintain service levels. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58899309 | 27342 | 13944 | [5 empty] | 274357 |  | 125825
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Footpath maintenance | Waipa District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Reduced NLTF for the 21/24 NLTP through moderation. Increases 111 sealed pavement maintenance by $600,000 to address priority pavement repairs after a very wet past 12 months and deteriorating road surface conditions. Increases 215 Structure component renewal by $1,800,000 for additional repairs to historic Victoria Bridge in Cambridge where a major repair and repaint contract is underway. Total increase sought $2,400,000. It is confirmed that Council has the local $$ share and has contracted resources engaged to complete this additional work. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58844596 | 10070 | 5136 | [5 empty] | 274520 |  | 125766
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Footpath maintenance | Whakatane District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | WhakatÄne DC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance cost increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in the Bay of Plenty have resulted in increased minor event response costs and larger pavement and surfacing maintenance work programmes due to saturated pavements. WhakatÄne DC has budgeted for their local share of funding to support this NLTF increase request and has supplier capacity to deliver these additional works. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58867310 | 59500 | 37485 | [5 empty] | 274801 |  | 125746
2023-09-01 | September 2023 Review | Cost Increase | Local road maintenance | Footpath renewal | Horowhenua District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | WC discussion undertaken to consolidate spending and programme capabilities resulting in change request. | 50000 | 30000 | [5 empty] | 272766 |  | 125670
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Footpath renewal | Kapiti Coast District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Our contract unit rates have increased by 25-30% since the start of LTP cycle. The escalation sits above 20%, with a further 5-10% felt due to increased operational cost (examples include the increased traffic management and HSE compliance costs, higher dumping costs, longer carts for aggregates). | 399384 | 203686 | [5 empty] | 272951 |  | 125506
2023-09-27 | September 2023 Review | Cost Decrease | Local road maintenance | Footpath renewal | Masterton District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Seeking small increase. Seeking additional local share and we may look to revise program if affordable. Council has local share for this request. | -6420 | -3595 | [5 empty] | 273111 |  | 125493
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Footpath renewal | Tauranga City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCC's MOR bid reduced by $10m at the start of the 21/24 NLTP. Inflation and historic under investment in the maintenance of the Transport Network have resulted n a perfect storm in which TCC find themselves. The commissioners have committed to additional funds for 2023/24 and beyond to close the gap. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58849106 | 1399610 | 713801 | [5 empty] | 274348 |  | 125744
2023-09-28 | September 2023 Review | Cost Decrease | Local road maintenance | Footpath renewal | Thames-Coromandel District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCDC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance rate increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in this district during 2022/23 have resulted in increased quantities of maintenance works required to maintain service levels. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58899309 | -95395 | -48651 | [5 empty] | 274373 |  | 125825
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Footpath renewal | Waipa District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Reduced NLTF for the 21/24 NLTP through moderation. Increases 111 sealed pavement maintenance by $600,000 to address priority pavement repairs after a very wet past 12 months and deteriorating road surface conditions. Increases 215 Structure component renewal by $1,800,000 for additional repairs to historic Victoria Bridge in Cambridge where a major repair and repaint contract is underway. Total increase sought $2,400,000. It is confirmed that Council has the local $$ share and has contracted resources engaged to complete this additional work. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58844596 | 100000 | 51000 | [5 empty] | 274536 |  | 125766
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Footpath renewal | Whakatane District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | WhakatÄne DC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance cost increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in the Bay of Plenty have resulted in increased minor event response costs and larger pavement and surfacing maintenance work programmes due to saturated pavements. WhakatÄne DC has budgeted for their local share of funding to support this NLTF increase request and has supplier capacity to deliver these additional works. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58867310 | 829752 | 522744 | [5 empty] | 274817 |  | 125746
2023-09-01 | September 2023 Review | Cost Decrease | Local road improvements | Low cost / low risk improvements | Horowhenua District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Changes to LRi due to issues on site and inability to remedy those in this financial year | -840167 | -504100 | [5 empty] | 276170 |  | 125671
2023-09-01 | September 2023 Review | Cost Decrease | Road to Zero | Low cost / low risk improvements | Horowhenua District Council | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Inability to complete programme due to issues on site, contractor availability. | -367336 | -220402 | [5 empty] | 276171 |  | 125672
2023-09-01 | September 2023 Review | Cost Decrease | Local road improvements | Low cost / low risk improvements | New Plymouth District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | WC discussion undertaken to consolidate spending and programme capabilities resulting in change request. | -2354176 | -1200630 | [5 empty] | 276324 |  | 125523
2023-09-01 | September 2023 Review | Cost Decrease | Road to Zero | Low cost / low risk improvements | New Plymouth District Council | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | WC discussion undertaken to consolidate spending and programme capabilities resulting in change request. | -2223532 | -1134001 | [5 empty] | 276317 |  | 125522
2023-09-15 | September 2023 Review | Cost Decrease | Road to Zero | Low cost / low risk improvements | Palmerston North City Council | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | WC discussion undertaken to consolidate spending and programme capabilities resulting in change request. | -6643679 | -3388276 | [5 empty] | 276344 |  | 125687
2023-09-15 | September 2023 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | Palmerston North City Council | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | WC discussion undertaken to consolidate spending and programme capabilities resulting in change request. | -9941218 | -5070021 | [5 empty] | 276345 |  | 125688
2023-09-01 | September 2023 Review | Cost Decrease | Local road improvements | Low cost / low risk improvements | Rangitikei District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | WC discussion undertaken to consolidate spending and programme capabilities resulting in change request. | -1054330 | -664228 | [5 empty] | 276367 |  | 125526
2023-09-21 | September 2023 Review | Cost Increase | Road to Zero | Low cost / low risk improvements | Rangitikei District Council | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Returning R2Z surplus for an approved project which had been surplussed in error. Funding surplused was $423k on 1Sep and increase request is $102k. | 102831 | 64784 | [5 empty] | 276365 |  | 125930
2023-09-01 | September 2023 Review | Cost Decrease | Road to Zero | Low cost / low risk improvements | Rangitikei District Council | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | WC discussion undertaken to consolidate spending and programme capabilities resulting in change request. | -423603 | -266870 | [5 empty] | 276365 |  | 125525
2023-09-15 | September 2023 Review | Cost Decrease | Local road improvements | Low cost / low risk improvements | Thames-Coromandel District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | TCDC has prioritised their 2023/24 local share investment and focus on completing those works required to reinstate levels of service following several severe weather events in 2022/23 | -1381425 | -704527 | [5 empty] | 276465 |  | 125827
2023-09-15 | September 2023 Review | Cost Decrease | Road to Zero | Low cost / low risk improvements | Thames-Coromandel District Council | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | TCDC has prioritised their 2023/24 local share investment and focus on completing those works required to reinstate levels of service following several severe weather events in 2022/23 | -236872 | -120804 | [5 empty] | 276461 |  | 125826
2023-09-15 | September 2023 Review | Cost Decrease | Local road improvements | Low cost / low risk improvements | Waitangi Trust | Low cost / low risk improvements 2021-24 | Local road improvements (SPR) |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The LCLR capital programme for Tau Henare Drive â€“ Special Purpose Road was delayed during 2021-24 NLTP and has further been requested through the 2024-27 NLTP. The resurfacing programmed during 2021-24 on Tau Henare Drive will be completed in 2023/24, however this was also delayed from 2022/23. Consultation with the LCLR capital programme will commence with the Waitangi Trust early 2024 in preparation for delivery in the next NLTP. | -851000 | -851000 | [5 empty] | 276519 |  | 125757
2023-09-27 | September 2023 Review | Cost Decrease | Local road maintenance | Minor events | Kapiti Coast District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Our contract unit rates have increased by 25-30% since the start of LTP cycle. The escalation sits above 20%, with a further 5-10% felt due to increased operational cost (examples include the increased traffic management and HSE compliance costs, higher dumping costs, longer carts for aggregates). | -74658 | -38076 | [5 empty] | 272936 |  | 125506
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Minor events | Masterton District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Seeking small increase. Seeking additional local share and we may look to revise program if affordable. Council has local share for this request. | 51700 | 28952 | [5 empty] | 273096 |  | 125493
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Minor events | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Additional MOR funding requested in the 2023/24 financial year. Reduced NLTF for the 21/24 NLTP through moderation. Increase in costs from year 2 in the 21/24 NLTP due to contract retender. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58846793 | 2310 | 1478 | [5 empty] | 274018 |  | 125748
2023-09-28 | September 2023 Review | Cost Decrease | Local road maintenance | Minor events | Thames-Coromandel District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCDC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance rate increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in this district during 2022/23 have resulted in increased quantities of maintenance works required to maintain service levels. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58899309 | -269833 | -137615 | [5 empty] | 274358 |  | 125825
2023-09-28 | September 2023 Review | Cost Decrease | Local road maintenance | Minor events | Waipa District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Reduced NLTF for the 21/24 NLTP through moderation. Increases 111 sealed pavement maintenance by $600,000 to address priority pavement repairs after a very wet past 12 months and deteriorating road surface conditions. Increases 215 Structure component renewal by $1,800,000 for additional repairs to historic Victoria Bridge in Cambridge where a major repair and repaint contract is underway. Total increase sought $2,400,000. It is confirmed that Council has the local $$ share and has contracted resources engaged to complete this additional work. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58844596 | -10500 | -5355 | [5 empty] | 274521 |  | 125766
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Minor events | Whakatane District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | WhakatÄne DC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance cost increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in the Bay of Plenty have resulted in increased minor event response costs and larger pavement and surfacing maintenance work programmes due to saturated pavements. WhakatÄne DC has budgeted for their local share of funding to support this NLTF increase request and has supplier capacity to deliver these additional works. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58867310 | 182000 | 114660 | [5 empty] | 274802 |  | 125746
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Network and asset management | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Request to increase the following WC's to a total of $3,285,480 is requested under the following WC's below: WC111 - request increase of $200,000 WC112 - request increase of $224,846 WC113 - request increase of $92,705 WC114 - request increase of $515,620 WC121 - request increase of $221,268 WC122 - request increase of $115,551 WC125 - request increase of $6,400 WC151 - request increase of $400,000 WC215 - request increase of $206,823 WC216 - request increase of $1,302,267 ZERO IMPACT ON BOTTOM LINE | 400000 | 276000 | [5 empty] | 272530 |  | 125756
2023-09-01 | September 2023 Review | Cost Increase | Local road maintenance | Network and asset management | Horowhenua District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | WC discussion undertaken to consolidate spending and programme capabilities resulting in change request. | 100000 | 60000 | [5 empty] | 272756 |  | 125670
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Network and asset management | Masterton District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Seeking small increase. Seeking additional local share and we may look to revise program if affordable. Council has local share for this request. | 1047260 | 586466 | [5 empty] | 273101 |  | 125493
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Network and asset management | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Additional MOR funding requested in the 2023/24 financial year. Reduced NLTF for the 21/24 NLTP through moderation. Increase in costs from year 2 in the 21/24 NLTP due to contract retender. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58846793 | 580539 | 371545 | [5 empty] | 274023 |  | 125748
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Network and asset management | Tauranga City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCC's MOR bid reduced by $10m at the start of the 21/24 NLTP. Inflation and historic under investment in the maintenance of the Transport Network have resulted n a perfect storm in which TCC find themselves. The commissioners have committed to additional funds for 2023/24 and beyond to close the gap. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58849106 | 6088872 | 3105325 | [5 empty] | 274338 |  | 125744
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Network and asset management | Thames-Coromandel District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCDC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance rate increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in this district during 2022/23 have resulted in increased quantities of maintenance works required to maintain service levels. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58899309 | 536364 | 273546 | [5 empty] | 274363 |  | 125825
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Network and asset management | Waipa District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Reduced NLTF for the 21/24 NLTP through moderation. Increases 111 sealed pavement maintenance by $600,000 to address priority pavement repairs after a very wet past 12 months and deteriorating road surface conditions. Increases 215 Structure component renewal by $1,800,000 for additional repairs to historic Victoria Bridge in Cambridge where a major repair and repaint contract is underway. Total increase sought $2,400,000. It is confirmed that Council has the local $$ share and has contracted resources engaged to complete this additional work. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58844596 | 267600 | 136476 | [5 empty] | 274526 |  | 125766
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Network and asset management | Whakatane District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | WhakatÄne DC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance cost increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in the Bay of Plenty have resulted in increased minor event response costs and larger pavement and surfacing maintenance work programmes due to saturated pavements. WhakatÄne DC has budgeted for their local share of funding to support this NLTF increase request and has supplier capacity to deliver these additional works. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58867310 | 606000 | 381780 | [5 empty] | 274807 |  | 125746
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Network operations | Tauranga City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCC's MOR bid reduced by $10m at the start of the 21/24 NLTP. Inflation and historic under investment in the maintenance of the Transport Network have resulted n a perfect storm in which TCC find themselves. The commissioners have committed to additional funds for 2023/24 and beyond to close the gap. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58849106 | 775901 | 395709 | [5 empty] | 274336 |  | 125744
2023-09-28 | September 2023 Review | Cost Decrease | Local road maintenance | Network operations | Waipa District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Reduced NLTF for the 21/24 NLTP through moderation. Increases 111 sealed pavement maintenance by $600,000 to address priority pavement repairs after a very wet past 12 months and deteriorating road surface conditions. Increases 215 Structure component renewal by $1,800,000 for additional repairs to historic Victoria Bridge in Cambridge where a major repair and repaint contract is underway. Total increase sought $2,400,000. It is confirmed that Council has the local $$ share and has contracted resources engaged to complete this additional work. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58844596 | -31450 | -16039 | [5 empty] | 274524 |  | 125766
2023-09-28 | September 2023 Review | Cost Decrease | Local road maintenance | Network operations | Whakatane District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | WhakatÄne DC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance cost increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in the Bay of Plenty have resulted in increased minor event response costs and larger pavement and surfacing maintenance work programmes due to saturated pavements. WhakatÄne DC has budgeted for their local share of funding to support this NLTF increase request and has supplier capacity to deliver these additional works. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58867310 | -3000 | -1890 | [5 empty] | 274805 |  | 125746
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Network service maintenance | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Request to increase the following WC's to a total of $3,285,480 is requested under the following WC's below: WC111 - request increase of $200,000 WC112 - request increase of $224,846 WC113 - request increase of $92,705 WC114 - request increase of $515,620 WC121 - request increase of $221,268 WC122 - request increase of $115,551 WC125 - request increase of $6,400 WC151 - request increase of $400,000 WC215 - request increase of $206,823 WC216 - request increase of $1,302,267 ZERO IMPACT ON BOTTOM LINE | 115551 | 79730 | [5 empty] | 272527 |  | 125756
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Network service maintenance | Kapiti Coast District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Our contract unit rates have increased by 25-30% since the start of LTP cycle. The escalation sits above 20%, with a further 5-10% felt due to increased operational cost (examples include the increased traffic management and HSE compliance costs, higher dumping costs, longer carts for aggregates). | 50000 | 25500 | [5 empty] | 272938 |  | 125506
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Network service maintenance | Masterton District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Seeking small increase. Seeking additional local share and we may look to revise program if affordable. Council has local share for this request. | 26860 | 15042 | [5 empty] | 273098 |  | 125493
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Network service maintenance | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Additional MOR funding requested in the 2023/24 financial year. Reduced NLTF for the 21/24 NLTP through moderation. Increase in costs from year 2 in the 21/24 NLTP due to contract retender. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58846793 | 89637 | 57368 | [5 empty] | 274020 |  | 125748
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Network service maintenance | Tauranga City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCC's MOR bid reduced by $10m at the start of the 21/24 NLTP. Inflation and historic under investment in the maintenance of the Transport Network have resulted n a perfect storm in which TCC find themselves. The commissioners have committed to additional funds for 2023/24 and beyond to close the gap. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58849106 | 2411868 | 1230053 | [5 empty] | 274335 |  | 125744
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Network service maintenance | Thames-Coromandel District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCDC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance rate increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in this district during 2022/23 have resulted in increased quantities of maintenance works required to maintain service levels. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58899309 | 264664 | 134979 | [5 empty] | 274360 |  | 125825
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Network service maintenance | Waipa District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Reduced NLTF for the 21/24 NLTP through moderation. Increases 111 sealed pavement maintenance by $600,000 to address priority pavement repairs after a very wet past 12 months and deteriorating road surface conditions. Increases 215 Structure component renewal by $1,800,000 for additional repairs to historic Victoria Bridge in Cambridge where a major repair and repaint contract is underway. Total increase sought $2,400,000. It is confirmed that Council has the local $$ share and has contracted resources engaged to complete this additional work. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58844596 | 158175 | 80669 | [5 empty] | 274523 |  | 125766
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Network service maintenance | Whakatane District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | WhakatÄne DC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance cost increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in the Bay of Plenty have resulted in increased minor event response costs and larger pavement and surfacing maintenance work programmes due to saturated pavements. WhakatÄne DC has budgeted for their local share of funding to support this NLTF increase request and has supplier capacity to deliver these additional works. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58867310 | 493000 | 310590 | [5 empty] | 274804 |  | 125746
2023-09-15 | September 2023 Review | Cost Decrease | Local road improvements | New roads | Auckland Transport | Matakana Link Road | Implementation | Matakana Link Road - IMP | HHH | MHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The project is substantially complete with further savings realised. The minor remaining cash flow is to cover AT staff costs in resolving close out activities. There is a concurrent property cost increase that reflects costs already incurred plus estimates of outstanding property commitments that is expected to be resolved through the Land Valuation Tribunal. This surplus & CSA has been discussed with the LRI ACM as per email chain attached in supporting documents & InfoHub reference https://infohub.nzta.govt.nz/otcs/cs.dll/link/58728244. | -5368947 | -5368947 |  |  | 0 | 7.7 | 323.2489 | 248909 |  | 125745
2023-09-15 | September 2023 Review | Cost Increase | Local road improvements | New roads | Auckland Transport | Matakana Link Road â€“ Repayment | Implementation | MLR - Repayment | H_H | M_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This request is balancing the repayment to align with the current surplus & CSA submitted for approval. | 2630784 | 2630784 |  |  | 0 | 7.7 | 323.2672 | 267243 |  | 125751
2023-09-08 | September 2023 Review | Cost Increase | State highway improvements | New roads | NZTA (Auckland) | Puhoi to Wellsford RoNS Development | Investigation |  | M_L | H_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer please move $372,279 from 6004441 to 60216905 due to increased costs and forecasts | 405784 | 405784 |  |  | 1.1 | 1.1 | 60216905 | 202323 | 60216905 | 125324
2023-09-15 | September 2023 Review | Cost Increase | State highway improvements | New roads | NZTA (Auckland) | SH1 Puhoi to Warkworth RoNS Detailed Design and Construction | Construction | Construction - other than the PPP component | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | interphase transfer funds of $3,756,996 from 60216906 pre imp to 60216907 implementation due to increased costs | 4095123 | 4095123 |  |  | 1.1 | 1.1 | 60216907 | 250957 | 60216907 | 125771
2023-09-15 | September 2023 Review | Cost Decrease | State highway improvements | New roads | NZTA (Auckland) | SH1 Puhoi to Warkworth RoNS Detailed Design and Construction | Pre-implementation* | Procurement & Design | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | interphase transfer funds of $3,756,996 from 60216906 pre imp to 60216907 implementation due to increased costs | -4095126 | -4095126 |  |  | 1.1 | 1.1 | 60216906 | 239928 | 60216906 | 125770
2023-09-01 | September 2023 Review | Cost Increase | Public transport services | Operations & maintenance of real-time and ticketing systems | Auckland Transport | Public Transport Programme 2021-24 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | This is to reduce the funding required to support the PT services element of the programme due to the roll-over of funding from FY23 subsequent to the Crown top-up provided in late FY23. This surplus will be offset by an increase in the PT infrastructure activity component of the continuous programme. | 568317 | 289842 | [5 empty] | 272179 |  | 125622
2023-09-11 | September 2023 Review | Cost Increase | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | Dunedin City Council | SFDT - Park and Ride Facilities - Mosgiel and Burnside | Single-Stage Business Case | Park and Ride - Mosgiel | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The recommended option is more expensive than budgeted ($15m up from $5m), which triggered a peer review that wasnâ€™t originally scoped. Because of the higher cost, DCC also has to consider staging options for local share affordability, which will need additional work on the business case. Waka Kotahi CFO has endorsed a prior agreement for retrospective funding. Next phase request now includes a request for this CSA. | 25000 | 12750 |  |  | 2.2 | 1.6 | Mosgiel park and ride | 276615 |  | 125449
2023-09-13 | September 2023 Review | Cost Decrease | External funding | Passenger services - bus | Auckland Transport | Community Connect - Auckland Trial | Implementation | Community Connect Bus Concessions | MHL | MHL | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move funds to Admin phase | -2367000 | -2367000 |  |  |  |  | 511.9105 | 288502 |  | 125821
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Passenger services - bus | Auckland Transport | Government reduced public transport fares scheme (Crown) | Implementation | Bus Services - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -4416818 | -4416818 |  |  |  |  | 511.2812 | 281217 |  | 125870
2023-09-01 | September 2023 Review | Cost Decrease | Public transport services | Passenger services - bus | Auckland Transport | Public Transport Programme 2021-24 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | This is to reduce the funding required to support the PT services element of the programme due to the roll-over of funding from FY23 subsequent to the Crown top-up provided in late FY23. This surplus will be offset by an increase in the PT infrastructure activity component of the continuous programme. | -66993925 | -34166902 | [5 empty] | 272172 |  | 125622
2023-09-13 | September 2023 Review | Cost Decrease | External funding | Passenger services - bus | Bay of Plenty Regional Council | CERF-CC Community Connect Scheme | Implementation | Community Connect Bus Concessions | MHL | MHL | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move funds to Admin phase | -105000 | -105000 | [5 empty] | 288519 |  | 125797
2023-09-13 | September 2023 Review | Cost Decrease | External funding | Passenger services - bus | Environment Canterbury | CERF-CC Community Connect Scheme | Implementation | Community Connect Bus Concessions | MHL | MHL | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move funds to Admin phase | -391000 | -391000 | [5 empty] | 283457 |  | 125799
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Passenger services - bus | Environment Canterbury | Government reduced public transport fares scheme (Crown) | Implementation | Bus Services - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -1078633 | -1078633 | [5 empty] | 281213 |  | 125835
2023-09-13 | September 2023 Review | Cost Decrease | External funding | Passenger services - bus | Gisborne District Council | CERF-CC Community Connect Scheme | Implementation | Community Connect Bus Concessions | MHL | MHL | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move funds to Admin phase | -4000 | -4000 | [5 empty] | 288529 |  | 125808
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Passenger services - bus | Gisborne District Council | Government reduced public transport fares scheme (Crown) | Implementation | Bus Services - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -26775 | -26775 | [5 empty] | 281227 |  | 125839
2023-09-12 | September 2023 Review | Cost Decrease | External funding | Passenger services - bus | Greater Wellington | CERF-Bus Driver Ts & Cs | Implementation | CERF driver uplift - wrong funding source | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move to correct funding source | -16894073 | -8615976 |  |  |  | 1 |  | 284583 |  | 125792
2023-09-13 | September 2023 Review | Cost Decrease | External funding | Passenger services - bus | Greater Wellington | CERF-CC Community Connect Scheme | Implementation | Community Connect Bus Concessions | MLL | MHL | N | 10 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move funds to Admin phase | -810000 | -810000 | [5 empty] | 288513 |  | 125802
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Passenger services - bus | Greater Wellington | Government reduced public transport fares scheme (Crown) | Implementation | Bus Services - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -2822489 | -2822489 | [5 empty] | 281231 |  | 125841
2023-09-13 | September 2023 Review | Cost Decrease | External funding | Passenger services - bus | Hawkes Bay Regional Council | CERF-CC Community Connect Scheme | Implementation | Community Connect Bus Concessions | MHL | MHL | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move funds to Admin phase | -21000 | -21000 | [5 empty] | 288525 |  | 125810
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Passenger services - bus | Hawkes Bay Regional Council | Government reduced public transport fares scheme (Crown) | Implementation | Bus Services - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -75087 | -75087 | [5 empty] | 281236 |  | 125845
2023-09-13 | September 2023 Review | Cost Decrease | External funding | Passenger services - bus | Horizons Manawatu | CERF-CC Community Connect Scheme | Implementation | Community Connect Bus Concessions | MHL | MHL | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move funds to Admin phase | -42000 | -42000 | [5 empty] | 288520 |  | 125812
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Passenger services - bus | Horizons Manawatu | Government reduced public transport fares scheme (Crown) | Implementation | Bus Services - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -72660 | -72660 | [5 empty] | 281258 |  | 125847
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Passenger services - bus | Invercargill City Council | Government reduced public transport fares scheme (Crown) | Implementation | Bus Services - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -54569 | -54569 | [5 empty] | 281261 |  | 125850
2023-09-12 | September 2023 Review | Cost Decrease | External funding | Passenger services - bus | Marlborough District Council | CERF-Bus Driver Ts & Cs | Implementation | CERF - Driver Wage Uplift - wrong funding source | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move to correct funding source | -38639 | -19705 | [5 empty] | 289016 |  | 125791
2023-09-13 | September 2023 Review | Cost Decrease | External funding | Passenger services - bus | Northland Regional Council | CERF-CC Community Connect Scheme | Implementation | Community Connect Bus Concessions | MHL | MHL | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move funds to Admin phase | -8000 | -8000 | [5 empty] | 288524 |  | 125817
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Passenger services - bus | Northland Regional Council | Government reduced public transport fares scheme (Crown) | Implementation | Bus Services - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -30563 | -30563 | [5 empty] | 281270 |  | 125855
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Passenger services - bus | Otago Regional Council | Government reduced public transport fares scheme (Crown) | Implementation | Bus Services - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -428181 | -428181 | [5 empty] | 281273 |  | 125858
2023-09-13 | September 2023 Review | Cost Decrease | External funding | Passenger services - bus | Taranaki Regional Council | CERF-CC Community Connect Scheme | Implementation | Community Connect Bus Concessions | MHL | MHL | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move funds to Admin phase | -26000 | -26000 | [5 empty] | 288526 |  | 125819
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Passenger services - bus | Taranaki Regional Council | Government reduced public transport fares scheme (Crown) | Implementation | Bus Services - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -165399 | -165399 | [5 empty] | 281277 |  | 125862
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Passenger services - bus | Waikato Regional Council | Government reduced public transport fares scheme (Crown) | Implementation | Bus Services - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -258132 | -258132 | [5 empty] | 281280 |  | 125866
2023-09-13 | September 2023 Review | Cost Decrease | External funding | Passenger services - ferry | Auckland Transport | Community Connect - Auckland Trial | Implementation | Community Connect Ferry Concessions | MHL | MHL | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move funds to Admin phase | -536000 | -536000 |  |  |  |  | 512.9105 | 288506 |  | 125822
2023-09-19 | September 2023 Review | Cost Decrease | Public transport services | Passenger services - ferry | Auckland Transport | Government reduced public transport fares scheme (Crown) | Implementation | Ferry Service - Reduced Fares | VHHL | VHHL | Y | 2 | Approved | Approved by Auckland Transport Chief Financial Officer |  | -2183022 | -2183022 |  |  |  |  | 512.2812 | 281218 |  | 125875
2023-09-01 | September 2023 Review | Cost Decrease | Public transport services | Passenger services - ferry | Auckland Transport | Public Transport Programme 2021-24 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | This is to reduce the funding required to support the PT services element of the programme due to the roll-over of funding from FY23 subsequent to the Crown top-up provided in late FY23. This surplus will be offset by an increase in the PT infrastructure activity component of the continuous programme. | -4868600 | -2482986 | [5 empty] | 272173 |  | 125622
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Passenger services - ferry | Bay of Plenty Regional Council | Government reduced public transport fares scheme (Crown) | Implementation | Ferry Service - Reduced Fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -3253 | -3253 | [5 empty] | 281223 |  | 125833
2023-09-13 | September 2023 Review | Cost Decrease | External funding | Passenger services - ferry | Environment Canterbury | CERF-CC Community Connect Scheme | Implementation | Community Connect Ferry Concessions | MHL | MHL | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move funds to Admin phase | -12000 | -12000 | [5 empty] | 288516 |  | 125800
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Passenger services - ferry | Far North District Council | Government reduced public transport fares scheme (Crown) | Implementation | Hokianga ferry service - Reduced fares | HHL | VHHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -4219 | -4219 | [5 empty] | 281226 |  | 125838
2023-09-13 | September 2023 Review | Cost Decrease | External funding | Passenger services - ferry | Greater Wellington | CERF-CC Community Connect Scheme | Implementation | Community Connect Ferry Concessions | MLL | MHL | N | 10 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move funds to Admin phase | -27000 | -27000 | [5 empty] | 288515 |  | 125803
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Passenger services - ferry | Otago Regional Council | Government reduced public transport fares scheme (Crown) | Implementation | Ferry Service - Reduced Fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -6147 | -6147 | [5 empty] | 281274 |  | 125859
2023-09-13 | September 2023 Review | Cost Decrease | External funding | Passenger services - rail | Auckland Transport | Community Connect - Auckland Trial | Implementation | Community Connect Rail Concessions | MHL | MHL | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move funds to Admin phase | -841000 | -841000 |  |  |  |  | 515.9105 | 288505 |  | 125823
2023-09-19 | September 2023 Review | Cost Decrease | Public transport services | Passenger services - rail | Auckland Transport | Government reduced public transport fares scheme (Crown) | Implementation | Rail services - Reduced fares | VHHL | VHHL | Y | 2 | Approved | Approved by Auckland Transport Chief Financial Officer |  | -2086475 | -2086475 |  |  |  |  | 515.2812 | 281219 |  | 125876
2023-09-01 | September 2023 Review | Cost Decrease | Public transport services | Passenger services - rail | Auckland Transport | Public Transport Programme 2021-24 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | This is to reduce the funding required to support the PT services element of the programme due to the roll-over of funding from FY23 subsequent to the Crown top-up provided in late FY23. This surplus will be offset by an increase in the PT infrastructure activity component of the continuous programme. | -23727674 | -12101114 | [5 empty] | 272174 |  | 125622
2023-09-13 | September 2023 Review | Cost Decrease | External funding | Passenger services - rail | Greater Wellington | CERF-CC Community Connect Scheme | Implementation | Community Connect Rail Concessions | MLL | MHL | N | 10 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move funds to Admin phase | -876000 | -876000 | [5 empty] | 288514 |  | 125804
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Passenger services - rail | Greater Wellington | Government reduced public transport fares scheme (Crown) | Implementation | Rail services - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -3747162 | -3747162 | [5 empty] | 281233 |  | 125842
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Passenger services - rail | Waikato Regional Council | Government reduced public transport fares scheme (Crown) | Implementation | Rail services - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -215485 | -215485 | [5 empty] | 281281 |  | 125867
2023-09-01 | September 2023 Review | Cost Decrease | Public transport services | Payments for Total Mobility wheelchair hoists and ramps | Auckland Transport | Public Transport Programme 2021-24 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | This is to reduce the funding required to support the PT services element of the programme due to the roll-over of funding from FY23 subsequent to the Crown top-up provided in late FY23. This surplus will be offset by an increase in the PT infrastructure activity component of the continuous programme. | -173460 | -173460 | [5 empty] | 272177 |  | 125622
2023-09-11 | September 2023 Review | Cost Decrease | Investment management (incl. Transport Planning) | Programme Business Case Development | NZ Transport Agency | Innovation Programme | Programme business case |  | HHL | VHHM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Updating 2022/23 actual to match SAP. | -359836 | -359836 |  |  |  |  | 60069122 | 277975 |  | 125788
2023-09-29 | September 2023 Review | Cost Increase | Investment management (incl. Transport Planning) | Programme Business Case Development | Waipa District Council | Cambridge Connections - Programme Business Case | Programme business case |  | HML | VHHVH | N | 6 | Approved | Approved by Chief Financial Officer (CFO) | Enables the completion of the Cambridge Connections Programme, providing certainty around Cambridge's future strategic connections in a lower-carbon future. | 185500 | 94605 |  |  |  |  | cambridge connections programme business | 283537 |  | 125642
2023-09-08 | September 2023 Review | Cost Decrease | State highway improvements | Property purchase (State highways) | NZTA (Auckland) | SH1 Warkworth to Wellsford RoNS - Detailed Design and Const | Property |  | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer please move $372,279 from 6004441 to 60216905 due to increased costs and forecasts | -394616 | -394616 |  |  | 1.1 | 1.1 | 60044441 | 197915 | 60044441 | 125325
2023-09-11 | September 2023 Review | Cost Decrease | State highway improvements | Property purchase (State highways) | NZTA (Waikato) | SH3/37 Waitomo Road Intersection | Property |  | H_H | H_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project close. | -22824 | -22824 |  |  | 4.5 | 4.5 | 60449052 | 247912 | 60449052 | 125786
2023-09-15 | September 2023 Review | Cost Increase | Local road improvements | Property purchase (local roads) | Auckland Transport | Matakana Link Road | Property | Matakana Link Road - PROPERTY | HHH | MHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The revised property costs reflect costs already incurred plus estimates of outstanding property commitments that is expected to be resolved through the Land Valuation Tribunal. This CSA has been discussed with the LRI ACM as per email chain attached in supporting documents & InfoHub reference https://infohub.nzta.govt.nz/otcs/cs.dll/link/58728244. | 9047543 | 9047543 |  |  | 0 | 7.7 | 332.2492 | 249232 |  | 125705
2023-09-15 | September 2023 Review | Cost Decrease | Local road improvements | Property purchase (local roads) | Auckland Transport | Matakana Link Road â€“ Repayment | Property | MLR - Repayment | H_H | M_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This request is balancing the repayment to align with the current surplus & CSA submitted for approval. | -4433297 | -4433297 |  |  | 0 | 7.7 | 332.2672 | 267244 |  | 125753
2023-09-01 | September 2023 Review | Cost Increase | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | Auckland Transport | Public Transport Programme 2021-24 - AC 5 | Operations |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This increase is to align with the original submission made for the 2021 NLTP that was not fully funded and as per the details provided in the CSA (developed in conjunction with Waka Kotahi). This increase is being offset by a surplus declaration in the PT services elements of the PT continuous programme. | 10832840 | 5524748 | [5 empty] | 272180 |  | 125623
2023-09-01 | September 2023 Review | Cost Increase | Public transport infrastructure | Public transport facilities & infrastructure - renewals | Auckland Transport | Public Transport Programme 2021-24 - AC 5 | Operations |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This increase is to align with the original submission made for the 2021 NLTP that was not fully funded and as per the details provided in the CSA (developed in conjunction with Waka Kotahi). This increase is being offset by a surplus declaration in the PT services elements of the PT continuous programme. | 15853251 | 8085158 | [5 empty] | 272181 |  | 125623
2023-09-19 | September 2023 Review | Cost Decrease | Public transport services | Public transport operations and management | Auckland Transport | Government reduced public transport fares scheme (Crown) | Implementation | PT Ops and Man - Reduced Fares | VHHL | VHHL | Y | 2 | Approved | Approved by Auckland Transport Chief Financial Officer |  | -148355 | -148355 |  |  |  |  | 524.2812 | 281221 |  | 125878
2023-09-01 | September 2023 Review | Cost Decrease | Public transport services | Public transport operations and management | Auckland Transport | Public Transport Programme 2021-24 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | This is to reduce the funding required to support the PT services element of the programme due to the roll-over of funding from FY23 subsequent to the Crown top-up provided in late FY23. This surplus will be offset by an increase in the PT infrastructure activity component of the continuous programme. | -1025873 | -523195 | [5 empty] | 272178 |  | 125622
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Public transport operations and management | Environment Canterbury | Government reduced public transport fares scheme (Crown) | Implementation | PT Ops and Man - Reduced Fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -24825 | -24825 | [5 empty] | 281216 |  | 125837
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Public transport operations and management | Gisborne District Council | Government reduced public transport fares scheme (Crown) | Implementation | PT Ops and Man - Reduced Fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -12500 | -12500 | [5 empty] | 281229 |  | 125840
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Public transport operations and management | Greater Wellington | Government reduced public transport fares scheme (Crown) | Implementation | PT Ops and Man - Reduced Fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -287500 | -287500 | [5 empty] | 281235 |  | 125844
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Public transport operations and management | Horizons Manawatu | Government reduced public transport fares scheme (Crown) | Implementation | PT Ops and Man - Reduced Fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -12282 | -12282 | [5 empty] | 281260 |  | 125849
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Public transport operations and management | Invercargill City Council | Government reduced public transport fares scheme (Crown) | Implementation | PT Ops and Man - Reduced Fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -12500 | -12500 | [5 empty] | 281263 |  | 125852
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Public transport operations and management | Northland Regional Council | Government reduced public transport fares scheme (Crown) | Implementation | PT Ops and Man - Reduced Fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -7974 | -7974 | [5 empty] | 281272 |  | 125857
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Public transport operations and management | Otago Regional Council | Government reduced public transport fares scheme (Crown) | Implementation | PT Ops and Man - Reduced Fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -136550 | -136550 | [5 empty] | 281276 |  | 125861
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Public transport operations and management | Taranaki Regional Council | Government reduced public transport fares scheme (Crown) | Implementation | PT Ops and Man - Reduced Fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -2500 | -2500 | [5 empty] | 281279 |  | 125864
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Public transport operations and management | Waikato Regional Council | Government reduced public transport fares scheme (Crown) | Implementation | PT Ops and Man - Reduced Fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -13750 | -13750 | [5 empty] | 281284 |  | 125869
2023-09-01 | September 2023 Review | Cost Increase | Local road maintenance | Rail level crossing warning devices maintenance | Horowhenua District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | WC discussion undertaken to consolidate spending and programme capabilities resulting in change request. | 18000 | 10800 | [5 empty] | 272755 |  | 125670
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Rail level crossing warning devices maintenance | Kapiti Coast District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Our contract unit rates have increased by 25-30% since the start of LTP cycle. The escalation sits above 20%, with a further 5-10% felt due to increased operational cost (examples include the increased traffic management and HSE compliance costs, higher dumping costs, longer carts for aggregates). | 8000 | 4080 | [5 empty] | 272940 |  | 125506
2023-09-27 | September 2023 Review | Cost Decrease | Local road maintenance | Rail level crossing warning devices maintenance | Masterton District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Seeking small increase. Seeking additional local share and we may look to revise program if affordable. Council has local share for this request. | -240 | -134 | [5 empty] | 273100 |  | 125493
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Rail level crossing warning devices maintenance | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Additional MOR funding requested in the 2023/24 financial year. Reduced NLTF for the 21/24 NLTP through moderation. Increase in costs from year 2 in the 21/24 NLTP due to contract retender. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58846793 | 332 | 212 | [5 empty] | 274022 |  | 125748
2023-09-28 | September 2023 Review | Cost Decrease | Local road maintenance | Rail level crossing warning devices maintenance | Tauranga City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCC's MOR bid reduced by $10m at the start of the 21/24 NLTP. Inflation and historic under investment in the maintenance of the Transport Network have resulted n a perfect storm in which TCC find themselves. The commissioners have committed to additional funds for 2023/24 and beyond to close the gap. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58849106 | -39000 | -19890 | [5 empty] | 274337 |  | 125744
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Rail level crossing warning devices maintenance | Waipa District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Reduced NLTF for the 21/24 NLTP through moderation. Increases 111 sealed pavement maintenance by $600,000 to address priority pavement repairs after a very wet past 12 months and deteriorating road surface conditions. Increases 215 Structure component renewal by $1,800,000 for additional repairs to historic Victoria Bridge in Cambridge where a major repair and repaint contract is underway. Total increase sought $2,400,000. It is confirmed that Council has the local $$ share and has contracted resources engaged to complete this additional work. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58844596 | 972 | 496 | [5 empty] | 274525 |  | 125766
2023-09-27 | September 2023 Review | Cost Decrease | Road to Zero | Road improvements | NZ Transport Agency | SIP - Programme Management | Pre-implementation* | SIP Programme Management | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | To align SAP and TIO actuals for past two years (includes admin of 5.5% in 21/22 and 6% in future years). Second is to reallocated $580k to regions of BoP for $220k and Waikato $360k | -614800 | -614800 |  |  | 2.2 | 2.2 | 60063778 Jamie K | 277979 |  | 125955
2023-09-15 | September 2023 Review | Cost Decrease | External funding | Road improvements | NZTA (Auckland) | NZUP SH22 Paeraataa Roundabout (funded by KiwiRail) | Pre-implementation* | Totally funded by KiwiRail | MMM | MMM | N | 8 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Align SAP and TiO and invoice Kiwi Rail for reimbursement | -390645 | -390645 |  |  | 3.9 | 2.8 |  | 282213 | 60068075 | 125765
2023-09-15 | September 2023 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (BOP) | SH33 (Te Ngae Junction to Paengaroa) - TNJ intersection | Implementation |  | VHMVL | VHHL | N | 8 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | moving $951 from Imp to Pre Imp to close out Pre Imp | -1037 | -1037 |  |  | 0 | 1.6 | SNP-SSI | 269854 | 60057419 | 125703
2023-09-15 | September 2023 Review | Cost Increase | Road to Zero | Road improvements | NZTA (BOP) | SH33 (Te Ngae Junction to Paengaroa) - TNJ intersection | Pre-implementation* |  | VHMVL | VHHL | N | 8 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | moving $951 from imp to Pre Imp to close out Pre Imp | 1037 | 1037 |  |  | 0 | 1.6 |  | 278539 | 60062266 | 125702
2023-09-26 | September 2023 Review | Cost Increase | Road to Zero | Road improvements | NZTA (BOP) | SH33 (Te Ngae Junction to Paengaroa), NSRRP | Implementation |  | H_H | HHL | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Funding increase of $4,618,644 excluding 9% admin. requested due to increase in escalation costs and revised TTM methodology | 5034321 | 5034321 |  |  | 1.2 | 1.2 |  | 278523 | 60062268 | 125560
2023-09-01 | September 2023 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Canterbury) | SH1 Clarence & Oaro Improvement (NLTF) - Kaikoura Nov 2016 | Implementation | Implementation | H_L | VH_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Surplus $13m from Imp (60042776). The Northern Realignment project was proposed at $17M, however on preparation of construction tender documents, the estimate was revised to $25M. The scope was then reviewed to reduce the cost. | -14169999 | -14169999 |  |  | 1.2 | 1.2 | 60042776 | 249714 | 60042776 | 125486
2023-09-27 | September 2023 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Canterbury) | SH1 Selwyn River to Ashburton Safety Imp | Pre-implementation* | SH1 Selwyn River to Ashburton Safety Imp | VHHL | HHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | Increase of $4.13M for pre-imp shortfall following project merger | 4500000 | 4500000 |  |  | 0 | 1.6 |  | 278557 | 60062300 | 125764
2023-09-15 | September 2023 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (Northland) | SH10 Kaeo to Pakaraka | Pre-implementation* | SH10 Kaeo to Pakaraka | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project cancelled - delayed to 29/30 funding cycle | -241776 | -241776 |  |  | 2.1 | 2.1 | 3 | 277232 | 60060834 | 125699
2023-09-07 | September 2023 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Wellington) | SH2 Masterton to Carterton (corridor improvements) | Implementation | R2Z | VHMM | HHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | Total Cost Increase: PLA for $5,293,632 excluding Admin ($5,770,059 admin inc) approved by CFO 29-Aug-23 | 5770059 | 5770059 |  |  | 0 | 1.6 | SNP-SSI | 278436 | 60056536 | 125698
2023-09-20 | September 2023 Review | Cost Decrease | Road to Zero | Road policing | NZ Transport Agency | SCS OPEX & CAPEX | Implementation | CAPEX - Capital costs assoc with the Safety Camera | HMM | VHMM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Change in the commercial model from a capital expenditure (capex) build model to an operating expenditure (opex) software as a service (SAAS) arrangement. surplus $30m from SCS Implementation â€“ Opex (phase ID 284586), the remainder $4.4m from capex (phase ID 284587). | -4400000 | -4400000 |  |  | 1.1 | 1.1 | 60070818 | 284587 |  | 125926
2023-09-20 | September 2023 Review | Cost Decrease | Road to Zero | Road policing | NZ Transport Agency | SCS OPEX & CAPEX | Implementation | OPEX- Operating costs related to the Safety Camera | HMM | VHMM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Change in the commercial model from a capital expenditure (capex) build model to an operating expenditure (opex) software as a service (SAAS) arrangement. surplus $30m from SCS Implementation â€“ Opex (phase ID 284586), the remainder $4.4m from capex (phase ID 284587). | -30000000 | -30000000 |  |  | 1.1 | 1.1 | 60070819 | 284586 |  | 125925
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Routine drainage maintenance | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Request to increase the following WC's to a total of $3,285,480 is requested under the following WC's below: WC111 - request increase of $200,000 WC112 - request increase of $224,846 WC113 - request increase of $92,705 WC114 - request increase of $515,620 WC121 - request increase of $221,268 WC122 - request increase of $115,551 WC125 - request increase of $6,400 WC151 - request increase of $400,000 WC215 - request increase of $206,823 WC216 - request increase of $1,302,267 ZERO IMPACT ON BOTTOM LINE | 92705 | 63966 | [5 empty] | 272521 |  | 125756
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Routine drainage maintenance | Kapiti Coast District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Our contract unit rates have increased by 25-30% since the start of LTP cycle. The escalation sits above 20%, with a further 5-10% felt due to increased operational cost (examples include the increased traffic management and HSE compliance costs, higher dumping costs, longer carts for aggregates). | 127000 | 64770 | [5 empty] | 272932 |  | 125506
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Routine drainage maintenance | Masterton District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Seeking small increase. Seeking additional local share and we may look to revise program if affordable. Council has local share for this request. | 100000 | 56000 | [5 empty] | 273092 |  | 125493
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Routine drainage maintenance | South Taranaki District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | After in depth discussions with STDC the local share for these WC has been guaranteed and the physical resources to undertake the increase in WC214 and WC212 is available. The AWPT have had the designs undertaken and NPV have been requested. Logging and weather events in the district have been continuous and the effect has been a reduced LOS and a loss in resilience. Ecxtra funding will allow the network to "recover" and increase the safety, improve efficiency of freight and improve resilience on the rural parts. | 300000 | 189000 | [5 empty] | 273989 |  | 125621
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Routine drainage maintenance | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Additional MOR funding requested in the 2023/24 financial year. Reduced NLTF for the 21/24 NLTP through moderation. Increase in costs from year 2 in the 21/24 NLTP due to contract retender. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58846793 | 337373 | 215919 | [5 empty] | 274014 |  | 125748
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Routine drainage maintenance | Tauranga City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCC's MOR bid reduced by $10m at the start of the 21/24 NLTP. Inflation and historic under investment in the maintenance of the Transport Network have resulted n a perfect storm in which TCC find themselves. The commissioners have committed to additional funds for 2023/24 and beyond to close the gap. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58849106 | 414436 | 211362 | [5 empty] | 274329 |  | 125744
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Routine drainage maintenance | Thames-Coromandel District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCDC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance rate increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in this district during 2022/23 have resulted in increased quantities of maintenance works required to maintain service levels. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58899309 | 559600 | 285396 | [5 empty] | 274354 |  | 125825
2023-09-28 | September 2023 Review | Cost Decrease | Local road maintenance | Routine drainage maintenance | Waipa District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Reduced NLTF for the 21/24 NLTP through moderation. Increases 111 sealed pavement maintenance by $600,000 to address priority pavement repairs after a very wet past 12 months and deteriorating road surface conditions. Increases 215 Structure component renewal by $1,800,000 for additional repairs to historic Victoria Bridge in Cambridge where a major repair and repaint contract is underway. Total increase sought $2,400,000. It is confirmed that Council has the local $$ share and has contracted resources engaged to complete this additional work. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58844596 | -41000 | -20910 | [5 empty] | 274517 |  | 125766
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Routine drainage maintenance | Whakatane District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | WhakatÄne DC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance cost increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in the Bay of Plenty have resulted in increased minor event response costs and larger pavement and surfacing maintenance work programmes due to saturated pavements. WhakatÄne DC has budgeted for their local share of funding to support this NLTF increase request and has supplier capacity to deliver these additional works. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58867310 | 206500 | 130095 | [5 empty] | 274798 |  | 125746
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Sealed pavement maintenance | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Request to increase the following WC's to a total of $3,285,480 is requested under the following WC's below: WC111 - request increase of $200,000 WC112 - request increase of $224,846 WC113 - request increase of $92,705 WC114 - request increase of $515,620 WC121 - request increase of $221,268 WC122 - request increase of $115,551 WC125 - request increase of $6,400 WC151 - request increase of $400,000 WC215 - request increase of $206,823 WC216 - request increase of $1,302,267 ZERO IMPACT ON BOTTOM LINE | 200000 | 138000 | [5 empty] | 272519 |  | 125756
2023-09-01 | September 2023 Review | Cost Decrease | Local road maintenance | Sealed pavement maintenance | Horowhenua District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | WC discussion undertaken to consolidate spending and programme capabilities resulting in change request. | -940019 | -564011 | [5 empty] | 272745 |  | 125670
2023-09-27 | September 2023 Review | Cost Decrease | Local road maintenance | Sealed pavement maintenance | Kapiti Coast District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Our contract unit rates have increased by 25-30% since the start of LTP cycle. The escalation sits above 20%, with a further 5-10% felt due to increased operational cost (examples include the increased traffic management and HSE compliance costs, higher dumping costs, longer carts for aggregates). | -230618 | -117615 | [5 empty] | 272930 |  | 125506
2023-09-27 | September 2023 Review | Cost Decrease | Local road maintenance | Sealed pavement maintenance | Masterton District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Seeking small increase. Seeking additional local share and we may look to revise program if affordable. Council has local share for this request. | -1363636 | -763637 | [5 empty] | 273090 |  | 125493
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Sealed pavement maintenance | Napier City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | This increase is representative of overall program cost increases and programming changes to meet the identified asset needs. Owen Street, Austin, and Dunlop have been site verified and are awaiting the NVPs to confirm the treatments. 21.09.2023 NPV's provided | 3209760 | 1636978 | [5 empty] | 273557 |  | 125543
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Sealed pavement maintenance | South Taranaki District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | After in depth discussions with STDC the local share for these WC has been guaranteed and the physical resources to undertake the increase in WC214 and WC212 is available. The AWPT have had the designs undertaken and NPV have been requested. Logging and weather events in the district have been continuous and the effect has been a reduced LOS and a loss in resilience. Ecxtra funding will allow the network to "recover" and increase the safety, improve efficiency of freight and improve resilience on the rural parts. | 457350 | 288130 | [5 empty] | 273987 |  | 125621
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Sealed pavement maintenance | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Additional MOR funding requested in the 2023/24 financial year. Reduced NLTF for the 21/24 NLTP through moderation. Increase in costs from year 2 in the 21/24 NLTP due to contract retender. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58846793 | 1160231 | 742548 | [5 empty] | 274012 |  | 125748
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Sealed pavement maintenance | Tasman District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Seeking additional funds to meet higher than expected escalation estimated in 2020. | 4704874 | 2399486 | [5 empty] | 274242 |  | 125510
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Sealed pavement maintenance | Tauranga City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCC's MOR bid reduced by $10m at the start of the 21/24 NLTP. Inflation and historic under investment in the maintenance of the Transport Network have resulted n a perfect storm in which TCC find themselves. The commissioners have committed to additional funds for 2023/24 and beyond to close the gap. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58849106 | 3937048 | 2007895 | [5 empty] | 274327 |  | 125744
2023-09-28 | September 2023 Review | Cost Decrease | Local road maintenance | Sealed pavement maintenance | Thames-Coromandel District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCDC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance rate increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in this district during 2022/23 have resulted in increased quantities of maintenance works required to maintain service levels. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58899309 | -119675 | -61035 | [5 empty] | 274352 |  | 125825
2023-09-28 | September 2023 Review | Cost Decrease | Local road maintenance | Sealed pavement maintenance | Waipa District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Reduced NLTF for the 21/24 NLTP through moderation. Increases 111 sealed pavement maintenance by $600,000 to address priority pavement repairs after a very wet past 12 months and deteriorating road surface conditions. Increases 215 Structure component renewal by $1,800,000 for additional repairs to historic Victoria Bridge in Cambridge where a major repair and repaint contract is underway. Total increase sought $2,400,000. It is confirmed that Council has the local $$ share and has contracted resources engaged to complete this additional work. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58844596 | -457931 | -233545 | [5 empty] | 274515 |  | 125766
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Sealed pavement maintenance | Whakatane District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | WhakatÄne DC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance cost increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in the Bay of Plenty have resulted in increased minor event response costs and larger pavement and surfacing maintenance work programmes due to saturated pavements. WhakatÄne DC has budgeted for their local share of funding to support this NLTF increase request and has supplier capacity to deliver these additional works. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58867310 | 1024498 | 645434 | [5 empty] | 274796 |  | 125746
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Sealed road pavement rehabilitation | Kapiti Coast District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Our contract unit rates have increased by 25-30% since the start of LTP cycle. The escalation sits above 20%, with a further 5-10% felt due to increased operational cost (examples include the increased traffic management and HSE compliance costs, higher dumping costs, longer carts for aggregates). | 550000 | 280500 | [5 empty] | 272945 |  | 125506
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Sealed road pavement rehabilitation | Masterton District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Seeking small increase. Seeking additional local share and we may look to revise program if affordable. Council has local share for this request. | 122970 | 68863 | [5 empty] | 273105 |  | 125493
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Sealed road pavement rehabilitation | South Taranaki District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | After in depth discussions with STDC the local share for these WC has been guaranteed and the physical resources to undertake the increase in WC214 and WC212 is available. The AWPT have had the designs undertaken and NPV have been requested. Logging and weather events in the district have been continuous and the effect has been a reduced LOS and a loss in resilience. Ecxtra funding will allow the network to "recover" and increase the safety, improve efficiency of freight and improve resilience on the rural parts. | 1000000 | 630000 | [5 empty] | 274002 |  | 125621
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Sealed road pavement rehabilitation | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Additional MOR funding requested in the 2023/24 financial year. Reduced NLTF for the 21/24 NLTP through moderation. Increase in costs from year 2 in the 21/24 NLTP due to contract retender. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58846793 | 846723 | 541903 | [5 empty] | 274027 |  | 125748
2023-09-28 | September 2023 Review | Cost Decrease | Local road maintenance | Sealed road pavement rehabilitation | Tauranga City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCC's MOR bid reduced by $10m at the start of the 21/24 NLTP. Inflation and historic under investment in the maintenance of the Transport Network have resulted n a perfect storm in which TCC find themselves. The commissioners have committed to additional funds for 2023/24 and beyond to close the gap. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58849106 | -134760 | -68728 | [5 empty] | 274342 |  | 125744
2023-09-28 | September 2023 Review | Cost Decrease | Local road maintenance | Sealed road pavement rehabilitation | Thames-Coromandel District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCDC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance rate increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in this district during 2022/23 have resulted in increased quantities of maintenance works required to maintain service levels. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58899309 | -1380294 | -703950 | [5 empty] | 274367 |  | 125825
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Sealed road pavement rehabilitation | Waipa District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Reduced NLTF for the 21/24 NLTP through moderation. Increases 111 sealed pavement maintenance by $600,000 to address priority pavement repairs after a very wet past 12 months and deteriorating road surface conditions. Increases 215 Structure component renewal by $1,800,000 for additional repairs to historic Victoria Bridge in Cambridge where a major repair and repaint contract is underway. Total increase sought $2,400,000. It is confirmed that Council has the local $$ share and has contracted resources engaged to complete this additional work. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58844596 | 958074 | 488618 | [5 empty] | 274530 |  | 125766
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Sealed road pavement rehabilitation | Whakatane District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | WhakatÄne DC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance cost increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in the Bay of Plenty have resulted in increased minor event response costs and larger pavement and surfacing maintenance work programmes due to saturated pavements. WhakatÄne DC has budgeted for their local share of funding to support this NLTF increase request and has supplier capacity to deliver these additional works. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58867310 | 1300000 | 819000 | [5 empty] | 274811 |  | 125746
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Sealed road resurfacing | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Request to increase the following WC's to a total of $3,285,480 is requested under the following WC's below: WC111 - request increase of $200,000 WC112 - request increase of $224,846 WC113 - request increase of $92,705 WC114 - request increase of $515,620 WC121 - request increase of $221,268 WC122 - request increase of $115,551 WC125 - request increase of $6,400 WC151 - request increase of $400,000 WC215 - request increase of $206,823 WC216 - request increase of $1,302,267 ZERO IMPACT ON BOTTOM LINE | 2000000 | 1380000 | [5 empty] | 272532 |  | 125756
2023-09-01 | September 2023 Review | Cost Increase | Local road maintenance | Sealed road resurfacing | Horowhenua District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | WC discussion undertaken to consolidate spending and programme capabilities resulting in change request. | 100000 | 60000 | [5 empty] | 272758 |  | 125670
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Sealed road resurfacing | Kapiti Coast District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Our contract unit rates have increased by 25-30% since the start of LTP cycle. The escalation sits above 20%, with a further 5-10% felt due to increased operational cost (examples include the increased traffic management and HSE compliance costs, higher dumping costs, longer carts for aggregates). | 476922 | 243230 | [5 empty] | 272943 |  | 125506
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Sealed road resurfacing | Masterton District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Seeking small increase. Seeking additional local share and we may look to revise program if affordable. Council has local share for this request. | 284310 | 159214 | [5 empty] | 273103 |  | 125493
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Sealed road resurfacing | Rotorua Lakes Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Additional MOR funding requested in the 2023/24 financial year. Reduced NLTF for the 21/24 NLTP through moderation. Cost fluctuations running at 18% has reduced our resealing programme in year 1 and 2 and current funding levels will halve our normal resurfacing for 2023-24. Environmental maintenance costs had increased significantly under new contract arrangement. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58885222 | 1369295 | 766805 | [5 empty] | 273902 |  | 125755
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Sealed road resurfacing | South Taranaki District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | After in depth discussions with STDC the local share for these WC has been guaranteed and the physical resources to undertake the increase in WC214 and WC212 is available. The AWPT have had the designs undertaken and NPV have been requested. Logging and weather events in the district have been continuous and the effect has been a reduced LOS and a loss in resilience. Ecxtra funding will allow the network to "recover" and increase the safety, improve efficiency of freight and improve resilience on the rural parts. | 500000 | 315000 | [5 empty] | 274000 |  | 125621
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Sealed road resurfacing | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Additional MOR funding requested in the 2023/24 financial year. Reduced NLTF for the 21/24 NLTP through moderation. Increase in costs from year 2 in the 21/24 NLTP due to contract retender. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58846793 | 609657 | 390180 | [5 empty] | 274025 |  | 125748
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Sealed road resurfacing | Tauranga City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCC's MOR bid reduced by $10m at the start of the 21/24 NLTP. Inflation and historic under investment in the maintenance of the Transport Network have resulted n a perfect storm in which TCC find themselves. The commissioners have committed to additional funds for 2023/24 and beyond to close the gap. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58849106 | 532000 | 271320 | [5 empty] | 274340 |  | 125744
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Sealed road resurfacing | Thames-Coromandel District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCDC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance rate increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in this district during 2022/23 have resulted in increased quantities of maintenance works required to maintain service levels. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58899309 | 631484 | 322057 | [5 empty] | 274365 |  | 125825
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Sealed road resurfacing | Whakatane District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | WhakatÄne DC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance cost increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in the Bay of Plenty have resulted in increased minor event response costs and larger pavement and surfacing maintenance work programmes due to saturated pavements. WhakatÄne DC has budgeted for their local share of funding to support this NLTF increase request and has supplier capacity to deliver these additional works. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58867310 | 643500 | 405405 | [5 empty] | 274809 |  | 125746
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Structures component replacements | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Request to increase the following WC's to a total of $3,285,480 is requested under the following WC's below: WC111 - request increase of $200,000 WC112 - request increase of $224,846 WC113 - request increase of $92,705 WC114 - request increase of $515,620 WC121 - request increase of $221,268 WC122 - request increase of $115,551 WC125 - request increase of $6,400 WC151 - request increase of $400,000 WC215 - request increase of $206,823 WC216 - request increase of $1,302,267 ZERO IMPACT ON BOTTOM LINE | 206823 | 142707 | [5 empty] | 272535 |  | 125756
2023-09-27 | September 2023 Review | Cost Decrease | Local road maintenance | Structures component replacements | Masterton District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Seeking small increase. Seeking additional local share and we may look to revise program if affordable. Council has local share for this request. | -1790 | -1002 | [5 empty] | 273106 |  | 125493
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Structures component replacements | Tauranga City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCC's MOR bid reduced by $10m at the start of the 21/24 NLTP. Inflation and historic under investment in the maintenance of the Transport Network have resulted n a perfect storm in which TCC find themselves. The commissioners have committed to additional funds for 2023/24 and beyond to close the gap. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58849106 | 529352 | 269970 | [5 empty] | 274343 |  | 125744
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Structures component replacements | Thames-Coromandel District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCDC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance rate increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in this district during 2022/23 have resulted in increased quantities of maintenance works required to maintain service levels. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58899309 | 126329 | 64428 | [5 empty] | 274368 |  | 125825
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Structures component replacements | Waipa District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Reduced NLTF for the 21/24 NLTP through moderation. Increases 111 sealed pavement maintenance by $600,000 to address priority pavement repairs after a very wet past 12 months and deteriorating road surface conditions. Increases 215 Structure component renewal by $1,800,000 for additional repairs to historic Victoria Bridge in Cambridge where a major repair and repaint contract is underway. Total increase sought $2,400,000. It is confirmed that Council has the local $$ share and has contracted resources engaged to complete this additional work. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58844596 | 1695090 | 864496 | [5 empty] | 274531 |  | 125766
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Structures component replacements | Whakatane District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | WhakatÄne DC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance cost increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in the Bay of Plenty have resulted in increased minor event response costs and larger pavement and surfacing maintenance work programmes due to saturated pavements. WhakatÄne DC has budgeted for their local share of funding to support this NLTF increase request and has supplier capacity to deliver these additional works. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58867310 | 356000 | 224280 | [5 empty] | 274812 |  | 125746
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Structures maintenance | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Request to increase the following WC's to a total of $3,285,480 is requested under the following WC's below: WC111 - request increase of $200,000 WC112 - request increase of $224,846 WC113 - request increase of $92,705 WC114 - request increase of $515,620 WC121 - request increase of $221,268 WC122 - request increase of $115,551 WC125 - request increase of $6,400 WC151 - request increase of $400,000 WC215 - request increase of $206,823 WC216 - request increase of $1,302,267 ZERO IMPACT ON BOTTOM LINE | 515620 | 355778 | [5 empty] | 272522 |  | 125756
2023-09-27 | September 2023 Review | Cost Decrease | Local road maintenance | Structures maintenance | Masterton District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Seeking small increase. Seeking additional local share and we may look to revise program if affordable. Council has local share for this request. | -1490 | -834 | [5 empty] | 273093 |  | 125493
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Structures maintenance | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Additional MOR funding requested in the 2023/24 financial year. Reduced NLTF for the 21/24 NLTP through moderation. Increase in costs from year 2 in the 21/24 NLTP due to contract retender. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58846793 | 932 | 596 | [5 empty] | 274015 |  | 125748
2023-09-28 | September 2023 Review | Cost Decrease | Local road maintenance | Structures maintenance | Tauranga City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCC's MOR bid reduced by $10m at the start of the 21/24 NLTP. Inflation and historic under investment in the maintenance of the Transport Network have resulted n a perfect storm in which TCC find themselves. The commissioners have committed to additional funds for 2023/24 and beyond to close the gap. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58849106 | -144200 | -73542 | [5 empty] | 274330 |  | 125744
2023-09-28 | September 2023 Review | Cost Decrease | Local road maintenance | Structures maintenance | Thames-Coromandel District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCDC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance rate increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in this district during 2022/23 have resulted in increased quantities of maintenance works required to maintain service levels. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58899309 | -5865 | -2991 | [5 empty] | 274355 |  | 125825
2023-09-28 | September 2023 Review | Cost Decrease | Local road maintenance | Structures maintenance | Waipa District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Reduced NLTF for the 21/24 NLTP through moderation. Increases 111 sealed pavement maintenance by $600,000 to address priority pavement repairs after a very wet past 12 months and deteriorating road surface conditions. Increases 215 Structure component renewal by $1,800,000 for additional repairs to historic Victoria Bridge in Cambridge where a major repair and repaint contract is underway. Total increase sought $2,400,000. It is confirmed that Council has the local $$ share and has contracted resources engaged to complete this additional work. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58844596 | -10000 | -5100 | [5 empty] | 274518 |  | 125766
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Structures maintenance | Whakatane District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | WhakatÄne DC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance cost increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in the Bay of Plenty have resulted in increased minor event response costs and larger pavement and surfacing maintenance work programmes due to saturated pavements. WhakatÄne DC has budgeted for their local share of funding to support this NLTF increase request and has supplier capacity to deliver these additional works. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58867310 | 18500 | 11655 | [5 empty] | 274799 |  | 125746
2023-09-19 | September 2023 Review | Cost Decrease | Public transport services | Total mobility operations | Auckland Transport | Government reduced public transport fares scheme (Crown) | Implementation | Total Mobility - Reduced fares | VHHL | VHHL | Y | 2 | Approved | Approved by Auckland Transport Chief Financial Officer |  | -461296 | -461296 |  |  |  |  | 517.2812 | 281220 |  | 125877
2023-09-01 | September 2023 Review | Cost Decrease | Public transport services | Total mobility operations | Auckland Transport | Public Transport Programme 2021-24 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | This is to reduce the funding required to support the PT services element of the programme due to the roll-over of funding from FY23 subsequent to the Crown top-up provided in late FY23. This surplus will be offset by an increase in the PT infrastructure activity component of the continuous programme. | -652949 | -391769 | [5 empty] | 272175 |  | 125622
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Total mobility operations | Bay of Plenty Regional Council | Government reduced public transport fares scheme (Crown) | Implementation | Total Mobility - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -77309 | -77309 | [5 empty] | 281224 |  | 125834
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Total mobility operations | Environment Canterbury | Government reduced public transport fares scheme (Crown) | Implementation | Total Mobility - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -180089 | -180089 | [5 empty] | 281215 |  | 125836
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Total mobility operations | Greater Wellington | Government reduced public transport fares scheme (Crown) | Implementation | Total Mobility - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -793112 | -793112 | [5 empty] | 281234 |  | 125843
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Total mobility operations | Hawkes Bay Regional Council | Government reduced public transport fares scheme (Crown) | Implementation | Total Mobility - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -107795 | -107795 | [5 empty] | 281237 |  | 125846
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Total mobility operations | Horizons Manawatu | Government reduced public transport fares scheme (Crown) | Implementation | Total Mobility - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -237318 | -237318 | [5 empty] | 281259 |  | 125848
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Total mobility operations | Invercargill City Council | Government reduced public transport fares scheme (Crown) | Implementation | Total Mobility - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -97557 | -97557 | [5 empty] | 281262 |  | 125851
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Total mobility operations | Marlborough District Council | Government reduced public transport fares scheme (Crown) | Implementation | Total Mobility - Reduced fares | VHHL | HHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -40042 | -40042 | [5 empty] | 281265 |  | 125853
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Total mobility operations | Nelson City Council | Government reduced public transport fares scheme (Crown) | Implementation | Total Mobility - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -15910 | -15910 | [5 empty] | 281268 |  | 125854
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Total mobility operations | Northland Regional Council | Government reduced public transport fares scheme (Crown) | Implementation | Total Mobility - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -10020 | -10020 | [5 empty] | 281271 |  | 125856
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Total mobility operations | Otago Regional Council | Government reduced public transport fares scheme (Crown) | Implementation | Total Mobility - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -139976 | -139976 | [5 empty] | 281275 |  | 125860
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Total mobility operations | Taranaki Regional Council | Government reduced public transport fares scheme (Crown) | Implementation | Total Mobility - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -110680 | -110680 | [5 empty] | 281278 |  | 125863
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Total mobility operations | Tasman District Council | Government reduced public transport fares scheme (Crown) | Implementation | Total Mobility - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -140720 | -140720 | [5 empty] | 281286 |  | 125865
2023-09-15 | September 2023 Review | Cost Decrease | Public transport services | Total mobility operations | Waikato Regional Council | Government reduced public transport fares scheme (Crown) | Implementation | Total Mobility - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Appropriation is complete. Surplus remaining funds. | -107084 | -107084 | [5 empty] | 281282 |  | 125868
2023-09-01 | September 2023 Review | Cost Increase | Local road maintenance | Traffic services renewals | Horowhenua District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | WC discussion undertaken to consolidate spending and programme capabilities resulting in change request. | 60000 | 36000 | [5 empty] | 272764 |  | 125670
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Traffic services renewals | Kapiti Coast District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Our contract unit rates have increased by 25-30% since the start of LTP cycle. The escalation sits above 20%, with a further 5-10% felt due to increased operational cost (examples include the increased traffic management and HSE compliance costs, higher dumping costs, longer carts for aggregates). | 161634 | 82433 | [5 empty] | 272949 |  | 125506
2023-09-27 | September 2023 Review | Cost Decrease | Local road maintenance | Traffic services renewals | Masterton District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Seeking small increase. Seeking additional local share and we may look to revise program if affordable. Council has local share for this request. | -5640 | -3158 | [5 empty] | 273109 |  | 125493
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Traffic services renewals | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Additional MOR funding requested in the 2023/24 financial year. Reduced NLTF for the 21/24 NLTP through moderation. Increase in costs from year 2 in the 21/24 NLTP due to contract retender. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58846793 | 12600 | 8064 | [5 empty] | 274031 |  | 125748
2023-09-28 | September 2023 Review | Cost Decrease | Local road maintenance | Traffic services renewals | Tauranga City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCC's MOR bid reduced by $10m at the start of the 21/24 NLTP. Inflation and historic under investment in the maintenance of the Transport Network have resulted n a perfect storm in which TCC find themselves. The commissioners have committed to additional funds for 2023/24 and beyond to close the gap. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58849106 | -324640 | -165566 | [5 empty] | 274346 |  | 125744
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Traffic services renewals | Thames-Coromandel District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCDC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance rate increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in this district during 2022/23 have resulted in increased quantities of maintenance works required to maintain service levels. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58899309 | 64418 | 32854 | [5 empty] | 274371 |  | 125825
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Traffic services renewals | Whakatane District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | WhakatÄne DC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance cost increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in the Bay of Plenty have resulted in increased minor event response costs and larger pavement and surfacing maintenance work programmes due to saturated pavements. WhakatÄne DC has budgeted for their local share of funding to support this NLTF increase request and has supplier capacity to deliver these additional works. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58867310 | 460000 | 289800 | [5 empty] | 274815 |  | 125746
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Unsealed pavement maintenance | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Request to increase the following WC's to a total of $3,285,480 is requested under the following WC's below: WC111 - request increase of $200,000 WC112 - request increase of $224,846 WC113 - request increase of $92,705 WC114 - request increase of $515,620 WC121 - request increase of $221,268 WC122 - request increase of $115,551 WC125 - request increase of $6,400 WC151 - request increase of $400,000 WC215 - request increase of $206,823 WC216 - request increase of $1,302,267 ZERO IMPACT ON BOTTOM LINE | 224846 | 155144 | [5 empty] | 272520 |  | 125756
2023-09-01 | September 2023 Review | Cost Decrease | Local road maintenance | Unsealed pavement maintenance | Horowhenua District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | WC discussion undertaken to consolidate spending and programme capabilities resulting in change request. | -55656 | -33394 | [5 empty] | 272746 |  | 125670
2023-09-27 | September 2023 Review | Cost Increase | Local road maintenance | Unsealed pavement maintenance | Masterton District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Seeking small increase. Seeking additional local share and we may look to revise program if affordable. Council has local share for this request. | 115634 | 64755 | [5 empty] | 273091 |  | 125493
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Unsealed pavement maintenance | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Additional MOR funding requested in the 2023/24 financial year. Reduced NLTF for the 21/24 NLTP through moderation. Increase in costs from year 2 in the 21/24 NLTP due to contract retender. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58846793 | 67486 | 43191 | [5 empty] | 274013 |  | 125748
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Unsealed pavement maintenance | Thames-Coromandel District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCDC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance rate increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in this district during 2022/23 have resulted in increased quantities of maintenance works required to maintain service levels. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58899309 | 106294 | 54210 | [5 empty] | 274353 |  | 125825
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Unsealed pavement maintenance | Waipa District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Reduced NLTF for the 21/24 NLTP through moderation. Increases 111 sealed pavement maintenance by $600,000 to address priority pavement repairs after a very wet past 12 months and deteriorating road surface conditions. Increases 215 Structure component renewal by $1,800,000 for additional repairs to historic Victoria Bridge in Cambridge where a major repair and repaint contract is underway. Total increase sought $2,400,000. It is confirmed that Council has the local $$ share and has contracted resources engaged to complete this additional work. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58844596 | 6400 | 3264 | [5 empty] | 274516 |  | 125766
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Unsealed pavement maintenance | Whakatane District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | WhakatÄne DC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance cost increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in the Bay of Plenty have resulted in increased minor event response costs and larger pavement and surfacing maintenance work programmes due to saturated pavements. WhakatÄne DC has budgeted for their local share of funding to support this NLTF increase request and has supplier capacity to deliver these additional works. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58867310 | 81000 | 51030 | [5 empty] | 274797 |  | 125746
2023-09-27 | September 2023 Review | Cost Decrease | Local road maintenance | Unsealed road metalling | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Request to increase the following WC's to a total of $3,285,480 is requested under the following WC's below: WC111 - request increase of $200,000 WC112 - request increase of $224,846 WC113 - request increase of $92,705 WC114 - request increase of $515,620 WC121 - request increase of $221,268 WC122 - request increase of $115,551 WC125 - request increase of $6,400 WC151 - request increase of $400,000 WC215 - request increase of $206,823 WC216 - request increase of $1,302,267 ZERO IMPACT ON BOTTOM LINE | -2000000 | -1380000 | [5 empty] | 272531 |  | 125756
2023-09-27 | September 2023 Review | Cost Decrease | Local road maintenance | Unsealed road metalling | Masterton District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Seeking small increase. Seeking additional local share and we may look to revise program if affordable. Council has local share for this request. | -8790 | -4922 | [5 empty] | 273102 |  | 125493
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Unsealed road metalling | South Taranaki District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | After in depth discussions with STDC the local share for these WC has been guaranteed and the physical resources to undertake the increase in WC214 and WC212 is available. The AWPT have had the designs undertaken and NPV have been requested. Logging and weather events in the district have been continuous and the effect has been a reduced LOS and a loss in resilience. Ecxtra funding will allow the network to "recover" and increase the safety, improve efficiency of freight and improve resilience on the rural parts. | 300000 | 189000 | [5 empty] | 273999 |  | 125621
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Unsealed road metalling | Thames-Coromandel District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | TCDC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance rate increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in this district during 2022/23 have resulted in increased quantities of maintenance works required to maintain service levels. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58899309 | 226920 | 115729 | [5 empty] | 274364 |  | 125825
2023-09-28 | September 2023 Review | Cost Decrease | Local road maintenance | Unsealed road metalling | Waipa District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Reduced NLTF for the 21/24 NLTP through moderation. Increases 111 sealed pavement maintenance by $600,000 to address priority pavement repairs after a very wet past 12 months and deteriorating road surface conditions. Increases 215 Structure component renewal by $1,800,000 for additional repairs to historic Victoria Bridge in Cambridge where a major repair and repaint contract is underway. Total increase sought $2,400,000. It is confirmed that Council has the local $$ share and has contracted resources engaged to complete this additional work. For detail cut and paste the link below into a browser. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58844596 | -39000 | -19890 | [5 empty] | 274527 |  | 125766
2023-09-28 | September 2023 Review | Cost Increase | Local road maintenance | Unsealed road metalling | Whakatane District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | WhakatÄne DC's request for increased MOR investment in 2023/24 is primarily due to the significant maintenance cost increases not foreseen when preparing their 2021-24 NLTP bid in 2020. In addition to the gap between actual costs and existing funding levels, the frequency and severity of weather events in the Bay of Plenty have resulted in increased minor event response costs and larger pavement and surfacing maintenance work programmes due to saturated pavements. WhakatÄne DC has budgeted for their local share of funding to support this NLTF increase request and has supplier capacity to deliver these additional works. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58867310 | 150000 | 94500 | [5 empty] | 274808 |  | 125746