## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Phase Label | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Decision Status | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR | Your Phase reference | TIO Phase id | SAP item id | TIO Request id
2023-10-17 | October 2023 Review | New approval | External funding | Cycling facilities | Central Hawkes Bay District Council | CERF-TC- Walkable Urban Hearts - Otane and Porangahau | Implementation | Early Implementation | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | Recommend funding of $140,000 as it aligns with the Crown-funded CERF TC PBC and approval has been confirmed by CERF-TC programme team | 140000 | 140000 |  |  | 0 | 0 |  | 290235 |  | 126079
2023-10-02 | October 2023 Review | New approval | External funding | Cycling facilities | Matamata-Piako District Council | CERF-TC MPDC Transport Choices Projects | Pre-implementation* | Te Aroha, Morrinsville and Matamata TC projects | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | as per CERF activity | 423930 | 423930 |  |  |  | 0 |  | 284168 |  | 123272
2023-10-11 | October 2023 Review | New approval | External funding | Cycling facilities | Waipa District Council | CERF-TC Cambridge & Kihikihi | Implementation | Te Ara Rimu Kihikihi Pathway | HHH | VHMH | N | 4 | Approved | Approved by Minister for Crown Appropriation | This has a signed schedule 2 under the CERF Transport Choices programme. The signed schedule 2 includes pre-imp funding also, I have checked the figures to ensure they sum to the correct amount. | 7500000 | 5280000 |  |  | 9.1 | 9.1 | PR 4293 Te Ara Rimu Kihikihi Pathway | 284116 |  | 122631
2023-10-11 | October 2023 Review | New approval | External funding | Cycling facilities | Waipa District Council | CERF-TC Cambridge & Kihikihi | Implementation | Cambridge Pathways | HHH | VHMH | N | 4 | Approved | Approved by Minister for Crown Appropriation | This has a signed schedule 2 under the CERF Transport Choices programme. The signed schedule 2 includes pre-imp funding also, I have checked the figures to ensure they sum to the correct amount. | 9615204 | 6815204 |  |  | 9.1 | 9.1 | PR 4292 cambridge pathways | 284114 |  | 122630
2023-10-25 | October 2023 Review | New approval | Local road maintenance | Emergency works | Ashburton District Council | EW Ashburton DC July 2023 Rain Event | Construction | Response and Recovery | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | Recommendation That the Senior Manager, Maintenance and Operations (Transport Services): Approves Ashburton District Councilâ€™s Emergency Works request at a total gross cost of $1,044,790 for Financial Year 23/24. | 1044790 | 532843 | [5 empty] | 288976 |  | 125722
2023-10-27 | October 2023 Review | New approval | Local road maintenance | Emergency works | Grey District Council | EW Grey DC April - May 2022 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | Recommendation That the Regional Manager, Maintenance and Operations (Transport Services): Approves Grey District Councilâ€™s Emergency Works request at a total gross cost of $357,698 for Financial Year 23/24. | 357698 | 296889 |  |  |  |  | Response and Remedial Works | 284552 |  | 125328
2023-10-25 | October 2023 Review | New approval | Local road maintenance | Emergency works | Grey District Council | EW Grey DC February 2022 | Construction | Response and Remedial Works | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | Recommendation That the Regional Manager, Maintenance and Operations (Transport Services): Approves Grey District Councilâ€™s Emergency Works request at a total gross cost of $160,081 for Financial Year 23/24. | 126343 | 79596 | [5 empty] | 284550 |  | 125327
2023-10-30 | October 2023 Review | New approval | Local road maintenance | Emergency works | Grey District Council | EW Grey DC June 2022 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | Recommendation That the Regional Manager, Maintenance and Operations (Transport Services): Approves Grey District Councilâ€™s Emergency Works request at a total gross cost of $165,845 for Financial Year 23/24. | 165845 | 137651 |  |  |  |  | Response and Remedial Works | 282011 |  | 120422
2023-10-09 | October 2023 Review | New approval | Local road maintenance | Emergency works | Mackenzie District Council | EW - Mackenzie DC July 2022 Flood Event | Construction | Subsequent Damage Recovery | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds to move from normal FAR to higher FAR. Adjust emergency works funding (Higher FAR). | 15728 | 11167 |  |  |  |  | Subsequent Recovery costs (Normal FAR+20%) | 290248 |  | 126084
2023-10-13 | October 2023 Review | New approval | State highway maintenance | Emergency works | NZTA (Wellington) | EW SH2 Remutaka Underslip 20230721 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | As the emergency work, the reinstate the level of service is critical. Since WTA already have the category design in place. The recovery works need to be programmed and carried out ASAP to remove the speed restriction, subject to Recovery Managerâ€™s approval. | 1378850 | 1378850 | [5 empty] | 288482 | 60071543 | 126096
2023-10-27 | October 2023 Review | New approval | State highway maintenance | Emergency works | NZTA (Wellington) | EW SH2 Rimutaka Overslip 20230811 | Construction |  | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | I am content that this application sits within the current PIKB funding guidance for emergency works. I recommend approval Nick Cook Recovery Manager | 171130 | 171130 | [5 empty] | 289535 | 60073088 | 126169
2023-10-26 | October 2023 Review | New approval | Local road maintenance | Emergency works | Opotiki District Council | EW ÅŒpÅtiki DC September 2023 | Construction | Initial Response & Clean up | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | Investment required to respond and recover from storm damage / achieve appropriate (pre-storm) LoS. | 61360 | 46020 | [5 empty] | 290255 |  | 126124
2023-10-26 | October 2023 Review | New approval | Local road maintenance | Emergency works | Opotiki District Council | EW ÅŒpÅtiki DC September 2023 | Construction | Permanent Reinstatement | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | Investment required to respond and recover from storm damage / achieve appropriate (pre-storm) LoS. | 124575 | 93431 | [5 empty] | 290256 |  | 126125
2023-10-09 | October 2023 Review | New approval | Local road maintenance | Emergency works | Waikato District Council | EW - Waikato DC Storm Damage Jan-Feb 2023 | Construction | 23/24 Phase 2 - Investigation and Design | ___ |  | N |  | Approved | Approved by National Manager, Programmes and Standards (Transport Services) | this funding application has been reviewed in some detail and initial options presented have been re-evaluated to a more appropriate level of service | 830000 | 423300 |  |  |  |  | Phase Two - Investigation and Design | 288480 |  | 125550
2023-10-09 | October 2023 Review | New approval | Local road maintenance | Emergency works | Waikato District Council | EW - Waikato DC Storm Damage Jan-Feb 2023 | Construction | Phase 2 - Construction of Practitioner Sites | ___ |  | N |  | Approved | Approved by National Manager, Programmes and Standards (Transport Services) | this funding application has been reviewed in some detail and initial options presented have been re-evaluated to a more appropriate level of service | 2338000 | 1192380 |  |  |  |  | Phase 2 - Construction of Practitioner Sites | 288479 |  | 125549
2023-10-12 | October 2023 Review | New approval | State highway maintenance | Network and asset management | NZ Transport Agency | Integrated Delivery Model | Pre-implementation* |  | HHM | HHM | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | The IDM is the proposed model to replace the current Network Outcomes Contracts (NOC) operating across the New Zealand State Highway Network. NOCs have largely met the objectives set by Waka Kotahi, however funding, network demand and climate have changed significantly since the contracts were established and there are opportunities to optimise and enhance outcomes in advance of procuring the new contracts in 2026. | 1000000 | 1000000 |  |  |  | 3 | 60073543 | 290244 |  | 126107
2023-10-13 | October 2023 Review | New approval | External funding | New activities influencing users of the transport system | Queenstown-Lakes District Council | CERF-TC - Wanaka Schools to Pool Active Travel | Implementation | Schools to Pool | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | Part of the Budget 2022 Cabinet approved initiatives with funding under the Climate Emergency response Fund (CERF) programme. CERF-TC projects do not follow the same NLTF business case assessment pathway. The business case assessment has been replaced with a bespoke application, assessment, monitoring process as detailed in Transport Choices Funding Agreement Guidance Notes. | 2259498 | 1500000 |  |  |  | 0 |  | 284499 |  | 125402
2023-10-06 | October 2023 Review | New approval | External funding | Passenger facilities and infrastructure improvements - bus | Hawkes Bay Regional Council | CERF-TC - Hawkeâ€™s Bay Bus Stop Accessibility | Pre-implementation* | Preimplementation | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | Recommend funding of $208,725 pre-implementation as it aligns with the Crown-funded CERF TC PBC and approval has been confirmed by CERF-TC programme team | 208725 | 208725 |  |  | 0 | 0 | TC Hawkeâ€™s Bay bus stop accessibility | 289043 |  | 126061
2023-10-05 | October 2023 Review | New approval | External funding | Programme Business Case Development | Tauranga City Council | CERF-VKT Reduction Tauranga | Programme business case |  | VHHL | VHHL | N | 2 | Approved | Approved by Minister for Crown Appropriation | Activity supports the establishment of a VKT reduction programme. | 200000 | 200000 | [5 empty] | 284332 |  | 126046
2023-10-26 | October 2023 Review | New approval | State highway improvements | Property purchase (State highways) | NZTA (Marlborough) | SH1 Picton Port Access Improvements | Property |  | VHHVL | VHHVL | N | 7 | Approved | Approved by Chief Financial Officer (CFO) | There are pre-existing safety and capacity issues in Pictonâ€™s transport system that will be exacerbated when KiwiRailâ€™s larger ferries arrive in mid-late 2025. The benefits from investment are: âˆ’ Port is enabled to handle current and future passenger and freight volumes (20%) âˆ’ Improved visitor and resident safety and wellbeing (40%) âˆ’ Community, visitor and business assess is maintained and enhanced (40%) | 127200 | 127200 |  |  | 2 | 2 |  | 283056 | 60067430 | 121218
2023-10-27 | October 2023 Review | New approval | State highway improvements | Replacement of bridges and other structures | NZTA (BOP) | SH29 Omanawa River Bridge | Single-Stage Business Case |  | VHML | VHLL | N | 3 | Approved | Approved by Chief Financial Officer (CFO) | This funding enables a package of fit for purpose business cases to be developed which will outline the optimal replacement time and option for our current structures which are at the end of their economic life. We note that the activity level BCRs will be determined in the next phase. The requirements of section 20 of the Land Transport Management Act 2003 have been met. | 432000 | 432000 |  |  |  | 1 |  | 290352 | 60073604 | 126151
2023-10-27 | October 2023 Review | New approval | State highway improvements | Replacement of bridges and other structures | NZTA (BOP) | SH36 Hauraki Stream Culvert | Single-Stage Business Case |  | HMM | VHLH | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | This funding enables a package of fit for purpose business cases to be developed which will outline the optimal replacement time and option for our current structures which are at the end of their economic life. We note that the activity level BCRs will be determined in the next phase. The requirements of section 20 of the Land Transport Management Act 2003 have been met. | 145001 | 145001 |  |  |  | 4 |  | 290345 | 60073590 | 126149
2023-10-27 | October 2023 Review | New approval | State highway improvements | Replacement of bridges and other structures | NZTA (Canterbury) | SH82 Waihao North Bridge | Single-Stage Business Case |  | LMH | HLL | N | 12 | Approved | Approved by Chief Financial Officer (CFO) | This funding enables a package of fit for purpose business cases to be developed which will outline the optimal replacement time and option for our current structures which are at the end of their economic life. We note that the activity level BCRs will be determined in the next phase. The requirements of section 20 of the Land Transport Management Act 2003 have been met. | 310000 | 310000 | [5 empty] | 290340 | 60073579 | 126148
2023-10-27 | October 2023 Review | New approval | State highway improvements | Replacement of bridges and other structures | NZTA (Gisborne) | SH35 Mangahauini No. 1 Bridge | Single-Stage Business Case |  | HHM | HHM | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | This funding enables a package of fit for purpose business cases to be developed which will outline the optimal replacement time and option for our current structures which are at the end of their economic life. We note that the activity level BCRs will be determined in the next phase. The requirements of section 20 of the Land Transport Management Act 2003 have been met. | 115000 | 115000 |  |  |  | 1 |  | 290346 | 60073595 | 126207
2023-10-27 | October 2023 Review | New approval | State highway improvements | Replacement of bridges and other structures | NZTA (Hawkes Bay) | SH38 Frasertown Bridge | Single-Stage Business Case |  | HHM | HHM | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | This funding enables a package of fit for purpose business cases to be developed which will outline the optimal replacement time and option for our current structures which are at the end of their economic life. We note that the activity level BCRs will be determined in the next phase. The requirements of section 20 of the Land Transport Management Act 2003 have been met. | 115000 | 115000 |  |  |  | 1 |  | 290350 | 60073602 | 126208
2023-10-27 | October 2023 Review | New approval | State highway improvements | Replacement of bridges and other structures | NZTA (Manawatu/Whanganui) | SH43 Kururau Stream water Drive | Single-Stage Business Case |  | HHM | HHM | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | This funding enables a package of fit for purpose business cases to be developed which will outline the optimal replacement time and option for our current structures which are at the end of their economic life. We note that the activity level BCRs will be determined in the next phase. The requirements of section 20 of the Land Transport Management Act 2003 have been met. | 110000 | 110000 |  |  |  | 1 |  | 290338 | 60073577 | 126209
2023-10-27 | October 2023 Review | New approval | State highway improvements | Replacement of bridges and other structures | NZTA (Taranaki) | SH3 Mangapepeki No. 2 Culvert | Single-Stage Business Case |  | HHM | HHM | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | This funding enables a package of fit for purpose business cases to be developed which will outline the optimal replacement time and option for our current structures which are at the end of their economic life. We note that the activity level BCRs will be determined in the next phase. The requirements of section 20 of the Land Transport Management Act 2003 have been met. | 110000 | 110000 |  |  |  | 1 |  | 290343 | 60073588 | 126210
2023-10-27 | October 2023 Review | New approval | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH25 Boundary Creek Bridge | Single-Stage Business Case |  | HHM | HHM | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | This funding enables a package of fit for purpose business cases to be developed which will outline the optimal replacement time and option for our current structures which are at the end of their economic life. We note that the activity level BCRs will be determined in the next phase. The requirements of section 20 of the Land Transport Management Act 2003 have been met. | 65000 | 65000 |  |  |  | 1 |  | 290364 | 60073583 | 126211
2023-10-27 | October 2023 Review | New approval | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH25 RAMARAMA STREAM BRIDGE | Single-Stage Business Case |  | HLL | HLVH | N | 8 | Approved | Approved by Chief Financial Officer (CFO) | This funding enables a package of fit for purpose business cases to be developed which will outline the optimal replacement time and option for our current structures which are at the end of their economic life. We note that the activity level BCRs will be determined in the next phase. The requirements of section 20 of the Land Transport Management Act 2003 have been met. | 245000 | 245000 | [5 empty] | 290337 | 60073572 | 126147
2023-10-27 | October 2023 Review | New approval | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH27 Ohinekaua Stream Bridge | Single-Stage Business Case |  | HLL | HLVH | N | 8 | Approved | Approved by Chief Financial Officer (CFO) | This funding enables a package of fit for purpose business cases to be developed which will outline the optimal replacement time and option for our current structures which are at the end of their economic life. We note that the activity level BCRs will be determined in the next phase. The requirements of section 20 of the Land Transport Management Act 2003 have been met. | 150000 | 150000 |  |  |  | 1 |  | 290348 | 60073597 | 126150
2023-10-27 | October 2023 Review | New approval | State highway improvements | Replacement of bridges and other structures | NZTA (West Coast) | SH6 Coal Creek Overbridge | Single-Stage Business Case |  | HLM | HLVH | N | 8 | Approved | Approved by Chief Financial Officer (CFO) | This funding enables a package of fit for purpose business cases to be developed which will outline the optimal replacement time and option for our current structures which are at the end of their economic life. We note that the activity level BCRs will be determined in the next phase. The requirements of section 20 of the Land Transport Management Act 2003 have been met. | 300000 | 300000 | [5 empty] | 290335 | 60073570 | 126146
2023-10-09 | October 2023 Review | New approval | Road to Zero | Road improvements | NZTA (Hawkes Bay) | SH5 Matea Road to SH2 S IMPR | Implementation | SH5 Matea Road to SH2 S IMPR | HML | VHHL | N | 6 | Approved | Approved by Chief Financial Officer (CFO) |  | 13625000 | 13625000 |  |  | 2.1 | 2.1 | 155 | 277291 | 60060920 | 125685
2023-10-26 | October 2023 Review | New approval | State highway improvements | Road improvements | NZTA (Marlborough) | SH1 Picton Port Access Improvements | Implementation | Picton Port Access | VHHVL | VHHVL | N | 7 | Approved | Approved by Chief Financial Officer (CFO) | There are pre-existing safety and capacity issues in Pictonâ€™s transport system that will be exacerbated when KiwiRailâ€™s larger ferries arrive in mid-late 2025. The benefits from investment are: âˆ’ Port is enabled to handle current and future passenger and freight volumes (20%) âˆ’ Improved visitor and resident safety and wellbeing (40%) âˆ’ Community, visitor and business assess is maintained and enhanced (40%) | 12344795 | 12344795 |  |  | 2 | 2 |  | 276608 | 60061007 | 121224
2023-10-26 | October 2023 Review | New approval | State highway improvements | Road improvements | NZTA (Marlborough) | SH1 Picton Port Access Improvements | Pre-implementation* | Picton Port Access | VHHVL | VHHVL | N | 7 | Approved | Approved by Chief Financial Officer (CFO) | There are pre-existing safety and capacity issues in Pictonâ€™s transport system that will be exacerbated when KiwiRailâ€™s larger ferries arrive in mid-late 2025. The benefits from investment are: âˆ’ Port is enabled to handle current and future passenger and freight volumes (20%) âˆ’ Improved visitor and resident safety and wellbeing (40%) âˆ’ Community, visitor and business assess is maintained and enhanced (40%) | 904155 | 904155 | An MoU be developed to document and agree the funding split and the governance and benefit management split for all parties. |  | 2 | 2 |  | 281499 | 60067402 | 121217
2023-10-06 | October 2023 Review | New approval | External funding | SuperGold trip payments | Waikato Regional Council | SuperGold Card Allocation | Implementation | SuperGold Card contracted services â€“ rail | M__ | LML | N | 0 | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2023/24 | 857 | 857 |  |  | 0 | 0 | 522 | 290233 |  | 126082
2023-10-06 | October 2023 Review | New approval | Public transport services | SuperGold trip payments | Waikato Regional Council | SuperGold Card Allocation | Implementation | SuperGold Card contracted services â€“ rail- contrac | M__ | LML | N | 0 | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2023/24 | 857 | 857 |  |  | 0 | 0 | 522 | 290215 |  | 126070
2023-10-09 | October 2023 Review | New approval | External funding | Walking facilities | Ruapehu District Council | CERF-TC Ruapehu Safe accessible paths for children & whanau | Pre-implementation* | Pre-implementation phase | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | Recommend funding of $3,720 as it aligns with the Crown-funded CERF TC PBC and approval has been confirmed by CERF-TC programme team | 3720 | 3720 |  |  | 0 | 0 |  | 289570 |  | 125982
2023-10-26 | October 2023 Review | Cash flow adjustment | Road to Zero | Activity management planning improvement | NZ Transport Agency | State Highway Speed Management Plan | Implementation | 60069223 | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update 2022/23 | 0 | 0 |  |  |  | 2.1 | SAP-PPM Id 157902022 / 60069223 | 283272 |  | 126162
2023-10-27 | October 2023 Review | Cash flow adjustment | Local road maintenance | Emergency works | Matamata-Piako District Council | EW - Matamata-Piako DC Jan - Feb 2023 | Construction | Pioneer Road Culvert | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Emergency works claiming for this activity is complete | -22 | -20 |  |  |  |  | Pioneer Road | 283716 |  | 126153
2023-10-27 | October 2023 Review | Cash flow adjustment | Local road maintenance | Emergency works | Matamata-Piako District Council | EW - Matamata-Piako DC Jan - Feb 2023 | Construction | General District Tidy up | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Emergency works claiming for this activity is complete | -2 | -2 | [5 empty] | 284227 |  | 126154
2023-10-13 | October 2023 Review | Cash flow adjustment | Local road maintenance | Footpath maintenance | Central Otago District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Better aligning Waka Kotahi funding availability with Council budgets. Partially addressing the need for significantly more funding in w/c151. | -5080 | -2591 | [5 empty] | 272326 |  | 125934
2023-10-13 | October 2023 Review | Cash flow adjustment | Local road maintenance | Network and asset management | Central Otago District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Better aligning Waka Kotahi funding availability with Council budgets. Partially addressing the need for significantly more funding in w/c151. | 275321 | 140413 | [5 empty] | 272332 |  | 125934
2023-10-13 | October 2023 Review | Cash flow adjustment | Local road maintenance | Network service maintenance | Central Otago District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Better aligning Waka Kotahi funding availability with Council budgets. Partially addressing the need for significantly more funding in w/c151. | -61800 | -31518 | [5 empty] | 272329 |  | 125934
2023-10-26 | October 2023 Review | Cash flow adjustment | External funding | New activities influencing users of the transport system | NZ Transport Agency | CERF - Transport Choices Council Support Package (OPEX) | Implementation | TC Improve PT Reliability & Ease-of-Use PTS (OPEX) | VHHL | VHHVH | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update last year's spend | 0 | 0 |  |  |  | 1 | 60069863 | 283630 |  | 126198
2023-10-26 | October 2023 Review | Cash flow adjustment | External funding | New activities influencing users of the transport system | NZ Transport Agency | CERF - Transport Choices Council Support Package (OPEX) | Implementation | TC Improve PT Reliability & Ease-of-Use PTI (OPEX) | VHHL | VHHVH | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update 2022/23 spend | 0 | 0 |  |  |  | 1 | 60069864 | 283631 |  | 126199
2023-10-11 | October 2023 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (BOP) | TEL Tauranga Eastern Link | Implementation | Tolls Supplement | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Updating revised costs - TEL Profile for TIO upload, 10 Oct 2023.xlsx https://infohub.nzta.govt.nz/otcs/cs.dll/link/60354543) | 0 | 0 |  |  | 2 | 2 |  | 264839 |  | 126102
2023-10-04 | October 2023 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Canterbury) | Western Belfast By-Pass | Construction | Construction | H_M | M_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project close | 0 | 0 |  |  | 2.1 | 2.1 | 60212455 | 200182 | 60212455 | 126038
2023-10-26 | October 2023 Review | Cash flow adjustment | External funding | Passenger services - bus | NZ Transport Agency | CERF - Public Transport Initiatives (OPEX) | Implementation | Bus Driver Terms & Conditions | VHHVH | VHHVH | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow funds back to 2022/23 | 0 | 0 |  |  |  | 1 | 60069915 | 283544 |  | 126161
2023-10-20 | October 2023 Review | Cash flow adjustment | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM Early Delivery Thorndon Quay and Hutt Road | Single-Stage Business Case | Thorndon Quay and Hutt Road | VHHL | VHHH | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update 3rd party to match SAP-PPM | 0 | 0 |  |  | 1.2 | 1 |  | 282067 | 60067841 | 126165
2023-10-27 | October 2023 Review | Cash flow adjustment | State highway improvements | Replacement of bridges and other structures | NZTA (Northland) | SH10 Kaeo Bridge upgrade | Implementation | NLTF-SH Improvements | HHL | MHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reallocation of 1.8M of funding from Y1 to current FY | 0 | 0 |  |  | 0.6 | 0.6 | 60038592 | 269811 | 60038592 | 126119
2023-10-02 | October 2023 Review | Cash flow adjustment | State highway improvements | Replacement of bridges and other structures | NZTA (Otago) | Seismic Retrofit - Otago | Construction | Construction | M_PV_EoL | H_H | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  | 0 | 0 | 60218497 | 213605 | 60218497 | 125617
2023-10-13 | October 2023 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Canterbury) | SH73 West Melton to Yaldhurst | Pre-implementation* | SH73 West Melton to Yaldhurst | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | To transfer $2,404,833 allocation from CY to Y1 due to delay to push out the PS contract. | 1 | 1 |  |  | 2.1 | 2.1 | 353 | 277341 | 60061027 | 126099
2023-10-02 | October 2023 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Otago) | SH1 Oamaru to Dunedin - (Hampden to Palmerston) | Pre-implementation* |  | MHL | HHM | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project on hold transfer allocation into 2024/25 | 0 | 0 |  |  | 0 | 1.6 |  | 278560 | 60062303 | 125935
2023-10-13 | October 2023 Review | Cash flow adjustment | Local road maintenance | Sealed pavement maintenance | Central Otago District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Better aligning Waka Kotahi funding availability with Council budgets. Partially addressing the need for significantly more funding in w/c151. | -208441 | -106305 | [5 empty] | 272321 |  | 125934
2023-10-03 | October 2023 Review | Cash flow adjustment | Local road maintenance | Sealed pavement maintenance | Waitangi Trust | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | SPR |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reallocating the carry forward from 2022/23 from WC111 to WC212 of $193,331 | -193331 | -193331 | [5 empty] | 274613 |  | 125956
2023-10-03 | October 2023 Review | Cash flow adjustment | Local road maintenance | Sealed road resurfacing | Waitangi Trust | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | SPR |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reallocating the carry forward from 2022/23 from WC111 to WC212 of $193,331 | 193331 | 193331 | [5 empty] | 274626 |  | 125956
2023-10-26 | October 2023 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | NZ Transport Agency | Nationally Delivered Walking and Cycling activities 2021-24 | Implementation | National Walking and Cycling Activities Implementa | HHH | HHH | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | Reflect admin increase | 50388 | 50388 |  |  |  | 6.2 | 60070563 | 277937 |  | 126163
2023-10-13 | October 2023 Review | Cost Decrease | Local road maintenance | Drainage renewals | DOC (Canterbury) | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | SPR |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Declaring an expected underspend | -30000 | -15300 | [5 empty] | 274944 |  | 126095
2023-10-03 | October 2023 Review | Cost Increase | Local road maintenance | Drainage renewals | Kawerau District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Following a highly disruptive year 22/23 focus upon catching up in 23/24 is our priority. | 250000 | 187500 | [5 empty] | 272969 |  | 125882
2023-10-16 | October 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Auckland Transport | EW - AT Anniversary Weekend & Cyclone Gabrielle 2023 | Construction | E/W - Reinstatement @ 51% | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting reinstatement to normal FAR as discussed with Melissa/Natalie/Heather on 16/10/23 | -22205456 | -11324782 |  |  |  |  | 141.2838 | 283756 |  | 126087
2023-10-17 | October 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Auckland Transport | EW - AT Anniversary Weekend & Cyclone Gabrielle 2023 | Construction | E/W - Reinstatement @ 51% | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving funds to Higher FAR | -127436658 | -64992696 |  |  |  |  | 141.2838 | 283756 |  | 126140
2023-10-09 | October 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Mackenzie District Council | EW - Mackenzie DC July 2022 Flood Event | Construction | Subsequent Damage Recovery | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -15728 | -8021 |  |  |  |  | Subsequent Recovery costs | 283034 |  | 126085
2023-10-27 | October 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Matamata-Piako District Council | EW MPDC July 2022 (Tills Road Slip) | Construction | Tills Road slip repair | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Emergency works claiming for this activity is complete | -1181 | -602 | [5 empty] | 282219 |  | 126155
2023-10-03 | October 2023 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Northland) | EW Gabrielle Northland RW 20230213 | Construction |  | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | This application is for the recovery works and enabling works to give SH1 through the Brynderwyns to achieve a balanced level of risk, access reliability and cost within a 10 year view. Please note that CFO decision was made under urgency. The preparation work needed to start by 3 October in order to carry out the construction work early 2024. The Board was verbally informed about the urgency of this work at the IDC meeting on 27 September. | 16350000 | 16350000 | [5 empty] | 283659 | 60069832 | 125929
2023-10-10 | October 2023 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Taranaki) | EW Taranaki Region Wide HR 20201208 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | Project needs additional funding to allow it to close out. Iâ€™m content that this event fits within the current PIKB guidance for emergency works funding. I support the application, its within 9% of the project costs and I recommend approval. NC Recovery Manager | 125672 | 125672 |  |  |  |  | EW Taranaki Region Wide HR 20201208 | 275504 | 60060063 | 126023
2023-10-24 | October 2023 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Waikato) | EW Gabrielle Waikato RW 20230213 | Construction |  | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | This funding request is to cover the cost of the NOC and other suppliers for recovery to Cyclone Gabrielle and reinstatement of damaged assets - increasing the approved total cost from $18,700,000 to $40,500,000 ($21,800,000) | 21800000 | 21800000 | [5 empty] | 283660 | 60069839 | 125431
2023-10-27 | October 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Opotiki District Council | EW - ÅŒpÅtiki DC - May 2023 | Construction | Initial Response and permanent reinstatement | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | All works and claiming complete for this EW event | -5630 | -5349 | [5 empty] | 284391 |  | 126122
2023-10-27 | October 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Opotiki District Council | EW ÅŒpÅtiki DC October 2022 | Construction | Initial Response & Cleanup | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | All works and claiming complete for this EW event | -32174 | -24131 | [5 empty] | 283332 |  | 126123
2023-10-27 | October 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Otorohanga District Council | EW - Otorohanga DC Jan - Feb 2023 Events | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | All EW event works completed in 2022/23 FY, therefore claiming is complete. | -579 | -579 | [5 empty] | 283840 |  | 126112
2023-10-13 | October 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Wairoa District Council | EW: Emergency Works March 2022 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Phase completed - Surplus of WC141 funds being returned | -3328 | -3328 |  |  |  |  | Emergency Works March 2022_Response & Clean-Up_SPR38 | 281420 |  | 126071
2023-10-03 | October 2023 Review | Cost Increase | Local road maintenance | Footpath renewal | Kawerau District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Following a highly disruptive year 22/23 focus upon catching up in 23/24 is our priority. | 30000 | 22500 | [5 empty] | 272976 |  | 125882
2023-10-03 | October 2023 Review | Cost Decrease | Local road improvements | Low cost / low risk improvements | Far North District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Seal Extensions previously approved no longer stack up | -3000000 | -2070000 | [5 empty] | 276128 |  | 125931
2023-10-27 | October 2023 Review | Cost Decrease | Local road improvements | Low cost / low risk improvements | Far North District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | A review was completed in 2022/23, and some projects were Declined. | -840000 | -579600 | [5 empty] | 276128 |  | 126121
2023-10-10 | October 2023 Review | Cost Increase | Local road improvements | Low cost / low risk improvements | Hutt City Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | Estimates updated to tender price. Aligning program to actual costs. | 1104976 | 563538 | [5 empty] | 276184 |  | 125939
2023-10-03 | October 2023 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | Hutt City Council | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Revised financial program to match proposed physical delivery. | -4507976 | -2299068 | [5 empty] | 276187 |  | 125879
2023-10-10 | October 2023 Review | Cost Increase | Local road improvements | Low cost / low risk improvements | Kaipara District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Cost increase being requested to cover increase of engineers estimate/tender prices to resilience projects from the inflated marketplace. Inclusion of Logan and Gordon street footpath projects within LRI as advised by WK IA | 1010790 | 626690 | [5 empty] | 276201 |  | 125887
2023-10-03 | October 2023 Review | Cost Decrease | Road to Zero | Low cost / low risk improvements | Kaipara District Council | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | minor increase in programme from LTP forecast due to changes in speed management and actual costs being incurred in the inflated market. | -549588 | -340744 | [5 empty] | 276202 |  | 125888
2023-10-03 | October 2023 Review | Cost Decrease | Road to Zero | Low cost / low risk improvements | Kawerau District Council | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reduction in funding (surplus) requested due to RtZ delivery risk in 2023/24. | -150000 | -112500 | [5 empty] | 276212 |  | 125952
2023-10-27 | October 2023 Review | Cost Increase | Local road improvements | Low cost / low risk improvements | Manawatu District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Incorrect LCLR category utilised for decrease this should have been Walking and Cycling and not LRI | 1000000 | 510000 | [5 empty] | 276218 |  | 126179
2023-10-03 | October 2023 Review | Cost Decrease | Local road improvements | Low cost / low risk improvements | Manawatu District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | WC discussion undertaken to consolidate spending and programme capabilities resulting in change request. | -1000000 | -510000 | [5 empty] | 276218 |  | 125527
2023-10-27 | October 2023 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | Manawatu District Council | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Original surplus was taken from LRI and not Walking and cycling. This is submitted to correct the mistakes by MDC | -1000000 | -510000 | [5 empty] | 276219 |  | 126180
2023-10-03 | October 2023 Review | Cost Decrease | Road to Zero | Low cost / low risk improvements | Matamata-Piako District Council | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Re-prioritisation of improvement work programme with reduced local share to fund RtZ projects. | -400000 | -204000 | [5 empty] | 276240 |  | 125947
2023-10-10 | October 2023 Review | Cost Increase | Walking and cycling improvements | Low cost / low risk improvements | New Plymouth District Council | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Budget increase due to realignment of projects following resourcing review | 997122 | 508532 | [5 empty] | 276323 |  | 125524
2023-10-10 | October 2023 Review | Cost Increase | Local road improvements | Low cost / low risk improvements | Selwyn District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Cost increase approved to allow for the delivery of Trents Road Widening in Financial Year 23/24 - the project is to be coordinated with the Shands/Trents Roundabout project funded in 21-24 under Road to Zero. | 770000 | 392700 | [5 empty] | 276387 |  | 125404
2023-10-10 | October 2023 Review | Cost Increase | Local road improvements | Low cost / low risk improvements | Tasman District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Additional minor safety improvements now affordable for both parties. | 313255 | 159760 | [5 empty] | 276436 |  | 125944
2023-10-10 | October 2023 Review | Cost Increase | Local road improvements | Low cost / low risk improvements | Tasman District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Re-instating cost increase as approved by CFO. There are two increases approved for LCLR for Tasman. One of ID 276444 and for ID 276436 | 313255 | 159760 | [5 empty] | 276436 |  | 126091
2023-10-10 | October 2023 Review | Cost Decrease | Local road improvements | Low cost / low risk improvements | Tasman District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Incorrect review item actioned. Should have been TIO Id 276444 (W&C) and not 276436. | -313255 | -159760 | [5 empty] | 276436 |  | 126088
2023-10-10 | October 2023 Review | Cost Increase | Walking and cycling improvements | Low cost / low risk improvements | Tasman District Council | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Additional funding to progress a prioritised footpath improvement previously unaffordable. | 312910 | 159584 | [5 empty] | 276444 |  | 125444
2023-10-27 | October 2023 Review | Cost Decrease | Local road improvements | Low cost / low risk improvements | Waikato District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Specific projects scope has changed, Harrisville Road Bridge and Pokeno Road bridge projects require further funding applications to be made in next LTP. Work is continuing in terms of design. Ford St project not progressing. | -2425000 | -1236750 | [5 empty] | 276480 |  | 126139
2023-10-10 | October 2023 Review | Cost Increase | Road to Zero | Low cost / low risk improvements | Waimakariri District Council | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Cost increase approved to allow for the delivery of Island/Ohoka intersection upgrade project which will signalise and raise the approaches to the intersection that is just after the SH1 offramp. | 750000 | 382500 | [5 empty] | 276486 |  | 125899
2023-10-03 | October 2023 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | Waitangi Trust | Low cost / low risk improvements 2021-24 | Walking and cycling improvements (SPR) |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The LCLR capital programme for Tau Henare Drive â€“ Special Purpose Road was delayed during 2021-24 NLTP and has further been requested through the 2024-27 NLTP. The resurfacing programmed during 2021-24 on Tau Henare Drive will be completed in 2023/24, however this was also delayed from 2022/23. Consultation with the LCLR capital programme will commence with the Waitangi Trust early 2024 in preparation for delivery in the next NLTP. | -450000 | -450000 | [5 empty] | 276521 |  | 125762
2023-10-10 | October 2023 Review | Cost Increase | Local road improvements | Low cost / low risk improvements | Western BoP District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The value of LCLR funding approved in the 2021-24 NLTP was $14.22M (or 51%) of WBOPDC's $27.73M LCLR bid. Council claimed the approved LCLR value in the first two years of the NLTP period and has retained their local share of their LCLR bid amount. Any increase in NLTF share will enable more of the planned LCLR works and resilience projects resulting from 2022/23 rainfall events to be delivered. WBOPDC has a high level of confidence regarding delivering the LCLR work programme, based on good record of delivery. | 9399000 | 4793490 | [5 empty] | 276538 |  | 125767
2023-10-03 | October 2023 Review | Cost Decrease | Road to Zero | Low cost / low risk improvements | Western BoP District Council | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reduced programme to match likely achievement over the remaining timeframe. Still some uncertainly around the speed management plan and its adoption and resulting implementation costs. | -2007508 | -1023829 | [5 empty] | 276537 |  | 125889
2023-10-10 | October 2023 Review | Cost Increase | Walking and cycling improvements | Low cost / low risk improvements | Whakatane District Council | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | WhakatÄne DC's request for increased NLTF investment in W & C improvements for 2023/24 will allow continued delivery of their new and improved active mode transport facilities in and around WhakatÄne township. These facilities will provide greater transport choices with benefits associated with reduced on-road congestion and improved public health and well-being. Please refer to the link below for more detail. https://infohub.nzta.govt.nz/otcs/cs.dll/link/58867310 | 1003006 | 631894 | [5 empty] | 276550 |  | 125747
2023-10-10 | October 2023 Review | Cost Increase | Public transport infrastructure | Low cost / low risk public transport improvements | Hamilton City Council | Low cost / low risk improvements 2021-24 | Public transport infrastructure |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Include additional PT Infrastructure projects as per spreadsheet, discussed with Waka Kotahi Investment Advisor and Activity Class Managers. | 1500000 | 765000 | [5 empty] | 276150 |  | 125945
2023-10-03 | October 2023 Review | Cost Decrease | Public transport infrastructure | Low cost / low risk public transport improvements | Western BoP District Council | Low cost / low risk improvements 2021-24 | Public transport infrastructure |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Surplus declared to reflect reduction in public transport infrastructure programme planned for delivery during 2023/24. | -200000 | -102000 | [5 empty] | 276535 |  | 125890
2023-10-03 | October 2023 Review | Cost Increase | Local road maintenance | Minor events | Kawerau District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Following a highly disruptive year 22/23 focus upon catching up in 23/24 is our priority. | 13000 | 9750 | [5 empty] | 272961 |  | 125882
2023-10-03 | October 2023 Review | Cost Increase | Local road maintenance | Network and asset management | Kawerau District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Following a highly disruptive year 22/23 focus upon catching up in 23/24 is our priority. | 17350 | 13013 | [5 empty] | 272966 |  | 125882
2023-10-12 | October 2023 Review | Cost Increase | State highway maintenance | Network and asset management | NZ Transport Agency | Asset Management Data Standard- State Highways | Implementation | Nationally Delivered Activity AMDS Implementation | MMM | VHMM | N | 8 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Admin adjustment for 2022/23 | 43120 | 43120 |  |  |  | 4.4 | SAP Item 60067460 | 281639 |  | 126108
2023-10-12 | October 2023 Review | Cost Increase | Local road maintenance | Network and asset management | NZ Transport Agency | Asset Management Data Standard- State Highways | Implementation | Roll out of data standard- LR Maintenance | MMM | VHMM | N | 8 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Admin Adjustment for 2022-23. | 36039 | 36039 |  |  |  | 4.4 | LR Maintenance part of funding, SAP item 60067372 | 277727 |  | 126109
2023-10-12 | October 2023 Review | Cost Increase | State highway maintenance | Network and asset management | NZ Transport Agency | Integrated Delivery Model | Pre-implementation* |  | HHM | HHM | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | 6% admin to be included in total approval as approved by CFO. See attached approval doc. | 60000 | 60000 |  |  |  | 3 | 60073543 | 290244 |  | 126113
2023-10-03 | October 2023 Review | Cost Increase | Local road maintenance | Network service maintenance | Kawerau District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Following a highly disruptive year 22/23 focus upon catching up in 23/24 is our priority. | 50000 | 37500 | [5 empty] | 272963 |  | 125882
2023-10-03 | October 2023 Review | Cost Decrease | Local road improvements | New roads | Hastings District Council | Whakatu Arterial Link 2012/15 | Construction | Whakatu Arterial Link: Construction 2012/15 | H_M | H_H | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project completed | -34588 | -21099 |  |  | 4.5 | 4.5 | NLTP 12/15 | 218715 |  | 125923
2023-10-25 | October 2023 Review | Cost Increase | External funding | New roads | NZTA (Manawatu/Whanganui) | NZUP Otaki to North of Levin | Implementation | NZUP Otaki to North of Levin | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 3435222 | 3435222 |  |  | 1.4 | 1.4 | 60216690 | 268692 | 60216690 | 126192
2023-10-27 | October 2023 Review | Cost Decrease | State highway improvements | New roads | NZTA (Nelson) | Nelson Future Access | Detailed Business Case |  | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Remove admin as this was originally Crown funded and does not have admin added in SAP-PPM. | -1126 | -1126 |  |  | 2.2 | 2.2 |  | 284618 | 60032525 | 126164
2023-10-27 | October 2023 Review | Cost Decrease | Local road improvements | New traffic management facilities | Hurunui District Council | Johnston Street Level Crossing Improvements | Construction |  | H_L* | H_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Council declaring a surplus as this Kiwirail project has been delayed many times before and there is no confirmation on whether it will be progressing this NLTP period. | -55000 | -55000 |  |  | 0 | 1 |  | 263086 |  | 126117
2023-10-26 | October 2023 Review | Cost Increase | External funding | Passenger facilities and infrastructure improvements - bus | Auckland Transport | CERF-TC Auckland Transport Packages | Implementation | CERF-TC NorthWest Bus Improvement (Imp)_S1-4 | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | This is to include Schedule 2 for Te Atatu South, Hobson Street, Newton Road and Programme Management activities (as per attachment in Supporting Docs & InfoHub reference https://infohub.nzta.govt.nz/otcs/cs.dll/link/58878274). Approved schedule cost and CSA change costs have been checked and match ($6,415,982) | 6415982 | 6415982 |  |  |  | 0 | 561.284 | 283958 |  | 126167
2023-10-27 | October 2023 Review | Cost Decrease | Public transport services | Passenger services - bus | Gisborne District Council | Government reduced public transport fares scheme (Crown) | Implementation | Bus Services - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2023/24 as activity is claiming complete | -14364 | -14364 | [5 empty] | 281227 |  | 126160
2023-10-27 | October 2023 Review | Cost Decrease | Public transport services | Passenger services - ferry | Greater Wellington | Government reduced public transport fares scheme (Crown) | Implementation | Ferry Service - Reduced Fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2023/24 as activity is claiming complete | -37769 | -37769 | [5 empty] | 281232 |  | 126194
2023-10-13 | October 2023 Review | Cost Decrease | Investment management (incl. Transport Planning) | Programme Business Case Development | Hamilton City Council | Hamilton Waikato Metro Spatial Plan | Programme business case |  | V_L* | V_H | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2023/24 as activity is claiming complete | -132739 | -67697 | [5 empty] | 278093 |  | 126098
2023-10-27 | October 2023 Review | Cost Decrease | Investment management (incl. Transport Planning) | Programme Business Case Development | Hauraki District Council | Transportation Infrastructure Planning along Wharekawa Coast | Programme business case |  | HHH | HHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | PBC projected to come in under budget | -34983 | -20990 |  |  |  |  | Transportation Planning | 279917 |  | 126168
2023-10-30 | October 2023 Review | Cost Decrease | Investment management (incl. Transport Planning) | Programme Business Case Development | NZ Transport Agency | Innovation Programme | Programme business case |  | HHL | VHHM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -3140164 | -3140164 |  |  |  |  | 60069122 | 277975 |  | 126222
2023-10-05 | October 2023 Review | Cost Increase | External funding | Programme Business Case Development | Tauranga City Council | CERF-VKT Reduction Tauranga | Programme business case |  | VHHL | VHHL | N | 2 | Approved | Approved by Minister for Crown Appropriation | Costs are increased to support the agreed schedule of eligible activities, Schedule 2 in the Funding Agreement. | 1160000 | 1160000 | [5 empty] | 284332 |  | 126069
2023-10-05 | October 2023 Review | Cost Increase | External funding | Programme Business Case Development | Waikato Regional Council | CERF-VKT Reduction Waikato | Programme business case |  | VHHL | VHHL | N | 2 | Approved | Approved by Minister for Crown Appropriation | Costs are increased to support the agreed schedule of eligible activities, Schedule 2 in the Funding Agreement. | 1360000 | 1360000 | [5 empty] | 284492 |  | 126021
2023-10-25 | October 2023 Review | Cost Decrease | State highway improvements | Property purchase (State highways) | NZTA (Canterbury) | Weigh Right Rakaia | Property |  | H_VH | HHVH | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Inter-Programme Transfer: Please transfer $3,000 from 60047933 - Property to 60047923 - Property to cover the overspend in FY 2022/23 | -3181 | -3181 |  |  | 14 | 14 |  | 260276 | 60047933 | 126157
2023-10-25 | October 2023 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Manawatu/Whanganui) | Weigh Right Ohakea | Property |  | H__ | HHVH | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Inter-Programme Transfer: Please transfer $3,000 from 60047933 - Property to 60047923 - Property to cover the overspend in FY 2022/23 | 3180 | 3180 |  |  | 14 | 14 |  | 260278 | 60047923 | 126156
2023-10-13 | October 2023 Review | Cost Decrease | Local road maintenance | Rail level crossing warning devices maintenance | Wairoa District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Program changes as agreed with IA | -3500 | -2625 | [5 empty] | 274573 |  | 126072
2023-10-25 | October 2023 Review | Cost Increase | State highway improvements | Replacement of bridges and other structures | NZTA (Northland) | SH10 Taipa Bridge (No 272) upgrade | Implementation | NLTF-SH Improvements | M_L | MHL | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Costs to close out project | 391623 | 391623 |  |  | 0.6 | 0.6 | 60038612 | 278789 | 60038612 | 126120
2023-10-27 | October 2023 Review | Cost Decrease | State highway improvements | Resilience improvements | NZTA (West Coast) | ENR Epitaph Resilience Improvement | Implementation |  | HMH | HHH | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | To surplus $83,890 and close project | -91440 | -91440 |  |  |  |  | 60042618 | 249593 | 60042618 | 126026
2023-10-03 | October 2023 Review | Cost Decrease | Local road improvements | Road improvements | Ashburton District Council | Ashburton Tinwald Connectivity | Detailed Business Case | Detailed Business Case | VHML | VHHM | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Detailed Business Case completed in 2022/23. | -544072 | -277477 |  |  |  | 1.2 | Detailed Business Case | 264996 |  | 125957
2023-10-03 | October 2023 Review | Cost Increase | Local road improvements | Road improvements | Christchurch City Council | AAC High Street (Cashel to Tuam) | Construction |  | H_L | HHH | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This change is due to additional cost to replace a damaged seat and install additional cycle stands. This is a cost increase but within $50k write off. No more increase will be alllowed in future without a formal application. | 47417 | 24183 |  |  | 2.9 | 2.9 |  | 233357 |  | 125958
2023-10-18 | October 2023 Review | Cost Decrease | Local road improvements | Road improvements | Horowhenua District Council | LED Street Lights Renewals | Construction | LED Renewals | M_H | M_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Activity completed years ago. | -2224 | -1334 |  |  | 5 | 5 | LED Renewals | 240094 |  | 126145
2023-10-27 | October 2023 Review | Cost Decrease | Local road improvements | Road improvements | Mackenzie District Council | LED Street Lighting accelerated renewals | Construction | Construction Rev 1 Led Implementation | H_H | M_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project complete - Council has declared a surplus. | -94268 | -48077 |  |  | 0 | 0 |  | 262898 |  | 126141
2023-10-13 | October 2023 Review | Cost Decrease | Road to Zero | Road improvements | NZ Transport Agency | National Speed Limit Register | Implementation | WBS 80002656 (R2Z) | VHHVL | VHHVL | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2023/24 as activity is claiming complete | -1059148 | -1059148 |  |  | 1 | 99 |  | 279937 |  | 126094
2023-10-26 | October 2023 Review | Cost Increase | Road to Zero | Road improvements | NZ Transport Agency | Road to Zero System Management | Implementation | RtZ System Management | VHHL | MHH | N | 2 | Approved | Approved by Auckland Transport Chief Financial Officer | CF approved admin increase. | 111621 | 111621 |  |  | 8 | 8 | SAP Item ID 60067001 | 277093 |  | 126159
2023-10-25 | October 2023 Review | Cost Increase | External funding | Road improvements | NZTA (Auckland) | NZUP Mill Road Corridor | Implementation | Mill Road Corridor NZUP | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 1059702 | 1059702 |  |  | 1.2 | 1.2 | NZ Upgrade Programme | 269744 | 60056119 | 126188
2023-10-31 | October 2023 Review | Cost Increase | External funding | Road improvements | NZTA (Auckland) | NZUP Penlink | Implementation |  | H_L | HML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 59600 | 59600 |  |  | 13.4 | 7.8 |  | 278976 | 60063233 | 126307
2023-10-10 | October 2023 Review | Cost Increase | External funding | Road improvements | NZTA (Auckland) | NZUP SH22 Paeraataa Roundabout (funded by KiwiRail) | Pre-implementation* | Totally funded by KiwiRail | MMM | MMM | N | 8 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Align SAP and TIO. This project is fully Kiwi Rail funded + 4% admin charged by Waka Kotahi as per agreement. | 390645 | 390645 |  |  | 3.9 | 2.8 |  | 282213 | 60068075 | 126093
2023-10-09 | October 2023 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Auckland) | Supporting Growth Auckland | Pre-implementation* | Supporting Growth Alliance - SH Post Lodgement | H_M | HHM | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | PLA submitted and approved for increase on costs of $5,995,000 inc admin ($5,500,000 to complete phase). | 5995000 | 5995000 |  |  | 1.6 | 1.6 | SH Post Lodgement | 267282 | 60053072 | 126081
2023-10-13 | October 2023 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Canterbury) | Kaikoura Nov 2016 EQ: Lewis Pass Altern Upg Rout - Canterbur | Implementation | Implementation | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Surplus $1,537 and close project | -1675 | -1675 |  |  | 1.4 | 1.4 | 60042759 | 253319 | 60042759 | 126027
2023-10-25 | October 2023 Review | Cost Increase | External funding | Road improvements | NZTA (Canterbury) | NZUP Brougham St Corridor Improvements | Implementation | NZUP Brougham St Corridor Improvements | H_L | HMM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 182488 | 182488 |  |  | 4 | 4 | 60056968 | 231610 | 60056968 | 126189
2023-10-13 | October 2023 Review | Cost Decrease | External funding | Road improvements | NZTA (Canterbury) | NZUP SH1 Tinwald Corridor Improvements | Implementation | NZUP Tinwald Corridor Improvements | VHHL | MMM | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $361,410 from Imp (60057077) to PreImp (60057074) to cover overspend in Preimp | -375868 | -375868 |  |  | 4.6 | 4.6 | 60057077 | 238976 | 60057077 | 126105
2023-10-25 | October 2023 Review | Cost Increase | External funding | Road improvements | NZTA (Canterbury) | NZUP SH1 Tinwald Corridor Improvements | Implementation |  | VHHL | MMM | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 3250 | 3250 |  |  | 4.6 | 4.6 |  | 278980 | 60063227 | 126190
2023-10-13 | October 2023 Review | Cost Increase | External funding | Road improvements | NZTA (Canterbury) | NZUP SH1 Tinwald Corridor Improvements | Pre-implementation* | NZ Upgrade Programme | VHHL | MMM | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $361,410 from Imp (60057077) to PreImp (60057074) to cover overspend in Preimp | 375866 | 375866 |  |  | 4.6 | 4.6 | 60057074 | 238975 | 60057074 | 126104
2023-10-25 | October 2023 Review | Cost Increase | External funding | Road improvements | NZTA (Canterbury) | NZUP SH75 Halswell Rd Imps | Implementation | NZUP SH75 Halswell Rd Imps | H_L | HML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 90665 | 90665 |  |  | 2 | 2 | 60031611 | 231955 | 60031611 | 126191
2023-10-02 | October 2023 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Otago) | Visiting Driver Signature Project Otago | Implementation | Implementation | M_H | M_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Surplus $80k | -87200 | -87200 |  |  | 6.9 | 6.9 | 60029890 | 233468 | 60029890 | 126024
2023-10-25 | October 2023 Review | Cost Increase | External funding | Road improvements | NZTA (Wellington) | NZUP SH2 Melling Efficiency & Safety Imp | Implementation |  | HMM | MMH | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 179500 | 179500 |  |  | 0 | 1.3 |  | 278984 | 60063250 | 126193
2023-10-25 | October 2023 Review | Cost Increase | External funding | Road improvements | NZTA (Wellington) | NZUP SH58 Safety Improvements - Stage 2 | Implementation |  | H_M | HML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 74750 | 74750 |  |  | 0 | 0 |  | 278979 | 60063239 | 126187
2023-10-09 | October 2023 Review | Cost Increase | Local road improvements | Road improvements | Selwyn District Council | LED Upgrade | Implementation | LED Upgrade | M_H | H_L | N | 0 | Approved | Approved by Chief Financial Officer (CFO) |  | 1600000 | 816000 |  |  | 0 | 0 |  | 251036 |  | 125782
2023-10-27 | October 2023 Review | Cost Decrease | Road to Zero | Road improvements | Waikato District Council | gordonton road corridor safety improvements (r2z) | Implementation | construction | VHHL | HHH | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | reduction in costs from original estimates. New revised total, remaining works to be completed this FY | -1000000 | -510000 |  |  |  | 5 | installation and construction | 277682 |  | 126138
2023-10-13 | October 2023 Review | Cost Decrease | Local road maintenance | Sealed pavement maintenance | DOC (Canterbury) | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | SPR |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Declaring an expected underspend | -600000 | -306000 | [5 empty] | 274930 |  | 126095
2023-10-03 | October 2023 Review | Cost Decrease | Local road maintenance | Sealed pavement maintenance | Kawerau District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Following a highly disruptive year 22/23 focus upon catching up in 23/24 is our priority. | -701344 | -526008 | [5 empty] | 272955 |  | 125882
2023-10-03 | October 2023 Review | Cost Increase | Local road maintenance | Sealed road pavement rehabilitation | Kawerau District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Following a highly disruptive year 22/23 focus upon catching up in 23/24 is our priority. | 70000 | 52500 | [5 empty] | 272970 |  | 125882
2023-10-13 | October 2023 Review | Cost Decrease | Local road maintenance | Sealed road pavement rehabilitation | Wairoa District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Program changes as agreed with IA | -305000 | -228750 | [5 empty] | 274578 |  | 126072
2023-10-13 | October 2023 Review | Cost Decrease | Local road maintenance | Sealed road resurfacing | DOC (Canterbury) | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | SPR |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Declaring an expected underspend | -320000 | -163200 | [5 empty] | 274943 |  | 126095
2023-10-03 | October 2023 Review | Cost Increase | Local road maintenance | Sealed road resurfacing | Kawerau District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Following a highly disruptive year 22/23 focus upon catching up in 23/24 is our priority. | 130000 | 97500 | [5 empty] | 272968 |  | 125882
2023-10-13 | October 2023 Review | Cost Increase | Local road maintenance | Sealed road resurfacing | Wairoa District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Program changes as agreed with IA | 305000 | 228750 | [5 empty] | 274576 |  | 126072
2023-10-05 | October 2023 Review | Cost Increase | External funding | SuperGold trip payments | Auckland Transport | SuperGold Card Allocation | Construction | SuperGold Card Exempt Services | M_M | LHL | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2023/24 | 2470029 | 2470029 |  |  | 0 | 0 | 522.9005 | 217751 |  | 126050
2023-10-05 | October 2023 Review | Cost Increase | External funding | SuperGold trip payments | Auckland Transport | SuperGold Card Allocation | Construction | SuperGold Card contracted services - bus | M_M | LHL | N | 0 | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2023/24 | 12886873 | 12886873 |  |  | 0 | 0 | 522.9015 | 251616 |  | 126047
2023-10-05 | October 2023 Review | Cost Increase | External funding | SuperGold trip payments | Auckland Transport | SuperGold Card Allocation | Construction | SuperGold Card contracted services - ferry | M_M | LHL | N | 0 | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2023/24 | 1062527 | 1062527 |  |  | 0 | 0 | 522.9025 | 264916 |  | 126049
2023-10-05 | October 2023 Review | Cost Increase | External funding | SuperGold trip payments | Auckland Transport | SuperGold Card Allocation | Construction | SuperGold Card contracted services - rail | M_M | LHL | N | 0 | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2023/24 | 2658851 | 2658851 |  |  | 0 | 0 | 522.9035 | 264917 |  | 126048
2023-10-05 | October 2023 Review | Cost Increase | External funding | SuperGold trip payments | Bay of Plenty Regional Council | SuperGold Card Allocation | Construction | SuperGold Card contracted services - bus | L__ | L_L | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2023/24. | 1020585 | 1020585 |  |  |  | 0 | Supergold | 220569 |  | 126059
2023-10-05 | October 2023 Review | Cost Increase | External funding | SuperGold trip payments | Environment Canterbury | SuperGold Card Allocations | Construction | SuperGold Card contracted services - ferry | M__ | M_M | N | 0 | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2023/24 | 74026 | 74026 |  |  | 0 | 0 |  | 264915 |  | 126056
2023-10-05 | October 2023 Review | Cost Increase | External funding | SuperGold trip payments | Environment Canterbury | SuperGold Card Allocations | Implementation | SuperGold Card contracted services - bus | M__ | M_M | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2023/24 | 3504699 | 3504699 |  |  | 0 | 0 |  | 221849 |  | 126055
2023-10-05 | October 2023 Review | Cost Increase | External funding | SuperGold trip payments | Gisborne District Council | SuperGold Card Allocations | Implementation | SuperGold Card contracted services - bus | H__ | M_M | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2023/24. | 35737 | 35737 |  |  |  | 0 |  | 221845 |  | 126067
2023-10-05 | October 2023 Review | Cost Increase | External funding | SuperGold trip payments | Greater Wellington | SuperGold Card Allocations | Construction | SuperGold Card contracted service - ferry | M_L | H_M | N | 0 | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2023/24 | 87394 | 87394 |  |  | 0 | 0 |  | 264913 |  | 126053
2023-10-05 | October 2023 Review | Cost Increase | External funding | SuperGold trip payments | Greater Wellington | SuperGold Card Allocations | Construction | SuperGold Card contracted service - rail | M_L | H_M | N | 0 | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2023/24 | 2748991 | 2748991 |  |  | 0 | 0 |  | 264914 |  | 126052
2023-10-05 | October 2023 Review | Cost Increase | External funding | SuperGold trip payments | Greater Wellington | SuperGold Card Allocations | Construction | SuperGold Card contracted services - bus | M_L | H_M | N | 0 | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2023/24 | 5871228 | 5871228 |  |  | 0 | 0 |  | 251617 |  | 126051
2023-10-05 | October 2023 Review | Cost Increase | External funding | SuperGold trip payments | Greater Wellington | SuperGold Card Allocations | Implementation | SuperGold Card Exempt services | M_L | H_M | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2023/24 | 108850 | 108850 |  |  | 0 | 0 |  | 221846 |  | 126054
2023-10-05 | October 2023 Review | Cost Increase | External funding | SuperGold trip payments | Hawkes Bay Regional Council | SuperGold Card Allocations | Implementation | SuperGold Card contracted services - bus | M__ | M_M | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2023/24. | 259960 | 259960 |  |  |  | 0 |  | 220130 |  | 126062
2023-10-05 | October 2023 Review | Cost Increase | External funding | SuperGold trip payments | Horizons Manawatu | SuperGold Card Allocation | Implementation | SuperGold Card contracted services - bus | M_M | H_H | N |  | Approved | Approved by Minister for Crown Appropriation |  | 288364 | 288364 |  |  |  | 0 |  | 218548 |  | 126060
2023-10-05 | October 2023 Review | Cost Increase | External funding | SuperGold trip payments | Invercargill City Council | SuperGold Card Allocations | Implementation | SuperGold Card contracted services - bus | M__ | M_M | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2023/24. | 68330 | 68330 |  |  |  | 0 |  | 221850 |  | 126066
2023-10-05 | October 2023 Review | Cost Increase | External funding | SuperGold trip payments | Marlborough District Council | SuperGold Card Allocations | Implementation | SuperGold Card contracted services - bus | M__ | M_M | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2023/24. | 35599 | 35599 |  |  |  | 0 |  | 221848 |  | 126068
2023-10-05 | October 2023 Review | Cost Increase | External funding | SuperGold trip payments | Nelson City Council | SuperGold Card Allocations | Implementation | SuperGold Card contracted services - bus | M__ | H_H | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2023/24. | 177197 | 177197 |  |  |  | 0 |  | 221847 |  | 126065
2023-10-05 | October 2023 Review | Cost Increase | External funding | SuperGold trip payments | Northland Regional Council | SuperGold Card Allocations | Implementation | SuperGold Card contracted services - bus | M__ | M_M | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2023/24. | 17296 | 17296 |  |  |  | 0 |  | 221852 |  | 126064
2023-10-05 | October 2023 Review | Cost Increase | External funding | SuperGold trip payments | Otago Regional Council | SuperGold Card Allocation | Construction | SuperGold Card contracted services - bus | H__ | H__ | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2023/24 | 1142088 | 1142088 |  |  | 1 | 0 | SGC | 218695 |  | 126057
2023-10-05 | October 2023 Review | Cost Increase | External funding | SuperGold trip payments | Taranaki Regional Council | SuperGold Card Allocations | Construction | SuperGold Card contracted services - bus | M__ | H_H | N |  | Approved | Approved by Minister for Crown Appropriation |  | 60028 | 60028 |  |  |  | 0 | SGC Taranaki 2012/15 | 215365 |  | 126063
2023-10-05 | October 2023 Review | Cost Increase | External funding | SuperGold trip payments | Waikato Regional Council | SuperGold Card Allocation | Construction | SuperGold Card contracted services - bus | M__ | LML | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2023/24 | 1025056 | 1025056 |  |  | 0 | 0 | Supergold | 215358 |  | 126058
2023-10-06 | October 2023 Review | Cost Decrease | Public transport services | SuperGold trip payments | Waikato Regional Council | SuperGold Card Allocation | Implementation | SuperGold Card contracted services â€“ rail- contrac | M__ | LML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -857 | -857 |  |  | 0 | 0 | 522 | 290215 |  | 126078
2023-10-15 | October 2023 Review | Cost Increase | Public transport services | Total mobility operations | West Coast Regional Council | Public Transport Programme 2021-24 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) |  | 99042 | 59426 | [5 empty] | 274690 |  | 125763
2023-10-03 | October 2023 Review | Cost Decrease | Local road maintenance | Traffic services renewals | Kawerau District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Following a highly disruptive year 22/23 focus upon catching up in 23/24 is our priority. | -20000 | -15000 | [5 empty] | 272974 |  | 125882