## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Phase Label | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Decision Status | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR | Your Phase reference | TIO Phase id | SAP item id | TIO Request id
2023-11-27 | November 2023 Review | New approval | Walking and cycling improvements | Cycling facilities | Dunedin City Council | SFDT - Central Cycle and Pedestrian improvements | Implementation | Albany Street Connection | VHHL | VHHM | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | Improvements include new separated cycling facility, reduction in posted speed limit, on-street parking rationalisation and street and intersection improvements to reduce conflicts between vehicles and vulnerable road users. The route will be a key east-west connection, connecting existing SH1 facilities to the recently completed Harbour Link, and traversing the perimeter of the Tertiary Precinct, which has the highest active mode share in the city. | 3486325 | 1778026 |  |  | 3.9 |  |  | 289300 |  | 126214
2023-11-27 | November 2023 Review | New approval | External funding | Cycling facilities | Nelson City Council | CERF-TC Nelson Cross Town links | Implementation | Maitai Path | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | CERF Activity | 385000 | 385000 |  |  |  | 0 |  | 283990 |  | 122731
2023-11-08 | November 2023 Review | New approval | External funding | Cycling facilities | Tasman District Council | CERF TC - Motueka cycleways and slow streets | Implementation | Construction | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | Consistent with agreed schedule 2 | 3534249 | 3060866 |  |  |  | 0 | Motueka Transport Choices Stage 1 | 289667 |  | 125960
2023-11-30 | November 2023 Review | New approval | Local road maintenance | Emergency works | Gisborne District Council | EW Tiniroto Road Landslide | Construction | EW Tiniroto Road Landslide | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | Initial response and Recovery works for Tiniroto Road slip as permitted under WC141 | 1143274 | 904905 |  |  |  |  | 485271.12 | 290565 |  | 126455
2023-11-24 | November 2023 Review | New approval | Local road maintenance | Emergency works | Rangitikei District Council | EW - November 2022 | Construction | Recover phase for Nov 2022 (Normal + 20%) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving funds from normal FAR to higher FAR (Normal +20%) as per NZTA EW FAR policy. | 197825 | 164195 | [5 empty] | 290607 |  | 126498
2023-11-13 | November 2023 Review | New approval | Local road maintenance | Emergency works | Rotorua Lakes Council | EW - Rotorua LC Storm Damage Sep 2023 | Construction | Phase 1 - Initial response and clean up | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | That the Regional Manager, Maintenance & Operations, Transport Services: â€¢ Approves emergency works funding to Rotorua District Council â€¢ for the EW - Rotorua LC Storm Damage Sep 2023 â€¢ at a cost of $280,000 (including 0% admin) â€¢ at a funding assistance rate of 76% ($212,800 out of the NLTF) â€¢ for phase 290482 â€¢ from activity class 8, work category 141. | 280000 | 212800 | [5 empty] | 290482 |  | 126366
2023-11-21 | November 2023 Review | New approval | Local road maintenance | Emergency works | Whanganui District Council | Cyclone Dovi - 13 February 2022 Emergency Works | Construction | C- Major Repairs Normal FAR | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Funds moved from existing phase and FAR set to Normal FAR (60%), remaining approved funds will be set to Higher FAR | 1301204 | 780722 | [5 empty] | 290579 |  | 126466
2023-11-23 | November 2023 Review | New approval | State highway improvements | New traffic management facilities | NZTA (Auckland) | NZUP Penlink | Implementation | Toll Infrastructure | H_L | HML | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | This investment enables tolling infrastructure installation on Penlink at a total phase cost of $25.4 million identified for tolls. One pager Funding Decision Report to inform the Waka Kotahi Board that CFO has approved funding for the scheme from the NLTF | 25432226 | 25432226 |  |  | 13.4 | 7.8 | Toll Infrastructure | 290380 | 60073640 | 126182
2023-11-30 | November 2023 Review | New approval | External funding | Operations & maintenance of real-time and ticketing systems | Far North District Council | CERF-CC Community Connect Scheme | Implementation | Community Connect - Admin | MHL | MHL | N | 7 | Approved | Approved by Minister for Crown Appropriation | The activity is a Crown-funded initiative. | 1000 | 1000 | [5 empty] | 289024 |  | 125806
2023-11-02 | November 2023 Review | New approval | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | Auckland Transport | Auckland Bus Depot and Stabling | Indicative Business Case | Auckland Bus Depot and Stabling | HHL | MHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | This investment enables Auckland Transport to investigate and consider viable options for the ownership and management of its bus depots and strategic assets in the future | 477976 | 243768 |  |  |  |  | 561.2893 | 289258 |  | 126020
2023-11-13 | November 2023 Review | New approval | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | Auckland Transport | Bus Improvements - Wellesley Street | Implementation | Mid-City Block Stage 1 - Imp | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) |  | 26699000 | 13616490 |  |  | 0 | 1.6 | 561.2778 | 277777 |  | 126152
2023-11-17 | November 2023 Review | New approval | External funding | Passenger facilities and infrastructure improvements - bus | Horizons Manawatu | CERF-TC - Horizons Palmerston North & Whanganui | Implementation | Horizons Palmerston North PT Improvements | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | Recommend total implementation funding of $1,706,000 as it aligns with the Crown funded CERF TC PBC and approval has been confirmed by CERF-TC programme team. The total funding also includes 10% savings as requested by Waka Kotahi. | 1706000 | 1535400 |  |  | 0 | 0 |  | 283909 |  | 122341
2023-11-27 | November 2023 Review | New approval | External funding | Passenger facilities and infrastructure improvements - bus | Nelson City Council | CERF-TC Nelson Cross Town links | Implementation | PT Upgrades | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | CERF Activity | 664807 | 664807 |  |  |  | 0 | PT Launch and Improvement Works | 290515 |  | 126518
2023-11-27 | November 2023 Review | New approval | External funding | Passenger facilities and infrastructure improvements - bus | Nelson City Council | CERF-TC Nelson Cross Town links | Implementation | Bridge Street interim bus hub | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | CERF Activity | 88000 | 88000 |  |  |  | 0 | 3778 | 284151 |  | 122732
2023-11-29 | November 2023 Review | New approval | External funding | Passenger facilities and infrastructure improvements - bus | Nelson City Council | CERF-TC Nelson Cross Town links | Pre-implementation* | pre-implementation | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | CERF activity | 493578 | 493578 |  |  |  | 0 |  | 283989 |  | 122730
2023-11-07 | November 2023 Review | New approval | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | Tauranga City Council | Park and Ride - Papamoa | Single-Stage Business Case | SSBC Lite | VHML | VHHH | N | 3 | Approved | Approved by Chief Financial Officer (CFO) | This investment progresses planning for a park and ride and associated express Public Transport services that offer more mode choice into the CBD | 181950 | 92795 |  |  | 2.7 | 2.7 | DBC | 276602 |  | 125943
2023-11-07 | November 2023 Review | New approval | Public transport services | Passenger services - bus | Taranaki Regional Council | Public Transport Review | Single-Stage Business Case |  | HHH | HHVH | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | This investment has a good alignment with GPS Strategic Priorities with the primary outcome is to provide better travel options | 120000 | 61200 | [5 empty] | 289394 |  | 125938
2023-11-03 | November 2023 Review | New approval | External funding | Passenger services - bus | Tasman District Council | CERF-Bus Driver Ts & Cs | Implementation | CERF - Driver Wage Uplift | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Crown allocation approved by National Manager Multimodal and Innovation | 145645 | 145645 |  |  |  | 1 |  | 289286 |  | 125928
2023-11-30 | November 2023 Review | New approval | External funding | Passenger services - ferry | Far North District Council | CERF-CC Community Connect Scheme | Implementation | Community Connect Ferry Concessions | MHL | MHL | N | 7 | Approved | Approved by Minister for Crown Appropriation | No IER has been completed. The activity is a Crown-funded initiative. | 10000 | 10000 | [5 empty] | 288531 |  | 125584
2023-11-24 | November 2023 Review | New approval | Investment management (incl. Transport Planning) | Programme Business Case Development | NZ Transport Agency | Land Transport Security Programme | Programme business case |  | VHHM | VHHH | N | 1 | Approved | Approved by Chief Financial Officer (CFO) |  | 1850000 | 1850000 | [5 empty] | 290369 |  | 126400
2023-11-24 | November 2023 Review | New approval | Road to Zero | Property purchase (local roads) | Selwyn District Council | Prebbleton Arterial CSM Related Upgrade Packages | Property | Shands/Trents Roundabout | HML | HML | N | 6 | Approved | Approved by Chief Financial Officer (CFO) |  | 2804751 | 1430423 |  |  | 1 | 1 |  | 290357 |  | 126144
2023-11-17 | November 2023 Review | New approval | External funding | Resilience improvements | NZ Transport Agency | Crown Resilience Programme Management | Implementation | 60071697 Crown Resilience Programme | HHM | VHHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | Project list in BRI-2843 as part of the agreed investment programme for the 2023/24 appropriation. | 37559667 | 37559667 |  |  |  | 4 | SAP Initiative: 162602023; SAP Item: 60071697 | 288961 |  | 126454
2023-11-16 | November 2023 Review | New approval | External funding | Resilience improvements | NZTA (Auckland) | Crown Resilience Programme LCLR AKL | Implementation | LCLR | VH_H | VHHH | N | 0 | Approved | Approved by Minister for Crown Appropriation | Project list in BRI-2843 as part of the agreed investment programme for the 2023/24 appropriation. | 7060000 | 7060000 |  |  |  | 4 |  | 288941 | 60071706 | 126200
2023-11-16 | November 2023 Review | New approval | External funding | Resilience improvements | NZTA (BOP) | Crown Resilience Programme LCLR BOP | Implementation |  | VH_H | VHHH | N | 0 | Approved | Approved by Minister for Crown Appropriation | Project list in BRI-2843 as part of the agreed investment programme for the 2023/24 appropriation. | 3823350 | 3823350 |  |  |  | 4 |  | 288942 | 60071720 | 126201
2023-11-16 | November 2023 Review | New approval | External funding | Resilience improvements | NZTA (Canterbury) | Crown Resilience Programme LCLR CAN | Implementation |  | VHHVH | VHHH | N | 1 | Approved | Approved by Minister for Crown Appropriation | Project list in BRI-2843 as part of the agreed investment programme for the 2023/24 appropriation. | 3381376 | 3381376 |  |  |  | 4 |  | 290389 | 60071724 | 126202
2023-11-16 | November 2023 Review | New approval | External funding | Resilience improvements | NZTA (Manawatu/Whanganui) | Crown Resilience Programme LCLR MNWI | Implementation |  | VH_H | VHHH | N | 0 | Approved | Approved by Minister for Crown Appropriation | Project list in BRI-2843 as part of the agreed investment programme for the 2023/24 appropriation. | 1651308 | 1651308 |  |  |  | 4 |  | 288944 | 60071731 | 126204
2023-11-16 | November 2023 Review | New approval | External funding | Resilience improvements | NZTA (Marlborough) | Crown Resilience Programme LCLR MARL | Implementation |  | VH_H | VHHH | N | 0 | Approved | Approved by Minister for Crown Appropriation | Project list in BRI-2843 as part of the agreed investment programme for the 2023/24 appropriation. | 4260000 | 4260000 |  |  |  | 4 |  | 288947 | 60071751 | 126203
2023-11-16 | November 2023 Review | New approval | State highway improvements | Resilience improvements | NZTA (Marlborough) | SH1 Tuamarina to Picton Flooding | Single-Stage Business Case | SSBC | VH_L | VHHL | N | 0 | Approved | Approved by Minister for Crown Appropriation | Project list in BRI-2843 as part of the agreed investment programme for the 2023/24 appropriation. | 54500 | 54500 |  |  |  | 2 | SSBC | 288497 | 60071590 | 126264
2023-11-17 | November 2023 Review | New approval | External funding | Resilience improvements | NZTA (Marlborough) | SH1 Weld Pass long term detour route | Single-Stage Business Case |  | VH_L | VHHL | N | 0 | Approved | Approved by Minister for Crown Appropriation | Project list in BRI-2843 as part of the agreed investment programme for the 2023/24 appropriation. | 53250 | 53250 |  |  | 1 | 1 |  | 290506 | 60071599 | 126449
2023-11-16 | November 2023 Review | New approval | External funding | Resilience improvements | NZTA (Northland) | Crown Resilience Programme LCLR NTLD | Implementation |  | VH_H | VHHH | N | 0 | Approved | Approved by Minister for Crown Appropriation | Project list in BRI-2843 as part of the agreed investment programme for the 2023/24 appropriation. | 4899000 | 4899000 |  |  |  | 4 |  | 288945 | 60071735 | 126205
2023-11-17 | November 2023 Review | New approval | External funding | Resilience improvements | NZTA (Northland) | NTLD Subsidence Strategy Implementation | Implementation |  | VH_L | VHHL | N | 0 | Approved | Approved by Minister for Crown Appropriation | Project list in BRI-2843 as part of the agreed investment programme for the 2023/24 appropriation. | 24495000 | 24495000 |  |  |  | 2 |  | 288493 | 60071577 | 126274
2023-11-16 | November 2023 Review | New approval | External funding | Resilience improvements | NZTA (Northland) | SH1 Schiska Rd Underslip | Implementation |  | VHHVH | VHHL | N | 1 | Approved | Approved by Minister for Crown Appropriation | Project list in BRI-2843 as part of the agreed investment programme for the 2023/24 appropriation. | 2130000 | 2130000 |  |  |  | 2 |  | 288492 | 60071573 | 126448
2023-11-16 | November 2023 Review | New approval | External funding | Resilience improvements | NZTA (Northland) | SH1 Schiska Rd Underslip | Single-Stage Business Case | SSBC | VHHVH | VHHL | N | 1 | Approved | Approved by Minister for Crown Appropriation | Project list in BRI-2843 as part of the agreed investment programme for the 2023/24 appropriation. | 372750 | 372750 |  |  |  | 2 | SSBC | 288491 | 60071572 | 126265
2023-11-16 | November 2023 Review | New approval | External funding | Resilience improvements | NZTA (Otago) | Crown Resilience Programme LCLR OTA | Implementation |  | VH_H | VHHH | N | 0 | Approved | Approved by Minister for Crown Appropriation | Project list in BRI-2843 as part of the agreed investment programme for the 2023/24 appropriation | 3354750 | 3354750 |  |  |  | 4 |  | 290381 | 60071739 | 126206
2023-11-30 | November 2023 Review | New approval | External funding | Resilience improvements | NZTA (Otago) | RIO SH01S Kakanui Rvr Flood Mitigation | Pre-implementation* | Design | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Not a new project but moving funds from activity ID 132976, phase Id 269725. Moving because it is now a mixture of funding from RIO and Crown Resilience (TRF) which old template can not accommodate. | -16895 | -16895 |  |  | 1 | 1 |  | 290580 |  | 126487
2023-11-16 | November 2023 Review | New approval | External funding | Resilience improvements | NZTA (Southland) | Crown Resilience Programme LCLR STLD | Implementation |  | VH_H | VHHH | N | 0 | Approved | Approved by Minister for Crown Appropriation | Project list in BRI-2843 as part of the agreed investment programme for the 2023/24 appropriation. | 3642300 | 3642300 |  |  |  | 4 |  | 290382 | 60071743 | 126212
2023-11-16 | November 2023 Review | New approval | External funding | Resilience improvements | NZTA (Taranaki) | Crown Resilience Programme LCLR TAR | Implementation |  | VH_H | VHHH | N | 0 | Approved | Approved by Minister for Crown Appropriation | Project list in BRI-2843 as part of the agreed investment programme for the 2023/24 appropriation. | 1544251 | 1544251 |  |  |  | 4 |  | 288960 | 60071747 | 126446
2023-11-17 | November 2023 Review | New approval | External funding | Resilience improvements | NZTA (Tasman) | Crown Resilience Programme LCLR TAS | Implementation |  | VH_H | VHHH | N | 0 | Approved | Approved by Minister for Crown Appropriation | Project list in BRI-2843 as part of the agreed investment programme for the 2023/24 appropriation. | 4792500 | 4792500 |  |  |  | 4 |  | 288948 | 60071755 | 126445
2023-11-17 | November 2023 Review | New approval | External funding | Resilience improvements | NZTA (Tasman) | SH60 Birds Hill Overslip | Implementation |  | VH_VL | VHHVL | N | 0 | Approved | Approved by Minister for Crown Appropriation | Project list in BRI-2843 as part of the agreed investment programme for the 2023/24 appropriation. | 2662500 | 2662500 |  |  | 1 | 1 |  | 290501 | 60071582 | 126453
2023-11-17 | November 2023 Review | New approval | External funding | Resilience improvements | NZTA (Tasman) | SH60 Birds Hill Overslip | Single-Stage Business Case |  | VH_VL | VHHVL | N | 0 | Approved | Approved by Minister for Crown Appropriation | Project list in BRI-2843 as part of the agreed investment programme for the 2023/24 appropriation. | 426000 | 426000 |  |  | 1 | 1 |  | 290500 | 60071581 | 126452
2023-11-17 | November 2023 Review | New approval | External funding | Resilience improvements | NZTA (Waikato) | Crown Resilience Programme LCLR WAI | Implementation |  | VH_H | VHHH | N | 0 | Approved | Approved by Minister for Crown Appropriation | Project list in BRI-2843 as part of the agreed investment programme for the 2023/24 appropriation. | 4025700 | 4025700 |  |  |  | 4 |  | 288949 | 60071759 | 126444
2023-11-17 | November 2023 Review | New approval | External funding | Resilience improvements | NZTA (Wellington) | Crown Resilience Programme LCLR WGTN | Implementation |  | VH_H | VHHH | N | 0 | Approved | Approved by Minister for Crown Appropriation | Project list in BRI-2843 as part of the agreed investment programme for the 2023/24 appropriation. | 1411126 | 1411126 |  |  |  | 4 |  | 288950 | 60071763 | 126443
2023-11-16 | November 2023 Review | New approval | External funding | Resilience improvements | NZTA (Wellington) | SH1 Tawa to Johnsonville Surface Floodin | Single-Stage Business Case |  | VH_L | VHHL | N | 0 | Approved | Approved by Minister for Crown Appropriation | Project list in BRI-2843 as part of the agreed investment programme for the 2023/24 appropriation. | 53250 | 53250 |  |  |  | 2 |  | 288501 | 60071603 | 126266
2023-11-17 | November 2023 Review | New approval | External funding | Resilience improvements | NZTA (West Coast) | Crown Resilience Programme LCLR WTCT | Implementation |  | VH_H | VHHH | N | 0 | Approved | Approved by Minister for Crown Appropriation | Project list in BRI-2843 as part of the agreed investment programme for the 2023/24 appropriation. | 12454110 | 12454110 |  |  |  | 4 |  | 290390 | 60071767 | 126442
2023-11-17 | November 2023 Review | New approval | State highway improvements | Resilience improvements | NZTA (West Coast) | SH6 Gates of Haast River Erosion | Implementation |  | VH_M | VHHM | N | 0 | Approved | Approved by Minister for Crown Appropriation | Project list in BRI-2843 as part of the agreed investment programme for the 2023/24 appropriation. | 9265000 | 9265000 |  |  | 1 | 1 |  | 288499 | 60071595 | 126268
2023-11-17 | November 2023 Review | New approval | External funding | Resilience improvements | NZTA (West Coast) | SH6 Gates of Haast River Erosion | Single-Stage Business Case |  | VH_M | VHHM | N | 0 | Approved | Approved by Minister for Crown Appropriation | Project list in BRI-2843 as part of the agreed investment programme for the 2023/24 appropriation. | 958500 | 958500 |  |  | 1 | 1 |  | 290504 | 60071594 | 126450
2023-11-21 | November 2023 Review | New approval | Local road improvements | Road improvements | Auckland Transport | High Risk Intersections and Corridors | Implementation | HRIC Opaheke Rd & Chapel St SSInt | HHM | VHHL | Y | 2 | Approved | Approved by Auckland Transport Chief Financial Officer |  | 2400024 | 1224012 |  |  |  | 4.5 | 324.2838 | 283823 |  | 126481
2023-11-30 | November 2023 Review | New approval | State highway improvements | Road improvements | NZTA (Auckland) | NZUP SH22 (Drury) Corridor Upgrade | Implementation |  | MML | MML | N | 9 | Approved | Approved by Minister for Crown Appropriation |  | 91653532 | 91653532 |  |  |  | 1.7 |  | 290216 |  | 126534
2023-11-30 | November 2023 Review | New approval | External funding | Road improvements | NZTA (Auckland) | NZUP SH22 (Drury) Corridor Upgrade | Implementation |  | MML | MML | N | 9 | Approved | Approved by Minister for Crown Appropriation |  | 22574093 | 22574093 |  |  |  | 1.7 |  | 290517 | 60074000 | 126505
2023-11-30 | November 2023 Review | New approval | External funding | Road improvements | NZTA (Auckland) | NZUP SH22 (Drury) Corridor Upgrade | Implementation |  | MML | MML | N | 9 | Approved | Approved by Minister for Crown Appropriation |  | 87449241 | 87449241 |  |  |  | 1.7 |  | 290656 | 60073489 | 126567
2023-11-30 | November 2023 Review | New approval | External funding | Road improvements | NZTA (Auckland) | NZUP Waihoehoe Road (Drury) Upgrade | Implementation |  | MML | MML | N | 9 | Approved | Approved by Minister for Crown Appropriation |  | 62914736 | 62914736 |  |  |  | 1.8 |  | 290571 | 60073510 | 126504
2023-11-30 | November 2023 Review | New approval | External funding | Road improvements | NZTA (Auckland) | NZUP Waihoehoe Road (Drury) Upgrade | Implementation |  | MML | MML | N | 9 | Approved | Approved by Minister for Crown Appropriation |  | 26663829 | 26663829 |  |  |  | 1.8 |  | 290518 | 60074001 | 126506
2023-11-07 | November 2023 Review | New approval | Road to Zero | Road improvements | NZTA (BOP) | SH2 Omokoroa to Te Puna Safety Improvement | Implementation |  | HMM | HMM | N | 5 | Approved with conditions precedent | Approved with conditions precedent by Chief Financial Officer (CFO) | Approving this request will enable mid-block line marking improvements and Intersection Speed Zones (2) to be implemented on SH2 between Omokoroa and Te Puna. This provides low-cost road safety improvements, reducing the likelihood of head-on crashes and addressing intersection risk. | 5000000 | 5000000 | NLTP Inclusion |  | 2.1 | 2.1 |  | 282955 | 60068551 | 125898
2023-11-03 | November 2023 Review | New approval | Road to Zero | Road improvements | NZTA (Hawkes Bay) | SH51 Napier to Hastings | Implementation | SH51 Elliston St to Tutaekuri Bridge - Stg 2 | VHHL | VHHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | The decision is neutral in relation to the climate change strategic priority set out in the GPS (including impacts on relevant transport emission reduction targets and consistency with the ERP) and the proposal is consistent with the GPS. | 19342945 | 19342945 |  |  | 2.1 | 2.1 |  | 283213 | 60068960 | 126275
2023-11-09 | November 2023 Review | New approval | State highway improvements | Road improvements | NZTA (Northland) | SH14 WhangÄrei to Maunu Corridor IBC | Indicative Business Case |  | MHL | MHL | N | 7 | Approved | Approved by Chief Financial Officer (CFO) | Funding the proposed IBC will enable Waka Kotahi together with other stakeholders to investigate and consider viable interventions for SH14 and the Whangarei hospital environs; and the broader strategic transport needs in response to Whangareiâ€™s future urban growth requirements | 396106 | 396106 | [5 empty] | 290172 | 60073488 | 126379
2023-11-13 | November 2023 Review | New approval | Road to Zero | Road improvements | NZTA (Wellington) | SH2 Hutt Valley | Implementation | SH2 and Liverton IS | VHMH | VHHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) |  | 1863900 | 1863900 |  |  | 2.1 | 2.1 | 19949 | 277316 | 60060971 | 125961
2023-11-13 | November 2023 Review | New approval | Road to Zero | Road improvements | NZTA (Wellington) | SH2 Hutt Valley | Implementation | SH2 and Hebden Cr IS | VHMH | VHHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) |  | 286670 | 286670 |  |  | 2.1 | 2.1 | 20622 | 277320 | 60060975 | 125962
2023-11-24 | November 2023 Review | New approval | Road to Zero | Road improvements | Taupo District Council | Intersection of Wairakei Dr/Huka Falls Rd/Karapiti Rd | Implementation |  | VHLM | VHHL | N | 3 | Approved | Approved by Chief Financial Officer (CFO) | This funding is to construct a safe roundabout at a high risk intersection which been nominated for and has been prioritised under the Speeds and Infrastructure Programme. The recommended project has a cost estimate of $2,351,720, and the programme has a BCR of 4.1. The programme meets the requirements of section 20 of the Land Transport Management Act 2003. The decision is neutral in relation to the climate change strategic priority set out in the GPS, with a focus on creating a safe intersection it is not expected to induce enabled carbon, and the proposal is consistent with the GPS as a whole. | 2351720 | 1199377 |  |  |  | 4.1 |  | 290423 |  | 126324
2023-11-03 | November 2023 Review | New approval | External funding | Walking facilities | Matamata-Piako District Council | CERF-TC MPDC Transport Choices Projects | Implementation | Te Aroha, Morrinsville and Matamata TC projects | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | As per CERF activity class | 910800 | 660800 |  |  |  | 0 |  | 284326 |  | 123277
2023-11-08 | November 2023 Review | New approval | External funding | Walking facilities | Tasman District Council | CERF TC - Richmond Cycleways and slow streets | Implementation | Construction | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | Project design agreed and schedule 2 signed. | 1742000 | 1536667 |  |  | 0 | 0 | Richmond Transport Choices Part 1 - William Street | 288422 |  | 125476
2023-11-23 | November 2023 Review | Cash flow adjustment | Local road maintenance | Bridge and structures renewals | Central Otago District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Alignment of renewals budgets with Council's renewals budgets and movement of surplus to WC151 and other maintenance WCs to address shortfalls. | -439475 | -224132 | [5 empty] | 272338 |  | 126418
2023-11-10 | November 2023 Review | Cash flow adjustment | Local road maintenance | Bridge and structures renewals | Rangitikei District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This net $0 change is to allow Rangitikei DC to undertake the strengthening and repair work to Otara Boundary bridge in conjunction with Manawatu DC. This bridge is a vital rural connector that links both councils to SH1 in Ohingaiti. | -96070 | -60524 | [5 empty] | 273881 |  | 126181
2023-11-03 | November 2023 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Cycling Investment - Mangere East | Pre-implementation* | Cycling Investment - Mangere East - PRE-IMP | HHL | HML | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, this activity has slipped due to budget constraints. This is a cost neutral cashflow adjustment to reflect the current position. | 0 | 0 |  |  | 0 | 2.2 | 452.2613 | 261308 |  | 126252
2023-11-03 | November 2023 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Cycling Investment - Manukau | Implementation | Cycling Investment - Manukau (Tranche 0) | HHM | HMM | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, this phase has slipped due to budget constraints. This is a neutral cashflow to reflect current forecast. | 0 | 0 |  |  | 0 | 3.2 | 452.2835 | 283535 |  | 126254
2023-11-03 | November 2023 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Cycling Investment - Manukau | Pre-implementation* | Cycling Investment - Manukau - PRE-IMP | HHM | HMM | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, this activity has slipped due to budget constraints. This is a cost neutral cashflow to reflect the current forecast. | 0 | 0 |  |  | 0 | 3.2 | 452.2613 | 261304 |  | 126253
2023-11-03 | November 2023 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Urban Cycleways Programme - Glen Innes to Tamaki Drive | Implementation | UCP - Glen Innes-Tamaki Dr C/way - Sec 4 (NLTF) | VHHVL | VHHVL | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, the timing for this activity has been delayed due to budget constraints and consenting. Consents have now been received and the project team is actively working to understand the budgets with Council for this FY and into the 2024 RLTP. AT are looking to complete a cost neutral cashflow at this time, but note that some may be pulled back into FY24 should budget be identified. | 0 | 0 |  |  | 0 | 0.7 | 452.2465 | 246508 |  | 126249
2023-11-03 | November 2023 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Urban Cycleways Programme - Great North Road Cycleway | Implementation | UCP - Wst Connx - Great North Road | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, this activity has been delayed due to internal decision making on the overall project. This is a cashflow adjustment to reflect the current forecast position. | 0 | 0 |  |  |  | 2.6 | 452.2777 | 277747 |  | 126251
2023-11-03 | November 2023 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Urban Cycleways Programme - Pt Chev to Westmere Cycleway | Implementation | UCP - Wst Connx - Pt Chev to Westmere | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, the tender for this activity has now been awarded and work is about to commence on this activity. This is a minor cashflow adjustment to reflect the project team's assumptions. | 0 | -1 |  |  |  | 1.8 | 452.2778 | 277751 |  | 126250
2023-11-23 | November 2023 Review | Cash flow adjustment | Local road maintenance | Drainage renewals | Central Otago District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Alignment of renewals budgets with Council's renewals budgets and movement of surplus to WC151 and other maintenance WCs to address shortfalls. | 13440 | 6854 | [5 empty] | 272335 |  | 126418
2023-11-08 | November 2023 Review | Cash flow adjustment | State highway maintenance | Emergency works | NZTA (Manawatu/Whanganui) | EW SH54 Rewa Retain Walls 20211004 | Construction |  | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | Email from Tiffany Canon 3.11.23 to close | 0 | 0 | [5 empty] | 280370 | 60066251 | 126382
2023-11-20 | November 2023 Review | Cash flow adjustment | Local road maintenance | Emergency works | Whanganui District Council | Cyclone Dovi - 13 February 2022 Emergency Works | Construction | Major Repairs | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Over-ride FAR to 60% to align with NZTA EW FAR policy | 0 | 0 |  |  |  |  | Request for emergency works funding | 281498 |  | 125673
2023-11-23 | November 2023 Review | Cash flow adjustment | Local road maintenance | Environmental maintenance | Central Otago District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Alignment of renewals budgets with Council's renewals budgets and movement of surplus to WC151 and other maintenance WCs to address shortfalls. | 21638 | 11036 | [5 empty] | 272328 |  | 126418
2023-11-23 | November 2023 Review | Cash flow adjustment | Local road maintenance | Footpath renewal | Central Otago District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Alignment of renewals budgets with Council's renewals budgets and movement of surplus to WC151 and other maintenance WCs to address shortfalls. | 42000 | 21420 | [5 empty] | 272342 |  | 126418
2023-11-23 | November 2023 Review | Cash flow adjustment | Local road maintenance | Network and asset management | Central Otago District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Alignment of renewals budgets with Council's renewals budgets and movement of surplus to WC151 and other maintenance WCs to address shortfalls. | 362439 | 184844 | [5 empty] | 272332 |  | 126418
2023-11-23 | November 2023 Review | Cash flow adjustment | Local road maintenance | Network service maintenance | Central Otago District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Alignment of renewals budgets with Council's renewals budgets and movement of surplus to WC151 and other maintenance WCs to address shortfalls. | -4 | -2 | [5 empty] | 272329 |  | 126418
2023-11-03 | November 2023 Review | Cash flow adjustment | Local road improvements | New roads | Auckland Transport | TNFG - Warkworth | Pre-implementation* | TNFG - Warkworth | VHHVL | VHHVL | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, this activity is looking to be delivered early than expected. This is a cost neutral cashflow to advance approval into FY24. | 0 | 1 |  |  |  |  | 323.2505 | 250459 |  | 126261
2023-11-03 | November 2023 Review | Cash flow adjustment | Public transport infrastructure | Passenger facilities and infrastructure improvements - ferry | Auckland Transport | Ferry new purchase and associated Infrastructure | Implementation | Ferry Vessel (Stage 1) Charging - Long Lead Items | VHHL | VHHVL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, the timing for the purchase of the long lead items has slipped so this cashflow adjust is to reflect current anticipated cashflow. | 0 | 0 |  |  |  | 1.4 | 562.2845 | 284494 |  | 126246
2023-11-10 | November 2023 Review | Cash flow adjustment | Public transport services | Passenger services - rail | Waikato Regional Council | Operational phase of start up passenger rail service | Implementation | Funding for the operations of the start-up service | H_L | HLL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Moving $1,089,332 in Yr 23/24 to 24/25. | 0 | 0 |  |  | 0.5 | 0 | H2A Trial Rail Service | 269681 |  | 125967
2023-11-23 | November 2023 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Auckland) | Vic Park Tunnel | Property |  | H_M | H_H | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | To move 4,464,881 allocation from CY to Y2 as potential property costs are not expected to be realised until Y2. | 0 | 0 |  |  | 0 | 2.8 | 60400022 | 194187 | 60400022 | 126488
2023-11-23 | November 2023 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Auckland) | WaitematÄ Harbour Connections | Property |  | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move $10,050,000 from CY to Year 3 as no property spend will eventuate thisCY. No plans for advance purchase yet. | 0 | 0 |  |  | 0.6 | 0.6 | 60429252 | 194477 | 60429252 | 126489
2023-11-10 | November 2023 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Waikato) | SH26 Kirikiri Stream Bridge Replacement | Property | SH26 Kirikiri Stream Bridge Replacement-property | M__ | M__ | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | reallocate $10,000 from CY to Y1 and $63,085 from CY to Y2: project delayed/ put on hold to manage PM resourcing constraints | 0 | 0 |  |  | 99 | 99 | 60462002 | 258937 | 60462002 | 126332
2023-11-23 | November 2023 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Waikato) | Weigh Right Taupo | Property | Weigh station property | H_H | MHH | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  | 14 | 14 |  | 260277 | 60047922 | 126429
2023-11-03 | November 2023 Review | Cash flow adjustment | Public transport infrastructure | Public transport infrastructure and major renewals | Auckland Transport | AMETI - Eastern Busway 1 (Previously part of AMETI Stage 2A) | Construction | Green Bond Project - Ameti Eastern Busway 1 | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, elements of this work have slipped, therefore this is a cost neutral cashflow adjustment. | 0 | 0 |  |  | 0 | 1.1 | 531.228 | 227971 |  | 126247
2023-11-03 | November 2023 Review | Cash flow adjustment | Public transport infrastructure | Public transport infrastructure and major renewals | Auckland Transport | NCI - Rosedale Station and Assoc. Local Road Improvements | Implementation | NCI - Rosedale PT Components - IMP | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, the delivery of this activity has slipped as it has now been passed back to AT (as opposed to being completed by the Alliance). A tender is underway for design and a full gap analysis of existing design work completed. The cost of the activity has also been signalled to increase, howeer this will be worked through once the gap analysis is complete and tender for construction underway. This an NLTF neutral cashflow while final costs / CSA are developed. | 0 | 0 |  |  | 0 | 1.1 | 531.2384 | 238358 |  | 126245
2023-11-10 | November 2023 Review | Cash flow adjustment | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH26 Kirikiri Stream Bridge Replacement | Implementation | SH 26 Kirikiri Stream Bridge Replacement Construct | M__ | M__ | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | reallocate $2,075,070 from CY to Y2 and $6,958,226 from CY to Y3. Reallocate $73,447 from Y1 to Y2: project delayed/ put on hold to manage PM resourcing constraints | 0 | 0 |  |  | 99 | 99 | 60031830 | 256636 | 60031830 | 126335
2023-11-03 | November 2023 Review | Cash flow adjustment | Local road improvements | Road improvements | Auckland Transport | AKL Network Optimisation | Implementation | AKL Network Optimisation - Stage 1 | MHM | MHM | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, this activity is forecast to deliver more in the FY24 period than currently approved. This is a cost neutral cashflow to advance funding from FY25. | 0 | 0 |  |  |  | 3.2 | 324.2383 | 238334 |  | 126258
2023-11-03 | November 2023 Review | Cash flow adjustment | Local road improvements | Road improvements | Auckland Transport | AKL Network Optimisation | Single-Stage Business Case | AKL Network Optimisation - Stage 1 | MHM | MHM | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, no SSBC Lites are anticipated this FY, so this is a cost neutral cashflow to push into FY25. | 0 | 0 |  |  |  | 3.2 | 324.2778 | 277772 |  | 126263
2023-11-03 | November 2023 Review | Cash flow adjustment | Local road improvements | Road improvements | Auckland Transport | Access for Everyone (A4E) | Indicative Business Case | IBC Phase for network changes | VHML | VHHL | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, elements of this work have slipped, therefore this is a cost neutral cashflow adjustment. | 0 | 0 |  |  |  | 2.8 | 324.2771 | 277118 |  | 126262
2023-11-03 | November 2023 Review | Cash flow adjustment | Local road improvements | Road improvements | Auckland Transport | Glenvar / East Coast Road Improvements | Implementation | Glenvar / East Coast Rd Improvements - IMP | VHHM | VHHM | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, this activity has been paused while the final design is considered (post Cyclone Gabrielle) and as part of the 2024 RLTP development. This is a cost neutral cashflow now while final timing decisions are considered. | 0 | 0 |  |  | 0 | 5.4 | 324.2383 | 238281 |  | 126255
2023-11-03 | November 2023 Review | Cash flow adjustment | Local road improvements | Road improvements | Auckland Transport | TNFG - North West | Pre-implementation* | TNFG - North West | VHHVL | VHHVL | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, this activity has slipped. This is a cost neutral cashflow adjustment. | 0 | 0 |  |  |  | 0.7 | 324.2505 | 250457 |  | 126256
2023-11-03 | November 2023 Review | Cash flow adjustment | Local road improvements | Road improvements | Auckland Transport | TNFG - South - SGA Takanini | Pre-implementation* | SGA-Takaanini Level Xing and FTN Route Protection | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, the timing for this has slipped slightly. This is a cost neutral cashflow to reflect current position. | 0 | 0 |  |  |  |  | 324.2505 | 250458 |  | 126257
2023-11-10 | November 2023 Review | Cash flow adjustment | Road to Zero | Road improvements | Hastings District Council | Maraekakaho / York Roundabout Construction | Implementation | Maraekakaho / York Roundabout Construction | VHHL | VHHM | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Tendered for construction in 22/23, two bids received were significantly higher than the budget. As such we have rescoped and redesigned in efforts to reduce costs. This work has meant that the project will be pushed out into next NLTP | 0 | 0 |  |  |  | 0.5 | Maraekakaho / York Roundabout Construction | 277789 |  | 126106
2023-11-09 | November 2023 Review | Cash flow adjustment | External funding | Road improvements | NZTA (Canterbury) | NZUP SH73 Weedons-Ross Road Intersection | Pre-implementation* | NZ Upgrade Programme | H_L | HML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project closure | 0 | 0 |  |  | 1.2 | 1.2 | 60031530 | 239002 | 60031530 | 126392
2023-11-23 | November 2023 Review | Cash flow adjustment | Local road maintenance | Sealed pavement maintenance | Central Otago District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Alignment of renewals budgets with Council's renewals budgets and movement of surplus to WC151 and other maintenance WCs to address shortfalls. | -57000 | -29070 | [5 empty] | 272321 |  | 126418
2023-11-23 | November 2023 Review | Cash flow adjustment | Local road maintenance | Sealed road pavement rehabilitation | Central Otago District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Alignment of renewals budgets with Council's renewals budgets and movement of surplus to WC151 and other maintenance WCs to address shortfalls. | -172000 | -87720 | [5 empty] | 272336 |  | 126418
2023-11-23 | November 2023 Review | Cash flow adjustment | Local road maintenance | Sealed road resurfacing | Central Otago District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Alignment of renewals budgets with Council's renewals budgets and movement of surplus to WC151 and other maintenance WCs to address shortfalls. | -25040 | -12770 | [5 empty] | 272334 |  | 126418
2023-11-23 | November 2023 Review | Cash flow adjustment | Local road maintenance | Structures component replacements | Central Otago District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Alignment of renewals budgets with Council's renewals budgets and movement of surplus to WC151 and other maintenance WCs to address shortfalls. | 286400 | 146064 | [5 empty] | 272337 |  | 126418
2023-11-10 | November 2023 Review | Cash flow adjustment | Local road maintenance | Structures component replacements | Rangitikei District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This net $0 change is to allow Rangitikei DC to undertake the strengthening and repair work to Otara Boundary bridge in conjunction with Manawatu DC. This bridge is a vital rural connector that links both councils to SH1 in Ohingaiti. | 96070 | 60524 | [5 empty] | 273880 |  | 126181
2023-11-23 | November 2023 Review | Cash flow adjustment | Local road maintenance | Structures maintenance | Central Otago District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Alignment of renewals budgets with Council's renewals budgets and movement of surplus to WC151 and other maintenance WCs to address shortfalls. | -8004 | -4082 | [5 empty] | 272324 |  | 126418
2023-11-23 | November 2023 Review | Cash flow adjustment | Local road maintenance | Traffic services renewals | Central Otago District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Alignment of renewals budgets with Council's renewals budgets and movement of surplus to WC151 and other maintenance WCs to address shortfalls. | -52000 | -26520 | [5 empty] | 272340 |  | 126418
2023-11-23 | November 2023 Review | Cash flow adjustment | Local road maintenance | Unsealed pavement maintenance | Central Otago District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Alignment of renewals budgets with Council's renewals budgets and movement of surplus to WC151 and other maintenance WCs to address shortfalls. | -81316 | -41471 | [5 empty] | 272322 |  | 126418
2023-11-23 | November 2023 Review | Cash flow adjustment | Local road maintenance | Unsealed road metalling | Central Otago District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Alignment of renewals budgets with Council's renewals budgets and movement of surplus to WC151 and other maintenance WCs to address shortfalls. | 108922 | 55550 | [5 empty] | 272333 |  | 126418
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Bridge and structures renewals | Timaru District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Due to significant changes in construction, material costs, compliance regulations, and fluctuations in contract expenses, we are seeking additional funding in various critical work categories. These increased costs and unforeseen events have adversely affected our ability to execute and complete essential projects within our current budgetary confines | 600000 | 306000 | [5 empty] | 274394 |  | 126197
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Cycle path maintenance | Dunedin City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Dunedin City Council (DCC) submitted a Maintenance, Operations and Renewals (MOR) bid of $124.89m, funding was approved to a ceiling of $104.25m, a shortfall of $20.64m on asset management-based network needs. DCC anticipated a shortfall in Waka Kotahi co-funding so budgeted to deliver $11m of renewals with 100% local share funding over the 2021-24 period whist reducing the volume of pavement rehabilitation and footpath renewals to meet approved bottom line budgets. Changes in the Temporary Traffic Management (TTM) requirements have led to an increase in costs in the region of $1m per annum, the TTM market is constrained in the region and more qualified STMS workers are in demand and remunerated accordingly. Under the DCC Maintenance Contract traffic management is separated from unit rates and charged at a day rate, this transparency results in a clear trend in increase in costs from 8% of overall works to 11%, with an overall annual contract spend of around $24m this is an unbudgeted increase of $720k this year which is required to be absorbed within existing budgets. Our contracts are escalated using the Waka Kotahi Network Outcomes index, while year on year escalations have stabilised in recent months the overall escalation from our funding bid to now are at 16%, well above budgeted inflation levels. In our operational budget the increase accounts for $2m of our local budget request for 2022-23 and 2023-24. Our overall forecast for the 2021-24 funding cycle is $119.23m against funding of $104.25m, taking into the account the $11m of locally funded renewals we have a shortfall in co-funding of $3.98m. The local share for this work is budgeted but without additional Waka Kotahi approvals DCC will need to rationalise MOR programmes to meet budget. Due to contract conditions this rationalisation will need to be found in resealing and pavement rehabilitation, this is sub-optimal situation with DCC having some of the worst condition indexes nationwide for carriageways and pavements. | 10000 | 5100 | [5 empty] | 272448 |  | 126339
2023-11-28 | November 2023 Review | Cost Decrease | Local road maintenance | Cycle path maintenance | Gore District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The requested increases are the result of cost inflation, renewed physical works contracts which contained higher rates including accommodating significant increased traffic management requirements. Significant increased quantities of work have been needed to maintain our level of service on both sealed and unsealed roads. This has been contributed to by significant detrimental weather events which appear to be occuring more regularly and of increasing magnitude. The Council recognised these factors in approving significant increased local funding for roading in its 2021/22 and 2023/24 Annual Plans. This request for cost scope adjustment will match these local funds already provided. Delivery of the increased works for which increased funding is requested has been delivered during the 2022/23 year which provides evidence that the Council has the ability to deliver the increased works. | -8581 | -5063 | [5 empty] | 272585 |  | 126330
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Cycle path maintenance | Selwyn District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | There has been significant cost pressure in recent years regarding the delivery of the MOR program. On top of inflation at 6% per year, industry-wide changes also added to the costs: 1) Regulatory changes: ECAN Dumping Fee, holiday pay and sick leave pay, adding $1m/year; 2) Market structure change: Bitumen cost increase, adding $1m/year; and 3) More emergency works from severe weather events. As a result, SDC had to use funds allocated to renewals to do maintenance and was only able to deliver 23km of reseals against a target of 75km in 22/23. For 23/24, SDC allocated $3,072,828 (see attached) in unsubsidized funds to supplement WK-approved MOR budget to deliver targeted reseals in 23/24. In the recent program monitor (see attached), we have planned $2,653,762 in unsubsidized MOR spending. This still leaves areas including sealed pavement maintenance, drainage maintenance and renewals, and pavement renewals underfunded. Since then, we have identified an additional $3,088,934 of work in those categories (see attached) that could be delivered in 23/24 if additional WK funding becomes available. Together we are requesting an increase of $5,742,696 in approved budget. The $3,072,828 already allocated by the SDC annual plan can cover the local share portion of the requested increase. Our contractor HEB has indicated that they will be able to deliver the works in 23/24 | 21586 | 11009 | [5 empty] | 273966 |  | 126225
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Cycle path maintenance | Waimakariri District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | In the September Programme Monitor Council indicated it would be supplementing the co-funded programme with a significant sum of unsubsidised budget. Council had given approval to an additional sum of around 2M, both to ensure that day to day work and levels of service could be maintained, and to try to tackle a few areas of significant defects in the drainage aspects of our network This application is to request co-funding to the level Council feels it requires order to maintain a safe and appropriate network this financial year. The current budget available to Council, including the unsubsidised share is $12.55M. Without additional co-funding a decline in our LOS and network safety is anticipated. Drivers for the increased costs include 22% cost fluctuations over the last two years, plus another significant increase this year, over and above he usual high growth and weather related impacts on our network | 8146 | 4155 | [5 empty] | 274469 |  | 126322
2023-11-03 | November 2023 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Auckland Transport | Cycling Investment - Central Isthmus & Sandringham | Detailed Business Case | Cycling Investment - Central & Sandringham - DBC | HLL | HMM | N | 8 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, this activity is nearing completion and a partial surplus is being declared while final costs are resolved. | -100221 | -51113 |  |  | 0 | 1.7 | 452.2613 | 261280 |  | 126236
2023-11-03 | November 2023 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Auckland Transport | Cycling Investment - City Centre & Fringe | Detailed Business Case | Cycling Investment - City Centre and Fringe - DBC | HLL | HMM | N | 8 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, this activity is nearing completion and a partial surplus is being declared while final costs are resolved. | -284045 | -144863 |  |  | 0 | 1.7 | 452.2613 | 261263 |  | 126235
2023-11-03 | November 2023 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Auckland Transport | Urban Cycleways Programme - Links to Glen Innes | Implementation | Links to GI - IMP - Package 1 Taniwha Street | HHL | HML | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, this project is nearing completion and costs are indicated to come in slightly under the approval. A partial surplus is declared while final costs are resolved. | -251887 | -128462 |  |  | 1.5 | 1.5 | 452.2801 | 280136 |  | 126234
2023-11-03 | November 2023 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Auckland Transport | Urban Cycleways Programme - Links to Glen Innes | Implementation | Links to GI - Package 2 (Other Works) | HHL | HML | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As per the programme monitor, this activity is now to be delivered through the maintenance contractor and therefore costs have come in lower than approved. AT is declaring a partial surplus while the project advances. | -10000000 | -5100000 |  |  | 1.5 | 1.5 | 452.2778 | 277812 |  | 126233
2023-11-23 | November 2023 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | NZTA (Auckland) | Glen Innes to Tamaki Shared Path - Sections 1 and 2 NZTA | Implementation | Green Bond Project -UCP GI2TD Section 2 IMP (NLTF) | H_L | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Partial Surplus of $6,331,054.00 | -6900850 | -6900850 |  |  | 0 | 3.6 |  | 239838 | 60216416 | 126471
2023-11-10 | November 2023 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Tasman District Council | SfP Tasman Towns | Implementation | SfP Mapua Cycle Lanes | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer. Pre-imp completed and half of remaining funds transferred to implementation project. This is not a cost increase but a transfer of fund from another project phase. | 22675 | 20407 |  |  |  | 1 |  | 282764 |  | 126364
2023-11-10 | November 2023 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Tasman District Council | SfP Tasman Towns | Implementation | SfP Richmond Cycle Lanes | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer. Pre-imp completed and half of remaining funds transferred to implementation project. This is not a cost increase but a transfer of fund from another project phase. | 22675 | 20407 |  |  |  | 1 |  | 282763 |  | 126218
2023-11-24 | November 2023 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Tasman District Council | SfP Tasman Towns | Implementation | SfP Mapua Cycle Lanes | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reinstating funding that was removed on 23 Nov 23 | 396661 | 356995 |  |  |  | 1 |  | 282764 |  | 126510
2023-11-23 | November 2023 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Tasman District Council | SfP Tasman Towns | Implementation | SfP Mapua Cycle Lanes | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2023/24 as activity is claiming complete | -396661 | -356995 |  |  |  | 1 |  | 282764 |  | 126404
2023-11-10 | November 2023 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Tasman District Council | SfP Tasman Towns | Pre-implementation* | SfP Tasman Towns | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2023/24 as activity is claiming complete | -45350 | -40815 |  |  |  | 1 |  | 281364 |  | 126217
2023-11-10 | November 2023 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Tauranga City Council | SfP - Streets for People - Tauranga City # | Pre-implementation* | SfP - Streets for People - Te Papa/Arataki | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2023/24 as activity is claiming complete | -95952 | -86357 |  |  | 1 | 10 | Pre-implementation | 281381 |  | 126221
2023-11-27 | November 2023 Review | Cost Increase | Local road maintenance | Drainage renewals | Chatham Islands Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Cost Scope Adjustment following phone call with Suv to advise of potential additional MOR funding available: Adjustments to programme - to recoup 23/24 programme adjustments to cover 2022/23 shortfalls due to elevated contractor and consultant cost fluctuation indices, and - to apply additional cost escalations for contractor and consultant cost fluctuation indices remaining high into FY 23/24. | 43000 | 37840 | [5 empty] | 272360 |  | 126215
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Drainage renewals | Clutha District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | New Roading Maintenance Contract rates resulting in budget blow outs and not wanting to cut back on work. In WC213, historical weather event repairs/renewals continuing. Council confirms availability of local share and works will be completed this Financial Year. | 500000 | 325000 | [5 empty] | 272433 |  | 126368
2023-11-28 | November 2023 Review | Cost Decrease | Local road maintenance | Drainage renewals | Dunedin City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Dunedin City Council (DCC) submitted a Maintenance, Operations and Renewals (MOR) bid of $124.89m, funding was approved to a ceiling of $104.25m, a shortfall of $20.64m on asset management-based network needs. DCC anticipated a shortfall in Waka Kotahi co-funding so budgeted to deliver $11m of renewals with 100% local share funding over the 2021-24 period whist reducing the volume of pavement rehabilitation and footpath renewals to meet approved bottom line budgets. Changes in the Temporary Traffic Management (TTM) requirements have led to an increase in costs in the region of $1m per annum, the TTM market is constrained in the region and more qualified STMS workers are in demand and remunerated accordingly. Under the DCC Maintenance Contract traffic management is separated from unit rates and charged at a day rate, this transparency results in a clear trend in increase in costs from 8% of overall works to 11%, with an overall annual contract spend of around $24m this is an unbudgeted increase of $720k this year which is required to be absorbed within existing budgets. Our contracts are escalated using the Waka Kotahi Network Outcomes index, while year on year escalations have stabilised in recent months the overall escalation from our funding bid to now are at 16%, well above budgeted inflation levels. In our operational budget the increase accounts for $2m of our local budget request for 2022-23 and 2023-24. Our overall forecast for the 2021-24 funding cycle is $119.23m against funding of $104.25m, taking into the account the $11m of locally funded renewals we have a shortfall in co-funding of $3.98m. The local share for this work is budgeted but without additional Waka Kotahi approvals DCC will need to rationalise MOR programmes to meet budget. Due to contract conditions this rationalisation will need to be found in resealing and pavement rehabilitation, this is sub-optimal situation with DCC having some of the worst condition indexes nationwide for carriageways and pavements. | -221000 | -112710 | [5 empty] | 272458 |  | 126339
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Drainage renewals | Gore District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The requested increases are the result of cost inflation, renewed physical works contracts which contained higher rates including accommodating significant increased traffic management requirements. Significant increased quantities of work have been needed to maintain our level of service on both sealed and unsealed roads. This has been contributed to by significant detrimental weather events which appear to be occuring more regularly and of increasing magnitude. The Council recognised these factors in approving significant increased local funding for roading in its 2021/22 and 2023/24 Annual Plans. This request for cost scope adjustment will match these local funds already provided. Delivery of the increased works for which increased funding is requested has been delivered during the 2022/23 year which provides evidence that the Council has the ability to deliver the increased works. | 22443 | 13241 | [5 empty] | 272595 |  | 126330
2023-11-28 | November 2023 Review | Cost Decrease | Local road maintenance | Drainage renewals | Invercargill City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Queens Drive SCRIM results indicates that an intervention is required. This surface was given a rejuvenation treatment in 2021 due to the surface letting go at that time. This is a section of road had a fatal crash (4 deaths). Temporary warning signage has been installed. Bringing the resurfacing of Queens Drive forward will eliminate the risk on the network entirely rather than a supplementary treatment on the rejuvenation which may have an unknown result. Local share has been approved. Invited tender for the work has been drafted, and we are confident that it will be delivered this financial year. | -633163 | -322913 | [5 empty] | 272857 |  | 126318
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Drainage renewals | Kaikoura District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The district spend on road maintenance, operations and renewals, when expressed as $/km, was amongst lowest in the country throughout the 2010s decade. Such very low levels of expenditure have been driven by a previous Council desire for austerity in an environment where an extremely small district had many competing financial pressures including those associated with the 2016 earthquake and it is not surprising that such sustained low expenditure has had negative effects on the network. Road conditions deteriorated and a significant backlog of pavement reconstruction and resealing work developed, further increasing the required level of investment. Since 2018 KDC has been attempting to escape from this vicious circle but it has proven difficult because of limited financial support for our NLTP programs. An attempt was made to significantly lift expenditure in the 2018-21 NLTP, but Waka Kotahiâ€™s funding of the proposed program fell well short of what was requested, with a result that relatively low levels of investment persisted. KDCâ€™s average 2018-2021 spend on sealed pavement maintenance was only $3,000/km, whilst the corresponding figure for the comparable provincial centres peer group was $5,775/km, and it is extremely difficult to prevent the condition of the network declining with a maintenance spend that is so low. A further attempt was made to increase road maintenance in the Districtâ€™s 2021-2024 NLTP, and in that case with our bid was supported by an Activity Management Plan which clearly evidenced the need for additional investment, and was a document which and which we understand was seen as an exemplar by Waka Kotahi. Unfortunately despite this there was again a large shortfall in subsidy allocation against our bid, in this case leaving 33% of the proposed subsidised program ($2,292,800 of $6,994,000 in total) unfunded. Whilst such a shortfall figure might be a relatively modest one for many districts, it is major for the Kaikoura District which has a population of less than 4000 people. The immediate consequence of the shortfall of funding against our 2021-24 NLTP bid has been that our Council has resolved to increase its use of debt funding for renewals and to cut overall operational budgets by 10%, even though these budgets were already very lean. At the present time around 71% of Councils roading costs are being locally funded, which is considered an unsatisfactory situation. The cost increase mentioned above primarily apply to the renewal budget, with the majority allocated to categories 212 and 214, aimed at addressing the persistent backlog in road maintenance. A significant allocation for category 225 has been dedicated to ensuring that the Council fulfills its commitment to enhancing and maintaining the level of service for footpaths. Adjustments in costs have been considered essential for routine drainage maintenance and the upkeep of unsealed pavements to ensure the minimum level of service is maintained during periods of heavy rain impacting the road infrastructure. | 6500 | 3315 | [5 empty] | 272894 |  | 126213
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Drainage renewals | Selwyn District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | There has been significant cost pressure in recent years regarding the delivery of the MOR program. On top of inflation at 6% per year, industry-wide changes also added to the costs: 1) Regulatory changes: ECAN Dumping Fee, holiday pay and sick leave pay, adding $1m/year; 2) Market structure change: Bitumen cost increase, adding $1m/year; and 3) More emergency works from severe weather events. As a result, SDC had to use funds allocated to renewals to do maintenance and was only able to deliver 23km of reseals against a target of 75km in 22/23. For 23/24, SDC allocated $3,072,828 (see attached) in unsubsidized funds to supplement WK-approved MOR budget to deliver targeted reseals in 23/24. In the recent program monitor (see attached), we have planned $2,653,762 in unsubsidized MOR spending. This still leaves areas including sealed pavement maintenance, drainage maintenance and renewals, and pavement renewals underfunded. Since then, we have identified an additional $3,088,934 of work in those categories (see attached) that could be delivered in 23/24 if additional WK funding becomes available. Together we are requesting an increase of $5,742,696 in approved budget. The $3,072,828 already allocated by the SDC annual plan can cover the local share portion of the requested increase. Our contractor HEB has indicated that they will be able to deliver the works in 23/24 | 650843 | 331930 | [5 empty] | 273976 |  | 126225
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Drainage renewals | Timaru District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Due to significant changes in construction, material costs, compliance regulations, and fluctuations in contract expenses, we are seeking additional funding in various critical work categories. These increased costs and unforeseen events have adversely affected our ability to execute and complete essential projects within our current budgetary confines | 307784 | 156970 | [5 empty] | 274391 |  | 126197
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Drainage renewals | Waimakariri District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | In the September Programme Monitor Council indicated it would be supplementing the co-funded programme with a significant sum of unsubsidised budget. Council had given approval to an additional sum of around 2M, both to ensure that day to day work and levels of service could be maintained, and to try to tackle a few areas of significant defects in the drainage aspects of our network This application is to request co-funding to the level Council feels it requires order to maintain a safe and appropriate network this financial year. The current budget available to Council, including the unsubsidised share is $12.55M. Without additional co-funding a decline in our LOS and network safety is anticipated. Drivers for the increased costs include 22% cost fluctuations over the last two years, plus another significant increase this year, over and above he usual high growth and weather related impacts on our network | 359536 | 183363 | [5 empty] | 274479 |  | 126322
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Drainage renewals | Waimate District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Work Categories adjusted to amounts forecasted in October programmed monitor. Increased amounts to cover increased contract cost due to cost fluctuations. 111 Seal Pavement Maintenace $180,000 113 Routine drainage maintenance $ 110,000 125 Footpath maintenance $ 10,000 213 Drainage renewals $ 47,000 (includes Dash Street K&C very poor condition with pavement failure) 214 Sealed Road pavement rehabilitation $55,000 225 Footpath renewal $ 58,000 (With Dash St K&C renewal) Total $460,000 Council Confirms Work can be completed by 30 June 2024 Local Council share is available. | 46800 | 29952 | [5 empty] | 274504 |  | 126224
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Drainage renewals | Wellington City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Seeking reinstatement of previously declared surpluses and addition funds. Request for urgent streetlighting repairs were funded from within the program creating a shortfall in current year. Also heavy bus loadings are unmet in current program. Increased environmental maintenance as a result of extended heavy rainfall that are not qualifying as emergency events. | 1428755 | 728665 | [5 empty] | 274676 |  | 125429
2023-11-07 | November 2023 Review | Cost Increase | Local road maintenance | Emergency works | Auckland Transport | EW - AT Anniversary Weekend & Cyclone Gabrielle 2023 | Construction | E/W - Reinstatement @ 71% | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Funds being moved to Higher FAR phase. | 7100295 | 5041209 |  |  |  |  | 141.2901 | 290103 |  | 126370
2023-11-07 | November 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Auckland Transport | EW - AT Anniversary Weekend & Cyclone Gabrielle 2023 | Construction | E/W - Reinstatement @ 51% | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Funds being moved to Higher FAR phase. | -7100295 | -3621150 |  |  |  |  | 141.2838 | 283756 |  | 126369
2023-11-23 | November 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Far North District Council | EW July 2020 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Automatic reconciliation of approved costs with claimed costs for 2023/24 as activity is claiming complete | -198534 | -136988 |  |  |  |  | EW July 2020 | 271000 |  | 126486
2023-11-10 | November 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Gisborne District Council | EW: Emergency Works: June 2020 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | staff have had an opportunity to look at outstanding work and revised forecasts accordingly | -2000000 | -1720000 |  |  |  |  | Construction -Emergency Works: June 2020 Flood Damage | 278152 |  | 126216
2023-11-15 | November 2023 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (BOP) | EW BOP Extreme HR 20230127 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | I am content that this event fits within the current PIKB guidance for emergency works funding. I recommend approval. NAC (Recovery Manager) | 1307008 | 1307008 | [5 empty] | 283625 | 60069770 | 126406
2023-11-13 | November 2023 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (BOP) | EW SH2-0334/6.0 Waioeka Gorge 20221222 | Construction |  | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | Closure requested at meeting Local AIA and SNWMgr 13.11.23. Groynes works will be resilience. | -1870621 | -1870621 | [5 empty] | 283517 | 60069502 | 126405
2023-11-09 | November 2023 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (BOP) | EW SH2-294/2.4 Waiotahe Slip 20221019 | Construction |  | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | I am content that this fits within the current PIKB guidance for emergency works funding. The EW works are complete, and this funding will allow the EW element to close out. I recommend approval. NAC Recovery Manager. | 80817 | 80817 | [5 empty] | 283201 | 60068953 | 126309
2023-11-09 | November 2023 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Canterbury) | EW Nth Canty Multi Events 20220820 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | All works have been completed. These works were mistakenly not notified, and the costs have gone to an incorrect code. While the this is not ideal, the EW application covered a period of several weeks of almost weekly occurrences of heavy rain and or severe gales. All of these contributed to the Event 11/7/22-22/8/22 not being processed even though it met the requirements to qualify as an emergency event(s). The approval will enable all cost to be journaled to the correct event and allow the event to be closed out. | 2542970 | 2542970 | [5 empty] | 284373 | 60070756 | 126360
2023-11-07 | November 2023 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Manawatu/Whanganui) | EW SH4 Hawken Rd HR 20221126 | Construction | 1 | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | I support the investment advisorâ€™s comments. The PLA looks reasonable and the additional works have been endorsed by Sigfrid Dupre Waka Kotahi Geotechnical SME. I recommend approval. | 397461 | 397461 | [5 empty] | 283375 | 60069268 | 126171
2023-11-07 | November 2023 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (Manawatu/Whanganui) | EW SH54 Rewa Retain Walls 20211004 | Construction |  | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | 3.11.23 Email from Tiffany Canon to close | -60794 | -60794 | [5 empty] | 280370 | 60066251 | 126376
2023-11-10 | November 2023 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (Taranaki) | EW SH3 Rauroa Underslip 20210617 | Construction |  | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | Jack Hansby advised further works will be Resilience. | -373359 | -373359 | [5 empty] | 279293 | 60064063 | 126393
2023-11-10 | November 2023 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (West Coast) | EW West Coast HR 20220202 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | 7.11.23 Email from Moira Whinham to close | -2744633 | -2744633 | [5 empty] | 280681 | 60066671 | 126399
2023-11-13 | November 2023 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (West Coast) | EW West Coast Northern HR 20221102 | Construction |  | ___ |  | N |  | Approved | Approved by National Manager, Programmes and Standards (Transport Services) | 7.11.23 Moria - "Complete. Can be closed. Remaining allocation surplus. (Mark Pinner is the project Manager for this one)." Closing out now and returning $785,709 | -856423 | -856423 | [5 empty] | 283313 | 60069175 | 126401
2023-11-13 | November 2023 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (West Coast) | EW West Coast SH 6 Ianthe HR 20230205 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | 7.11.23 Moira - Appears to have been closed already, but if it hasnâ€™t it can be. Closed today and $25,172 to 141 | -27437 | -27437 | [5 empty] | 283636 | 60069793 | 126402
2023-11-13 | November 2023 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (West Coast) | EW West Coast Turiwhate Ck HR 20230309 | Construction |  | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | 7.11.23 Moira - "Complete. Can be closed.Â Remaining allocation surplus." Closing now and returning $340K to 141 | -370600 | -370600 | [5 empty] | 283833 | 60070024 | 126403
2023-11-10 | November 2023 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (West Coast) | EW Westport Storm Event 20210717 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Returning $1,023,620 to 141 bucket as only consents left | -1115746 | -1115746 | [5 empty] | 278813 | 60063006 | 126383
2023-11-24 | November 2023 Review | Cost Increase | Local road maintenance | Emergency works | Rangitikei District Council | EW - Cyclone Gabrielle February 2023 | Construction | Recovery phase | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving normal FAR to higher FAR as per NZTA EW FAR policy. | 0 | 78640 |  |  |  |  | Recovery - road network | 283945 |  | 126496
2023-11-24 | November 2023 Review | Cost Increase | Local road maintenance | Emergency works | Rangitikei District Council | EW - January 2023 event | Construction | Recovery phase | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving normal FAR to higher FAR as per NZTA EW FAR policy. | 0 | 233495 |  |  |  |  | Recovery - road network | 283987 |  | 126497
2023-11-24 | November 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Rangitikei District Council | EW - November 2022 | Construction | Recover phase for November 2022 weather event | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving funds from $341,730 to $143,905 and remaining $197,825 to higher FAR (Normal +20%) as per NZTA EW FAR policy. | -197825 | -124630 |  |  |  |  | RDC: November 2022 Emergency works event - Recovery | 284264 |  | 126495
2023-11-23 | November 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Thames-Coromandel District Council | EW TCDC - Queen's Birthday Weekend 2020 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Automatic reconciliation of approved costs with claimed costs for 2023/24 as activity is claiming complete | -2822 | -1439 | [5 empty] | 270880 |  | 126417
2023-11-21 | November 2023 Review | Cost Increase | Local road maintenance | Emergency works | Whanganui District Council | Cyclone Dovi - 13 February 2022 Emergency Works | Construction | Major Repairs | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Need to split between Normal and Higher FAR. Since claims against this phase are already over the threshold, this is being set to the Higher FAR and the threshold amount is being moved to a new phase at Normal FAR. | -1301204 | 500937 |  |  |  |  | Request for emergency works funding | 281498 |  | 126485
2023-11-20 | November 2023 Review | Cost Increase | Local road maintenance | Emergency works | Whanganui District Council | Cyclone Dovi - 13 February 2022 Emergency Works | Construction | Clean up and Minor Repairs (Normal FAR+20%) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Override FAR to 80% to allign with NZTA EW FAR policy | 0 | 41648 |  |  |  |  | Clean up and Minor Repairs (Normal FAR+2 | 283072 |  | 126462
2023-11-20 | November 2023 Review | Cost Increase | Local road maintenance | Emergency works | Whanganui District Council | EW - May 2022 Weather Event | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Over-ride FAR to 80% to align with NZTA EW FAR policy | 0 | 158816 |  |  |  |  | Initial clean up and permanent repairs | 282144 |  | 126463
2023-11-20 | November 2023 Review | Cost Increase | Local road maintenance | Emergency works | Whanganui District Council | EW Whanganui DC February 2023 Flood Event | Construction | Cleanup, Minor Repairs and Permanent Reinstatement | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Over-ride FAR to 80% to align with NZTA EW FAR policy | 0 | 48550 |  |  |  |  | Cleanup, Minor Repairs and Permanent Reinstatement | 283684 |  | 126465
2023-11-20 | November 2023 Review | Cost Increase | Local road maintenance | Emergency works | Whanganui District Council | EW Whanganui DC October 2022 | Construction | Emergency Response and Permanent Reinstatement | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Over-ride FAR to 80% to align with NZTA EW FAR policy | 0 | 126760 | [5 empty] | 283415 |  | 126464
2023-11-27 | November 2023 Review | Cost Increase | Local road maintenance | Environmental maintenance | Chatham Islands Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Cost Scope Adjustment following phone call with Suv to advise of potential additional MOR funding available: Adjustments to programme - to recoup 23/24 programme adjustments to cover 2022/23 shortfalls due to elevated contractor and consultant cost fluctuation indices, and - to apply additional cost escalations for contractor and consultant cost fluctuation indices remaining high into FY 23/24. | 9000 | 7920 | [5 empty] | 272353 |  | 126215
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Environmental maintenance | Clutha District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | New Roading Maintenance Contract rates resulting in budget blow outs and not wanting to cut back on work. In WC213, historical weather event repairs/renewals continuing. Council confirms availability of local share and works will be completed this Financial Year. | 600000 | 390000 | [5 empty] | 272426 |  | 126368
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Environmental maintenance | Dunedin City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Dunedin City Council (DCC) submitted a Maintenance, Operations and Renewals (MOR) bid of $124.89m, funding was approved to a ceiling of $104.25m, a shortfall of $20.64m on asset management-based network needs. DCC anticipated a shortfall in Waka Kotahi co-funding so budgeted to deliver $11m of renewals with 100% local share funding over the 2021-24 period whist reducing the volume of pavement rehabilitation and footpath renewals to meet approved bottom line budgets. Changes in the Temporary Traffic Management (TTM) requirements have led to an increase in costs in the region of $1m per annum, the TTM market is constrained in the region and more qualified STMS workers are in demand and remunerated accordingly. Under the DCC Maintenance Contract traffic management is separated from unit rates and charged at a day rate, this transparency results in a clear trend in increase in costs from 8% of overall works to 11%, with an overall annual contract spend of around $24m this is an unbudgeted increase of $720k this year which is required to be absorbed within existing budgets. Our contracts are escalated using the Waka Kotahi Network Outcomes index, while year on year escalations have stabilised in recent months the overall escalation from our funding bid to now are at 16%, well above budgeted inflation levels. In our operational budget the increase accounts for $2m of our local budget request for 2022-23 and 2023-24. Our overall forecast for the 2021-24 funding cycle is $119.23m against funding of $104.25m, taking into the account the $11m of locally funded renewals we have a shortfall in co-funding of $3.98m. The local share for this work is budgeted but without additional Waka Kotahi approvals DCC will need to rationalise MOR programmes to meet budget. Due to contract conditions this rationalisation will need to be found in resealing and pavement rehabilitation, this is sub-optimal situation with DCC having some of the worst condition indexes nationwide for carriageways and pavements. | 425667 | 217090 | [5 empty] | 272451 |  | 126339
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Environmental maintenance | Gore District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The requested increases are the result of cost inflation, renewed physical works contracts which contained higher rates including accommodating significant increased traffic management requirements. Significant increased quantities of work have been needed to maintain our level of service on both sealed and unsealed roads. This has been contributed to by significant detrimental weather events which appear to be occuring more regularly and of increasing magnitude. The Council recognised these factors in approving significant increased local funding for roading in its 2021/22 and 2023/24 Annual Plans. This request for cost scope adjustment will match these local funds already provided. Delivery of the increased works for which increased funding is requested has been delivered during the 2022/23 year which provides evidence that the Council has the ability to deliver the increased works. | 70034 | 41320 | [5 empty] | 272588 |  | 126330
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Environmental maintenance | Kaikoura District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The district spend on road maintenance, operations and renewals, when expressed as $/km, was amongst lowest in the country throughout the 2010s decade. Such very low levels of expenditure have been driven by a previous Council desire for austerity in an environment where an extremely small district had many competing financial pressures including those associated with the 2016 earthquake and it is not surprising that such sustained low expenditure has had negative effects on the network. Road conditions deteriorated and a significant backlog of pavement reconstruction and resealing work developed, further increasing the required level of investment. Since 2018 KDC has been attempting to escape from this vicious circle but it has proven difficult because of limited financial support for our NLTP programs. An attempt was made to significantly lift expenditure in the 2018-21 NLTP, but Waka Kotahiâ€™s funding of the proposed program fell well short of what was requested, with a result that relatively low levels of investment persisted. KDCâ€™s average 2018-2021 spend on sealed pavement maintenance was only $3,000/km, whilst the corresponding figure for the comparable provincial centres peer group was $5,775/km, and it is extremely difficult to prevent the condition of the network declining with a maintenance spend that is so low. A further attempt was made to increase road maintenance in the Districtâ€™s 2021-2024 NLTP, and in that case with our bid was supported by an Activity Management Plan which clearly evidenced the need for additional investment, and was a document which and which we understand was seen as an exemplar by Waka Kotahi. Unfortunately despite this there was again a large shortfall in subsidy allocation against our bid, in this case leaving 33% of the proposed subsidised program ($2,292,800 of $6,994,000 in total) unfunded. Whilst such a shortfall figure might be a relatively modest one for many districts, it is major for the Kaikoura District which has a population of less than 4000 people. The immediate consequence of the shortfall of funding against our 2021-24 NLTP bid has been that our Council has resolved to increase its use of debt funding for renewals and to cut overall operational budgets by 10%, even though these budgets were already very lean. At the present time around 71% of Councils roading costs are being locally funded, which is considered an unsatisfactory situation. The cost increase mentioned above primarily apply to the renewal budget, with the majority allocated to categories 212 and 214, aimed at addressing the persistent backlog in road maintenance. A significant allocation for category 225 has been dedicated to ensuring that the Council fulfills its commitment to enhancing and maintaining the level of service for footpaths. Adjustments in costs have been considered essential for routine drainage maintenance and the upkeep of unsealed pavements to ensure the minimum level of service is maintained during periods of heavy rain impacting the road infrastructure. | 16400 | 8364 | [5 empty] | 272887 |  | 126213
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Environmental maintenance | Selwyn District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | There has been significant cost pressure in recent years regarding the delivery of the MOR program. On top of inflation at 6% per year, industry-wide changes also added to the costs: 1) Regulatory changes: ECAN Dumping Fee, holiday pay and sick leave pay, adding $1m/year; 2) Market structure change: Bitumen cost increase, adding $1m/year; and 3) More emergency works from severe weather events. As a result, SDC had to use funds allocated to renewals to do maintenance and was only able to deliver 23km of reseals against a target of 75km in 22/23. For 23/24, SDC allocated $3,072,828 (see attached) in unsubsidized funds to supplement WK-approved MOR budget to deliver targeted reseals in 23/24. In the recent program monitor (see attached), we have planned $2,653,762 in unsubsidized MOR spending. This still leaves areas including sealed pavement maintenance, drainage maintenance and renewals, and pavement renewals underfunded. Since then, we have identified an additional $3,088,934 of work in those categories (see attached) that could be delivered in 23/24 if additional WK funding becomes available. Together we are requesting an increase of $5,742,696 in approved budget. The $3,072,828 already allocated by the SDC annual plan can cover the local share portion of the requested increase. Our contractor HEB has indicated that they will be able to deliver the works in 23/24 | 407000 | 207570 | [5 empty] | 273969 |  | 126225
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Environmental maintenance | Waimakariri District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | In the September Programme Monitor Council indicated it would be supplementing the co-funded programme with a significant sum of unsubsidised budget. Council had given approval to an additional sum of around 2M, both to ensure that day to day work and levels of service could be maintained, and to try to tackle a few areas of significant defects in the drainage aspects of our network This application is to request co-funding to the level Council feels it requires order to maintain a safe and appropriate network this financial year. The current budget available to Council, including the unsubsidised share is $12.55M. Without additional co-funding a decline in our LOS and network safety is anticipated. Drivers for the increased costs include 22% cost fluctuations over the last two years, plus another significant increase this year, over and above he usual high growth and weather related impacts on our network | 82375 | 42011 | [5 empty] | 274472 |  | 126322
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Environmental maintenance | Waimate District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Work Categories adjusted to amounts forecasted in October programmed monitor. Increased amounts to cover increased contract cost due to cost fluctuations. 111 Seal Pavement Maintenace $180,000 113 Routine drainage maintenance $ 110,000 125 Footpath maintenance $ 10,000 213 Drainage renewals $ 47,000 (includes Dash Street K&C very poor condition with pavement failure) 214 Sealed Road pavement rehabilitation $55,000 225 Footpath renewal $ 58,000 (With Dash St K&C renewal) Total $460,000 Council Confirms Work can be completed by 30 June 2024 Local Council share is available. | 2728 | 1746 | [5 empty] | 274497 |  | 126224
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Environmental maintenance | Wellington City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Seeking reinstatement of previously declared surpluses and addition funds. Request for urgent streetlighting repairs were funded from within the program creating a shortfall in current year. Also heavy bus loadings are unmet in current program. Increased environmental maintenance as a result of extended heavy rainfall that are not qualifying as emergency events. | 2344192 | 1195538 | [5 empty] | 274669 |  | 125429
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Environmental renewals | Mackenzie District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Additional funding required for construction of two new washover fords. Total combined cost - $250,000 Nixon Road ford is required as the adjacent bridge is now not operational. Work was originally programmed to be completed in December '23. Construction is able to be completed in the 23/24 financial year. Local share for funding is confirmed. Jack Lovelock Track ford is deteriorating due to increased rainfall events. This project can be completed at the same time as Nixons Rd ford creating a saving in construction costs. Both fords have approved ECAN consent. | 901 | 460 | [5 empty] | 272998 |  | 126328
2023-11-27 | November 2023 Review | Cost Increase | Local road maintenance | Footpath maintenance | Chatham Islands Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Cost Scope Adjustment following phone call with Suv to advise of potential additional MOR funding available: Adjustments to programme - to recoup 23/24 programme adjustments to cover 2022/23 shortfalls due to elevated contractor and consultant cost fluctuation indices, and - to apply additional cost escalations for contractor and consultant cost fluctuation indices remaining high into FY 23/24. | 100 | 88 | [5 empty] | 272351 |  | 126215
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Footpath maintenance | Dunedin City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Dunedin City Council (DCC) submitted a Maintenance, Operations and Renewals (MOR) bid of $124.89m, funding was approved to a ceiling of $104.25m, a shortfall of $20.64m on asset management-based network needs. DCC anticipated a shortfall in Waka Kotahi co-funding so budgeted to deliver $11m of renewals with 100% local share funding over the 2021-24 period whist reducing the volume of pavement rehabilitation and footpath renewals to meet approved bottom line budgets. Changes in the Temporary Traffic Management (TTM) requirements have led to an increase in costs in the region of $1m per annum, the TTM market is constrained in the region and more qualified STMS workers are in demand and remunerated accordingly. Under the DCC Maintenance Contract traffic management is separated from unit rates and charged at a day rate, this transparency results in a clear trend in increase in costs from 8% of overall works to 11%, with an overall annual contract spend of around $24m this is an unbudgeted increase of $720k this year which is required to be absorbed within existing budgets. Our contracts are escalated using the Waka Kotahi Network Outcomes index, while year on year escalations have stabilised in recent months the overall escalation from our funding bid to now are at 16%, well above budgeted inflation levels. In our operational budget the increase accounts for $2m of our local budget request for 2022-23 and 2023-24. Our overall forecast for the 2021-24 funding cycle is $119.23m against funding of $104.25m, taking into the account the $11m of locally funded renewals we have a shortfall in co-funding of $3.98m. The local share for this work is budgeted but without additional Waka Kotahi approvals DCC will need to rationalise MOR programmes to meet budget. Due to contract conditions this rationalisation will need to be found in resealing and pavement rehabilitation, this is sub-optimal situation with DCC having some of the worst condition indexes nationwide for carriageways and pavements. | 79667 | 40630 | [5 empty] | 272449 |  | 126339
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Footpath maintenance | Kaikoura District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The district spend on road maintenance, operations and renewals, when expressed as $/km, was amongst lowest in the country throughout the 2010s decade. Such very low levels of expenditure have been driven by a previous Council desire for austerity in an environment where an extremely small district had many competing financial pressures including those associated with the 2016 earthquake and it is not surprising that such sustained low expenditure has had negative effects on the network. Road conditions deteriorated and a significant backlog of pavement reconstruction and resealing work developed, further increasing the required level of investment. Since 2018 KDC has been attempting to escape from this vicious circle but it has proven difficult because of limited financial support for our NLTP programs. An attempt was made to significantly lift expenditure in the 2018-21 NLTP, but Waka Kotahiâ€™s funding of the proposed program fell well short of what was requested, with a result that relatively low levels of investment persisted. KDCâ€™s average 2018-2021 spend on sealed pavement maintenance was only $3,000/km, whilst the corresponding figure for the comparable provincial centres peer group was $5,775/km, and it is extremely difficult to prevent the condition of the network declining with a maintenance spend that is so low. A further attempt was made to increase road maintenance in the Districtâ€™s 2021-2024 NLTP, and in that case with our bid was supported by an Activity Management Plan which clearly evidenced the need for additional investment, and was a document which and which we understand was seen as an exemplar by Waka Kotahi. Unfortunately despite this there was again a large shortfall in subsidy allocation against our bid, in this case leaving 33% of the proposed subsidised program ($2,292,800 of $6,994,000 in total) unfunded. Whilst such a shortfall figure might be a relatively modest one for many districts, it is major for the Kaikoura District which has a population of less than 4000 people. The immediate consequence of the shortfall of funding against our 2021-24 NLTP bid has been that our Council has resolved to increase its use of debt funding for renewals and to cut overall operational budgets by 10%, even though these budgets were already very lean. At the present time around 71% of Councils roading costs are being locally funded, which is considered an unsatisfactory situation. The cost increase mentioned above primarily apply to the renewal budget, with the majority allocated to categories 212 and 214, aimed at addressing the persistent backlog in road maintenance. A significant allocation for category 225 has been dedicated to ensuring that the Council fulfills its commitment to enhancing and maintaining the level of service for footpaths. Adjustments in costs have been considered essential for routine drainage maintenance and the upkeep of unsealed pavements to ensure the minimum level of service is maintained during periods of heavy rain impacting the road infrastructure. | 13000 | 6630 | [5 empty] | 272885 |  | 126213
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Footpath maintenance | Selwyn District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | There has been significant cost pressure in recent years regarding the delivery of the MOR program. On top of inflation at 6% per year, industry-wide changes also added to the costs: 1) Regulatory changes: ECAN Dumping Fee, holiday pay and sick leave pay, adding $1m/year; 2) Market structure change: Bitumen cost increase, adding $1m/year; and 3) More emergency works from severe weather events. As a result, SDC had to use funds allocated to renewals to do maintenance and was only able to deliver 23km of reseals against a target of 75km in 22/23. For 23/24, SDC allocated $3,072,828 (see attached) in unsubsidized funds to supplement WK-approved MOR budget to deliver targeted reseals in 23/24. In the recent program monitor (see attached), we have planned $2,653,762 in unsubsidized MOR spending. This still leaves areas including sealed pavement maintenance, drainage maintenance and renewals, and pavement renewals underfunded. Since then, we have identified an additional $3,088,934 of work in those categories (see attached) that could be delivered in 23/24 if additional WK funding becomes available. Together we are requesting an increase of $5,742,696 in approved budget. The $3,072,828 already allocated by the SDC annual plan can cover the local share portion of the requested increase. Our contractor HEB has indicated that they will be able to deliver the works in 23/24 | 77742 | 39649 | [5 empty] | 273967 |  | 126225
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Footpath maintenance | Waimakariri District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | In the September Programme Monitor Council indicated it would be supplementing the co-funded programme with a significant sum of unsubsidised budget. Council had given approval to an additional sum of around 2M, both to ensure that day to day work and levels of service could be maintained, and to try to tackle a few areas of significant defects in the drainage aspects of our network This application is to request co-funding to the level Council feels it requires order to maintain a safe and appropriate network this financial year. The current budget available to Council, including the unsubsidised share is $12.55M. Without additional co-funding a decline in our LOS and network safety is anticipated. Drivers for the increased costs include 22% cost fluctuations over the last two years, plus another significant increase this year, over and above he usual high growth and weather related impacts on our network | 25378 | 12943 | [5 empty] | 274470 |  | 126322
2023-11-28 | November 2023 Review | Cost Decrease | Local road maintenance | Footpath maintenance | Waimate District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Work Categories adjusted to amounts forecasted in October programmed monitor. Increased amounts to cover increased contract cost due to cost fluctuations. 111 Seal Pavement Maintenace $180,000 113 Routine drainage maintenance $ 110,000 125 Footpath maintenance $ 10,000 213 Drainage renewals $ 47,000 (includes Dash Street K&C very poor condition with pavement failure) 214 Sealed Road pavement rehabilitation $55,000 225 Footpath renewal $ 58,000 (With Dash St K&C renewal) Total $460,000 Council Confirms Work can be completed by 30 June 2024 Local Council share is available. | -4222 | -2702 | [5 empty] | 274495 |  | 126224
2023-11-28 | November 2023 Review | Cost Decrease | Local road maintenance | Footpath maintenance | Wellington City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Seeking reinstatement of previously declared surpluses and addition funds. Request for urgent streetlighting repairs were funded from within the program creating a shortfall in current year. Also heavy bus loadings are unmet in current program. Increased environmental maintenance as a result of extended heavy rainfall that are not qualifying as emergency events. | -1120427 | -571418 | [5 empty] | 274667 |  | 125429
2023-11-27 | November 2023 Review | Cost Increase | Local road maintenance | Footpath renewal | Chatham Islands Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Cost Scope Adjustment following phone call with Suv to advise of potential additional MOR funding available: Adjustments to programme - to recoup 23/24 programme adjustments to cover 2022/23 shortfalls due to elevated contractor and consultant cost fluctuation indices, and - to apply additional cost escalations for contractor and consultant cost fluctuation indices remaining high into FY 23/24. | 757 | 666 | [5 empty] | 272367 |  | 126215
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Footpath renewal | Dunedin City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Dunedin City Council (DCC) submitted a Maintenance, Operations and Renewals (MOR) bid of $124.89m, funding was approved to a ceiling of $104.25m, a shortfall of $20.64m on asset management-based network needs. DCC anticipated a shortfall in Waka Kotahi co-funding so budgeted to deliver $11m of renewals with 100% local share funding over the 2021-24 period whist reducing the volume of pavement rehabilitation and footpath renewals to meet approved bottom line budgets. Changes in the Temporary Traffic Management (TTM) requirements have led to an increase in costs in the region of $1m per annum, the TTM market is constrained in the region and more qualified STMS workers are in demand and remunerated accordingly. Under the DCC Maintenance Contract traffic management is separated from unit rates and charged at a day rate, this transparency results in a clear trend in increase in costs from 8% of overall works to 11%, with an overall annual contract spend of around $24m this is an unbudgeted increase of $720k this year which is required to be absorbed within existing budgets. Our contracts are escalated using the Waka Kotahi Network Outcomes index, while year on year escalations have stabilised in recent months the overall escalation from our funding bid to now are at 16%, well above budgeted inflation levels. In our operational budget the increase accounts for $2m of our local budget request for 2022-23 and 2023-24. Our overall forecast for the 2021-24 funding cycle is $119.23m against funding of $104.25m, taking into the account the $11m of locally funded renewals we have a shortfall in co-funding of $3.98m. The local share for this work is budgeted but without additional Waka Kotahi approvals DCC will need to rationalise MOR programmes to meet budget. Due to contract conditions this rationalisation will need to be found in resealing and pavement rehabilitation, this is sub-optimal situation with DCC having some of the worst condition indexes nationwide for carriageways and pavements. | 1500000 | 765000 | [5 empty] | 272465 |  | 126339
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Footpath renewal | Invercargill City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Queens Drive SCRIM results indicates that an intervention is required. This surface was given a rejuvenation treatment in 2021 due to the surface letting go at that time. This is a section of road had a fatal crash (4 deaths). Temporary warning signage has been installed. Bringing the resurfacing of Queens Drive forward will eliminate the risk on the network entirely rather than a supplementary treatment on the rejuvenation which may have an unknown result. Local share has been approved. Invited tender for the work has been drafted, and we are confident that it will be delivered this financial year. | 145109 | 74006 | [5 empty] | 272864 |  | 126318
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Footpath renewal | Kaikoura District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The district spend on road maintenance, operations and renewals, when expressed as $/km, was amongst lowest in the country throughout the 2010s decade. Such very low levels of expenditure have been driven by a previous Council desire for austerity in an environment where an extremely small district had many competing financial pressures including those associated with the 2016 earthquake and it is not surprising that such sustained low expenditure has had negative effects on the network. Road conditions deteriorated and a significant backlog of pavement reconstruction and resealing work developed, further increasing the required level of investment. Since 2018 KDC has been attempting to escape from this vicious circle but it has proven difficult because of limited financial support for our NLTP programs. An attempt was made to significantly lift expenditure in the 2018-21 NLTP, but Waka Kotahiâ€™s funding of the proposed program fell well short of what was requested, with a result that relatively low levels of investment persisted. KDCâ€™s average 2018-2021 spend on sealed pavement maintenance was only $3,000/km, whilst the corresponding figure for the comparable provincial centres peer group was $5,775/km, and it is extremely difficult to prevent the condition of the network declining with a maintenance spend that is so low. A further attempt was made to increase road maintenance in the Districtâ€™s 2021-2024 NLTP, and in that case with our bid was supported by an Activity Management Plan which clearly evidenced the need for additional investment, and was a document which and which we understand was seen as an exemplar by Waka Kotahi. Unfortunately despite this there was again a large shortfall in subsidy allocation against our bid, in this case leaving 33% of the proposed subsidised program ($2,292,800 of $6,994,000 in total) unfunded. Whilst such a shortfall figure might be a relatively modest one for many districts, it is major for the Kaikoura District which has a population of less than 4000 people. The immediate consequence of the shortfall of funding against our 2021-24 NLTP bid has been that our Council has resolved to increase its use of debt funding for renewals and to cut overall operational budgets by 10%, even though these budgets were already very lean. At the present time around 71% of Councils roading costs are being locally funded, which is considered an unsatisfactory situation. The cost increase mentioned above primarily apply to the renewal budget, with the majority allocated to categories 212 and 214, aimed at addressing the persistent backlog in road maintenance. A significant allocation for category 225 has been dedicated to ensuring that the Council fulfills its commitment to enhancing and maintaining the level of service for footpaths. Adjustments in costs have been considered essential for routine drainage maintenance and the upkeep of unsealed pavements to ensure the minimum level of service is maintained during periods of heavy rain impacting the road infrastructure. | 473000 | 241230 | [5 empty] | 272901 |  | 126213
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Footpath renewal | Timaru District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Due to significant changes in construction, material costs, compliance regulations, and fluctuations in contract expenses, we are seeking additional funding in various critical work categories. These increased costs and unforeseen events have adversely affected our ability to execute and complete essential projects within our current budgetary confines | 1071720 | 546577 | [5 empty] | 274398 |  | 126197
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Footpath renewal | Waimakariri District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | In the September Programme Monitor Council indicated it would be supplementing the co-funded programme with a significant sum of unsubsidised budget. Council had given approval to an additional sum of around 2M, both to ensure that day to day work and levels of service could be maintained, and to try to tackle a few areas of significant defects in the drainage aspects of our network This application is to request co-funding to the level Council feels it requires order to maintain a safe and appropriate network this financial year. The current budget available to Council, including the unsubsidised share is $12.55M. Without additional co-funding a decline in our LOS and network safety is anticipated. Drivers for the increased costs include 22% cost fluctuations over the last two years, plus another significant increase this year, over and above he usual high growth and weather related impacts on our network | 225681 | 115097 | [5 empty] | 274486 |  | 126322
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Footpath renewal | Waimate District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Work Categories adjusted to amounts forecasted in October programmed monitor. Increased amounts to cover increased contract cost due to cost fluctuations. 111 Seal Pavement Maintenace $180,000 113 Routine drainage maintenance $ 110,000 125 Footpath maintenance $ 10,000 213 Drainage renewals $ 47,000 (includes Dash Street K&C very poor condition with pavement failure) 214 Sealed Road pavement rehabilitation $55,000 225 Footpath renewal $ 58,000 (With Dash St K&C renewal) Total $460,000 Council Confirms Work can be completed by 30 June 2024 Local Council share is available. | 57940 | 37082 | [5 empty] | 274511 |  | 126224
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Footpath renewal | Waitaki District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | *sealed pavement maintenance - increased rates in new road maintenance contract October 2022 and $300k to allow pre-reseal repairs to be completed a year ahead of reseals *unsealed pavement maintenance - increased rates in new road maintenance contract October 2022 and to allow for achieving level of service in grading of unsealed network *routine drainage maintenance - increased rates in new road maintenance contract October 2022 and annual commitment of new contract *network service maintenance - increase in road marking to complete full remark of road network to ensure that levels of service are achieved *unsealed road metalling - increased rates in new road maintenance contract October 2022 and annual commitment of new contract | 19489 | 11109 | [5 empty] | 274609 |  | 126226
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Footpath renewal | Wellington City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Seeking reinstatement of previously declared surpluses and addition funds. Request for urgent streetlighting repairs were funded from within the program creating a shortfall in current year. Also heavy bus loadings are unmet in current program. Increased environmental maintenance as a result of extended heavy rainfall that are not qualifying as emergency events. | 632519 | 322585 | [5 empty] | 274683 |  | 125429
2023-11-03 | November 2023 Review | Cost Decrease | Local road improvements | Low cost / low risk improvements | Auckland Transport | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, this activity is expected to come in below approved costs. AT will continue to monitor and discuss with Waka Kotahi staff, however a partial surplus is declared at this time. | -10000000 | -5100000 |  |  |  |  | 341.9003 | 275991 |  | 126240
2023-11-03 | November 2023 Review | Cost Decrease | Road to Zero | Low cost / low risk improvements | Auckland Transport | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, this activity is anticipated to come in under approval due to budget constraints within AT. A partial surplus is being declared at this time but costs will continue to get monitored through the regular engagement with Waka Kotahi staff. | -10000000 | -5100000 |  |  |  |  | 341.9023 | 275993 |  | 126239
2023-11-10 | November 2023 Review | Cost Decrease | Local road improvements | Low cost / low risk improvements | Dunedin City Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Surplus for re-prioritised programme | -1000000 | -510000 |  |  |  |  | Local road improvements | 276113 |  | 126384
2023-11-10 | November 2023 Review | Cost Decrease | Road to Zero | Low cost / low risk improvements | Dunedin City Council | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Surplus for re-prioritised programme | -3000000 | -1530000 | [5 empty] | 276116 |  | 126380
2023-11-10 | November 2023 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | Dunedin City Council | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Surplus for re-prioritised programme | -1000000 | -510000 | [5 empty] | 276114 |  | 126385
2023-11-23 | November 2023 Review | Cost Decrease | Local road improvements | Low cost / low risk improvements | Hastings District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Program reprioritisation as a result of pressures on resources and local share post-Cyclone | -5298779 | -2808353 | [5 empty] | 276156 |  | 126408
2023-11-23 | November 2023 Review | Cost Decrease | Road to Zero | Low cost / low risk improvements | Hastings District Council | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Program reprioritisation as a result of pressures on resources and local share post-Cyclone | -3808650 | -2018584 | [5 empty] | 276152 |  | 126409
2023-11-23 | November 2023 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | Hastings District Council | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Program reprioritisation as a result of pressures on resources and local share post-Cyclone | -6530371 | -3461097 | [5 empty] | 276154 |  | 126407
2023-11-23 | November 2023 Review | Cost Decrease | Local road improvements | Low cost / low risk improvements | Napier City Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reduction in original programme, inclusion of Puketitiri Rd works | -796603 | -406268 | [5 empty] | 276309 |  | 126468
2023-11-23 | November 2023 Review | Cost Decrease | Road to Zero | Low cost / low risk improvements | Napier City Council | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Surplus funds as indicated by the council | -739552 | -377172 | [5 empty] | 276308 |  | 126469
2023-11-23 | November 2023 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | Napier City Council | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Surplus funds as indicated by the council | -1030960 | -525790 | [5 empty] | 276307 |  | 126470
2023-11-10 | November 2023 Review | Cost Decrease | Road to Zero | Low cost / low risk improvements | Rotorua Lakes Council | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Surplus funds | -1161087 | -650209 | [5 empty] | 276371 |  | 126388
2023-11-10 | November 2023 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | Rotorua Lakes Council | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Surplus funds | -818492 | -458356 | [5 empty] | 276368 |  | 126387
2023-11-10 | November 2023 Review | Cost Decrease | Road to Zero | Low cost / low risk improvements | Taupo District Council | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reduction in funding by $550k as Waikakei / Huka Falls / Karapiti intersection is being taken out of the LCLR programme and being applied for as an improvement activity. | -550000 | -280500 | [5 empty] | 276447 |  | 125661
2023-11-03 | November 2023 Review | Cost Decrease | Public transport infrastructure | Low cost / low risk public transport improvements | Auckland Transport | Low cost / low risk improvements 2021-24 | Public transport infrastructure |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As requested by Waka Kotahi (as part of the 2024 NLTP development). AT have been asked to revert the approval (declare surplus) this activity while further work is undertaken on it and its priority in the 2024 RLTP. | -2580243 | -1315924 |  |  |  |  | 531.9005 | 275989 |  | 126229
2023-11-23 | November 2023 Review | Cost Decrease | Public transport infrastructure | Low cost / low risk public transport improvements | Christchurch City Council | Low cost / low risk improvements 2021-24 | Public transport infrastructure |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As per discussions with CCC's Funding Team - Council has declared a surplus. | -730022 | -372311 | [5 empty] | 276028 |  | 126416
2023-11-23 | November 2023 Review | Cost Decrease | Public transport infrastructure | Low cost / low risk public transport improvements | Hastings District Council | Low cost / low risk improvements 2021-24 | Public transport infrastructure |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Program reprioritisation as a result of pressures on resources and local share post-Cyclone | -216950 | -114984 | [5 empty] | 276155 |  | 126410
2023-11-23 | November 2023 Review | Cost Decrease | Public transport infrastructure | Low cost / low risk public transport improvements | Palmerston North City Council | Low cost / low risk improvements 2021-24 | Public transport infrastructure |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | WC discussion undertaken to consolidate spending and programme capabilities resulting in change request. | -67861 | -34609 | [5 empty] | 276347 |  | 125689
2023-11-01 | November 2023 Review | Cost Increase | Investment management (incl. Transport Planning) | Management of the funding allocation system | NZ Transport Agency | Investment in the Funding Allocation System (IFAS) | Implementation | TS assurance and decision making improvements | HHVH | HHVH | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 2019 | 2019 |  |  | 1 | 1 | TS Assurance & Decision Making Improve:60068894 | 282948 |  | 126184
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Minor events | Ashburton District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Increase of $1,000,000 for sealed road pavement rehabilitation. Council has awarded two contracts for the current approved subsidised funding. Council has budgeted $1,000,000 unsubsidised for sealed rural road overlays and is about to award a third contract for that work. So Council's share will be available from that and construction will be completed in 2023/24. | 3075 | 1568 | [5 empty] | 272153 |  | 126195
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Minor events | Kaikoura District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The district spend on road maintenance, operations and renewals, when expressed as $/km, was amongst lowest in the country throughout the 2010s decade. Such very low levels of expenditure have been driven by a previous Council desire for austerity in an environment where an extremely small district had many competing financial pressures including those associated with the 2016 earthquake and it is not surprising that such sustained low expenditure has had negative effects on the network. Road conditions deteriorated and a significant backlog of pavement reconstruction and resealing work developed, further increasing the required level of investment. Since 2018 KDC has been attempting to escape from this vicious circle but it has proven difficult because of limited financial support for our NLTP programs. An attempt was made to significantly lift expenditure in the 2018-21 NLTP, but Waka Kotahiâ€™s funding of the proposed program fell well short of what was requested, with a result that relatively low levels of investment persisted. KDCâ€™s average 2018-2021 spend on sealed pavement maintenance was only $3,000/km, whilst the corresponding figure for the comparable provincial centres peer group was $5,775/km, and it is extremely difficult to prevent the condition of the network declining with a maintenance spend that is so low. A further attempt was made to increase road maintenance in the Districtâ€™s 2021-2024 NLTP, and in that case with our bid was supported by an Activity Management Plan which clearly evidenced the need for additional investment, and was a document which and which we understand was seen as an exemplar by Waka Kotahi. Unfortunately despite this there was again a large shortfall in subsidy allocation against our bid, in this case leaving 33% of the proposed subsidised program ($2,292,800 of $6,994,000 in total) unfunded. Whilst such a shortfall figure might be a relatively modest one for many districts, it is major for the Kaikoura District which has a population of less than 4000 people. The immediate consequence of the shortfall of funding against our 2021-24 NLTP bid has been that our Council has resolved to increase its use of debt funding for renewals and to cut overall operational budgets by 10%, even though these budgets were already very lean. At the present time around 71% of Councils roading costs are being locally funded, which is considered an unsatisfactory situation. The cost increase mentioned above primarily apply to the renewal budget, with the majority allocated to categories 212 and 214, aimed at addressing the persistent backlog in road maintenance. A significant allocation for category 225 has been dedicated to ensuring that the Council fulfills its commitment to enhancing and maintaining the level of service for footpaths. Adjustments in costs have been considered essential for routine drainage maintenance and the upkeep of unsealed pavements to ensure the minimum level of service is maintained during periods of heavy rain impacting the road infrastructure. | 29274 | 14930 | [5 empty] | 272886 |  | 126213
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Minor events | Timaru District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Due to significant changes in construction, material costs, compliance regulations, and fluctuations in contract expenses, we are seeking additional funding in various critical work categories. These increased costs and unforeseen events have adversely affected our ability to execute and complete essential projects within our current budgetary confines | 60828 | 31022 | [5 empty] | 274383 |  | 126197
2023-11-27 | November 2023 Review | Cost Increase | Local road maintenance | Network and asset management | Chatham Islands Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Cost Scope Adjustment following phone call with Suv to advise of potential additional MOR funding available: Adjustments to programme - to recoup 23/24 programme adjustments to cover 2022/23 shortfalls due to elevated contractor and consultant cost fluctuation indices, and - to apply additional cost escalations for contractor and consultant cost fluctuation indices remaining high into FY 23/24. | 3000 | 2640 | [5 empty] | 272357 |  | 126215
2023-11-20 | November 2023 Review | Cost Increase | State highway maintenance | Network and asset management | NZTA (Canterbury) | 2021-24 NLTP funds management | Repayment | AC9 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 5771656 | 5771656 | [5 empty] | 279053 |  | 126478
2023-11-20 | November 2023 Review | Cost Decrease | State highway maintenance | Network and asset management | NZTA (Gisborne) | 2021-24 NLTP Funds Management | Repayment | AC-9 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -130659 | -130659 | [5 empty] | 282285 |  | 126474
2023-11-20 | November 2023 Review | Cost Decrease | State highway maintenance | Network and asset management | NZTA (Northland) | 2021-24 NLTP funds management | Repayment | AC-9 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -6331341 | -6331341 | [5 empty] | 282286 |  | 126475
2023-11-20 | November 2023 Review | Cost Decrease | State highway maintenance | Network and asset management | NZTA (Taranaki) | 2021-24 NLTP Funds Management | Repayment | AC-9 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -125672 | -125672 | [5 empty] | 282289 |  | 126479
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Network and asset management | Waimakariri District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | In the September Programme Monitor Council indicated it would be supplementing the co-funded programme with a significant sum of unsubsidised budget. Council had given approval to an additional sum of around 2M, both to ensure that day to day work and levels of service could be maintained, and to try to tackle a few areas of significant defects in the drainage aspects of our network This application is to request co-funding to the level Council feels it requires order to maintain a safe and appropriate network this financial year. The current budget available to Council, including the unsubsidised share is $12.55M. Without additional co-funding a decline in our LOS and network safety is anticipated. Drivers for the increased costs include 22% cost fluctuations over the last two years, plus another significant increase this year, over and above he usual high growth and weather related impacts on our network | 760 | 388 | [5 empty] | 274476 |  | 126322
2023-11-28 | November 2023 Review | Cost Decrease | Local road maintenance | Network and asset management | Waimate District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Work Categories adjusted to amounts forecasted in October programmed monitor. Increased amounts to cover increased contract cost due to cost fluctuations. 111 Seal Pavement Maintenace $180,000 113 Routine drainage maintenance $ 110,000 125 Footpath maintenance $ 10,000 213 Drainage renewals $ 47,000 (includes Dash Street K&C very poor condition with pavement failure) 214 Sealed Road pavement rehabilitation $55,000 225 Footpath renewal $ 58,000 (With Dash St K&C renewal) Total $460,000 Council Confirms Work can be completed by 30 June 2024 Local Council share is available. | -34998 | -22399 | [5 empty] | 274501 |  | 126224
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Network and asset management | Wellington City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Seeking reinstatement of previously declared surpluses and addition funds. Request for urgent streetlighting repairs were funded from within the program creating a shortfall in current year. Also heavy bus loadings are unmet in current program. Increased environmental maintenance as a result of extended heavy rainfall that are not qualifying as emergency events. | 669699 | 341546 | [5 empty] | 274673 |  | 125429
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Network operations | Waimakariri District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | In the September Programme Monitor Council indicated it would be supplementing the co-funded programme with a significant sum of unsubsidised budget. Council had given approval to an additional sum of around 2M, both to ensure that day to day work and levels of service could be maintained, and to try to tackle a few areas of significant defects in the drainage aspects of our network This application is to request co-funding to the level Council feels it requires order to maintain a safe and appropriate network this financial year. The current budget available to Council, including the unsubsidised share is $12.55M. Without additional co-funding a decline in our LOS and network safety is anticipated. Drivers for the increased costs include 22% cost fluctuations over the last two years, plus another significant increase this year, over and above he usual high growth and weather related impacts on our network | 11831 | 6034 | [5 empty] | 274474 |  | 126322
2023-11-27 | November 2023 Review | Cost Increase | Local road maintenance | Network service maintenance | Chatham Islands Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Cost Scope Adjustment following phone call with Suv to advise of potential additional MOR funding available: Adjustments to programme - to recoup 23/24 programme adjustments to cover 2022/23 shortfalls due to elevated contractor and consultant cost fluctuation indices, and - to apply additional cost escalations for contractor and consultant cost fluctuation indices remaining high into FY 23/24. | 3000 | 2640 | [5 empty] | 272354 |  | 126215
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Network service maintenance | Dunedin City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Dunedin City Council (DCC) submitted a Maintenance, Operations and Renewals (MOR) bid of $124.89m, funding was approved to a ceiling of $104.25m, a shortfall of $20.64m on asset management-based network needs. DCC anticipated a shortfall in Waka Kotahi co-funding so budgeted to deliver $11m of renewals with 100% local share funding over the 2021-24 period whist reducing the volume of pavement rehabilitation and footpath renewals to meet approved bottom line budgets. Changes in the Temporary Traffic Management (TTM) requirements have led to an increase in costs in the region of $1m per annum, the TTM market is constrained in the region and more qualified STMS workers are in demand and remunerated accordingly. Under the DCC Maintenance Contract traffic management is separated from unit rates and charged at a day rate, this transparency results in a clear trend in increase in costs from 8% of overall works to 11%, with an overall annual contract spend of around $24m this is an unbudgeted increase of $720k this year which is required to be absorbed within existing budgets. Our contracts are escalated using the Waka Kotahi Network Outcomes index, while year on year escalations have stabilised in recent months the overall escalation from our funding bid to now are at 16%, well above budgeted inflation levels. In our operational budget the increase accounts for $2m of our local budget request for 2022-23 and 2023-24. Our overall forecast for the 2021-24 funding cycle is $119.23m against funding of $104.25m, taking into the account the $11m of locally funded renewals we have a shortfall in co-funding of $3.98m. The local share for this work is budgeted but without additional Waka Kotahi approvals DCC will need to rationalise MOR programmes to meet budget. Due to contract conditions this rationalisation will need to be found in resealing and pavement rehabilitation, this is sub-optimal situation with DCC having some of the worst condition indexes nationwide for carriageways and pavements. | 830000 | 423300 | [5 empty] | 272452 |  | 126339
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Network service maintenance | Gore District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The requested increases are the result of cost inflation, renewed physical works contracts which contained higher rates including accommodating significant increased traffic management requirements. Significant increased quantities of work have been needed to maintain our level of service on both sealed and unsealed roads. This has been contributed to by significant detrimental weather events which appear to be occuring more regularly and of increasing magnitude. The Council recognised these factors in approving significant increased local funding for roading in its 2021/22 and 2023/24 Annual Plans. This request for cost scope adjustment will match these local funds already provided. Delivery of the increased works for which increased funding is requested has been delivered during the 2022/23 year which provides evidence that the Council has the ability to deliver the increased works. | 19208 | 11333 | [5 empty] | 272589 |  | 126330
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Network service maintenance | Selwyn District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | There has been significant cost pressure in recent years regarding the delivery of the MOR program. On top of inflation at 6% per year, industry-wide changes also added to the costs: 1) Regulatory changes: ECAN Dumping Fee, holiday pay and sick leave pay, adding $1m/year; 2) Market structure change: Bitumen cost increase, adding $1m/year; and 3) More emergency works from severe weather events. As a result, SDC had to use funds allocated to renewals to do maintenance and was only able to deliver 23km of reseals against a target of 75km in 22/23. For 23/24, SDC allocated $3,072,828 (see attached) in unsubsidized funds to supplement WK-approved MOR budget to deliver targeted reseals in 23/24. In the recent program monitor (see attached), we have planned $2,653,762 in unsubsidized MOR spending. This still leaves areas including sealed pavement maintenance, drainage maintenance and renewals, and pavement renewals underfunded. Since then, we have identified an additional $3,088,934 of work in those categories (see attached) that could be delivered in 23/24 if additional WK funding becomes available. Together we are requesting an increase of $5,742,696 in approved budget. The $3,072,828 already allocated by the SDC annual plan can cover the local share portion of the requested increase. Our contractor HEB has indicated that they will be able to deliver the works in 23/24 | 55560 | 28336 | [5 empty] | 273970 |  | 126225
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Network service maintenance | Waimakariri District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | In the September Programme Monitor Council indicated it would be supplementing the co-funded programme with a significant sum of unsubsidised budget. Council had given approval to an additional sum of around 2M, both to ensure that day to day work and levels of service could be maintained, and to try to tackle a few areas of significant defects in the drainage aspects of our network This application is to request co-funding to the level Council feels it requires order to maintain a safe and appropriate network this financial year. The current budget available to Council, including the unsubsidised share is $12.55M. Without additional co-funding a decline in our LOS and network safety is anticipated. Drivers for the increased costs include 22% cost fluctuations over the last two years, plus another significant increase this year, over and above he usual high growth and weather related impacts on our network | 1013798 | 517037 | [5 empty] | 274473 |  | 126322
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Network service maintenance | Waimate District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Work Categories adjusted to amounts forecasted in October programmed monitor. Increased amounts to cover increased contract cost due to cost fluctuations. 111 Seal Pavement Maintenace $180,000 113 Routine drainage maintenance $ 110,000 125 Footpath maintenance $ 10,000 213 Drainage renewals $ 47,000 (includes Dash Street K&C very poor condition with pavement failure) 214 Sealed Road pavement rehabilitation $55,000 225 Footpath renewal $ 58,000 (With Dash St K&C renewal) Total $460,000 Council Confirms Work can be completed by 30 June 2024 Local Council share is available. | 34344 | 21980 | [5 empty] | 274498 |  | 126224
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Network service maintenance | Waitaki District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | *sealed pavement maintenance - increased rates in new road maintenance contract October 2022 and $300k to allow pre-reseal repairs to be completed a year ahead of reseals *unsealed pavement maintenance - increased rates in new road maintenance contract October 2022 and to allow for achieving level of service in grading of unsealed network *routine drainage maintenance - increased rates in new road maintenance contract October 2022 and annual commitment of new contract *network service maintenance - increase in road marking to complete full remark of road network to ensure that levels of service are achieved *unsealed road metalling - increased rates in new road maintenance contract October 2022 and annual commitment of new contract | 100000 | 57000 | [5 empty] | 274596 |  | 126226
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Network service maintenance | Wellington City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Seeking reinstatement of previously declared surpluses and addition funds. Request for urgent streetlighting repairs were funded from within the program creating a shortfall in current year. Also heavy bus loadings are unmet in current program. Increased environmental maintenance as a result of extended heavy rainfall that are not qualifying as emergency events. | 819904 | 418151 | [5 empty] | 274670 |  | 125429
2023-11-03 | November 2023 Review | Cost Decrease | Local road improvements | New roads | Auckland Transport | Medallion Drive Upgrade | Implementation | Medallion Drive Upgrade - Implementation | H_L | M_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, this project is now complete, with only property costs still in Land Valuation Tribunal. AT is declaring the minor balance surplus. | -49352 | -25170 |  |  | 0 | 2.4 | 323.2383 | 238306 |  | 126243
2023-11-03 | November 2023 Review | Cost Decrease | Debt Funding | New roads | Auckland Transport | TNFG - North West HIF | Implementation | TNFG - NW HIF - Redhills (IMP) | HHH | HLH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Redhills section B and C have been taken out of this activity resulting in the reduction of funding to Auckland Transport for this activity. Note - section B and C of the Redhills area will use the standard RLTP/NLTP process and funds at a later date based on Auckland Transport prioritisation. | -17581205 | -17581205 |  |  | 5 | 1.4 | 323.264 | 263982 |  | 126316
2023-11-03 | November 2023 Review | Cost Decrease | Local road improvements | New roads | Auckland Transport | TNFG - South - Drury Local | Pre-implementation* | TNFG - South - Drury Local | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, this activity is being finalised and costs have been less than approved. A partial surplus is declared while final costs are determined. | -1000000 | -510000 |  |  | 1.1 | 1 | 324.2604 | 260420 |  | 126241
2023-11-30 | November 2023 Review | Cost Increase | External funding | New roads | NZTA (Auckland) | SH1 Papakura to Bombay | Implementation |  | H_M | VHHM | N | 0 | Approved | Approved by Minister for Crown Appropriation | Funding change after the FY23 new delegation letter. P2D is getting the previous programme held P50 contingency plus new funding minus the 0.5% increase in TIO admin. | 111342901 | 111342901 |  |  | 2.5 |  |  | 278974 | 60063236 | 126361
2023-11-16 | November 2023 Review | Cost Increase | Local road improvements | New roads | Opotiki District Council | Opotiki Harbour Access Road | Implementation | Opotiki Harbour Access Road Development - LR Imp | HHL | MHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | This funding enables the completion of Snell Road, servicing the harbour entrance and future boat ramp, and providing a safe walking and cycling facility. | 2107897 | 1580922 |  |  | 0 | 1.2 |  | 278743 |  | 125951
2023-11-13 | November 2023 Review | Cost Increase | State highway improvements | New traffic management facilities | NZTA (Canterbury) | Weigh Right Rakaia | Implementation | Construction/Implementation (C) | H_VH | HHVH | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Inter-Programme Transfer: Please transfer $132,367 from 60047945 - Property, $31,208 to 60047933 - Property and $101,159 to 60044273 Implementation | 110263 | 110263 |  |  | 14 | 14 |  | 250273 | 60044273 | 126394
2023-11-10 | November 2023 Review | Cost Decrease | External funding | Passenger facilities and infrastructure improvements - bus | Horizons Manawatu | CERF-TC - Horizons Palmerston North & Whanganui | Pre-implementation* | Horizons TC | HHH | HHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As per CERF programme directive to reduce 10% of budget across all projects | -178311 | -169911 |  |  | 0 | 0 |  | 283908 |  | 126378
2023-11-06 | November 2023 Review | Cost Increase | External funding | Passenger services - bus | Auckland Transport | CERF - Bus Driver Ts & Cs | Implementation | CERF - Driver Wage Uplift | VHHL | VHHL | N | 2 | Approved | Approved by Minister for Crown Appropriation | Tranche 2 of Crown funding. | 26767140 | 13651242 |  |  |  | 1 | 511.2842 | 284190 |  | 126358
2023-11-06 | November 2023 Review | Cost Increase | External funding | Passenger services - bus | Auckland Transport | CERF - Bus Driver Ts & Cs | Implementation | CERF - Driver Wage Uplift | VHHL | VHHL | N | 2 | Approved | Approved by Minister for Crown Appropriation | Original tranche of funding was missing $30k for years 3 and 4. | 60000 | 30600 |  |  |  | 1 | 511.2842 | 284190 |  | 126359
2023-11-03 | November 2023 Review | Cost Decrease | External funding | Passenger services - bus | Tasman District Council | CERF-Bus Driver Ts & Cs | Implementation | CERF share of driver wage uplift-wrong funding | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -145645 | -74279 |  |  |  | 1 |  | 284197 |  | 125927
2023-11-08 | November 2023 Review | Cost Decrease | External funding | Passenger services - bus | Tasman District Council | CERF-Bus Driver Ts & Cs | Implementation | CERF - Driver Wage Uplift | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Correct FAR | 0 | -71366 |  |  |  | 1 |  | 289286 |  | 126386
2023-11-10 | November 2023 Review | Cost Decrease | Investment management (incl. Transport Planning) | Programme Business Case Development | Auckland Transport | Electric Vehicle Uptake PBC | Programme business case |  | VHHL | HML | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, AT has paused the development of the PBC and so the balance of this activity is being declared surplus and a new POE will be considered when this becomes a priority. | -417944 | -213151 |  |  |  |  | 4.2811 | 281120 |  | 126232
2023-11-20 | November 2023 Review | Cost Increase | Investment management (incl. Transport Planning) | Programme Business Case Development | NZ Transport Agency | Innovation Programme | Programme business case |  | HHL | VHHM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 1035000 | 1035000 |  |  |  |  | 60069122 | 277975 |  | 126415
2023-11-01 | November 2023 Review | Cost Increase | Investment management (incl. Transport Planning) | Programme Business Case Development | NZ Transport Agency | Land Transport Security Programme | Programme business case |  | VHHM | VHHH | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 13059 | 13059 |  |  |  |  | SAP Item Id: 60065998 (continuation) | 278082 |  | 126183
2023-11-03 | November 2023 Review | Cost Decrease | Investment management (incl. Transport Planning) | Programme Business Case Development | NZ Transport Agency | National Resilience Programme Business Case | Programme business case |  | H__ | H__ | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project complete in previous years. This is now being surplused. | -100242 | -100242 |  |  |  |  | 80002479 | 266302 |  | 126331
2023-11-10 | November 2023 Review | Cost Decrease | Investment management (incl. Transport Planning) | Programme Business Case Development | NZ Transport Agency | Transport Planning activities - Internal Costs | Programme business case |  | HH_ | HH_ | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2023/24 as activity is claiming complete | -3193905 | -3193905 | [5 empty] | 237589 |  | 126367
2023-11-23 | November 2023 Review | Cost Decrease | Investment management (incl. Transport Planning) | Programme Business Case Development | NZTA (BOP) | Tauranga Eastern Link equity assessment | Programme business case |  | HHH | HHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | project close | -16028 | -16028 | [5 empty] | 281981 | 60067744 | 126303
2023-11-17 | November 2023 Review | Cost Increase | Investment management (incl. Transport Planning) | Programme Business Case Development | NZTA (Gisborne) | TairÄwhiti and Wairoa Resilience PBC | Programme business case |  | VHHVH | VHHH | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please transfer $15,775 from 60070304 - Programme Business Case to 60070071 - Programme Business Case, Both Programme Business Cases can then be closed. | 17171 | 17171 |  |  |  |  | Admin rate of 9% included | 283876 | 60070071 | 126424
2023-11-17 | November 2023 Review | Cost Decrease | Investment management (incl. Transport Planning) | Programme Business Case Development | NZTA (Hawkes Bay) | Hawkes Bay Resilience Strategic PBC | Programme business case |  | VHHM | VHHVH | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please transfer $15,775 from 60070304 - Programme Business Case to 60070071 - Programme Business Case, Both Programme Business Cases can then be closed. | -17196 | -17196 | [5 empty] | 284039 | 60070304 | 126423
2023-11-10 | November 2023 Review | Cost Decrease | Investment management (incl. Transport Planning) | Programme Business Case Development | NZTA (Waikato) | Waikato Hospital Travel Planning Initiat | Programme business case |  | HHM | HHL | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | project close | -14985 | -14985 | [5 empty] | 277992 | 60060874 | 126306
2023-11-30 | November 2023 Review | Cost Increase | External funding | Property purchase (State highways) | NZTA (Auckland) | NZUP Mill Road Corridor | Property | NZ Upgrade Programme | H_L | HHL | N | 0 | Approved | Approved by Minister for Crown Appropriation | Actuals exceed Funding Allocation | 72571 | 72571 |  |  | 1.2 | 1.2 |  | 269743 | 60056118 | 126508
2023-11-30 | November 2023 Review | Cost Decrease | External funding | Property purchase (State highways) | NZTA (Auckland) | NZUP SH22 (Drury) Corridor Upgrade | Property |  | MML | MML | N | 9 | Approved | Approved by Minister for Crown Appropriation |  | -7182457 | -7182457 |  |  |  | 1.7 |  | 282184 | 60067986 | 126503
2023-11-30 | November 2023 Review | Cost Decrease | External funding | Property purchase (State highways) | NZTA (Auckland) | NZUP Waihoehoe Road (Drury) Upgrade | Property |  | MML | MML | N | 9 | Approved | Approved by Minister for Crown Appropriation |  | -2785155 | -2785155 |  |  |  | 1.8 |  | 282204 | 60067985 | 126502
2023-11-13 | November 2023 Review | Cost Decrease | State highway improvements | Property purchase (State highways) | NZTA (Auckland) | Weigh Right Bombay | Property |  | HMH | HMVH | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Inter-Programme Transfer: Please transfer $1,056 from 60047944 - Inter-Programme Transfer: Please transfer $132,367 from 60047945 - Property $16,984 from 60048365, $31,208 to 60047933 - Property and $101,159 to 60044273 Implementation | -1119 | -1119 |  |  | 14 | 14 |  | 261996 | 60047944 | 126397
2023-11-23 | November 2023 Review | Cost Decrease | State highway improvements | Property purchase (State highways) | NZTA (BOP) | Poike Road Pedestrian & Cycle Facility | Property |  | L_M | H_L | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | project close surplus | -4092 | -4092 |  |  | 2.5 | 2.5 | 60039160 | 246968 | 60039160 | 126438
2023-11-13 | November 2023 Review | Cost Decrease | State highway improvements | Property purchase (State highways) | NZTA (BOP) | Weigh Right Tauranga Port | Property |  | H_VH | HHVH | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Inter-Programme Transfer: Please transfer $132,367 from 60047945 - Property, $31,208 to 60047933 - Property and $101,159 to 60044273 Implementation | -140309 | -140309 |  |  | 14 | 14 |  | 260623 | 60047945 | 126398
2023-11-13 | November 2023 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Canterbury) | Weigh Right Rakaia | Property |  | H_VH | HHVH | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Inter-Programme Transfer: Please transfer $31,208 from 60047945 - Property & $16,984 from 60048365 - Property & $1,056 from 60047944 - Property to 60047933 - Property (Total Transfer $ 49,248) | 52202 | 52202 |  |  | 14 | 14 |  | 260276 | 60047933 | 126396
2023-11-13 | November 2023 Review | Cost Decrease | State highway improvements | Property purchase (State highways) | NZTA (Wellington) | Weigh Right MacKay's | Property |  | H_H | MMM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Inter-Programme Transfer: Please transfer $132,367 from 60047945 - Property $16,984 from 60048365, $31,208 to 60047933 - Property and $101,159 to 60044273 Implementation | -18003 | -18003 |  |  | 14 | 14 | 60048365 | 262617 | 60048365 | 126395
2023-11-03 | November 2023 Review | Cost Decrease | Local road improvements | Property purchase (local roads) | Auckland Transport | Lincoln Road Corridor Improvement | Property | Lincoln Road Corridor Imp-Property | HHVH | HHVH | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As requested by Waka Kotahi (as part of the 2024 NLTP development). AT have been asked to revert the approval (declare surplus) this activity while further work is undertaken on it and its priority in the 2024 RLTP. | -32393000 | -16520430 |  |  | 7.5 | 7.5 | 332.219 | 218995 |  | 126260
2023-11-03 | November 2023 Review | Cost Decrease | Local road improvements | Property purchase (local roads) | Auckland Transport | Ormiston Town Centre - Main Street Link | Property | Flat Bush Main St Coll Link - PROP | M_M | MMM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, this activity is now complete. A small costs is anticipated for final property gazetting however a partial surplus is declared while final costs are confirmed. | -100000 | -51000 |  |  | 0 | 3 | 332.2401 | 240088 |  | 126242
2023-11-03 | November 2023 Review | Cost Decrease | Debt Funding | Property purchase (local roads) | Auckland Transport | TNFG - North West HIF | Property | TNFG - NW HIF - Trig South (PROP) | HHH | HLH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The Trig Road works component is being descoped from this activity due to Auckland Council plan change work. | -53519972 | -53519972 |  |  | 5 | 1.4 | 332.264 | 263985 |  | 126314
2023-11-03 | November 2023 Review | Cost Decrease | Debt Funding | Property purchase (local roads) | Auckland Transport | TNFG - North West HIF | Property | TNFG - NW HIF - Redhills (PROP) | HHH | HLH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Redhills section B and C have been taken out of this activity resulting in the reduction of funding to Auckland Transport for this activity. Note - section B and C of the Redhills area will use the standard RLTP/NLTP process and funds at a later date based on Auckland Transport prioritisation. | -32289351 | -32289351 |  |  | 5 | 1.4 | 332.264 | 263983 |  | 126317
2023-11-03 | November 2023 Review | Cost Decrease | Public transport infrastructure | Public transport infrastructure and major renewals | Auckland Transport | Auckland Metro Train Capacity | Implementation | Auckland Metro Train Capacity - Imp | H_M | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, this activity is now complete so the residual balance is being declared surplus. | -57633 | -29393 |  |  | 2.8 | 2.8 | 531.2382 | 238206 |  | 126230
2023-11-03 | November 2023 Review | Cost Decrease | Public transport infrastructure | Public transport infrastructure and major renewals | Auckland Transport | NCI - Rosedale Station and Assoc. Local Road Improvements | Property | Green Bond Project - NCI - Rosedale Stn - Prop | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, and previous updates to Waka Kotahi, this phase has now been completed and the residual balance is being declared surplus. | -55070 | -28086 |  |  | 0 | 1.1 | 531.2384 | 238357 |  | 126231
2023-11-06 | November 2023 Review | Cost Increase | Public transport infrastructure | Public transport infrastructure and major renewals | Tauranga City Council | Tauranga Eastern Corridor Growth - Te Tumu Internal Infrastr | Single-Stage Business Case | SSBC | VHHL | VHHH | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | Completing the business case delivers a preferred option integrating the public transport facility in the Wairakei Town Centre in the overall development along with the internal transport corridors of the Te Tumu growth area. The Benefits will include: - Lower emissions and higher mode share for public transport and active modes (compared to traditionally planed suburbs) â€“ aiming for 30% public transport and active mode share. - Healthier, safer and more accessible communities with higher social and environmental outcomes â€“ self-contained trips within Te Tumu - Effective land use and a connected community â€“ affordability. | 380880 | 194249 |  |  | 2.7 | 2.7 | SSBC | 276702 |  | 126166
2023-11-28 | November 2023 Review | Cost Decrease | Local road maintenance | Rail level crossing warning devices maintenance | Waimakariri District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | In the September Programme Monitor Council indicated it would be supplementing the co-funded programme with a significant sum of unsubsidised budget. Council had given approval to an additional sum of around 2M, both to ensure that day to day work and levels of service could be maintained, and to try to tackle a few areas of significant defects in the drainage aspects of our network This application is to request co-funding to the level Council feels it requires order to maintain a safe and appropriate network this financial year. The current budget available to Council, including the unsubsidised share is $12.55M. Without additional co-funding a decline in our LOS and network safety is anticipated. Drivers for the increased costs include 22% cost fluctuations over the last two years, plus another significant increase this year, over and above he usual high growth and weather related impacts on our network | -117 | -59 | [5 empty] | 274475 |  | 126322
2023-11-28 | November 2023 Review | Cost Decrease | Local road maintenance | Rail level crossing warning devices maintenance | Waimate District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Work Categories adjusted to amounts forecasted in October programmed monitor. Increased amounts to cover increased contract cost due to cost fluctuations. 111 Seal Pavement Maintenace $180,000 113 Routine drainage maintenance $ 110,000 125 Footpath maintenance $ 10,000 213 Drainage renewals $ 47,000 (includes Dash Street K&C very poor condition with pavement failure) 214 Sealed Road pavement rehabilitation $55,000 225 Footpath renewal $ 58,000 (With Dash St K&C renewal) Total $460,000 Council Confirms Work can be completed by 30 June 2024 Local Council share is available. | -306 | -195 | [5 empty] | 274500 |  | 126224
2023-11-03 | November 2023 Review | Cost Decrease | Local road improvements | Replacement of bridges and other structures | Auckland Transport | NCI - Rosedale Station and Assoc. Local Road Improvements | Implementation | NCI - Rosedale LR Components - IMP | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, this phase is complete. AT is declaring the minor balance surplus. | -41688 | -21261 |  |  | 0 | 1.1 | 322.2665 | 266505 |  | 126244
2023-11-10 | November 2023 Review | Cost Decrease | State highway improvements | Replacement of bridges and other structures | NZTA (Auckland) | AHB Edge Barrier Strengthening | Implementation | AHB Edge Barrier Strengthening | HHVL | HHL | N | 9 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | project close | -1049956 | -1049956 |  |  |  | 0.8 |  | 275386 | 60059824 | 126305
2023-11-16 | November 2023 Review | Cost Increase | External funding | Resilience improvements | NZTA (Auckland) | Crown Resilience Programme LCLR AKL | Implementation | LCLR | VH_H | VHHH | N | 0 | Approved | Approved by Minister for Crown Appropriation | Admin cost of 6.5% to be included in approval | 458901 | 458901 |  |  |  | 4 |  | 288941 | 60071706 | 126422
2023-11-28 | November 2023 Review | Cost Decrease | External funding | Resilience improvements | NZTA (Otago) | Crown Resilience Programme LCLR OTA | Implementation |  | VH_H | VHHH | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transferring $300,000 allocation from Crown Resilience Programme LCLR OTA (item ID 60071739) to Crown Resilience Programme LCLR STLD (item ID 60071743) to move "SH94 Shooting Rail (Milford Road)" project from Otago to Southland. | -319500 | -319500 |  |  |  | 4 |  | 290381 | 60071739 | 126542
2023-11-30 | November 2023 Review | Cost Decrease | External funding | Resilience improvements | NZTA (Otago) | RIO SH01S Kakanui Rvr Flood Mitigation | Pre-implementation* |  | H_L | M_L | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funding removed and transferred to activity ID 171941 & phase Id 290580 as need to set up this activity using new template. | -200000 | -200000 |  |  |  |  | Design | 269725 | 60056073 | 126555
2023-11-06 | November 2023 Review | Cost Increase | Local road improvements | Road improvements | Auckland Transport | LRGF - Huapai / Kumeu SHA | Implementation | Kumeu/Huapai SHA - IMP | H_L | HHL | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Price increase without any scope change due to market escalation and constraints. A detailed break-down of the cost increase was analysed and is considered an acceptable request that complies with the Waka Kotahi requirements. | 1621612 | 827022 |  |  | 0 | 3.7 | 324.2384 | 238389 |  | 125706
2023-11-03 | November 2023 Review | Cost Decrease | Local road improvements | Road improvements | Auckland Transport | Lincoln Road Corridor Improvement | Implementation | Lincoln Road Corridor Imp-Const | HHVH | HHVH | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As requested by Waka Kotahi (as part of the 2024 NLTP development). AT have been asked to revert the approval (declare surplus) this activity while further work is undertaken on it and its priority in the 2024 RLTP. | -46446000 | -23687460 |  |  | 7.5 | 7.5 | 324.219 | 218977 |  | 126259
2023-11-03 | November 2023 Review | Cost Decrease | Debt Funding | Road improvements | Auckland Transport | TNFG - North West HIF | Implementation | TNFG - NW HIF - Trig South (IMP) | HHH | HLH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The Trig Road works component is being descoped from this activity due to Auckland Council plan change work. | -64051899 | -64051899 |  |  | 5 | 1.4 | 324.264 | 263984 |  | 126315
2023-11-30 | November 2023 Review | Cost Increase | External funding | Road improvements | NZTA (Auckland) | NZUP Mill Road Corridor | Detailed Business Case | NZ Upgrade Programme | H_L | HHL | N | 0 | Approved | Approved by Minister for Crown Appropriation | Actuals exceed Funding Allocation | 182124 | 182124 |  |  | 1.2 | 1.2 |  | 270661 | 60057736 | 126509
2023-11-30 | November 2023 Review | Cost Decrease | External funding | Road improvements | NZTA (Auckland) | NZUP Mill Road Corridor | Implementation | Mill Road Corridor NZUP | H_L | HHL | N | 0 | Approved | Approved by Minister for Crown Appropriation | Project is not going ahead at this stage. Funding decreases from $211,940,343.00 to $0 | -220417957 | -220417957 |  |  | 1.2 | 1.2 | NZ Upgrade Programme | 269744 | 60056119 | 126533
2023-11-30 | November 2023 Review | Cost Decrease | External funding | Road improvements | NZTA (Auckland) | NZUP Mill Road Corridor | Pre-implementation* | NZ Upgrade Programme | H_L | HHL | N | 0 | Approved | Approved by Minister for Crown Appropriation | Project is not going ahead at this stage. Funding decrease from $37,036,313.64 to $67,408.00. | -38447662 | -38447662 |  |  | 1.2 | 1.2 |  | 269742 | 60056117 | 126507
2023-11-30 | November 2023 Review | Cost Increase | External funding | Road improvements | NZTA (Auckland) | NZUP Penlink | Implementation |  | H_L | HML | N | 0 | Approved | Approved by Minister for Crown Appropriation | applying new funding per delegation letter to Penlink. approved by joint ministers (see attachment) | 52624574 | 52624574 |  |  | 13.4 | 7.8 |  | 278976 | 60063233 | 126308
2023-11-30 | November 2023 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Auckland) | NZUP SH22 (Drury) Corridor Upgrade | Implementation |  | MML | MML | N | 9 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -91653532 | -91653532 |  |  |  | 1.7 |  | 290216 |  | 126566
2023-11-30 | November 2023 Review | Cost Increase | External funding | Road improvements | NZTA (Auckland) | NZUP SH22 (Drury) Corridor Upgrade | Pre-implementation* |  | MML | MML | N | 9 | Approved | Approved by Minister for Crown Appropriation | New Funding approved by the minister. Funding increases from $6,763,284.83 to $13,530,929.10 | 7038350 | 7038350 |  |  |  | 1.7 |  | 281986 | 60067768 | 126500
2023-11-30 | November 2023 Review | Cost Increase | External funding | Road improvements | NZTA (Auckland) | NZUP Waihoehoe Road (Drury) Upgrade | Pre-implementation* |  | MML | MML | N | 9 | Approved | Approved by Minister for Crown Appropriation | New funding approved by the minister.Funding increases from $4,830,918.47 to $24,125,620.55 | 20066490 | 20066490 |  |  |  | 1.8 |  | 281988 | 60067770 | 126501
2023-11-20 | November 2023 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Auckland) | Northern Corridor Improvements (NCI) | Construction | Construction - Main | H_M | HHM | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | COVID Protection Framework (Traffic Light system) Claim: $15,475,786 (excl admin) approved 9/11/2023 | 16868604 | 16868604 |  |  | 3 | 3 | 60027507 | 254897 | 60027507 | 126436
2023-11-20 | November 2023 Review | Cost Increase | State highway improvements | Road improvements | NZTA (BOP) | 2021-24 NLTP funds management | Repayment | AC13 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 1484372 | 1484372 | [5 empty] | 278955 |  | 126472
2023-11-30 | November 2023 Review | Cost Increase | External funding | Road improvements | NZTA (BOP) | NZUP Takitimu North Link Stage 1 | Implementation | NZ Upgrade Programme | H_L | HHM | N | 0 | Approved | Approved by Minister for Crown Appropriation | Applying additional new delegation funding to Implementation phase. | 120749385 | 120749385 |  |  | 2 | 2 | 60057025 | 270272 | 60057025 | 126484
2023-11-30 | November 2023 Review | Cost Increase | External funding | Road improvements | NZTA (BOP) | NZUP Takitimu North Link Stage 1 | Implementation |  | H_L | HHM | N | 0 | Approved | Approved by Minister for Crown Appropriation | Applying new delegation letter funding to TNL1, to come to a $56m project contingency position | 28909040 | 28909040 |  |  | 2 | 2 |  | 278963 | 60063230 | 126483
2023-11-30 | November 2023 Review | Cost Decrease | External funding | Road improvements | NZTA (BOP) | NZUP Takitimu North Link Stage 2 | Pre-implementation* | NZ Upgrade Programme | H_L | H_L | N | 0 | Approved | Approved by Minister for Crown Appropriation | Applying TIO admin change to TNL2 (from 3.5% to 4%) | -193948 | -193948 |  |  | 1.3 | 1.3 | 60057026 | 263931 | 60057026 | 126532
2023-11-03 | November 2023 Review | Cost Decrease | External funding | Road improvements | NZTA (Gisborne) | SH35 and connecting routes: Resilience | Implementation | PGF | H__ | HMM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please transfer $900,000 from 60051600 Construction to 60051589 Pre-Implementation. Pre-Imp Phase can then be closed | -900001 | -900001 |  |  | 1 | 1 |  | 267791 | 60051600 | 126326
2023-11-03 | November 2023 Review | Cost Increase | External funding | Road improvements | NZTA (Gisborne) | SH35 and connecting routes: Resilience | Pre-implementation* | PGF | H__ | HMM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please transfer $900,000 from 60051600 Construction to 60051589 Pre-Implementation. Pre-Imp Phase can then be closed | 900000 | 900000 |  |  | 1 | 1 |  | 264778 | 60051589 | 126320
2023-11-03 | November 2023 Review | Cost Decrease | External funding | Road improvements | NZTA (Hawkes Bay) | SH2 Inter-Reg connections: Passing Opps | Implementation | PGF | H__ | HMM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please transfer $1,507,690 from 60052056 Construction, to 60052060 Pre-Implementation, Pre-Imp Phase can then be closed. | -1507694 | -1507694 |  |  | 1 | 0.8 | Implementation | 264871 | 60052056 | 126327
2023-11-03 | November 2023 Review | Cost Increase | External funding | Road improvements | NZTA (Hawkes Bay) | SH2 Inter-Reg connections: Passing Opps | Pre-implementation* | PGF | H__ | HMM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please transfer $1,507,690 from 60052056 Construction, to 60052060 Pre-Implementation, Pre-Imp Phase can then be closed. | 1507690 | 1507690 |  |  | 1 | 0.8 | Pre-implementation | 264870 | 60052060 | 126323
2023-11-20 | November 2023 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Hawkes Bay) | SH38 Wairoa to Murupara Business Case | Detailed Business Case | NLTF-SH Improvements | HLL | HLL | N | 8 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please transfer $9,526 from 60055024 - Pre Implementation to 60055023 - Detailed Business Case, Detailed Business Cases can then be closed. | 10383 | 10383 |  |  | 2.1 | 0.9 | 60055023 | 278804 | 60055023 | 126457
2023-11-30 | November 2023 Review | Cost Increase | External funding | Road improvements | NZTA (Manawatu/Whanganui) | NZUP Otaki to North of Levin | Implementation |  | H_L | HHL | N | 0 | Approved | Approved by Minister for Crown Appropriation | Giving previously programme held p50 contingency minus $5.4m (0.5% TIO increase) to O2NL's project contingency. | 103882497 | 103882497 |  |  | 1.4 | 1.4 |  | 279038 | 60063267 | 126540
2023-11-20 | November 2023 Review | Cost Increase | External funding | Road improvements | NZTA (Manawatu/Whanganui) | NZUP Otaki to North of Levin | Implementation |  | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 525249 | 525249 |  |  | 1.4 | 1.4 |  | 279038 | 60063267 | 126467
2023-11-20 | November 2023 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (Marlborough) | SH6 Blenheim to Woodbourne Safety Improvements | Implementation |  | VHML | VHHL | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please transfer $85,727 from 60044735 - Construction to 60062290 - Pre-Implementation, Pre-Imp phase can then be closed | -93442 | -93442 |  |  | 0 | 1.6 |  | 278197 | 60044735 | 126459
2023-11-20 | November 2023 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Marlborough) | SH6 Blenheim to Woodbourne Safety Improvements | Pre-implementation* | R2Z | VHML | VHHL | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please transfer $85,727 from 60044735 - Construction to 60062290 - Pre-Implementation, Pre-Imp phase can then be closed | 93442 | 93442 |  |  | 0 | 1.6 |  | 278544 | 60062290 | 126456
2023-11-20 | November 2023 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Northland) | 2021-24 NLTP funds management | Repayment | AC13 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -275283 | -275283 | [5 empty] | 279232 |  | 126476
2023-11-10 | November 2023 Review | Cost Decrease | External funding | Road improvements | NZTA (Northland) | NZUP SH1 Whangarei to Port Marsden H'way | Detailed Business Case | NZ Upgrade Programme | H_L | HML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer $59,801.00 from 60057017 to 60063196 to cover cost increase of 60063196 â€“ as per PSC approval | -62193 | -62193 |  |  | 1.1 | 1.1 | External Funding 60057017 | 270290 | 60057017 | 126278
2023-11-23 | November 2023 Review | Cost Decrease | External funding | Road improvements | NZTA (Northland) | NZUP SH1 Whangarei to Port Marsden H'way | Detailed Business Case |  | H_L | HML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | interphase transfer $178,230 from DBC 60063194 across to Preimplementation 60063196 due to increase in pre imp costs and closure of DBC | -185359 | -185359 |  |  | 1.1 | 1.1 | External Funding | 279033 | 60063194 | 126419
2023-11-10 | November 2023 Review | Cost Decrease | External funding | Road improvements | NZTA (Northland) | NZUP SH1 Whangarei to Port Marsden H'way | Pre-implementation* | NZ Upgrade Programme | H_L | HML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer $47,674.00 from 60046692 to 60063196 to cover cost increase of 60063196 â€“ as per PSC approval | -49581 | -49581 |  |  | 1.1 | 1.1 | External Funding | 258543 | 60046692 | 126277
2023-11-10 | November 2023 Review | Cost Increase | External funding | Road improvements | NZTA (Northland) | NZUP SH1 Whangarei to Port Marsden H'way | Pre-implementation* |  | H_L | HML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | (1) interphase transfer of (a) $47,674.00 from 60046692 and (b) $59,801.00 from 60057017 â€“ as per PSC approval; (2) Cashflow/allocation adjustment based on updated project programme | 111773 | 111773 |  |  | 1.1 | 1.1 | External Funding | 278969 | 60063196 | 126276
2023-11-23 | November 2023 Review | Cost Increase | External funding | Road improvements | NZTA (Northland) | NZUP SH1 Whangarei to Port Marsden H'way | Pre-implementation* |  | H_L | HML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | interphase transfer $178,230 from DBC 60063194 across to Preimplementation 60063196 due to increase in pre imp costs and closure of DBC | 185359 | 185359 |  |  | 1.1 | 1.1 | External Funding | 278969 | 60063196 | 126420
2023-11-24 | November 2023 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Northland) | SH1 Whangarei to Wellsford - (Southern Section) | Pre-implementation* |  | HML | HHM | N | 6 | Approved | Approved by Chief Financial Officer (CFO) |  | 699073 | 699073 |  |  | 0 | 1.6 |  | 278489 | 60062179 | 126186
2023-11-30 | November 2023 Review | Cost Increase | External funding | Road improvements | NZTA (Otago) | NZUP Queenstown Package | Implementation |  | M_M | MHM | N | 0 | Approved | Approved by Minister for Crown Appropriation | Applying additional funding from the FY23 Delegation letter. $22.6m is made up of $15m additional funding and $9m previous held programme contingency amount minus $0.5m of TIO admin rate increase. | 23546134 | 23546134 |  |  | 3.5 | 3.5 |  | 278964 | 60063228 | 126548
2023-11-10 | November 2023 Review | Cost Decrease | External funding | Road improvements | NZTA (Taranaki) | RIO SH43 Passing Opps & Wayfinding | Implementation | Construction | M_L | M_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Complete | -111 | -111 |  |  | 1 | 1 | 60056112 | 269739 | 60056112 | 126313
2023-11-20 | November 2023 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Wellington) | 2021-24 NLTP funds management | Repayment | AC13 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -1464132 | -1464132 | [5 empty] | 279277 |  | 126473
2023-11-30 | November 2023 Review | Cost Decrease | External funding | Road improvements | NZTA (Wellington) | NZUP Programme Contingency | Implementation | NZUP Programme Contingency | M_M | M_M | N | 0 | Approved | Approved by Minister for Crown Appropriation | Updating programme contingency allocation to match the new P95 contingency estimates | -21177528 | -21177528 |  |  | 0 | 0 |  | 271843 | 60059443 | 126552
2023-11-30 | November 2023 Review | Cost Increase | External funding | Road improvements | NZTA (Wellington) | NZUP SH2 Melling Efficiency & Safety Imp | Implementation |  | HMM | MMH | N | 5 | Approved | Approved by Minister for Crown Appropriation |  | 335182064 | 335182064 |  |  | 0 | 1.3 |  | 278984 | 60063250 | 126550
2023-11-24 | November 2023 Review | Cost Increase | Road to Zero | Road improvements | Selwyn District Council | Prebbleton Arterial CSM Related Upgrade Packages | Implementation | Shands/Trents Rd Roundabout | HML | HML | N | 6 | Approved | Approved by Chief Financial Officer (CFO) |  | 2328425 | 160477 |  |  | 1 | 1 |  | 260906 |  | 125936
2023-11-06 | November 2023 Review | Cost Increase | Local road improvements | Road improvements | Whangarei District Council | Port Rd/Kioreroa Rd Intersection Improvement | Implementation |  | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | A Cost/Scope Adjustment is required due to significant scope and cost change due to the following: â€¢ Significant cost escalation since the original contract award in July 2021. â€¢ Substantial increase in KiwiRail requirements and costs compared to what was originally allowed for. â€¢ Scope change during the development of the detailed design and construction stages. | 3485000 | 1847050 |  |  |  | 2.6 |  | 276968 |  | 126103
2023-11-27 | November 2023 Review | Cost Increase | Local road maintenance | Routine drainage maintenance | Chatham Islands Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Cost Scope Adjustment following phone call with Suv to advise of potential additional MOR funding available: Adjustments to programme - to recoup 23/24 programme adjustments to cover 2022/23 shortfalls due to elevated contractor and consultant cost fluctuation indices, and - to apply additional cost escalations for contractor and consultant cost fluctuation indices remaining high into FY 23/24. | 3000 | 2640 | [5 empty] | 272348 |  | 126215
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Routine drainage maintenance | Dunedin City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Dunedin City Council (DCC) submitted a Maintenance, Operations and Renewals (MOR) bid of $124.89m, funding was approved to a ceiling of $104.25m, a shortfall of $20.64m on asset management-based network needs. DCC anticipated a shortfall in Waka Kotahi co-funding so budgeted to deliver $11m of renewals with 100% local share funding over the 2021-24 period whist reducing the volume of pavement rehabilitation and footpath renewals to meet approved bottom line budgets. Changes in the Temporary Traffic Management (TTM) requirements have led to an increase in costs in the region of $1m per annum, the TTM market is constrained in the region and more qualified STMS workers are in demand and remunerated accordingly. Under the DCC Maintenance Contract traffic management is separated from unit rates and charged at a day rate, this transparency results in a clear trend in increase in costs from 8% of overall works to 11%, with an overall annual contract spend of around $24m this is an unbudgeted increase of $720k this year which is required to be absorbed within existing budgets. Our contracts are escalated using the Waka Kotahi Network Outcomes index, while year on year escalations have stabilised in recent months the overall escalation from our funding bid to now are at 16%, well above budgeted inflation levels. In our operational budget the increase accounts for $2m of our local budget request for 2022-23 and 2023-24. Our overall forecast for the 2021-24 funding cycle is $119.23m against funding of $104.25m, taking into the account the $11m of locally funded renewals we have a shortfall in co-funding of $3.98m. The local share for this work is budgeted but without additional Waka Kotahi approvals DCC will need to rationalise MOR programmes to meet budget. Due to contract conditions this rationalisation will need to be found in resealing and pavement rehabilitation, this is sub-optimal situation with DCC having some of the worst condition indexes nationwide for carriageways and pavements. | 271933 | 138686 | [5 empty] | 272446 |  | 126339
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Routine drainage maintenance | Gore District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The requested increases are the result of cost inflation, renewed physical works contracts which contained higher rates including accommodating significant increased traffic management requirements. Significant increased quantities of work have been needed to maintain our level of service on both sealed and unsealed roads. This has been contributed to by significant detrimental weather events which appear to be occuring more regularly and of increasing magnitude. The Council recognised these factors in approving significant increased local funding for roading in its 2021/22 and 2023/24 Annual Plans. This request for cost scope adjustment will match these local funds already provided. Delivery of the increased works for which increased funding is requested has been delivered during the 2022/23 year which provides evidence that the Council has the ability to deliver the increased works. | 99209 | 58533 | [5 empty] | 272583 |  | 126330
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Routine drainage maintenance | Kaikoura District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The district spend on road maintenance, operations and renewals, when expressed as $/km, was amongst lowest in the country throughout the 2010s decade. Such very low levels of expenditure have been driven by a previous Council desire for austerity in an environment where an extremely small district had many competing financial pressures including those associated with the 2016 earthquake and it is not surprising that such sustained low expenditure has had negative effects on the network. Road conditions deteriorated and a significant backlog of pavement reconstruction and resealing work developed, further increasing the required level of investment. Since 2018 KDC has been attempting to escape from this vicious circle but it has proven difficult because of limited financial support for our NLTP programs. An attempt was made to significantly lift expenditure in the 2018-21 NLTP, but Waka Kotahiâ€™s funding of the proposed program fell well short of what was requested, with a result that relatively low levels of investment persisted. KDCâ€™s average 2018-2021 spend on sealed pavement maintenance was only $3,000/km, whilst the corresponding figure for the comparable provincial centres peer group was $5,775/km, and it is extremely difficult to prevent the condition of the network declining with a maintenance spend that is so low. A further attempt was made to increase road maintenance in the Districtâ€™s 2021-2024 NLTP, and in that case with our bid was supported by an Activity Management Plan which clearly evidenced the need for additional investment, and was a document which and which we understand was seen as an exemplar by Waka Kotahi. Unfortunately despite this there was again a large shortfall in subsidy allocation against our bid, in this case leaving 33% of the proposed subsidised program ($2,292,800 of $6,994,000 in total) unfunded. Whilst such a shortfall figure might be a relatively modest one for many districts, it is major for the Kaikoura District which has a population of less than 4000 people. The immediate consequence of the shortfall of funding against our 2021-24 NLTP bid has been that our Council has resolved to increase its use of debt funding for renewals and to cut overall operational budgets by 10%, even though these budgets were already very lean. At the present time around 71% of Councils roading costs are being locally funded, which is considered an unsatisfactory situation. The cost increase mentioned above primarily apply to the renewal budget, with the majority allocated to categories 212 and 214, aimed at addressing the persistent backlog in road maintenance. A significant allocation for category 225 has been dedicated to ensuring that the Council fulfills its commitment to enhancing and maintaining the level of service for footpaths. Adjustments in costs have been considered essential for routine drainage maintenance and the upkeep of unsealed pavements to ensure the minimum level of service is maintained during periods of heavy rain impacting the road infrastructure. | 46200 | 23562 | [5 empty] | 272882 |  | 126213
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Routine drainage maintenance | Selwyn District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | There has been significant cost pressure in recent years regarding the delivery of the MOR program. On top of inflation at 6% per year, industry-wide changes also added to the costs: 1) Regulatory changes: ECAN Dumping Fee, holiday pay and sick leave pay, adding $1m/year; 2) Market structure change: Bitumen cost increase, adding $1m/year; and 3) More emergency works from severe weather events. As a result, SDC had to use funds allocated to renewals to do maintenance and was only able to deliver 23km of reseals against a target of 75km in 22/23. For 23/24, SDC allocated $3,072,828 (see attached) in unsubsidized funds to supplement WK-approved MOR budget to deliver targeted reseals in 23/24. In the recent program monitor (see attached), we have planned $2,653,762 in unsubsidized MOR spending. This still leaves areas including sealed pavement maintenance, drainage maintenance and renewals, and pavement renewals underfunded. Since then, we have identified an additional $3,088,934 of work in those categories (see attached) that could be delivered in 23/24 if additional WK funding becomes available. Together we are requesting an increase of $5,742,696 in approved budget. The $3,072,828 already allocated by the SDC annual plan can cover the local share portion of the requested increase. Our contractor HEB has indicated that they will be able to deliver the works in 23/24 | 657000 | 335070 | [5 empty] | 273964 |  | 126225
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Routine drainage maintenance | Waimakariri District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | In the September Programme Monitor Council indicated it would be supplementing the co-funded programme with a significant sum of unsubsidised budget. Council had given approval to an additional sum of around 2M, both to ensure that day to day work and levels of service could be maintained, and to try to tackle a few areas of significant defects in the drainage aspects of our network This application is to request co-funding to the level Council feels it requires order to maintain a safe and appropriate network this financial year. The current budget available to Council, including the unsubsidised share is $12.55M. Without additional co-funding a decline in our LOS and network safety is anticipated. Drivers for the increased costs include 22% cost fluctuations over the last two years, plus another significant increase this year, over and above he usual high growth and weather related impacts on our network | 352057 | 179549 | [5 empty] | 274467 |  | 126322
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Routine drainage maintenance | Waimate District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Work Categories adjusted to amounts forecasted in October programmed monitor. Increased amounts to cover increased contract cost due to cost fluctuations. 111 Seal Pavement Maintenace $180,000 113 Routine drainage maintenance $ 110,000 125 Footpath maintenance $ 10,000 213 Drainage renewals $ 47,000 (includes Dash Street K&C very poor condition with pavement failure) 214 Sealed Road pavement rehabilitation $55,000 225 Footpath renewal $ 58,000 (With Dash St K&C renewal) Total $460,000 Council Confirms Work can be completed by 30 June 2024 Local Council share is available. | 197648 | 126495 | [5 empty] | 274492 |  | 126224
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Routine drainage maintenance | Waitaki District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | *sealed pavement maintenance - increased rates in new road maintenance contract October 2022 and $300k to allow pre-reseal repairs to be completed a year ahead of reseals *unsealed pavement maintenance - increased rates in new road maintenance contract October 2022 and to allow for achieving level of service in grading of unsealed network *routine drainage maintenance - increased rates in new road maintenance contract October 2022 and annual commitment of new contract *network service maintenance - increase in road marking to complete full remark of road network to ensure that levels of service are achieved *unsealed road metalling - increased rates in new road maintenance contract October 2022 and annual commitment of new contract | 425954 | 242794 | [5 empty] | 274590 |  | 126226
2023-11-03 | November 2023 Review | Cost Decrease | Road to Zero | Safety promotion, education and advertising | Auckland Transport | Public Transport Programme 2021-24 - AC 23 | Operations |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, due to the rollover from FY23, the current approval exceeds expected spend for the yuear. AT is providing a partial surplus at this time. | -2314052 | -1180167 | [5 empty] | 272182 |  | 126238
2023-11-20 | November 2023 Review | Cost Decrease | State highway improvements | Seal extension | NZTA (Hawkes Bay) | SH38 Wairoa to Murupara Business Case | Pre-implementation* | Trial | HLL | HLL | N | 8 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please transfer $9,526 from 60055024 - Pre Implementation to 60055023 - Detailed Business Case, Detailed Business Cases can then be closed. | -10384 | -10384 |  |  | 2.1 | 0.9 | Pre Impl Trial | 254942 | 60055024 | 126458
2023-11-28 | November 2023 Review | Cost Decrease | Local road maintenance | Sealed pavement maintenance | Ashburton District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Increase of $1,000,000 for sealed road pavement rehabilitation. Council has awarded two contracts for the current approved subsidised funding. Council has budgeted $1,000,000 unsubsidised for sealed rural road overlays and is about to award a third contract for that work. So Council's share will be available from that and construction will be completed in 2023/24. | -3075 | -1568 | [5 empty] | 272147 |  | 126195
2023-11-27 | November 2023 Review | Cost Increase | Local road maintenance | Sealed pavement maintenance | Chatham Islands Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Cost Scope Adjustment following phone call with Suv to advise of potential additional MOR funding available: Adjustments to programme - to recoup 23/24 programme adjustments to cover 2022/23 shortfalls due to elevated contractor and consultant cost fluctuation indices, and - to apply additional cost escalations for contractor and consultant cost fluctuation indices remaining high into FY 23/24. | 6894 | 6067 | [5 empty] | 272346 |  | 126215
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Sealed pavement maintenance | Christchurch City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Christchurch City Council has been facing increasing cost escalations due to the rising costs of materials (in particular bitumen which impacts a number of activities), construction costs and increased costs within our maintenance contracts. The maintenance contracts for the Central, Southern, and Northern areas expired last October and were re-let. This led to an approximate increase of 20-30% across the contracts. In the past Council has consistently delivered additional works above the approved subsidised amount. This is now becoming more difficult due to current economic factors | 1728000 | 881280 | [5 empty] | 272371 |  | 126223
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Sealed pavement maintenance | Dunedin City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Dunedin City Council (DCC) submitted a Maintenance, Operations and Renewals (MOR) bid of $124.89m, funding was approved to a ceiling of $104.25m, a shortfall of $20.64m on asset management-based network needs. DCC anticipated a shortfall in Waka Kotahi co-funding so budgeted to deliver $11m of renewals with 100% local share funding over the 2021-24 period whist reducing the volume of pavement rehabilitation and footpath renewals to meet approved bottom line budgets. Changes in the Temporary Traffic Management (TTM) requirements have led to an increase in costs in the region of $1m per annum, the TTM market is constrained in the region and more qualified STMS workers are in demand and remunerated accordingly. Under the DCC Maintenance Contract traffic management is separated from unit rates and charged at a day rate, this transparency results in a clear trend in increase in costs from 8% of overall works to 11%, with an overall annual contract spend of around $24m this is an unbudgeted increase of $720k this year which is required to be absorbed within existing budgets. Our contracts are escalated using the Waka Kotahi Network Outcomes index, while year on year escalations have stabilised in recent months the overall escalation from our funding bid to now are at 16%, well above budgeted inflation levels. In our operational budget the increase accounts for $2m of our local budget request for 2022-23 and 2023-24. Our overall forecast for the 2021-24 funding cycle is $119.23m against funding of $104.25m, taking into the account the $11m of locally funded renewals we have a shortfall in co-funding of $3.98m. The local share for this work is budgeted but without additional Waka Kotahi approvals DCC will need to rationalise MOR programmes to meet budget. Due to contract conditions this rationalisation will need to be found in resealing and pavement rehabilitation, this is sub-optimal situation with DCC having some of the worst condition indexes nationwide for carriageways and pavements. | 1310999 | 668609 | [5 empty] | 272444 |  | 126339
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Sealed pavement maintenance | Gore District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The requested increases are the result of cost inflation, renewed physical works contracts which contained higher rates including accommodating significant increased traffic management requirements. Significant increased quantities of work have been needed to maintain our level of service on both sealed and unsealed roads. This has been contributed to by significant detrimental weather events which appear to be occuring more regularly and of increasing magnitude. The Council recognised these factors in approving significant increased local funding for roading in its 2021/22 and 2023/24 Annual Plans. This request for cost scope adjustment will match these local funds already provided. Delivery of the increased works for which increased funding is requested has been delivered during the 2022/23 year which provides evidence that the Council has the ability to deliver the increased works. | 114193 | 67374 | [5 empty] | 272581 |  | 126330
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Sealed pavement maintenance | Hurunui District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Costs have been revised for WC 111 & 112 requesting an overall increase of $1.2m. Currently HDC is having to top up both budgets with unsubsidised funding to undertake these core maintenance activities due to the impact of our new maintenance contract item rates including the cost escalations which were not known at the time of the 2021-2024 bid, the 2024-2027 AMP provides further detail regarding this. The works required this financial year are committed to this level of expenditure and we have a very high level of confidence these will be delivered. Any approved increase in funding will offset the amount of unsubsidised funding being provided by HDC. | 768000 | 399360 | [5 empty] | 272793 |  | 126227
2023-11-28 | November 2023 Review | Cost Decrease | Local road maintenance | Sealed pavement maintenance | Mackenzie District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Additional funding required for construction of two new washover fords. Total combined cost - $250,000 Nixon Road ford is required as the adjacent bridge is now not operational. Work was originally programmed to be completed in December '23. Construction is able to be completed in the 23/24 financial year. Local share for funding is confirmed. Jack Lovelock Track ford is deteriorating due to increased rainfall events. This project can be completed at the same time as Nixons Rd ford creating a saving in construction costs. Both fords have approved ECAN consent. | -901 | -460 | [5 empty] | 272980 |  | 126328
2023-11-20 | November 2023 Review | Cost Decrease | State highway maintenance | Sealed pavement maintenance | NZTA (BOP) | 2021-24 NLTP funds management | Implementation | Repayment - AC9 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -1849277 | -1849277 | [5 empty] | 288893 |  | 126477
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Sealed pavement maintenance | Selwyn District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | There has been significant cost pressure in recent years regarding the delivery of the MOR program. On top of inflation at 6% per year, industry-wide changes also added to the costs: 1) Regulatory changes: ECAN Dumping Fee, holiday pay and sick leave pay, adding $1m/year; 2) Market structure change: Bitumen cost increase, adding $1m/year; and 3) More emergency works from severe weather events. As a result, SDC had to use funds allocated to renewals to do maintenance and was only able to deliver 23km of reseals against a target of 75km in 22/23. For 23/24, SDC allocated $3,072,828 (see attached) in unsubsidized funds to supplement WK-approved MOR budget to deliver targeted reseals in 23/24. In the recent program monitor (see attached), we have planned $2,653,762 in unsubsidized MOR spending. This still leaves areas including sealed pavement maintenance, drainage maintenance and renewals, and pavement renewals underfunded. Since then, we have identified an additional $3,088,934 of work in those categories (see attached) that could be delivered in 23/24 if additional WK funding becomes available. Together we are requesting an increase of $5,742,696 in approved budget. The $3,072,828 already allocated by the SDC annual plan can cover the local share portion of the requested increase. Our contractor HEB has indicated that they will be able to deliver the works in 23/24 | 1065821 | 543569 | [5 empty] | 273962 |  | 126225
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Sealed pavement maintenance | Timaru District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Due to significant changes in construction, material costs, compliance regulations, and fluctuations in contract expenses, we are seeking additional funding in various critical work categories. These increased costs and unforeseen events have adversely affected our ability to execute and complete essential projects within our current budgetary confines | 351520 | 179275 | [5 empty] | 274377 |  | 126197
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Sealed pavement maintenance | Waimakariri District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | In the September Programme Monitor Council indicated it would be supplementing the co-funded programme with a significant sum of unsubsidised budget. Council had given approval to an additional sum of around 2M, both to ensure that day to day work and levels of service could be maintained, and to try to tackle a few areas of significant defects in the drainage aspects of our network This application is to request co-funding to the level Council feels it requires order to maintain a safe and appropriate network this financial year. The current budget available to Council, including the unsubsidised share is $12.55M. Without additional co-funding a decline in our LOS and network safety is anticipated. Drivers for the increased costs include 22% cost fluctuations over the last two years, plus another significant increase this year, over and above he usual high growth and weather related impacts on our network | 75634 | 38573 | [5 empty] | 274465 |  | 126322
2023-11-28 | November 2023 Review | Cost Decrease | Local road maintenance | Sealed pavement maintenance | Waimate District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Work Categories adjusted to amounts forecasted in October programmed monitor. Increased amounts to cover increased contract cost due to cost fluctuations. 111 Seal Pavement Maintenace $180,000 113 Routine drainage maintenance $ 110,000 125 Footpath maintenance $ 10,000 213 Drainage renewals $ 47,000 (includes Dash Street K&C very poor condition with pavement failure) 214 Sealed Road pavement rehabilitation $55,000 225 Footpath renewal $ 58,000 (With Dash St K&C renewal) Total $460,000 Council Confirms Work can be completed by 30 June 2024 Local Council share is available. | -17086 | -10935 | [5 empty] | 274490 |  | 126224
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Sealed pavement maintenance | Waitaki District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | *sealed pavement maintenance - increased rates in new road maintenance contract October 2022 and $300k to allow pre-reseal repairs to be completed a year ahead of reseals *unsealed pavement maintenance - increased rates in new road maintenance contract October 2022 and to allow for achieving level of service in grading of unsealed network *routine drainage maintenance - increased rates in new road maintenance contract October 2022 and annual commitment of new contract *network service maintenance - increase in road marking to complete full remark of road network to ensure that levels of service are achieved *unsealed road metalling - increased rates in new road maintenance contract October 2022 and annual commitment of new contract | 280511 | 159891 | [5 empty] | 274588 |  | 126226
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Sealed pavement maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The Councils joint maintenance contract extension rate increases have and will occur during the course of this 3 year NLTF period. This has impacted the cost of delivery for the 2 previous years which has limited the remaining approved sum for the current year (as previously noted in program monitor). A 20 month contract extension offer of service for the maintenance, operations and renewals is pending for 1 November 2023 but early indications expect cost increases over the previous 2022/23 year. | 15395923 | 7851921 | [5 empty] | 274700 |  | 125558
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Sealed road pavement rehabilitation | Ashburton District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Increase of $1,000,000 for sealed road pavement rehabilitation. Council has awarded two contracts for the current approved subsidised funding. Council has budgeted $1,000,000 unsubsidised for sealed rural road overlays and is about to award a third contract for that work. So Council's share will be available from that and construction will be completed in 2023/24. | 1000000 | 510000 | [5 empty] | 272162 |  | 126195
2023-11-27 | November 2023 Review | Cost Increase | Local road maintenance | Sealed road pavement rehabilitation | Chatham Islands Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Cost Scope Adjustment following phone call with Suv to advise of potential additional MOR funding available: Adjustments to programme - to recoup 23/24 programme adjustments to cover 2022/23 shortfalls due to elevated contractor and consultant cost fluctuation indices, and - to apply additional cost escalations for contractor and consultant cost fluctuation indices remaining high into FY 23/24. | 1000 | 880 | [5 empty] | 272361 |  | 126215
2023-11-28 | November 2023 Review | Cost Decrease | Local road maintenance | Sealed road pavement rehabilitation | Dunedin City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Dunedin City Council (DCC) submitted a Maintenance, Operations and Renewals (MOR) bid of $124.89m, funding was approved to a ceiling of $104.25m, a shortfall of $20.64m on asset management-based network needs. DCC anticipated a shortfall in Waka Kotahi co-funding so budgeted to deliver $11m of renewals with 100% local share funding over the 2021-24 period whist reducing the volume of pavement rehabilitation and footpath renewals to meet approved bottom line budgets. Changes in the Temporary Traffic Management (TTM) requirements have led to an increase in costs in the region of $1m per annum, the TTM market is constrained in the region and more qualified STMS workers are in demand and remunerated accordingly. Under the DCC Maintenance Contract traffic management is separated from unit rates and charged at a day rate, this transparency results in a clear trend in increase in costs from 8% of overall works to 11%, with an overall annual contract spend of around $24m this is an unbudgeted increase of $720k this year which is required to be absorbed within existing budgets. Our contracts are escalated using the Waka Kotahi Network Outcomes index, while year on year escalations have stabilised in recent months the overall escalation from our funding bid to now are at 16%, well above budgeted inflation levels. In our operational budget the increase accounts for $2m of our local budget request for 2022-23 and 2023-24. Our overall forecast for the 2021-24 funding cycle is $119.23m against funding of $104.25m, taking into the account the $11m of locally funded renewals we have a shortfall in co-funding of $3.98m. The local share for this work is budgeted but without additional Waka Kotahi approvals DCC will need to rationalise MOR programmes to meet budget. Due to contract conditions this rationalisation will need to be found in resealing and pavement rehabilitation, this is sub-optimal situation with DCC having some of the worst condition indexes nationwide for carriageways and pavements. | -345667 | -176290 | [5 empty] | 272459 |  | 126339
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Sealed road pavement rehabilitation | Kaikoura District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The district spend on road maintenance, operations and renewals, when expressed as $/km, was amongst lowest in the country throughout the 2010s decade. Such very low levels of expenditure have been driven by a previous Council desire for austerity in an environment where an extremely small district had many competing financial pressures including those associated with the 2016 earthquake and it is not surprising that such sustained low expenditure has had negative effects on the network. Road conditions deteriorated and a significant backlog of pavement reconstruction and resealing work developed, further increasing the required level of investment. Since 2018 KDC has been attempting to escape from this vicious circle but it has proven difficult because of limited financial support for our NLTP programs. An attempt was made to significantly lift expenditure in the 2018-21 NLTP, but Waka Kotahiâ€™s funding of the proposed program fell well short of what was requested, with a result that relatively low levels of investment persisted. KDCâ€™s average 2018-2021 spend on sealed pavement maintenance was only $3,000/km, whilst the corresponding figure for the comparable provincial centres peer group was $5,775/km, and it is extremely difficult to prevent the condition of the network declining with a maintenance spend that is so low. A further attempt was made to increase road maintenance in the Districtâ€™s 2021-2024 NLTP, and in that case with our bid was supported by an Activity Management Plan which clearly evidenced the need for additional investment, and was a document which and which we understand was seen as an exemplar by Waka Kotahi. Unfortunately despite this there was again a large shortfall in subsidy allocation against our bid, in this case leaving 33% of the proposed subsidised program ($2,292,800 of $6,994,000 in total) unfunded. Whilst such a shortfall figure might be a relatively modest one for many districts, it is major for the Kaikoura District which has a population of less than 4000 people. The immediate consequence of the shortfall of funding against our 2021-24 NLTP bid has been that our Council has resolved to increase its use of debt funding for renewals and to cut overall operational budgets by 10%, even though these budgets were already very lean. At the present time around 71% of Councils roading costs are being locally funded, which is considered an unsatisfactory situation. The cost increase mentioned above primarily apply to the renewal budget, with the majority allocated to categories 212 and 214, aimed at addressing the persistent backlog in road maintenance. A significant allocation for category 225 has been dedicated to ensuring that the Council fulfills its commitment to enhancing and maintaining the level of service for footpaths. Adjustments in costs have been considered essential for routine drainage maintenance and the upkeep of unsealed pavements to ensure the minimum level of service is maintained during periods of heavy rain impacting the road infrastructure. | 290000 | 147900 | [5 empty] | 272895 |  | 126213
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Sealed road pavement rehabilitation | Queenstown-Lakes District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Increase in 214 to $2,220,489. In the recent Cardrona Valley Rehab tender there was a significant cost escalation in all submissions. This substantial increase is associated with the uncertainty around supply and cost of bitumen as well as other market escalations. Procurement is being finalised, tender award is about to be confirmed to ensure we are ready for the summer construction season. QLDC can confirm that we have local share to support this increase and can deliver prior to 30 June 2024. | 800000 | 408000 | [5 empty] | 273831 |  | 126273
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Sealed road pavement rehabilitation | Selwyn District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | There has been significant cost pressure in recent years regarding the delivery of the MOR program. On top of inflation at 6% per year, industry-wide changes also added to the costs: 1) Regulatory changes: ECAN Dumping Fee, holiday pay and sick leave pay, adding $1m/year; 2) Market structure change: Bitumen cost increase, adding $1m/year; and 3) More emergency works from severe weather events. As a result, SDC had to use funds allocated to renewals to do maintenance and was only able to deliver 23km of reseals against a target of 75km in 22/23. For 23/24, SDC allocated $3,072,828 (see attached) in unsubsidized funds to supplement WK-approved MOR budget to deliver targeted reseals in 23/24. In the recent program monitor (see attached), we have planned $2,653,762 in unsubsidized MOR spending. This still leaves areas including sealed pavement maintenance, drainage maintenance and renewals, and pavement renewals underfunded. Since then, we have identified an additional $3,088,934 of work in those categories (see attached) that could be delivered in 23/24 if additional WK funding becomes available. Together we are requesting an increase of $5,742,696 in approved budget. The $3,072,828 already allocated by the SDC annual plan can cover the local share portion of the requested increase. Our contractor HEB has indicated that they will be able to deliver the works in 23/24 | 2739664 | 1397229 | [5 empty] | 273977 |  | 126225
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Sealed road pavement rehabilitation | Timaru District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Due to significant changes in construction, material costs, compliance regulations, and fluctuations in contract expenses, we are seeking additional funding in various critical work categories. These increased costs and unforeseen events have adversely affected our ability to execute and complete essential projects within our current budgetary confines | 1919200 | 978792 | [5 empty] | 274392 |  | 126197
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Sealed road pavement rehabilitation | Waimakariri District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | In the September Programme Monitor Council indicated it would be supplementing the co-funded programme with a significant sum of unsubsidised budget. Council had given approval to an additional sum of around 2M, both to ensure that day to day work and levels of service could be maintained, and to try to tackle a few areas of significant defects in the drainage aspects of our network This application is to request co-funding to the level Council feels it requires order to maintain a safe and appropriate network this financial year. The current budget available to Council, including the unsubsidised share is $12.55M. Without additional co-funding a decline in our LOS and network safety is anticipated. Drivers for the increased costs include 22% cost fluctuations over the last two years, plus another significant increase this year, over and above he usual high growth and weather related impacts on our network | 210298 | 107252 | [5 empty] | 274480 |  | 126322
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Sealed road pavement rehabilitation | Waimate District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Work Categories adjusted to amounts forecasted in October programmed monitor. Increased amounts to cover increased contract cost due to cost fluctuations. 111 Seal Pavement Maintenace $180,000 113 Routine drainage maintenance $ 110,000 125 Footpath maintenance $ 10,000 213 Drainage renewals $ 47,000 (includes Dash Street K&C very poor condition with pavement failure) 214 Sealed Road pavement rehabilitation $55,000 225 Footpath renewal $ 58,000 (With Dash St K&C renewal) Total $460,000 Council Confirms Work can be completed by 30 June 2024 Local Council share is available. | 192880 | 123443 | [5 empty] | 274505 |  | 126224
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Sealed road pavement rehabilitation | Wellington City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Seeking reinstatement of previously declared surpluses and addition funds. Request for urgent streetlighting repairs were funded from within the program creating a shortfall in current year. Also heavy bus loadings are unmet in current program. Increased environmental maintenance as a result of extended heavy rainfall that are not qualifying as emergency events. | 1651350 | 842189 | [5 empty] | 274677 |  | 125429
2023-11-27 | November 2023 Review | Cost Increase | Local road maintenance | Sealed road resurfacing | Chatham Islands Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Cost Scope Adjustment following phone call with Suv to advise of potential additional MOR funding available: Adjustments to programme - to recoup 23/24 programme adjustments to cover 2022/23 shortfalls due to elevated contractor and consultant cost fluctuation indices, and - to apply additional cost escalations for contractor and consultant cost fluctuation indices remaining high into FY 23/24. | 300 | 264 | [5 empty] | 272359 |  | 126215
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Sealed road resurfacing | Christchurch City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Christchurch City Council has been facing increasing cost escalations due to the rising costs of materials (in particular bitumen which impacts a number of activities), construction costs and increased costs within our maintenance contracts. The maintenance contracts for the Central, Southern, and Northern areas expired last October and were re-let. This led to an approximate increase of 20-30% across the contracts. In the past Council has consistently delivered additional works above the approved subsidised amount. This is now becoming more difficult due to current economic factors | 6400000 | 3264000 | [5 empty] | 272384 |  | 126223
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Sealed road resurfacing | Dunedin City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Dunedin City Council (DCC) submitted a Maintenance, Operations and Renewals (MOR) bid of $124.89m, funding was approved to a ceiling of $104.25m, a shortfall of $20.64m on asset management-based network needs. DCC anticipated a shortfall in Waka Kotahi co-funding so budgeted to deliver $11m of renewals with 100% local share funding over the 2021-24 period whist reducing the volume of pavement rehabilitation and footpath renewals to meet approved bottom line budgets. Changes in the Temporary Traffic Management (TTM) requirements have led to an increase in costs in the region of $1m per annum, the TTM market is constrained in the region and more qualified STMS workers are in demand and remunerated accordingly. Under the DCC Maintenance Contract traffic management is separated from unit rates and charged at a day rate, this transparency results in a clear trend in increase in costs from 8% of overall works to 11%, with an overall annual contract spend of around $24m this is an unbudgeted increase of $720k this year which is required to be absorbed within existing budgets. Our contracts are escalated using the Waka Kotahi Network Outcomes index, while year on year escalations have stabilised in recent months the overall escalation from our funding bid to now are at 16%, well above budgeted inflation levels. In our operational budget the increase accounts for $2m of our local budget request for 2022-23 and 2023-24. Our overall forecast for the 2021-24 funding cycle is $119.23m against funding of $104.25m, taking into the account the $11m of locally funded renewals we have a shortfall in co-funding of $3.98m. The local share for this work is budgeted but without additional Waka Kotahi approvals DCC will need to rationalise MOR programmes to meet budget. Due to contract conditions this rationalisation will need to be found in resealing and pavement rehabilitation, this is sub-optimal situation with DCC having some of the worst condition indexes nationwide for carriageways and pavements. | 828000 | 422280 | [5 empty] | 272457 |  | 126339
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Sealed road resurfacing | Gore District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The requested increases are the result of cost inflation, renewed physical works contracts which contained higher rates including accommodating significant increased traffic management requirements. Significant increased quantities of work have been needed to maintain our level of service on both sealed and unsealed roads. This has been contributed to by significant detrimental weather events which appear to be occuring more regularly and of increasing magnitude. The Council recognised these factors in approving significant increased local funding for roading in its 2021/22 and 2023/24 Annual Plans. This request for cost scope adjustment will match these local funds already provided. Delivery of the increased works for which increased funding is requested has been delivered during the 2022/23 year which provides evidence that the Council has the ability to deliver the increased works. | 234371 | 138279 | [5 empty] | 272594 |  | 126330
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Sealed road resurfacing | Invercargill City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Queens Drive SCRIM results indicates that an intervention is required. This surface was given a rejuvenation treatment in 2021 due to the surface letting go at that time. This is a section of road had a fatal crash (4 deaths). Temporary warning signage has been installed. Bringing the resurfacing of Queens Drive forward will eliminate the risk on the network entirely rather than a supplementary treatment on the rejuvenation which may have an unknown result. Local share has been approved. Invited tender for the work has been drafted, and we are confident that it will be delivered this financial year. | 1266918 | 646128 | [5 empty] | 272856 |  | 126318
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Sealed road resurfacing | Kaikoura District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The district spend on road maintenance, operations and renewals, when expressed as $/km, was amongst lowest in the country throughout the 2010s decade. Such very low levels of expenditure have been driven by a previous Council desire for austerity in an environment where an extremely small district had many competing financial pressures including those associated with the 2016 earthquake and it is not surprising that such sustained low expenditure has had negative effects on the network. Road conditions deteriorated and a significant backlog of pavement reconstruction and resealing work developed, further increasing the required level of investment. Since 2018 KDC has been attempting to escape from this vicious circle but it has proven difficult because of limited financial support for our NLTP programs. An attempt was made to significantly lift expenditure in the 2018-21 NLTP, but Waka Kotahiâ€™s funding of the proposed program fell well short of what was requested, with a result that relatively low levels of investment persisted. KDCâ€™s average 2018-2021 spend on sealed pavement maintenance was only $3,000/km, whilst the corresponding figure for the comparable provincial centres peer group was $5,775/km, and it is extremely difficult to prevent the condition of the network declining with a maintenance spend that is so low. A further attempt was made to increase road maintenance in the Districtâ€™s 2021-2024 NLTP, and in that case with our bid was supported by an Activity Management Plan which clearly evidenced the need for additional investment, and was a document which and which we understand was seen as an exemplar by Waka Kotahi. Unfortunately despite this there was again a large shortfall in subsidy allocation against our bid, in this case leaving 33% of the proposed subsidised program ($2,292,800 of $6,994,000 in total) unfunded. Whilst such a shortfall figure might be a relatively modest one for many districts, it is major for the Kaikoura District which has a population of less than 4000 people. The immediate consequence of the shortfall of funding against our 2021-24 NLTP bid has been that our Council has resolved to increase its use of debt funding for renewals and to cut overall operational budgets by 10%, even though these budgets were already very lean. At the present time around 71% of Councils roading costs are being locally funded, which is considered an unsatisfactory situation. The cost increase mentioned above primarily apply to the renewal budget, with the majority allocated to categories 212 and 214, aimed at addressing the persistent backlog in road maintenance. A significant allocation for category 225 has been dedicated to ensuring that the Council fulfills its commitment to enhancing and maintaining the level of service for footpaths. Adjustments in costs have been considered essential for routine drainage maintenance and the upkeep of unsealed pavements to ensure the minimum level of service is maintained during periods of heavy rain impacting the road infrastructure. | 227200 | 115872 | [5 empty] | 272893 |  | 126213
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Sealed road resurfacing | Taupo District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The request for additional funding is all related to actual pricing already received or contracts already tendered and almost ready for award This additional funding is for work that will be for subsudisable work that would have been carried out fully funded by council. Taupo DC's bid for 2021-24 MOR bid was revised down by $7m. Is was a combination of lack of local share and NLTF. Council have local share now to match the increase ($800k) requested. In addition tender prices have increased somewhat from initial estimates. | 800000 | 408000 | [5 empty] | 274315 |  | 126365
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Sealed road resurfacing | Timaru District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Due to significant changes in construction, material costs, compliance regulations, and fluctuations in contract expenses, we are seeking additional funding in various critical work categories. These increased costs and unforeseen events have adversely affected our ability to execute and complete essential projects within our current budgetary confines | 338398 | 172583 | [5 empty] | 274390 |  | 126197
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Sealed road resurfacing | Waimakariri District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | In the September Programme Monitor Council indicated it would be supplementing the co-funded programme with a significant sum of unsubsidised budget. Council had given approval to an additional sum of around 2M, both to ensure that day to day work and levels of service could be maintained, and to try to tackle a few areas of significant defects in the drainage aspects of our network This application is to request co-funding to the level Council feels it requires order to maintain a safe and appropriate network this financial year. The current budget available to Council, including the unsubsidised share is $12.55M. Without additional co-funding a decline in our LOS and network safety is anticipated. Drivers for the increased costs include 22% cost fluctuations over the last two years, plus another significant increase this year, over and above he usual high growth and weather related impacts on our network | 347039 | 176990 | [5 empty] | 274478 |  | 126322
2023-11-28 | November 2023 Review | Cost Decrease | Local road maintenance | Sealed road resurfacing | Waimate District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Work Categories adjusted to amounts forecasted in October programmed monitor. Increased amounts to cover increased contract cost due to cost fluctuations. 111 Seal Pavement Maintenace $180,000 113 Routine drainage maintenance $ 110,000 125 Footpath maintenance $ 10,000 213 Drainage renewals $ 47,000 (includes Dash Street K&C very poor condition with pavement failure) 214 Sealed Road pavement rehabilitation $55,000 225 Footpath renewal $ 58,000 (With Dash St K&C renewal) Total $460,000 Council Confirms Work can be completed by 30 June 2024 Local Council share is available. | -150500 | -96320 | [5 empty] | 274503 |  | 126224
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Sealed road resurfacing | Wellington City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Seeking reinstatement of previously declared surpluses and addition funds. Request for urgent streetlighting repairs were funded from within the program creating a shortfall in current year. Also heavy bus loadings are unmet in current program. Increased environmental maintenance as a result of extended heavy rainfall that are not qualifying as emergency events. | 4176784 | 2130160 | [5 empty] | 274675 |  | 125429
2023-11-27 | November 2023 Review | Cost Increase | Local road maintenance | Structures component replacements | Chatham Islands Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Cost Scope Adjustment following phone call with Suv to advise of potential additional MOR funding available: Adjustments to programme - to recoup 23/24 programme adjustments to cover 2022/23 shortfalls due to elevated contractor and consultant cost fluctuation indices, and - to apply additional cost escalations for contractor and consultant cost fluctuation indices remaining high into FY 23/24. | 5000 | 4400 | [5 empty] | 272362 |  | 126215
2023-11-28 | November 2023 Review | Cost Decrease | Local road maintenance | Structures component replacements | Dunedin City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Dunedin City Council (DCC) submitted a Maintenance, Operations and Renewals (MOR) bid of $124.89m, funding was approved to a ceiling of $104.25m, a shortfall of $20.64m on asset management-based network needs. DCC anticipated a shortfall in Waka Kotahi co-funding so budgeted to deliver $11m of renewals with 100% local share funding over the 2021-24 period whist reducing the volume of pavement rehabilitation and footpath renewals to meet approved bottom line budgets. Changes in the Temporary Traffic Management (TTM) requirements have led to an increase in costs in the region of $1m per annum, the TTM market is constrained in the region and more qualified STMS workers are in demand and remunerated accordingly. Under the DCC Maintenance Contract traffic management is separated from unit rates and charged at a day rate, this transparency results in a clear trend in increase in costs from 8% of overall works to 11%, with an overall annual contract spend of around $24m this is an unbudgeted increase of $720k this year which is required to be absorbed within existing budgets. Our contracts are escalated using the Waka Kotahi Network Outcomes index, while year on year escalations have stabilised in recent months the overall escalation from our funding bid to now are at 16%, well above budgeted inflation levels. In our operational budget the increase accounts for $2m of our local budget request for 2022-23 and 2023-24. Our overall forecast for the 2021-24 funding cycle is $119.23m against funding of $104.25m, taking into the account the $11m of locally funded renewals we have a shortfall in co-funding of $3.98m. The local share for this work is budgeted but without additional Waka Kotahi approvals DCC will need to rationalise MOR programmes to meet budget. Due to contract conditions this rationalisation will need to be found in resealing and pavement rehabilitation, this is sub-optimal situation with DCC having some of the worst condition indexes nationwide for carriageways and pavements. | -1175000 | -599250 | [5 empty] | 272460 |  | 126339
2023-11-28 | November 2023 Review | Cost Decrease | Local road maintenance | Structures component replacements | Invercargill City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Queens Drive SCRIM results indicates that an intervention is required. This surface was given a rejuvenation treatment in 2021 due to the surface letting go at that time. This is a section of road had a fatal crash (4 deaths). Temporary warning signage has been installed. Bringing the resurfacing of Queens Drive forward will eliminate the risk on the network entirely rather than a supplementary treatment on the rejuvenation which may have an unknown result. Local share has been approved. Invited tender for the work has been drafted, and we are confident that it will be delivered this financial year. | -31549 | -16090 | [5 empty] | 272859 |  | 126318
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Structures component replacements | Mackenzie District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Additional funding required for construction of two new washover fords. Total combined cost - $250,000 Nixon Road ford is required as the adjacent bridge is now not operational. Work was originally programmed to be completed in December '23. Construction is able to be completed in the 23/24 financial year. Local share for funding is confirmed. Jack Lovelock Track ford is deteriorating due to increased rainfall events. This project can be completed at the same time as Nixons Rd ford creating a saving in construction costs. Both fords have approved ECAN consent. | 250000 | 127500 | [5 empty] | 272996 |  | 126328
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Structures component replacements | Timaru District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Due to significant changes in construction, material costs, compliance regulations, and fluctuations in contract expenses, we are seeking additional funding in various critical work categories. These increased costs and unforeseen events have adversely affected our ability to execute and complete essential projects within our current budgetary confines | 500000 | 255000 | [5 empty] | 274393 |  | 126197
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Structures component replacements | Waimakariri District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | In the September Programme Monitor Council indicated it would be supplementing the co-funded programme with a significant sum of unsubsidised budget. Council had given approval to an additional sum of around 2M, both to ensure that day to day work and levels of service could be maintained, and to try to tackle a few areas of significant defects in the drainage aspects of our network This application is to request co-funding to the level Council feels it requires order to maintain a safe and appropriate network this financial year. The current budget available to Council, including the unsubsidised share is $12.55M. Without additional co-funding a decline in our LOS and network safety is anticipated. Drivers for the increased costs include 22% cost fluctuations over the last two years, plus another significant increase this year, over and above he usual high growth and weather related impacts on our network | 116293 | 59309 | [5 empty] | 274481 |  | 126322
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Structures component replacements | Waimate District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Work Categories adjusted to amounts forecasted in October programmed monitor. Increased amounts to cover increased contract cost due to cost fluctuations. 111 Seal Pavement Maintenace $180,000 113 Routine drainage maintenance $ 110,000 125 Footpath maintenance $ 10,000 213 Drainage renewals $ 47,000 (includes Dash Street K&C very poor condition with pavement failure) 214 Sealed Road pavement rehabilitation $55,000 225 Footpath renewal $ 58,000 (With Dash St K&C renewal) Total $460,000 Council Confirms Work can be completed by 30 June 2024 Local Council share is available. | 123132 | 78804 | [5 empty] | 274506 |  | 126224
2023-11-27 | November 2023 Review | Cost Increase | Local road maintenance | Structures maintenance | Chatham Islands Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Cost Scope Adjustment following phone call with Suv to advise of potential additional MOR funding available: Adjustments to programme - to recoup 23/24 programme adjustments to cover 2022/23 shortfalls due to elevated contractor and consultant cost fluctuation indices, and - to apply additional cost escalations for contractor and consultant cost fluctuation indices remaining high into FY 23/24. | 4000 | 3520 | [5 empty] | 272349 |  | 126215
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Structures maintenance | Dunedin City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Dunedin City Council (DCC) submitted a Maintenance, Operations and Renewals (MOR) bid of $124.89m, funding was approved to a ceiling of $104.25m, a shortfall of $20.64m on asset management-based network needs. DCC anticipated a shortfall in Waka Kotahi co-funding so budgeted to deliver $11m of renewals with 100% local share funding over the 2021-24 period whist reducing the volume of pavement rehabilitation and footpath renewals to meet approved bottom line budgets. Changes in the Temporary Traffic Management (TTM) requirements have led to an increase in costs in the region of $1m per annum, the TTM market is constrained in the region and more qualified STMS workers are in demand and remunerated accordingly. Under the DCC Maintenance Contract traffic management is separated from unit rates and charged at a day rate, this transparency results in a clear trend in increase in costs from 8% of overall works to 11%, with an overall annual contract spend of around $24m this is an unbudgeted increase of $720k this year which is required to be absorbed within existing budgets. Our contracts are escalated using the Waka Kotahi Network Outcomes index, while year on year escalations have stabilised in recent months the overall escalation from our funding bid to now are at 16%, well above budgeted inflation levels. In our operational budget the increase accounts for $2m of our local budget request for 2022-23 and 2023-24. Our overall forecast for the 2021-24 funding cycle is $119.23m against funding of $104.25m, taking into the account the $11m of locally funded renewals we have a shortfall in co-funding of $3.98m. The local share for this work is budgeted but without additional Waka Kotahi approvals DCC will need to rationalise MOR programmes to meet budget. Due to contract conditions this rationalisation will need to be found in resealing and pavement rehabilitation, this is sub-optimal situation with DCC having some of the worst condition indexes nationwide for carriageways and pavements. | 23667 | 12070 | [5 empty] | 272447 |  | 126339
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Structures maintenance | Selwyn District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | There has been significant cost pressure in recent years regarding the delivery of the MOR program. On top of inflation at 6% per year, industry-wide changes also added to the costs: 1) Regulatory changes: ECAN Dumping Fee, holiday pay and sick leave pay, adding $1m/year; 2) Market structure change: Bitumen cost increase, adding $1m/year; and 3) More emergency works from severe weather events. As a result, SDC had to use funds allocated to renewals to do maintenance and was only able to deliver 23km of reseals against a target of 75km in 22/23. For 23/24, SDC allocated $3,072,828 (see attached) in unsubsidized funds to supplement WK-approved MOR budget to deliver targeted reseals in 23/24. In the recent program monitor (see attached), we have planned $2,653,762 in unsubsidized MOR spending. This still leaves areas including sealed pavement maintenance, drainage maintenance and renewals, and pavement renewals underfunded. Since then, we have identified an additional $3,088,934 of work in those categories (see attached) that could be delivered in 23/24 if additional WK funding becomes available. Together we are requesting an increase of $5,742,696 in approved budget. The $3,072,828 already allocated by the SDC annual plan can cover the local share portion of the requested increase. Our contractor HEB has indicated that they will be able to deliver the works in 23/24 | 11920 | 6079 | [5 empty] | 273965 |  | 126225
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Structures maintenance | Timaru District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Due to significant changes in construction, material costs, compliance regulations, and fluctuations in contract expenses, we are seeking additional funding in various critical work categories. These increased costs and unforeseen events have adversely affected our ability to execute and complete essential projects within our current budgetary confines | 7494 | 3822 | [5 empty] | 274380 |  | 126197
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Structures maintenance | Waimakariri District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | In the September Programme Monitor Council indicated it would be supplementing the co-funded programme with a significant sum of unsubsidised budget. Council had given approval to an additional sum of around 2M, both to ensure that day to day work and levels of service could be maintained, and to try to tackle a few areas of significant defects in the drainage aspects of our network This application is to request co-funding to the level Council feels it requires order to maintain a safe and appropriate network this financial year. The current budget available to Council, including the unsubsidised share is $12.55M. Without additional co-funding a decline in our LOS and network safety is anticipated. Drivers for the increased costs include 22% cost fluctuations over the last two years, plus another significant increase this year, over and above he usual high growth and weather related impacts on our network | 111415 | 56821 | [5 empty] | 274468 |  | 126322
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Structures maintenance | Waimate District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Work Categories adjusted to amounts forecasted in October programmed monitor. Increased amounts to cover increased contract cost due to cost fluctuations. 111 Seal Pavement Maintenace $180,000 113 Routine drainage maintenance $ 110,000 125 Footpath maintenance $ 10,000 213 Drainage renewals $ 47,000 (includes Dash Street K&C very poor condition with pavement failure) 214 Sealed Road pavement rehabilitation $55,000 225 Footpath renewal $ 58,000 (With Dash St K&C renewal) Total $460,000 Council Confirms Work can be completed by 30 June 2024 Local Council share is available. | 29546 | 18909 | [5 empty] | 274493 |  | 126224
2023-11-01 | November 2023 Review | Cost Increase | Public transport infrastructure | Technology to improve effectiveness of public transport systems | NZ Transport Agency | National Ticketing Solution (NTS) | Implementation | ECAN acceleration | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 130331 | 130331 |  |  | 1.7 | 1.7 | SAP Item ID 60068497 | 280395 |  | 125897
2023-11-27 | November 2023 Review | Cost Increase | Local road maintenance | Traffic services renewals | Chatham Islands Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Cost Scope Adjustment following phone call with Suv to advise of potential additional MOR funding available: Adjustments to programme - to recoup 23/24 programme adjustments to cover 2022/23 shortfalls due to elevated contractor and consultant cost fluctuation indices, and - to apply additional cost escalations for contractor and consultant cost fluctuation indices remaining high into FY 23/24. | 2000 | 1760 | [5 empty] | 272365 |  | 126215
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Traffic services renewals | Dunedin City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Dunedin City Council (DCC) submitted a Maintenance, Operations and Renewals (MOR) bid of $124.89m, funding was approved to a ceiling of $104.25m, a shortfall of $20.64m on asset management-based network needs. DCC anticipated a shortfall in Waka Kotahi co-funding so budgeted to deliver $11m of renewals with 100% local share funding over the 2021-24 period whist reducing the volume of pavement rehabilitation and footpath renewals to meet approved bottom line budgets. Changes in the Temporary Traffic Management (TTM) requirements have led to an increase in costs in the region of $1m per annum, the TTM market is constrained in the region and more qualified STMS workers are in demand and remunerated accordingly. Under the DCC Maintenance Contract traffic management is separated from unit rates and charged at a day rate, this transparency results in a clear trend in increase in costs from 8% of overall works to 11%, with an overall annual contract spend of around $24m this is an unbudgeted increase of $720k this year which is required to be absorbed within existing budgets. Our contracts are escalated using the Waka Kotahi Network Outcomes index, while year on year escalations have stabilised in recent months the overall escalation from our funding bid to now are at 16%, well above budgeted inflation levels. In our operational budget the increase accounts for $2m of our local budget request for 2022-23 and 2023-24. Our overall forecast for the 2021-24 funding cycle is $119.23m against funding of $104.25m, taking into the account the $11m of locally funded renewals we have a shortfall in co-funding of $3.98m. The local share for this work is budgeted but without additional Waka Kotahi approvals DCC will need to rationalise MOR programmes to meet budget. Due to contract conditions this rationalisation will need to be found in resealing and pavement rehabilitation, this is sub-optimal situation with DCC having some of the worst condition indexes nationwide for carriageways and pavements. | 934667 | 476680 | [5 empty] | 272463 |  | 126339
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Traffic services renewals | Gore District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The requested increases are the result of cost inflation, renewed physical works contracts which contained higher rates including accommodating significant increased traffic management requirements. Significant increased quantities of work have been needed to maintain our level of service on both sealed and unsealed roads. This has been contributed to by significant detrimental weather events which appear to be occuring more regularly and of increasing magnitude. The Council recognised these factors in approving significant increased local funding for roading in its 2021/22 and 2023/24 Annual Plans. This request for cost scope adjustment will match these local funds already provided. Delivery of the increased works for which increased funding is requested has been delivered during the 2022/23 year which provides evidence that the Council has the ability to deliver the increased works. | 79868 | 47122 | [5 empty] | 272600 |  | 126330
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Traffic services renewals | Invercargill City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Queens Drive SCRIM results indicates that an intervention is required. This surface was given a rejuvenation treatment in 2021 due to the surface letting go at that time. This is a section of road had a fatal crash (4 deaths). Temporary warning signage has been installed. Bringing the resurfacing of Queens Drive forward will eliminate the risk on the network entirely rather than a supplementary treatment on the rejuvenation which may have an unknown result. Local share has been approved. Invited tender for the work has been drafted, and we are confident that it will be delivered this financial year. | 140618 | 71715 | [5 empty] | 272862 |  | 126318
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Traffic services renewals | Kaikoura District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The district spend on road maintenance, operations and renewals, when expressed as $/km, was amongst lowest in the country throughout the 2010s decade. Such very low levels of expenditure have been driven by a previous Council desire for austerity in an environment where an extremely small district had many competing financial pressures including those associated with the 2016 earthquake and it is not surprising that such sustained low expenditure has had negative effects on the network. Road conditions deteriorated and a significant backlog of pavement reconstruction and resealing work developed, further increasing the required level of investment. Since 2018 KDC has been attempting to escape from this vicious circle but it has proven difficult because of limited financial support for our NLTP programs. An attempt was made to significantly lift expenditure in the 2018-21 NLTP, but Waka Kotahiâ€™s funding of the proposed program fell well short of what was requested, with a result that relatively low levels of investment persisted. KDCâ€™s average 2018-2021 spend on sealed pavement maintenance was only $3,000/km, whilst the corresponding figure for the comparable provincial centres peer group was $5,775/km, and it is extremely difficult to prevent the condition of the network declining with a maintenance spend that is so low. A further attempt was made to increase road maintenance in the Districtâ€™s 2021-2024 NLTP, and in that case with our bid was supported by an Activity Management Plan which clearly evidenced the need for additional investment, and was a document which and which we understand was seen as an exemplar by Waka Kotahi. Unfortunately despite this there was again a large shortfall in subsidy allocation against our bid, in this case leaving 33% of the proposed subsidised program ($2,292,800 of $6,994,000 in total) unfunded. Whilst such a shortfall figure might be a relatively modest one for many districts, it is major for the Kaikoura District which has a population of less than 4000 people. The immediate consequence of the shortfall of funding against our 2021-24 NLTP bid has been that our Council has resolved to increase its use of debt funding for renewals and to cut overall operational budgets by 10%, even though these budgets were already very lean. At the present time around 71% of Councils roading costs are being locally funded, which is considered an unsatisfactory situation. The cost increase mentioned above primarily apply to the renewal budget, with the majority allocated to categories 212 and 214, aimed at addressing the persistent backlog in road maintenance. A significant allocation for category 225 has been dedicated to ensuring that the Council fulfills its commitment to enhancing and maintaining the level of service for footpaths. Adjustments in costs have been considered essential for routine drainage maintenance and the upkeep of unsealed pavements to ensure the minimum level of service is maintained during periods of heavy rain impacting the road infrastructure. | 10000 | 5100 | [5 empty] | 272899 |  | 126213
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Traffic services renewals | Timaru District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Due to significant changes in construction, material costs, compliance regulations, and fluctuations in contract expenses, we are seeking additional funding in various critical work categories. These increased costs and unforeseen events have adversely affected our ability to execute and complete essential projects within our current budgetary confines | 215000 | 109650 | [5 empty] | 274396 |  | 126197
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Traffic services renewals | Waimakariri District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | In the September Programme Monitor Council indicated it would be supplementing the co-funded programme with a significant sum of unsubsidised budget. Council had given approval to an additional sum of around 2M, both to ensure that day to day work and levels of service could be maintained, and to try to tackle a few areas of significant defects in the drainage aspects of our network This application is to request co-funding to the level Council feels it requires order to maintain a safe and appropriate network this financial year. The current budget available to Council, including the unsubsidised share is $12.55M. Without additional co-funding a decline in our LOS and network safety is anticipated. Drivers for the increased costs include 22% cost fluctuations over the last two years, plus another significant increase this year, over and above he usual high growth and weather related impacts on our network | 137613 | 70183 | [5 empty] | 274484 |  | 126322
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Traffic services renewals | Waimate District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Work Categories adjusted to amounts forecasted in October programmed monitor. Increased amounts to cover increased contract cost due to cost fluctuations. 111 Seal Pavement Maintenace $180,000 113 Routine drainage maintenance $ 110,000 125 Footpath maintenance $ 10,000 213 Drainage renewals $ 47,000 (includes Dash Street K&C very poor condition with pavement failure) 214 Sealed Road pavement rehabilitation $55,000 225 Footpath renewal $ 58,000 (With Dash St K&C renewal) Total $460,000 Council Confirms Work can be completed by 30 June 2024 Local Council share is available. | 576 | 369 | [5 empty] | 274509 |  | 126224
2023-11-27 | November 2023 Review | Cost Increase | Local road maintenance | Unsealed pavement maintenance | Chatham Islands Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Cost Scope Adjustment following phone call with Suv to advise of potential additional MOR funding available: Adjustments to programme - to recoup 23/24 programme adjustments to cover 2022/23 shortfalls due to elevated contractor and consultant cost fluctuation indices, and - to apply additional cost escalations for contractor and consultant cost fluctuation indices remaining high into FY 23/24. | 31000 | 27280 | [5 empty] | 272347 |  | 126215
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Unsealed pavement maintenance | Clutha District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | New Roading Maintenance Contract rates resulting in budget blow outs and not wanting to cut back on work. In WC213, historical weather event repairs/renewals continuing. Council confirms availability of local share and works will be completed this Financial Year. | 900000 | 585000 | [5 empty] | 272420 |  | 126368
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Unsealed pavement maintenance | Gore District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The requested increases are the result of cost inflation, renewed physical works contracts which contained higher rates including accommodating significant increased traffic management requirements. Significant increased quantities of work have been needed to maintain our level of service on both sealed and unsealed roads. This has been contributed to by significant detrimental weather events which appear to be occuring more regularly and of increasing magnitude. The Council recognised these factors in approving significant increased local funding for roading in its 2021/22 and 2023/24 Annual Plans. This request for cost scope adjustment will match these local funds already provided. Delivery of the increased works for which increased funding is requested has been delivered during the 2022/23 year which provides evidence that the Council has the ability to deliver the increased works. | 127823 | 75416 | [5 empty] | 272582 |  | 126330
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Unsealed pavement maintenance | Hurunui District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Costs have been revised for WC 111 & 112 requesting an overall increase of $1.2m. Currently HDC is having to top up both budgets with unsubsidised funding to undertake these core maintenance activities due to the impact of our new maintenance contract item rates including the cost escalations which were not known at the time of the 2021-2024 bid, the 2024-2027 AMP provides further detail regarding this. The works required this financial year are committed to this level of expenditure and we have a very high level of confidence these will be delivered. Any approved increase in funding will offset the amount of unsubsidised funding being provided by HDC. | 432000 | 224640 | [5 empty] | 272794 |  | 126227
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Unsealed pavement maintenance | Kaikoura District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The district spend on road maintenance, operations and renewals, when expressed as $/km, was amongst lowest in the country throughout the 2010s decade. Such very low levels of expenditure have been driven by a previous Council desire for austerity in an environment where an extremely small district had many competing financial pressures including those associated with the 2016 earthquake and it is not surprising that such sustained low expenditure has had negative effects on the network. Road conditions deteriorated and a significant backlog of pavement reconstruction and resealing work developed, further increasing the required level of investment. Since 2018 KDC has been attempting to escape from this vicious circle but it has proven difficult because of limited financial support for our NLTP programs. An attempt was made to significantly lift expenditure in the 2018-21 NLTP, but Waka Kotahiâ€™s funding of the proposed program fell well short of what was requested, with a result that relatively low levels of investment persisted. KDCâ€™s average 2018-2021 spend on sealed pavement maintenance was only $3,000/km, whilst the corresponding figure for the comparable provincial centres peer group was $5,775/km, and it is extremely difficult to prevent the condition of the network declining with a maintenance spend that is so low. A further attempt was made to increase road maintenance in the Districtâ€™s 2021-2024 NLTP, and in that case with our bid was supported by an Activity Management Plan which clearly evidenced the need for additional investment, and was a document which and which we understand was seen as an exemplar by Waka Kotahi. Unfortunately despite this there was again a large shortfall in subsidy allocation against our bid, in this case leaving 33% of the proposed subsidised program ($2,292,800 of $6,994,000 in total) unfunded. Whilst such a shortfall figure might be a relatively modest one for many districts, it is major for the Kaikoura District which has a population of less than 4000 people. The immediate consequence of the shortfall of funding against our 2021-24 NLTP bid has been that our Council has resolved to increase its use of debt funding for renewals and to cut overall operational budgets by 10%, even though these budgets were already very lean. At the present time around 71% of Councils roading costs are being locally funded, which is considered an unsatisfactory situation. The cost increase mentioned above primarily apply to the renewal budget, with the majority allocated to categories 212 and 214, aimed at addressing the persistent backlog in road maintenance. A significant allocation for category 225 has been dedicated to ensuring that the Council fulfills its commitment to enhancing and maintaining the level of service for footpaths. Adjustments in costs have been considered essential for routine drainage maintenance and the upkeep of unsealed pavements to ensure the minimum level of service is maintained during periods of heavy rain impacting the road infrastructure. | 21380 | 10904 | [5 empty] | 272881 |  | 126213
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Unsealed pavement maintenance | Timaru District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Due to significant changes in construction, material costs, compliance regulations, and fluctuations in contract expenses, we are seeking additional funding in various critical work categories. These increased costs and unforeseen events have adversely affected our ability to execute and complete essential projects within our current budgetary confines | 69862 | 35630 | [5 empty] | 274378 |  | 126197
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Unsealed pavement maintenance | Waimakariri District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | In the September Programme Monitor Council indicated it would be supplementing the co-funded programme with a significant sum of unsubsidised budget. Council had given approval to an additional sum of around 2M, both to ensure that day to day work and levels of service could be maintained, and to try to tackle a few areas of significant defects in the drainage aspects of our network This application is to request co-funding to the level Council feels it requires order to maintain a safe and appropriate network this financial year. The current budget available to Council, including the unsubsidised share is $12.55M. Without additional co-funding a decline in our LOS and network safety is anticipated. Drivers for the increased costs include 22% cost fluctuations over the last two years, plus another significant increase this year, over and above he usual high growth and weather related impacts on our network | 200149 | 102076 | [5 empty] | 274466 |  | 126322
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Unsealed pavement maintenance | Waimate District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Work Categories adjusted to amounts forecasted in October programmed monitor. Increased amounts to cover increased contract cost due to cost fluctuations. 111 Seal Pavement Maintenace $180,000 113 Routine drainage maintenance $ 110,000 125 Footpath maintenance $ 10,000 213 Drainage renewals $ 47,000 (includes Dash Street K&C very poor condition with pavement failure) 214 Sealed Road pavement rehabilitation $55,000 225 Footpath renewal $ 58,000 (With Dash St K&C renewal) Total $460,000 Council Confirms Work can be completed by 30 June 2024 Local Council share is available. | 47678 | 30514 | [5 empty] | 274491 |  | 126224
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Unsealed pavement maintenance | Waitaki District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | *sealed pavement maintenance - increased rates in new road maintenance contract October 2022 and $300k to allow pre-reseal repairs to be completed a year ahead of reseals *unsealed pavement maintenance - increased rates in new road maintenance contract October 2022 and to allow for achieving level of service in grading of unsealed network *routine drainage maintenance - increased rates in new road maintenance contract October 2022 and annual commitment of new contract *network service maintenance - increase in road marking to complete full remark of road network to ensure that levels of service are achieved *unsealed road metalling - increased rates in new road maintenance contract October 2022 and annual commitment of new contract | 150000 | 85500 | [5 empty] | 274589 |  | 126226
2023-11-27 | November 2023 Review | Cost Increase | Local road maintenance | Unsealed road metalling | Chatham Islands Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Cost Scope Adjustment following phone call with Suv to advise of potential additional MOR funding available: Adjustments to programme - to recoup 23/24 programme adjustments to cover 2022/23 shortfalls due to elevated contractor and consultant cost fluctuation indices, and - to apply additional cost escalations for contractor and consultant cost fluctuation indices remaining high into FY 23/24. | 173000 | 152240 | [5 empty] | 272358 |  | 126215
2023-11-28 | November 2023 Review | Cost Decrease | Local road maintenance | Unsealed road metalling | Dunedin City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Dunedin City Council (DCC) submitted a Maintenance, Operations and Renewals (MOR) bid of $124.89m, funding was approved to a ceiling of $104.25m, a shortfall of $20.64m on asset management-based network needs. DCC anticipated a shortfall in Waka Kotahi co-funding so budgeted to deliver $11m of renewals with 100% local share funding over the 2021-24 period whist reducing the volume of pavement rehabilitation and footpath renewals to meet approved bottom line budgets. Changes in the Temporary Traffic Management (TTM) requirements have led to an increase in costs in the region of $1m per annum, the TTM market is constrained in the region and more qualified STMS workers are in demand and remunerated accordingly. Under the DCC Maintenance Contract traffic management is separated from unit rates and charged at a day rate, this transparency results in a clear trend in increase in costs from 8% of overall works to 11%, with an overall annual contract spend of around $24m this is an unbudgeted increase of $720k this year which is required to be absorbed within existing budgets. Our contracts are escalated using the Waka Kotahi Network Outcomes index, while year on year escalations have stabilised in recent months the overall escalation from our funding bid to now are at 16%, well above budgeted inflation levels. In our operational budget the increase accounts for $2m of our local budget request for 2022-23 and 2023-24. Our overall forecast for the 2021-24 funding cycle is $119.23m against funding of $104.25m, taking into the account the $11m of locally funded renewals we have a shortfall in co-funding of $3.98m. The local share for this work is budgeted but without additional Waka Kotahi approvals DCC will need to rationalise MOR programmes to meet budget. Due to contract conditions this rationalisation will need to be found in resealing and pavement rehabilitation, this is sub-optimal situation with DCC having some of the worst condition indexes nationwide for carriageways and pavements. | -421000 | -214710 | [5 empty] | 272456 |  | 126339
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Unsealed road metalling | Gore District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The requested increases are the result of cost inflation, renewed physical works contracts which contained higher rates including accommodating significant increased traffic management requirements. Significant increased quantities of work have been needed to maintain our level of service on both sealed and unsealed roads. This has been contributed to by significant detrimental weather events which appear to be occuring more regularly and of increasing magnitude. The Council recognised these factors in approving significant increased local funding for roading in its 2021/22 and 2023/24 Annual Plans. This request for cost scope adjustment will match these local funds already provided. Delivery of the increased works for which increased funding is requested has been delivered during the 2022/23 year which provides evidence that the Council has the ability to deliver the increased works. | 18879 | 11139 | [5 empty] | 272593 |  | 126330
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Unsealed road metalling | Invercargill City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Queens Drive SCRIM results indicates that an intervention is required. This surface was given a rejuvenation treatment in 2021 due to the surface letting go at that time. This is a section of road had a fatal crash (4 deaths). Temporary warning signage has been installed. Bringing the resurfacing of Queens Drive forward will eliminate the risk on the network entirely rather than a supplementary treatment on the rejuvenation which may have an unknown result. Local share has been approved. Invited tender for the work has been drafted, and we are confident that it will be delivered this financial year. | 13740 | 7007 | [5 empty] | 272855 |  | 126318
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Unsealed road metalling | Kaikoura District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The district spend on road maintenance, operations and renewals, when expressed as $/km, was amongst lowest in the country throughout the 2010s decade. Such very low levels of expenditure have been driven by a previous Council desire for austerity in an environment where an extremely small district had many competing financial pressures including those associated with the 2016 earthquake and it is not surprising that such sustained low expenditure has had negative effects on the network. Road conditions deteriorated and a significant backlog of pavement reconstruction and resealing work developed, further increasing the required level of investment. Since 2018 KDC has been attempting to escape from this vicious circle but it has proven difficult because of limited financial support for our NLTP programs. An attempt was made to significantly lift expenditure in the 2018-21 NLTP, but Waka Kotahiâ€™s funding of the proposed program fell well short of what was requested, with a result that relatively low levels of investment persisted. KDCâ€™s average 2018-2021 spend on sealed pavement maintenance was only $3,000/km, whilst the corresponding figure for the comparable provincial centres peer group was $5,775/km, and it is extremely difficult to prevent the condition of the network declining with a maintenance spend that is so low. A further attempt was made to increase road maintenance in the Districtâ€™s 2021-2024 NLTP, and in that case with our bid was supported by an Activity Management Plan which clearly evidenced the need for additional investment, and was a document which and which we understand was seen as an exemplar by Waka Kotahi. Unfortunately despite this there was again a large shortfall in subsidy allocation against our bid, in this case leaving 33% of the proposed subsidised program ($2,292,800 of $6,994,000 in total) unfunded. Whilst such a shortfall figure might be a relatively modest one for many districts, it is major for the Kaikoura District which has a population of less than 4000 people. The immediate consequence of the shortfall of funding against our 2021-24 NLTP bid has been that our Council has resolved to increase its use of debt funding for renewals and to cut overall operational budgets by 10%, even though these budgets were already very lean. At the present time around 71% of Councils roading costs are being locally funded, which is considered an unsatisfactory situation. The cost increase mentioned above primarily apply to the renewal budget, with the majority allocated to categories 212 and 214, aimed at addressing the persistent backlog in road maintenance. A significant allocation for category 225 has been dedicated to ensuring that the Council fulfills its commitment to enhancing and maintaining the level of service for footpaths. Adjustments in costs have been considered essential for routine drainage maintenance and the upkeep of unsealed pavements to ensure the minimum level of service is maintained during periods of heavy rain impacting the road infrastructure. | 52600 | 26826 | [5 empty] | 272892 |  | 126213
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Unsealed road metalling | Selwyn District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | There has been significant cost pressure in recent years regarding the delivery of the MOR program. On top of inflation at 6% per year, industry-wide changes also added to the costs: 1) Regulatory changes: ECAN Dumping Fee, holiday pay and sick leave pay, adding $1m/year; 2) Market structure change: Bitumen cost increase, adding $1m/year; and 3) More emergency works from severe weather events. As a result, SDC had to use funds allocated to renewals to do maintenance and was only able to deliver 23km of reseals against a target of 75km in 22/23. For 23/24, SDC allocated $3,072,828 (see attached) in unsubsidized funds to supplement WK-approved MOR budget to deliver targeted reseals in 23/24. In the recent program monitor (see attached), we have planned $2,653,762 in unsubsidized MOR spending. This still leaves areas including sealed pavement maintenance, drainage maintenance and renewals, and pavement renewals underfunded. Since then, we have identified an additional $3,088,934 of work in those categories (see attached) that could be delivered in 23/24 if additional WK funding becomes available. Together we are requesting an increase of $5,742,696 in approved budget. The $3,072,828 already allocated by the SDC annual plan can cover the local share portion of the requested increase. Our contractor HEB has indicated that they will be able to deliver the works in 23/24 | 55560 | 28336 | [5 empty] | 273974 |  | 126225
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Unsealed road metalling | Timaru District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Due to significant changes in construction, material costs, compliance regulations, and fluctuations in contract expenses, we are seeking additional funding in various critical work categories. These increased costs and unforeseen events have adversely affected our ability to execute and complete essential projects within our current budgetary confines | 22216 | 11330 | [5 empty] | 274389 |  | 126197
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Unsealed road metalling | Waimakariri District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | In the September Programme Monitor Council indicated it would be supplementing the co-funded programme with a significant sum of unsubsidised budget. Council had given approval to an additional sum of around 2M, both to ensure that day to day work and levels of service could be maintained, and to try to tackle a few areas of significant defects in the drainage aspects of our network This application is to request co-funding to the level Council feels it requires order to maintain a safe and appropriate network this financial year. The current budget available to Council, including the unsubsidised share is $12.55M. Without additional co-funding a decline in our LOS and network safety is anticipated. Drivers for the increased costs include 22% cost fluctuations over the last two years, plus another significant increase this year, over and above he usual high growth and weather related impacts on our network | 54457 | 27773 | [5 empty] | 274477 |  | 126322
2023-11-28 | November 2023 Review | Cost Decrease | Local road maintenance | Unsealed road metalling | Waimate District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Work Categories adjusted to amounts forecasted in October programmed monitor. Increased amounts to cover increased contract cost due to cost fluctuations. 111 Seal Pavement Maintenace $180,000 113 Routine drainage maintenance $ 110,000 125 Footpath maintenance $ 10,000 213 Drainage renewals $ 47,000 (includes Dash Street K&C very poor condition with pavement failure) 214 Sealed Road pavement rehabilitation $55,000 225 Footpath renewal $ 58,000 (With Dash St K&C renewal) Total $460,000 Council Confirms Work can be completed by 30 June 2024 Local Council share is available. | -66160 | -42342 | [5 empty] | 274502 |  | 126224
2023-11-28 | November 2023 Review | Cost Increase | Local road maintenance | Unsealed road metalling | Waitaki District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | *sealed pavement maintenance - increased rates in new road maintenance contract October 2022 and $300k to allow pre-reseal repairs to be completed a year ahead of reseals *unsealed pavement maintenance - increased rates in new road maintenance contract October 2022 and to allow for achieving level of service in grading of unsealed network *routine drainage maintenance - increased rates in new road maintenance contract October 2022 and annual commitment of new contract *network service maintenance - increase in road marking to complete full remark of road network to ensure that levels of service are achieved *unsealed road metalling - increased rates in new road maintenance contract October 2022 and annual commitment of new contract | 415000 | 236550 | [5 empty] | 274600 |  | 126226
2023-11-03 | November 2023 Review | Cost Decrease | Walking and cycling improvements | Walking facilities | Auckland Transport | Safer Communities - Mt Roskill | Implementation | SC - Mt Roskill - IMP | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As noted in the programme monitor, this activity is coming in under budget. A partial surplus is declared while final costs are being resolved. | -100000 | -51000 |  |  | 0 | 1.8 | 451.2608 | 260797 |  | 126237