## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Phase Label | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Decision Status | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR | Your Phase reference | TIO Phase id | SAP item id | TIO Request id
2023-12-20 | December 2023 Review | New approval | Local road maintenance | Emergency works | Far North District Council | EW Far North DC May 2023 | Construction | Phase 3 - Major Remedial Works - EW May 2023 | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | This funding approval enables the transport services at this network to be reinstated to the appropriate levels of service. | 7995554 | 5672872 |  |  |  |  | Phase 3 - Major Remedial Works - EW May 2023 | 284263 |  | 125346
2023-12-21 | December 2023 Review | New approval | Local road maintenance | Emergency works | Gisborne District Council | EW Cyclone Gabrielle | Construction | Initial Response $11m (old funding) | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | This funding approval enables the transport services at this network to be reinstated to the appropriate levels of service. | 11860005 | 11860005 | [5 empty] | 289414 |  | 125940
2023-12-11 | December 2023 Review | New approval | Local road maintenance | Emergency works | Manawatu District Council | EW May 2023 - Manawatu DC | Construction | Recovery | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | As recommended by Regional office. To enable Manawatu DC to undertake initial response of various roads withing the district and return those to the required pre-event levels of service. | 1854204 | 1316485 |  |  |  |  | Recovery phase for May 2023 weather event | 284580 |  | 123415
2023-12-11 | December 2023 Review | New approval | Local road maintenance | Emergency works | Manawatu District Council | EW May 2023 - Manawatu DC | Construction | Response | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | Complies with the requirements of WC141 Emergency Works | 618376 | 439047 |  |  |  |  | Response phase for May 2023 weather event | 284579 |  | 123414
2023-12-22 | December 2023 Review | New approval | State highway maintenance | Emergency works | NZTA (BOP) | EW BOPE RW late Sept HR 20230922 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | I support this application. Itâ€™s taken so long to submit. The recovery works that are within the TREC contract boundary should be completed by TREC. NAC | 3591074 | 3591074 | [5 empty] | 289960 | 60073395 | 126721
2023-12-14 | December 2023 Review | New approval | State highway maintenance | Emergency works | NZTA (Otago) | EW Central Otago RW HR 20230921 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | Looks like a straightforward response application not much in the way of recovery. Whatâ€™s the long term strategy for Muddy Creek, resilience or just clean it up, as it comes down? Continue with future EW applications as required? We wonâ€™t be able to keep this application open indefinitely to allow for continued clean up. | 1274950 | 1274950 | [5 empty] | 289959 | 60073358 | 126643
2023-12-12 | December 2023 Review | New approval | State highway maintenance | Emergency works | NZTA (Southland) | EW Southland Regn Wide Flooding 20230921 | Construction |  | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | I support the application. The recovery elements look reasonable. It should be noted that the event should not remain open to enable continued monitoring. Itâ€™s appropriate for the short term only. Itâ€™s disappointing that this application has taken so long to come through the system | 328765 | 328765 | [5 empty] | 289637 | 60073140 | 126642
2023-12-12 | December 2023 Review | New approval | State highway maintenance | Emergency works | NZTA (Waikato) | EW Waikato Region Extreme HR 20230127 | Construction | EW SH25a Extreme HR 20230127 | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | This review request was approved by the CFO on 22/08/2023, under the title of EW East Waikato Cyclone Hale 20230110 and referring to TIO Reference No (Activity ID) 160736. As the damage substantially relates to the later Auckland Anniversary storm event, rather than Cyclone Hale, the project together with approved funding are being progressed under EW Waikato Region Extreme HR 20230127. | 43600000 | 43600000 | [5 empty] | 288521 | 60071632 | 125591
2023-12-07 | December 2023 Review | New approval | Local road maintenance | Emergency works | New Plymouth District Council | EW - Cyclone Gabrielle NPDC | Construction | First Response | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | As recommended by Regional office. To enable New Plymouth District Council to undertake initial response to various roads within the district and return those roads to the required pre-event levels of service. | 177806 | 161803 |  |  |  |  | First Response | 283877 |  | 122395
2023-12-20 | December 2023 Review | New approval | Local road maintenance | Emergency works | Waikato District Council | EW - Waikato DC Storm Damage Jan-Feb 2023 | Construction | Phase 3 - Construction & MSQA of Critical Sites | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | This funding approval enables the transport service at this network to be reinstated to the appropriate levels of service. | 2366396 | 1206862 |  |  |  |  | Phase 3 - Construction & MSQA of Critical Sites | 290631 |  | 126604
2023-12-07 | December 2023 Review | New approval | Local road maintenance | Network and asset management | Marlborough District Council | 2021/22 & 2022/23 MOR overpayment | Repayment |  | LLL | LLL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Audit of Marlborough DC identified $203,575 over claim related Network Management & Minor Events for 2021/22 & 2022/23 financial years. | -203575 | -203575 | [5 empty] | 290703 |  | 126615
2023-12-07 | December 2023 Review | New approval | Local road improvements | Road improvements | Central Otago District Council | 2017/181 LCLR Repayment | Repayment | Overpayment of LC/LR | LLL | LLL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Audit of CODC for the 2017/18 identified $71,591 total cost (FAR at 51% is $36,511) overspend in the LC/LR programme. | -36511 | -36511 | [5 empty] | 290704 |  | 126616
2023-12-11 | December 2023 Review | New approval | State highway improvements | Road improvements | NZTA (Auckland) | ANO SH1 Onewa Bus Improvements | Pre-implementation* |  | MHM | MHM | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer $400,000 to 60074164 ANO SH1 Onewa Pre imp phase & Transfer $300,000 to 60073742 & 60056410 SH16 SH1 Grafton Link -$700,000 | 436000 | 436000 |  |  | 3.6 | 3.6 |  | 290652 | 60074164 | 126559
2023-12-11 | December 2023 Review | New approval | State highway improvements | Road improvements | NZTA (Auckland) | ANO SH16 SH1 Grafton Link | Pre-implementation* |  | MHM | MHM | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer $400,000 to 60074164 ANO SH1 Onewa Pre imp phase & Transfer $300,000 to 60073742 & 60056410 SH16 SH1 Grafton Link -$700,000 | 327000 | 327000 |  |  |  | 2.9 |  | 290484 | 60073742 | 126624
2023-12-11 | December 2023 Review | New approval | State highway improvements | Road improvements | NZTA (BOP) | SH2 Hewletts Road Sub area Access | Indicative Business Case |  | VHHL | HML | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | SSBC 60061770 is being closed and $999998 surplus to be reallocated to 60073991 IBC to correct phase type | 1089999 | 1089999 |  |  |  | 2.7 |  | 290709 | 60073991 | 126626
2023-12-04 | December 2023 Review | New approval | Road to Zero | Road improvements | NZTA (Manawatu/Whanganui) | Otaki to North of Levin - SH1/SH57 - northern section | Implementation | Whirokino to Levin - Stg 2 | HHL | HHH | N | 5 | Approved | Approved by Chief Financial Officer (CFO) |  | 14682300 | 14682300 |  |  | 0 | 1.6 |  | 283408 | 60069394 | 126302
2023-12-19 | December 2023 Review | New approval | Road to Zero | Road improvements | NZTA (Tasman) | SH60 Ruby Bay Bypass | Implementation |  | HMM | HMM | N | 5 | Approved | Approved by Chief Financial Officer (CFO) |  | 7308232 | 7308232 |  |  |  | 5 |  | 288453 | 60071511 | 126753
2023-12-21 | December 2023 Review | New approval | Road to Zero | Road improvements | NZTA (Waikato) | SH1 Cambridge to Piarere online safety improvements | Implementation | Stg 3A-2 | VHML | VHLL | N | 3 | Approved | Approved by Chief Financial Officer (CFO) |  | 10910000 | 10910000 |  |  | 0 | 1.6 |  | 283562 | 60069670 | 126774
2023-12-18 | December 2023 Review | New approval | Road to Zero | Road improvements | NZTA (Waikato) | SH1 ETA Corridor Improvements | Implementation | Stage 3 RtZ | VHML | VHML | N | 3 | Approved | Approved by Chief Financial Officer (CFO) | will enable Median Barrier and supporting treatments to be implemented along Stage 3 of SH1 East Taupo Arterial project between SH5 and the Taupo Airport | 8702212 | 8702212 |  |  | 2.6 | 2.6 | Stage 3 RtZ | 288436 | 60071442 | 126372
2023-12-12 | December 2023 Review | New approval | Public transport infrastructure | Technology to improve effectiveness of public transport systems | NZ Transport Agency | Public transport systems optimisation project | Single-Stage Business Case | SSBC | HHM | HHM | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | Ready to proceed to SSBC | 250000 | 250000 |  |  | 99 | 99 | SAP 60074224 | 290588 |  | 126480
2023-12-08 | December 2023 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Auckland) | SH1 Puhoi to Warkworth RoNS Detailed Design and Construction | Pre-implementation* | Procurement & Design | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project close | 0 | 0 |  |  | 1.1 | 1.1 | 60216906 | 239928 | 60216906 | 126580
2023-12-19 | December 2023 Review | Cash flow adjustment | Public transport services | Passenger services - bus | Gisborne District Council | Government reduced public transport fares scheme (Crown) | Implementation | Bus Services - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Crown appropriation finished. | -24 | -24 | [5 empty] | 281227 |  | 126719
2023-12-08 | December 2023 Review | Cash flow adjustment | State highway improvements | Replacement of bridges and other structures | NZTA (Auckland) | AHB Edge Barrier Strengthening | Implementation | AHB Edge Barrier Strengthening | HHVL | HHL | N | 9 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project closed | 0 | 0 |  |  |  | 0.8 |  | 275386 | 60059824 | 126564
2023-12-08 | December 2023 Review | Cash flow adjustment | External funding | Replacement of bridges and other structures | NZTA (Northland) | CIP SH10 Papakawau Culvert Improvements | Pre-implementation* | Crown Infrastructure Partners | M_M | MMM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  | 0 | 0 | CIP SH10 Papakawau Culvert Improvements | 271521 | 60059170 | 126585
2023-12-08 | December 2023 Review | Cash flow adjustment | State highway improvements | Resilience improvements | NZTA (Northland) | SH12 Opononi Foreshore Resilience Improvement | Construction |  | HHH | HHH | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project close-out; project is complete and no further invoices are due. | 0 | 0 |  |  |  |  | 60047703 | 257026 | 60047703 | 126584
2023-12-08 | December 2023 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (BOP) | W2T Waihi to Omokoroa (Safer Corridor) | Detailed Business Case | Waihi to Omokoroa | VHHL | HHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | project close | 0 | 0 |  |  | 0 | 1 | 60039786 | 247057 | 60039786 | 126583
2023-12-08 | December 2023 Review | Cash flow adjustment | Local road improvements | Road improvements | Whangarei District Council | Maunu Road/Central Ave/Walton St/Water St Intersection Imp | Implementation | Maunu/Central Intersection | HMM | HHM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Will not be constructed in 2021-24 | 0 | 0 |  |  | 0 | 3.8 |  | 260579 |  | 126040
2023-12-19 | December 2023 Review | Cost Decrease | Local road maintenance | Bridge and structures renewals | Manawatu District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This net change is to allow Manawatu DC to undertake the strengthening and repair work to Otara Boundary bridge in conjunction with Rangitikei DC. This bridge is a vital rural connector that links both councils to SH1 in Ohingaiti. All supporting documents are located in TIO | -732686 | -373670 | [5 empty] | 273022 |  | 126178
2023-12-19 | December 2023 Review | Cost Increase | Local road maintenance | Cycle path maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The recent (November 2023) MOR review item resulted in incorrect TIO allocations across MOR work categories. This review item will correct MOR allocations to the approved values. | 44077 | 22479 | [5 empty] | 274704 |  | 126718
2023-12-19 | December 2023 Review | Cost Decrease | Local road maintenance | Cycle path renewal | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The recent (November 2023) MOR review item resulted in incorrect TIO allocations across MOR work categories. This review item will correct MOR allocations to the approved values. | -59963 | -30581 | [5 empty] | 274720 |  | 126718
2023-12-20 | December 2023 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Dunedin City Council | Dunedin Urban Cycleways | Single-Stage Business Case | DUC - North East Valley | VHLL | HHL | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Phase complete. | -340400 | -173604 |  |  | 1.4 | 1.4 |  | 267542 |  | 126747
2023-12-20 | December 2023 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Hutt City Council | SfP Hutt City Suburban Centres Tactical Urbanism | Implementation | SfP Wainuiomata Implementation | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | increased cost for Rata St. and agreed with SfP team lead oct 4 2023 | 38889 | 35000 |  |  |  |  | C00033.SFP.300 | 282745 |  | 126299
2023-12-11 | December 2023 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Tasman District Council | SfP Tasman Towns | Implementation | SfP Mapua Cycle Lanes | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reinstating $855,730 in Yr 2 during cashflow as system thinks that this project is claiming complete | 396661 | 356995 |  |  |  | 1 |  | 282764 |  | 126641
2023-12-08 | December 2023 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Tasman District Council | SfP Tasman Towns | Implementation | SfP Mapua Cycle Lanes | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2023/24 as activity is claiming complete | -396661 | -356995 |  |  |  | 1 |  | 282764 |  | 126511
2023-12-08 | December 2023 Review | Cost Increase | Local road maintenance | Drainage renewals | Hamilton City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The Hamilton City Transport network is degrading and costs are rising (see detail below) and recently Council has approved additional funding for the 2023/24 financial year of $5,000,000 for progressing additional Transport Renewals works to address the network need. Maintenance & Operations costs are also rising but we were not successful in obtaining additional M&O funding in the current financial environment. The previously existing HCC Transport Combined Subsidised Maintenance, Operations and Renewals Budget for 2023/24 is $34.23m which is supported by an approved Waka Kotahi programme level of $32.45m, and Council is committed to undertaking approx. $1.7m of subsidisable works at full local share cost, as has been the case in both 2021/22 and 2022/23. The new renewals budget has elevated the unsupported value of works through the continuous programme to approx. $6.7m. The Council has advised that if we are successful in obtaining additional Waka Kotahi support for the Continuous programme that value is to be reinvested on the transport network, allowing additional progress against the renewals forward works plan, and pavement / footpath maintenance defects list. Council is already committed and resourced to deliver this value of work, and thanks to the Alliance / Collaborative supplier contract in place as Connect Hamilton we are able to easily increase the level of resources to complete works to a value of $5m plus any Waka Kotahi funding. Some issues which have had an impact on the costs for the Hamilton City Transport network Maintenance, Operations and Renewals works in 2023/24, | 1000000 | 510000 | [5 empty] | 272658 |  | 125964
2023-12-19 | December 2023 Review | Cost Increase | Local road maintenance | Drainage renewals | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The recent (November 2023) MOR review item resulted in incorrect TIO allocations across MOR work categories. This review item will correct MOR allocations to the approved values. | 415683 | 211998 | [5 empty] | 274714 |  | 126718
2023-12-20 | December 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Kaipara District Council | EW - Baylys Beach Entrance 7 Oct 2021 event | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Phase complete. | -319248 | -197934 |  |  |  |  | Immediate Response and Permanent repair | 280425 |  | 126740
2023-12-22 | December 2023 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (BOP) | EW BOP Extreme HR 20230127 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | There seems to have been some confusion around who was delivery what. Hopefully this is sorted out now and we can get on the repairs. I support this application. NAC | 1378849 | 1378849 | [5 empty] | 283625 | 60069770 | 126649
2023-12-11 | December 2023 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Manawatu/Whanganui) | EW Otanga Road Slip 20220226 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | I am content that this slip fits within the current PIKB guidance for emergency works. I recommend approval NC Recovery Manager. | 2516968 | 2516968 | [5 empty] | 282908 | 60068503 | 126371
2023-12-14 | December 2023 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Tasman) | EW Dellows Rockfall 20220720 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | This PLA should have been prepared once detail design was completed and before construction, not at the end of construction. Limited details of the additional cost other than increased scope. Any opportunity for a change in outcome has been lost. I am content that the event fits within the current PIKB guidance for emergency works funding and in the interest of closing this project out I support approval. N Cook. | 1405266 | 1405266 | [5 empty] | 282224 | 60068109 | 126545
2023-12-20 | December 2023 Review | Cost Increase | Local road maintenance | Emergency works | Waikato District Council | EW - Waikato DC Storm Damage Jan-Feb 2023 | Construction | 23/24 Phase 2 - Investigation and Design | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | This funding approval enables the transport service at this network to be reinstated to the appropriate levels of service. | 673000 | 343230 |  |  |  |  | Phase Two - Investigation and Design | 288480 |  | 126525
2023-12-20 | December 2023 Review | Cost Increase | Local road maintenance | Emergency works | Waikato District Council | EW - Waikato DC Storm Damage Jan-Feb 2023 | Construction | Phase 2 - Construction of Practitioner Sites | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | This funding approval enables the transport service at this network to be reinstated to the appropriate levels of service. | 2229000 | 1136790 |  |  |  |  | Phase 2 - Construction of Practitioner Sites | 288479 |  | 126524
2023-12-14 | December 2023 Review | Cost Increase | Local road maintenance | Emergency works | Whanganui District Council | Cyclone Dovi - 13 February 2022 Emergency Works | Construction | Major Repairs | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | As agreed with VOS and signed by Ben White | 2540000 | 2032000 |  |  |  |  | Request for emergency works funding | 281498 |  | 126701
2023-12-19 | December 2023 Review | Cost Increase | Local road maintenance | Environmental maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The recent (November 2023) MOR review item resulted in incorrect TIO allocations across MOR work categories. This review item will correct MOR allocations to the approved values. | 1596517 | 814223 | [5 empty] | 274707 |  | 126718
2023-12-19 | December 2023 Review | Cost Increase | Local road maintenance | Environmental renewals | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The recent (November 2023) MOR review item resulted in incorrect TIO allocations across MOR work categories. This review item will correct MOR allocations to the approved values. | 10472 | 5341 | [5 empty] | 274718 |  | 126718
2023-12-19 | December 2023 Review | Cost Increase | Local road maintenance | Footpath maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The recent (November 2023) MOR review item resulted in incorrect TIO allocations across MOR work categories. This review item will correct MOR allocations to the approved values. | 130771 | 66693 | [5 empty] | 274705 |  | 126718
2023-12-08 | December 2023 Review | Cost Increase | Local road maintenance | Footpath renewal | Hamilton City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The Hamilton City Transport network is degrading and costs are rising (see detail below) and recently Council has approved additional funding for the 2023/24 financial year of $5,000,000 for progressing additional Transport Renewals works to address the network need. Maintenance & Operations costs are also rising but we were not successful in obtaining additional M&O funding in the current financial environment. The previously existing HCC Transport Combined Subsidised Maintenance, Operations and Renewals Budget for 2023/24 is $34.23m which is supported by an approved Waka Kotahi programme level of $32.45m, and Council is committed to undertaking approx. $1.7m of subsidisable works at full local share cost, as has been the case in both 2021/22 and 2022/23. The new renewals budget has elevated the unsupported value of works through the continuous programme to approx. $6.7m. The Council has advised that if we are successful in obtaining additional Waka Kotahi support for the Continuous programme that value is to be reinvested on the transport network, allowing additional progress against the renewals forward works plan, and pavement / footpath maintenance defects list. Council is already committed and resourced to deliver this value of work, and thanks to the Alliance / Collaborative supplier contract in place as Connect Hamilton we are able to easily increase the level of resources to complete works to a value of $5m plus any Waka Kotahi funding. Some issues which have had an impact on the costs for the Hamilton City Transport network Maintenance, Operations and Renewals works in 2023/24, | 600000 | 306000 | [5 empty] | 272665 |  | 125964
2023-12-19 | December 2023 Review | Cost Increase | Local road maintenance | Footpath renewal | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The recent (November 2023) MOR review item resulted in incorrect TIO allocations across MOR work categories. This review item will correct MOR allocations to the approved values. | 131932 | 67285 | [5 empty] | 274721 |  | 126718
2023-12-20 | December 2023 Review | Cost Decrease | Local road improvements | Low cost / low risk improvements | Hauraki District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Unable to utilise all of the 2023/24 approved allocation. | -58298 | -34979 | [5 empty] | 276160 |  | 126739
2023-12-20 | December 2023 Review | Cost Decrease | Road to Zero | Low cost / low risk improvements | Hauraki District Council | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Deferral of speed management plan to 2024/25. | -482000 | -289200 | [5 empty] | 276157 |  | 126738
2023-12-04 | December 2023 Review | Cost Increase | Walking and cycling improvements | Low cost / low risk improvements | Queenstown-Lakes District Council | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | CSA is to cover price increases in tender box. Council has proven delivery this NLTP | 640000 | 326400 | [5 empty] | 276359 |  | 126390
2023-12-04 | December 2023 Review | Cost Increase | Local road improvements | Low cost / low risk improvements | Rotorua Lakes Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Project to deliver a resilience improvement that was not successful in attracting funding from the Transport Resilience Fund. The project will improve drainage on a road that has been closed three times this year due to flooding, scour and damaged pavement. Rotorua LC is surplusing funds from LCLR R2Z and W&C activity classes to offset the request in LRI. | 622068 | 348358 | [5 empty] | 276369 |  | 126389
2023-12-19 | December 2023 Review | Cost Decrease | Local road maintenance | Minor events | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The recent (November 2023) MOR review item resulted in incorrect TIO allocations across MOR work categories. This review item will correct MOR allocations to the approved values. | -117476 | -59913 | [5 empty] | 274706 |  | 126718
2023-12-19 | December 2023 Review | Cost Increase | Local road maintenance | Network and asset management | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The recent (November 2023) MOR review item resulted in incorrect TIO allocations across MOR work categories. This review item will correct MOR allocations to the approved values. | 636561 | 324646 | [5 empty] | 274711 |  | 126718
2023-12-19 | December 2023 Review | Cost Increase | Local road maintenance | Network operations | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The recent (November 2023) MOR review item resulted in incorrect TIO allocations across MOR work categories. This review item will correct MOR allocations to the approved values. | 246619 | 125776 | [5 empty] | 274709 |  | 126718
2023-12-08 | December 2023 Review | Cost Increase | Local road maintenance | Network service maintenance | Hamilton City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The Hamilton City Transport network is degrading and costs are rising (see detail below) and recently Council has approved additional funding for the 2023/24 financial year of $5,000,000 for progressing additional Transport Renewals works to address the network need. Maintenance & Operations costs are also rising but we were not successful in obtaining additional M&O funding in the current financial environment. The previously existing HCC Transport Combined Subsidised Maintenance, Operations and Renewals Budget for 2023/24 is $34.23m which is supported by an approved Waka Kotahi programme level of $32.45m, and Council is committed to undertaking approx. $1.7m of subsidisable works at full local share cost, as has been the case in both 2021/22 and 2022/23. The new renewals budget has elevated the unsupported value of works through the continuous programme to approx. $6.7m. The Council has advised that if we are successful in obtaining additional Waka Kotahi support for the Continuous programme that value is to be reinvested on the transport network, allowing additional progress against the renewals forward works plan, and pavement / footpath maintenance defects list. Council is already committed and resourced to deliver this value of work, and thanks to the Alliance / Collaborative supplier contract in place as Connect Hamilton we are able to easily increase the level of resources to complete works to a value of $5m plus any Waka Kotahi funding. Some issues which have had an impact on the costs for the Hamilton City Transport network Maintenance, Operations and Renewals works in 2023/24, | 500000 | 255000 | [5 empty] | 272652 |  | 125964
2023-12-19 | December 2023 Review | Cost Increase | Local road maintenance | Network service maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The recent (November 2023) MOR review item resulted in incorrect TIO allocations across MOR work categories. This review item will correct MOR allocations to the approved values. | 604638 | 308366 | [5 empty] | 274708 |  | 126718
2023-12-20 | December 2023 Review | Cost Decrease | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | Dunedin City Council | SFDT - Park and Ride Facilities - Mosgiel and Burnside | Single-Stage Business Case | Park and Ride - Mosgiel | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Phase complete. | -25000 | -12750 |  |  | 2.2 | 1.6 | Mosgiel park and ride | 276615 |  | 126748
2023-12-11 | December 2023 Review | Cost Decrease | External funding | Passenger services - bus | Tasman District Council | CERF-Bus Driver Ts & Cs | Implementation | CERF - Driver Wage Uplift | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reset FAR back to 51% | 0 | -113725 |  |  |  | 1 |  | 289286 |  | 126648
2023-12-20 | December 2023 Review | Cost Decrease | Investment management (incl. Transport Planning) | Programme Business Case Development | Queenstown-Lakes District Council | Queenstown Integrated Transport PBC (Frankton Masterplan) | Programme business case |  | H__ | V__ | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Phase complete | -101774 | -51905 |  |  |  |  | PBC QIT | 260907 |  | 126741
2023-12-20 | December 2023 Review | Cost Decrease | Investment management (incl. Transport Planning) | Programme Business Case Development | Queenstown-Lakes District Council | Queenstown Lakes Partnership | Programme business case |  | H__ | H__ | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Phase complete | -1240 | -632 |  |  |  |  | QLSP Development | 269796 |  | 126742
2023-12-04 | December 2023 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (BOP) | Minden Te Puna Intersection Improvements | Property |  | H_M | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | interphase transfer of $439,110 from 60217896 Construction to 60467682 Property due to increased costs | 465457 | 465457 |  |  | 2.5 | 2.5 | 60467682 | 232655 | 60467682 | 126582
2023-12-04 | December 2023 Review | Cost Increase | External funding | Property purchase (State highways) | NZTA (Canterbury) | NZUP Rolleston Access Improvements | Property | NZ Upgrade Programme | VHHM | VHHM | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | To transfer $33,727,493 from Imp 1) Interphase transfer $10,439,495 from Imp(60057117) to PreImp(60057114)& 2) Interphase transfer $23,287,998 from Imp (60057117) to Property (60057115) due to increase PreImp fees/M-costs & incr Prop costs/more land requisition | 24219518 | 24219518 |  |  | 3.6 | 3.6 |  | 270420 | 60057115 | 126574
2023-12-20 | December 2023 Review | Cost Increase | External funding | Property purchase (State highways) | NZTA (Canterbury) | NZUP Walnut Avenue Intersection Improvements | Property | NZ Upgrade Programme | M_L | MHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cost neutral. | 1166671 | 1166671 |  |  | 1.8 | 1.8 | 60057032 | 270286 | 60057032 | 126727
2023-12-19 | December 2023 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Waikato) | SH30 Kopaki Bridge Replacement | Property | Property | H__ | H__ | N | 0 | Approved | Approved by Chief Financial Officer (CFO) |  | 50652 | 50652 |  |  | 99 | 99 | End of life bridge replacement | 269934 | 60052600 | 126493
2023-12-22 | December 2023 Review | Cost Increase | Road to Zero | Property purchase (local roads) | Selwyn District Council | Prebbleton Arterial CSM Related Upgrade Packages | Property | Shands/Hamptons Roundabout | HML | HML | N | 6 | Approved | Approved by Chief Financial Officer (CFO) |  | 913600 | 465936 |  |  | 1 | 1 | Shands/Hamptons in conjunction with Implementation phase | 282188 |  | 126143
2023-12-20 | December 2023 Review | Cost Decrease | Public transport infrastructure | Public transport infrastructure and major renewals | Queenstown-Lakes District Council | Park and Ride Transport Services | Single-Stage Business Case | Single Stage Business Case | MML | HHM | N | 9 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Phase complete | -14407 | -7348 |  |  | 1.2 | 0 |  | 258097 |  | 126743
2023-12-19 | December 2023 Review | Cost Increase | Local road maintenance | Rail level crossing warning devices maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The recent (November 2023) MOR review item resulted in incorrect TIO allocations across MOR work categories. This review item will correct MOR allocations to the approved values. | 4122 | 2102 | [5 empty] | 274710 |  | 126718
2023-12-18 | December 2023 Review | Cost Increase | Public transport infrastructure | Rapid Transit Infrastructure | NZTA (Auckland) | Supporting Growth Auckland | Pre-implementation* | Supporting Growth Alliance - PT Post Lodgement | H_M | HHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This funding approval enables the Supporting Growth Alliance to progress to the route protection phase for the proposed North Integrated Transport Network, to future proof for transport infrastructure that will meet Waka Kotahiâ€™s strategic objectives. | 5010905 | 5010905 |  |  | 1.6 | 1.6 |  | 284214 | 60070514 | 126558
2023-12-21 | December 2023 Review | Cost Increase | State highway improvements | Replacement of bridges and other structures | NZTA (Northland) | SH12 Matakohe Bridges | Implementation | NLTF-SH Improvements | H_L | MHL | N | 0 | Approved | Approved by Chief Financial Officer (CFO) |  | 313407 | 313407 |  |  | 1.3 | 1.3 | 60040765 | 278774 | 60040765 | 126677
2023-12-05 | December 2023 Review | Cost Increase | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH26 Onetai Stream Bridge Replacement | Implementation | SH26 Onetai Stream Bridge Replacement | H_PV_EoL | MMH | N | 0 | Approved | Approved by Chief Financial Officer (CFO) |  | 1186299 | 1186299 |  |  | 0 | 0 |  | 231694 | 60052985 | 126563
2023-12-05 | December 2023 Review | Cost Increase | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH26 Onetai Stream Bridge Replacement | Pre-implementation* | SH26 Onetai Stream Bridge Replacement | H_PV_EoL | MMH | N | 0 | Approved | Approved by Chief Financial Officer (CFO) |  | 65400 | 65400 |  |  | 0 | 0 |  | 231693 | 60052984 | 126562
2023-12-19 | December 2023 Review | Cost Increase | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH30 Kopaki Bridge Replacement | Implementation |  | H__ | H__ | N | 0 | Approved | Approved by Chief Financial Officer (CFO) |  | 1346330 | 1346330 |  |  | 99 | 99 |  | 254885 | 60052983 | 126492
2023-12-19 | December 2023 Review | Cost Increase | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH30 Kopaki Bridge Replacement | Pre-implementation* |  | H__ | H__ | N | 0 | Approved | Approved by Chief Financial Officer (CFO) |  | 19701 | 19701 |  |  | 99 | 99 |  | 258502 | 60052080 | 126494
2023-12-08 | December 2023 Review | Cost Decrease | State highway improvements | Replacement of bridges and other structures | NZTA (West Coast) | SH7 Ahaura River Bridge Replacement | Implementation | Construction | H__ | H__ | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Surplus $44,913 to close project | -48956 | -48956 |  |  | 0 | 0 | 60030967 | 232575 | 60030967 | 126598
2023-12-04 | December 2023 Review | Cost Increase | External funding | Resilience improvements | NZTA (Southland) | Crown Resilience Programme LCLR STLD | Implementation |  | VH_H | VHHH | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transferring $300,000 allocation from Crown Resilience Programme LCLR OTA (item ID 60071739) to Crown Resilience Programme LCLR STLD (item ID 60071743) to move "SH94 Shooting Rail (Milford Road)" project from Otago to Southland. | 319500 | 319500 |  |  |  | 4 |  | 290382 | 60071743 | 126543
2023-12-12 | December 2023 Review | Cost Increase | Local road improvements | Road improvements | Auckland Transport | Transport Network for Growth - Combined | Detailed Business Case | TNFG - Combined - DBC and Pre-lodgement | H_M | HHM | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | The price level increase enables completion of the detailed business cases phase of the programme specifically pre-lodgement preparation for the Notices of Requirements. The purpose of the business case and subsequent pre-lodgement work is to outline the case for route protecting the preferred transport network, ahead of the planned growth identified in Auckland Councilâ€™s Future Urban Land Supply Strategy. Route protecting enables the following outcomes to be achieved, improved safety of the transport network, long term development of a low carbon transport system, facilitated through mode shift from single occupancy vehicles towards PT and active modes reducing greenhouse gas emissions. The future network will also support improving economic and social opportunities for present and future communities through improved land-use and transport integration. | 9407276 | 4797711 |  |  | 1.1 | 1 | 324.2682 | 268152 |  | 125521
2023-12-20 | December 2023 Review | Cost Decrease | Local road improvements | Road improvements | Dunedin City Council | Blackhead Road Standard Safety Intervention (SSI) | Implementation | Design and construct | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Phase complete. | -109119 | -77474 |  |  | 0 | 0 |  | 269171 |  | 126744
2023-12-04 | December 2023 Review | Cost Increase | Local road improvements | Road improvements | Dunedin City Council | Central City Plan Upgrade | Implementation | Retail Quarter Upgrade | VHHL | VHHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | Cost increase caused by higher escalation than anticipated (22% over 2 years vs 4%), unexpected concrete below existing footpaths and unidentified utilities being found. Funding will enable DCC to complete the project and reinstate the streetscape to an acceptable standard | 4000000 | 2040000 |  |  | 1.3 | 1.3 |  | 230513 |  | 126196
2023-12-20 | December 2023 Review | Cost Decrease | Local road improvements | Road improvements | Dunedin City Council | SFDT - Harbour Arterial Efficiency Improvements | Single-Stage Business Case | Harbour Arterial Stage two and three | VHHL | VHHH | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Phase complete. | -54133 | -27608 |  |  |  | 1.7 | Harbour Arterial Stage 2 and 3 SSBC | 276612 |  | 126749
2023-12-11 | December 2023 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Auckland) | Auckland Network Optimisation (ANO) Programme | Pre-implementation* | Auckland System Optimisation SH - Stage 1 | MHM | MHM | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer $400,000 to 60074164 ANO SH1 Onewa Pre imp phase & Transfer $300,000 to 60073742 & 60056410 SH16 SH1 Grafton Link -$700,000 | -763002 | -763002 |  |  |  | 3.2 | InfoHub ID 28116348 ¦ SAP 60056410 | 254838 | 60056410 | 126561
2023-12-18 | December 2023 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Auckland) | Supporting Growth Auckland | Pre-implementation* | Supporting Growth Alliance - SH Post Lodgement | H_M | HHM | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | This funding approval enables the Supporting Growth Alliance to progress to the route protection phase for the proposed North Integrated Transport Network, to future proof for transport infrastructure that will meet Waka Kotahiâ€™s strategic objectives. | 4761120 | 4761120 |  |  | 1.6 | 1.6 | SH Post Lodgement | 267282 | 60053072 | 126560
2023-12-04 | December 2023 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (BOP) | Minden Te Puna Intersection Improvements | Construction | Construction | H_M | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | interphase transfer of $439,110 from 60217896 Construction to 60467682 Property due to increased costs | -478630 | -478630 |  |  | 2.5 | 2.5 | 60217896 | 231383 | 60217896 | 126581
2023-12-11 | December 2023 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (BOP) | SH2 Hewletts Road Sub area Access | Single-Stage Business Case | Indicative Business Case phase | VHHL | HML | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | SSBC 60061770 is being closed and $999998 surplus to be reallocated to 60073991 IBC to correct phase type(All costs will follow) | -1089999 | -1089999 |  |  |  | 2.7 |  | 277415 | 60061770 | 126521
2023-12-20 | December 2023 Review | Cost Decrease | External funding | Road improvements | NZTA (Canterbury) | NZUP Canterbury Package Contingency | Implementation | NZUP Canterbury Package Contingency | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cost neutral transfer | -2414671 | -2414671 |  |  | 0 | 0 |  | 284105 | 60070383 | 126725
2023-12-04 | December 2023 Review | Cost Decrease | External funding | Road improvements | NZTA (Canterbury) | NZUP Rolleston Access Improvements | Implementation | NZUP Rolleston Access Improvements | VHHM | VHHM | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | To transfer $33,727,493 from Imp 1) Interphase transfer $10,439,495 from Imp(60057117) to PreImp(60057114)& 2) Interphase transfer $23,287,998 from Imp (60057117) to Property (60057115) due to increase PreImp fees/M-costs & incr Prop costs/more land requisition | -35076592 | -35076592 |  |  | 3.6 | 3.6 |  | 231732 | 60057117 | 123010
2023-12-04 | December 2023 Review | Cost Increase | External funding | Road improvements | NZTA (Canterbury) | NZUP Rolleston Access Improvements | Pre-implementation* | NZ Upgrade Programme | VHHM | VHHM | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | To transfer $33,727,493 from Imp 1) Interphase transfer $10,439,495 from Imp(60057117) to PreImp(60057114)& 2) Interphase transfer $23,287,998 from Imp (60057117) to Property (60057115) due to increase PreImp fees/M-costs & incr Prop costs/more land requisition | 10857075 | 10857075 |  |  | 3.6 | 3.6 |  | 231731 | 60057114 | 126573
2023-12-20 | December 2023 Review | Cost Increase | External funding | Road improvements | NZTA (Canterbury) | NZUP Walnut Avenue Intersection Improvements | Implementation | NZ Upgrade | M_L | MHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cost neutral transfer | 1248000 | 1248000 |  |  | 1.8 | 1.8 | 60211591 | 231796 | 60211591 | 126726
2023-12-22 | December 2023 Review | Cost Increase | Road to Zero | Road improvements | Selwyn District Council | Prebbleton Arterial CSM Related Upgrade Packages | Implementation | Shands/Hamptons Rd Roundabout | HML | HML | N | 6 | Approved | Approved by Chief Financial Officer (CFO) |  | 3096925 | 1406504 |  |  | 1 | 1 | Shands/Hamptons in conjunction with property phase | 260904 |  | 125937
2023-12-19 | December 2023 Review | Cost Increase | Local road maintenance | Routine drainage maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The recent (November 2023) MOR review item resulted in incorrect TIO allocations across MOR work categories. This review item will correct MOR allocations to the approved values. | 169420 | 86405 | [5 empty] | 274702 |  | 126718
2023-12-18 | December 2023 Review | Cost Decrease | Road to Zero | Safety promotion, education and advertising | NZTA (Auckland) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please move $90,610 rom â€˜60065061â€™ â€˜(construction) to â€˜60065057â€™Â (construction)Â due to anticipated State highway billbaord refresh in Northland | 0 | -98765 |  |  |  |  | 60065061 | 273190 | 60065061 | 126708
2023-12-20 | December 2023 Review | Cost Decrease | Road to Zero | Safety promotion, education and advertising | NZTA (BOP) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funding surplus to requirements | 0 | -47418 |  |  |  |  | 60065069 | 273242 | 60065069 | 126710
2023-12-18 | December 2023 Review | Cost Decrease | Road to Zero | Safety promotion, education and advertising | NZTA (Canterbury) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please move $22,667 from â€˜60065103â€™ â€˜(construction) to â€˜60065107â€™Â (construction)Â due West coast billboards | 0 | -24707 |  |  |  |  | 60065103 | 273398 | 60065103 | 126702
2023-12-20 | December 2023 Review | Cost Decrease | Road to Zero | Safety promotion, education and advertising | NZTA (Gisborne) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funding surplus to requirements | 0 | -10900 |  |  |  |  | 60065073 | 273268 | 60065073 | 126711
2023-12-20 | December 2023 Review | Cost Decrease | Road to Zero | Safety promotion, education and advertising | NZTA (Hawkes Bay) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funding surplus to requirements | 0 | -132991 |  |  |  |  | 60065077 | 273294 | 60065077 | 126712
2023-12-18 | December 2023 Review | Cost Decrease | Road to Zero | Safety promotion, education and advertising | NZTA (Manawatu/Whanganui) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please move $158,173 from â€˜60065081â€™ â€˜(construction) to â€˜60065085â€™ (construction) due to setting aside funds to cease SH Billboard programme if required | 0 | -172408 |  |  |  |  | 60065081 | 273346 | 60065081 | 126713
2023-12-20 | December 2023 Review | Cost Decrease | Road to Zero | Safety promotion, education and advertising | NZTA (Marlborough) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funding surplus to requirements | 0 | -169351 |  |  |  |  | 60065093 | 273502 | 60065093 | 126716
2023-12-20 | December 2023 Review | Cost Decrease | Road to Zero | Safety promotion, education and advertising | NZTA (Nelson) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funding surplus to requirements | 0 | -115491 |  |  |  |  | 60065089 | 273528 | 60065089 | 126715
2023-12-18 | December 2023 Review | Cost Increase | Road to Zero | Safety promotion, education and advertising | NZTA (Northland) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please move $90,610 from â€˜60065061â€™ â€˜(construction) to â€˜60065057â€™Â (construction)Â due cost of State highway billbaord refresh in Northlandrefresh in Northland | 0 | 98763 |  |  |  |  | 60065057 | 273164 | 60065057 | 126707
2023-12-20 | December 2023 Review | Cost Decrease | Road to Zero | Safety promotion, education and advertising | NZTA (Southland) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds surplus to requirements | 0 | -289367 |  |  |  |  | 60065115 | 273476 | 60065115 | 126705
2023-12-20 | December 2023 Review | Cost Decrease | Road to Zero | Safety promotion, education and advertising | NZTA (Tasman) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds surplus to requirements | 0 | -171675 |  |  |  |  | 60065097 | 273554 | 60065097 | 126717
2023-12-20 | December 2023 Review | Cost Decrease | Road to Zero | Safety promotion, education and advertising | NZTA (Waikato) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds surplus to requirements | 0 | -164477 | [5 empty] | 273216 | 60065065 | 126709
2023-12-18 | December 2023 Review | Cost Increase | Road to Zero | Safety promotion, education and advertising | NZTA (Wellington) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please move $158,173 from â€˜60065081â€™ â€˜(construction) to â€˜60065085â€™Â (construction)Â due setting aside funds to cease SH Billboard programme if required | 0 | 172407 | [5 empty] | 273372 | 60065085 | 126714
2023-12-18 | December 2023 Review | Cost Increase | Road to Zero | Safety promotion, education and advertising | NZTA (West Coast) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please move $22,667 from â€˜60065103â€™ â€˜(construction) to â€˜60065107â€™Â (construction)Â due West coast billboards | 0 | 24709 |  |  |  |  | 60065107 | 273424 | 60065107 | 126703
2023-12-08 | December 2023 Review | Cost Increase | Local road maintenance | Sealed pavement maintenance | Hamilton City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The Hamilton City Transport network is degrading and costs are rising (see detail below) and recently Council has approved additional funding for the 2023/24 financial year of $5,000,000 for progressing additional Transport Renewals works to address the network need. Maintenance & Operations costs are also rising but we were not successful in obtaining additional M&O funding in the current financial environment. The previously existing HCC Transport Combined Subsidised Maintenance, Operations and Renewals Budget for 2023/24 is $34.23m which is supported by an approved Waka Kotahi programme level of $32.45m, and Council is committed to undertaking approx. $1.7m of subsidisable works at full local share cost, as has been the case in both 2021/22 and 2022/23. The new renewals budget has elevated the unsupported value of works through the continuous programme to approx. $6.7m. The Council has advised that if we are successful in obtaining additional Waka Kotahi support for the Continuous programme that value is to be reinvested on the transport network, allowing additional progress against the renewals forward works plan, and pavement / footpath maintenance defects list. Council is already committed and resourced to deliver this value of work, and thanks to the Alliance / Collaborative supplier contract in place as Connect Hamilton we are able to easily increase the level of resources to complete works to a value of $5m plus any Waka Kotahi funding. Some issues which have had an impact on the costs for the Hamilton City Transport network Maintenance, Operations and Renewals works in 2023/24, | 1500000 | 765000 | [5 empty] | 272644 |  | 125964
2023-12-19 | December 2023 Review | Cost Decrease | Local road maintenance | Sealed pavement maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The recent (November 2023) MOR review item resulted in incorrect TIO allocations across MOR work categories. This review item will correct MOR allocations to the approved values. | -14123530 | -7203000 | [5 empty] | 274700 |  | 126718
2023-12-08 | December 2023 Review | Cost Increase | Local road maintenance | Sealed road pavement rehabilitation | Hamilton City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The Hamilton City Transport network is degrading and costs are rising (see detail below) and recently Council has approved additional funding for the 2023/24 financial year of $5,000,000 for progressing additional Transport Renewals works to address the network need. Maintenance & Operations costs are also rising but we were not successful in obtaining additional M&O funding in the current financial environment. The previously existing HCC Transport Combined Subsidised Maintenance, Operations and Renewals Budget for 2023/24 is $34.23m which is supported by an approved Waka Kotahi programme level of $32.45m, and Council is committed to undertaking approx. $1.7m of subsidisable works at full local share cost, as has been the case in both 2021/22 and 2022/23. The new renewals budget has elevated the unsupported value of works through the continuous programme to approx. $6.7m. The Council has advised that if we are successful in obtaining additional Waka Kotahi support for the Continuous programme that value is to be reinvested on the transport network, allowing additional progress against the renewals forward works plan, and pavement / footpath maintenance defects list. Council is already committed and resourced to deliver this value of work, and thanks to the Alliance / Collaborative supplier contract in place as Connect Hamilton we are able to easily increase the level of resources to complete works to a value of $5m plus any Waka Kotahi funding. Some issues which have had an impact on the costs for the Hamilton City Transport network Maintenance, Operations and Renewals works in 2023/24, | 2000000 | 1020000 | [5 empty] | 272659 |  | 125964
2023-12-19 | December 2023 Review | Cost Increase | Local road maintenance | Sealed road pavement rehabilitation | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The recent (November 2023) MOR review item resulted in incorrect TIO allocations across MOR work categories. This review item will correct MOR allocations to the approved values. | 240425 | 122617 | [5 empty] | 274715 |  | 126718
2023-12-08 | December 2023 Review | Cost Increase | Local road maintenance | Sealed road resurfacing | Hamilton City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The Hamilton City Transport network is degrading and costs are rising (see detail below) and recently Council has approved additional funding for the 2023/24 financial year of $5,000,000 for progressing additional Transport Renewals works to address the network need. Maintenance & Operations costs are also rising but we were not successful in obtaining additional M&O funding in the current financial environment. The previously existing HCC Transport Combined Subsidised Maintenance, Operations and Renewals Budget for 2023/24 is $34.23m which is supported by an approved Waka Kotahi programme level of $32.45m, and Council is committed to undertaking approx. $1.7m of subsidisable works at full local share cost, as has been the case in both 2021/22 and 2022/23. The new renewals budget has elevated the unsupported value of works through the continuous programme to approx. $6.7m. The Council has advised that if we are successful in obtaining additional Waka Kotahi support for the Continuous programme that value is to be reinvested on the transport network, allowing additional progress against the renewals forward works plan, and pavement / footpath maintenance defects list. Council is already committed and resourced to deliver this value of work, and thanks to the Alliance / Collaborative supplier contract in place as Connect Hamilton we are able to easily increase the level of resources to complete works to a value of $5m plus any Waka Kotahi funding. Some issues which have had an impact on the costs for the Hamilton City Transport network Maintenance, Operations and Renewals works in 2023/24, | 1500000 | 765000 | [5 empty] | 272657 |  | 125964
2023-12-19 | December 2023 Review | Cost Increase | Local road maintenance | Sealed road resurfacing | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The recent (November 2023) MOR review item resulted in incorrect TIO allocations across MOR work categories. This review item will correct MOR allocations to the approved values. | 2500254 | 1275130 | [5 empty] | 274713 |  | 126718
2023-12-19 | December 2023 Review | Cost Increase | Local road maintenance | Structures component replacements | Manawatu District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This net change is to allow Manawatu DC to undertake the strengthening and repair work to Otara Boundary bridge in conjunction with Rangitikei DC. This bridge is a vital rural connector that links both councils to SH1 in Ohingaiti. All supporting documents are located in TIO | 370000 | 188700 | [5 empty] | 273021 |  | 126178
2023-12-19 | December 2023 Review | Cost Increase | Local road maintenance | Structures component replacements | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The recent (November 2023) MOR review item resulted in incorrect TIO allocations across MOR work categories. This review item will correct MOR allocations to the approved values. | 247088 | 126015 | [5 empty] | 274716 |  | 126718
2023-12-19 | December 2023 Review | Cost Increase | Local road maintenance | Structures maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The recent (November 2023) MOR review item resulted in incorrect TIO allocations across MOR work categories. This review item will correct MOR allocations to the approved values. | 65106 | 33204 | [5 empty] | 274703 |  | 126718
2023-12-08 | December 2023 Review | Cost Decrease | Local road maintenance | Traffic services renewals | Hamilton City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The Hamilton City Transport network is degrading and costs are rising (see detail below) and recently Council has approved additional funding for the 2023/24 financial year of $5,000,000 for progressing additional Transport Renewals works to address the network need. Maintenance & Operations costs are also rising but we were not successful in obtaining additional M&O funding in the current financial environment. The previously existing HCC Transport Combined Subsidised Maintenance, Operations and Renewals Budget for 2023/24 is $34.23m which is supported by an approved Waka Kotahi programme level of $32.45m, and Council is committed to undertaking approx. $1.7m of subsidisable works at full local share cost, as has been the case in both 2021/22 and 2022/23. The new renewals budget has elevated the unsupported value of works through the continuous programme to approx. $6.7m. The Council has advised that if we are successful in obtaining additional Waka Kotahi support for the Continuous programme that value is to be reinvested on the transport network, allowing additional progress against the renewals forward works plan, and pavement / footpath maintenance defects list. Council is already committed and resourced to deliver this value of work, and thanks to the Alliance / Collaborative supplier contract in place as Connect Hamilton we are able to easily increase the level of resources to complete works to a value of $5m plus any Waka Kotahi funding. Some issues which have had an impact on the costs for the Hamilton City Transport network Maintenance, Operations and Renewals works in 2023/24, | -400000 | -204000 | [5 empty] | 272663 |  | 125964
2023-12-19 | December 2023 Review | Cost Increase | Local road maintenance | Traffic services renewals | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The recent (November 2023) MOR review item resulted in incorrect TIO allocations across MOR work categories. This review item will correct MOR allocations to the approved values. | 87621 | 44687 | [5 empty] | 274719 |  | 126718
2023-12-19 | December 2023 Review | Cost Increase | Local road maintenance | Unsealed pavement maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The recent (November 2023) MOR review item resulted in incorrect TIO allocations across MOR work categories. This review item will correct MOR allocations to the approved values. | 100549 | 51280 | [5 empty] | 274701 |  | 126718
2023-12-19 | December 2023 Review | Cost Decrease | Local road maintenance | Unsealed road metalling | Western BoP District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The recent (November 2023) MOR review item resulted in incorrect TIO allocations across MOR work categories. This review item will correct MOR allocations to the approved values. | -26809 | -13672 | [5 empty] | 274712 |  | 126718
2023-12-20 | December 2023 Review | Cost Decrease | Walking and cycling improvements | Walking facilities | NZ Transport Agency | Innovating Streets Programme 2021-24 | Implementation | Green Bond Project- Imp Funding allocated to AOs | HHL | VHHVH | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds transferred to Hutt City | -38889 | -38889 |  |  | 1 | 1 | Green Bond Project-Implementation - Funding allocated to AOs | 279202 |  | 126698