## Risk Register
| Project/Contract Description | To be inserted |  | NZTA Lead | To be inserted
| Contract ID | To be inserted |  | Supplier Lead | To be inserted
| Contract Value | To be inserted |  | Supplier Risk Mgmt Specialist (if applicable) | To be inserted
Contract Risk Register
Risk identifier | Date raised (dd/mm/yyyy) | Risk Description (include whether this is a threat or an opportunity) | Risk Cause(s) | Risk Consequence(s) | Risk Owning Organisation | Risk Owner | Controls | Current Risk Likelihood | Current Risk Consequence | Consequence Category | Current Controlled Risk Level | Level of risk acceptable, when compared to Risk Tolerance Threshold (Y/N) | Planned Risk Trmt Actions Note: If more than one treatment action, either: . Include numbers to identify separate treatments, or: . Refer to Actions Register on separate tab | Treatment Owner(s) | Planned Treatment Implementation Date(s) (dd/mm/yyyy) | Risk Treatment Progress Updates | Residual (Target) Risk Likelihood | Residual (Target) Risk Consequence | Residual (Target) Risk Level | Risk status | Comments
Note on A6: A unique number, may include a prefix specific to this project
Note on F6: Organisation with accountability and responsibility for managing the risk. May be NZTA or another party
Note on G6: Person with accountability and authority to manage risk
Note on H6: Any pre-existing processes, policies, devices, practices or other actions which modify the risk. Note that controls may not always have the intended or assumed modifying effect.
Note on I6: Taking into consideration adequacy and effectiveness of controls currently in place (including completed treatments) - refer tab labelled "rating info - highways (Z44)"
Note on J6: Taking into consideration adequacy and effectiveness of controls currently in place (including completed treatments) - refer tab labelled "rating info - highways (Z44)"
Note on K6: Select the category that reflects the main consequence of the risk
Note on L6: Taking into consideration adequacy and effectiveness of controls currently in place (including completed treatments)
Note on N6: Each unacceptable risk will have treatments which when implemented will modify the risk.
Note on O6: Person/Position and organisation responsible for treating risk
Note on R6: After controls and planned treatments are taken into account - refer tab labelled "rating info - highways (Z44)"
Note on S6: After controls and planned treatments are taken into account - refer tab labelled "rating info - highways (Z44)"
Note on U6: As defined in NZTA's Z44 standard (see tab labelled Risk Status) definitions

## Actions Register
|  | Project/Contract Description | To be inserted
|  | Project/Contract ID | To be inserted
|  | NZTA Lead | To be inserted
ACTIONS REGISTER FOR RISK TREATMENT PLAN
Risk Identifier | Risk Description | Risk Owner | Action ID | Action Description | Action owner | Status | Target Start Date (dd/mm/yyyy) | Target Completion Date (dd/mm/yyyy) | Treatment Cost ($) | Comment (include date of comment)

## Rating info - highways (Z44)
| Project/Contract Description | To be inserted
| Project/Contract ID | To be inserted
| NZTA Lead | To be inserted
For use in rating risks (threats & opportunities) for State Highways contracts - extract from NZTA's Risk Management Practice Guide (minimum standard Z/44)
Note: User to enter details into "Delivery" and "Cost" columns as indicated in red text, to reflect tolerance thresholds for this particular project or activity
NZ Transport Agency Threat Criteria (consequence) | [7 empty] | NZ Transport Agency Opportunity Criteria (consequence)
| Reputation |  |  | Performance |  |  |  |  | Reputation |  | Performance
Rating Scale | Stakeholders | Public / Media | Legal/Compliance | Delivery | Cost | Health & Safety | Environmental | Rating Scale | Stakeholders | Public / Media | Delivery | Cost | Health & Safety | Environmental
Extreme | Disruption to stakeholder relationship slowing progression of nationally strategic activity, and/or Loss of route availability of a national strategic high volume highway. | Sustained national and/or international media coverage Intervention by Minister required, possibly leading to loss of Ministerial confidence. Commission of Inquiry instigated. | High profile prosecution(s) with potential for custodial sentence. | Programme slippage resulting in late delivery by more than 0 days. | Negative financial impact of more than $0M | Loss of life, permanent disability or injury, or multiple serious injuries. | Permanent pollution damage or other environmental damage | Extreme | Enhancement to stakeholder relationship likely to lead to improved implementation of either national or regional strategic activity, and/or Improvement of route availability of either a national strategic high volume highway or a national strategic highway. | Enhancement to NZTA reputation from positive international or national media coverage likely to lead to recognition from Minister. | Programme advancement resulting in early delivery by more than 0 days. | Positive financial impact of more than $0M. | Demonstrate Health & Safety innovation likely to lead to changes in international standards. | Demonstrate environmental innovation likely to lead to changes in international standards.
Severe | Disruption to stakeholder relationship slowing progression of regionally strategic activity, and/or Loss of route availability of a national strategic highway. | Sustained media coverage (weeks) Possible Ministerial inquiry leading to loss of Ministerial confidence/formal enquiry by OAG or statutory agency. | Individual prosecution. | Programme slippage resulting in late delivery by between 0 and 0 days. | Negative financial impact between $0M to $0M. | Serious injury (injuries) requiring specialist medical treatment or lost time greater than three weeks | Significant and widespread pollution or other environmental damage, with long term effects. | Severe | Enhancement to stakeholder relationship likely to lead to improved implementation of a regional activity, and/or Potential for improvement of route availability of a regional strategic highway. | Enhancement to NZTA reputation from positive international or national media coverage likely to lead to recognition from NZTA Board. | Programme advancement resulting in early delivery by between 0 and 0 days. | Positive financial benefit between $0M to $0M. | Demonstrate Health & Safety innovation likely to lead to changes in national standards. | Demonstrate environmental innovation likely to lead to changes in national standards.
Moderate | Disruption to stakeholder relationship slowing progression of regional activity, and/or Loss of route availability of a regional strategic highway. | Short term (days) media coverage Parliamentary/Ministerial questions or 3rd party investigation. | Breach with legal rebuke /abatement notice/restrictions. | Programme slippage resulting in late delivery by between 0 and 0 days. | Negative financial impact between $0M to $0M. | Injury requiring medical treatment or lost time of 1 day to three weeks | Pollution or other environmental damage at a localised level, with medium term effects. | Moderate | Enhancement to NZTA reputation from recorded regional stakeholder feedback, and/or Potential for improvement of route availability of a regional connector highway. | Enhancement to NZTA reputation from regional media coverage likely to lead to recognition from Senior Leadership Team. | Programme advancement resulting in early delivery by between 0 and 0 days. | Positive financial benefit between $0M to $0M. | Demonstrate a number of enhancements to Health & Safety best practice. | Demonstrate a number of enhancements to environmental best practice.
Minor | Disruption to stakeholder relationship slowing progression of site specific activity, and/or Loss of route availability of a regional connector highway. | Local media coverage for 1-5 days Official information request. Negative feedback from Minister. | Breach with letter from authority requesting action. | Programme slippage resulting in late delivery by between 0 and 0 days. | Negative financial impact between $0M to $0M. | Injury requiring short term medical treatment and workplace absence less than one day | Minimum pollution or other environmental damage. Short term effects only. | Minor | Perceived enhancement to NZTA reputation from non- recorded regional stakeholder feedback , and/or Improvement of route availability of a regional distributor highway. | Enhancement to NZTA reputation from positive industry media coverage. | Programme advancement resulting in early delivery by between 0 and 0 days. | Positive financial benefit between $0M to $0M. | Demonstrate industry leading application of Health & Safety best practice. | Demonstrate industry leading application of environmental best practice.
Insignificant | Disruption to stakeholder relationship, and/or Loss of route availability of a regional distributor highway. | Local media coverage for 1 day | Breach managed at a regional level. | Programme slippage resulting in late delivery by less than 0 days. | Negative financial impact of less than $0M. | Injury requiring short-term first-aid care and no absence from the workplace | Small scale pollution or other environmental damage is localised with no resultant effects. Contained locally. | Insignificant | Perceived enhancement to NZTA reputation from non- recorded supplier/partner feedback. | Perceived enhancement to NZTA reputation arising from an absence of negative media coverage. | Programme advancement resulting in early delivery by less than 0 days. | Positive financial benefit of less than $0M. | Demonstrates compliance with Health & Safety practice. | Demonstrates compliance with environmental practice.

## data lists
| Insignificant | Minor | Moderate | Severe | Extreme | Risk status | Consequence Categories | Trmt status
Almost certain | Low | Medium | High | Critical | Critical | Draft | Stakeholders | Proposed
Likely | Low | Medium | High | Critical | Critical | Live-Treat | Public/Media | Live
Possible | Low | Medium | Medium | High | Critical | Live-Parked | Legal/Compliance | Completed - successful
Unlikely | Low | Low | Medium | Medium | High | Impacted | Delivery | Completed - unsuccessful
Rare | Low | Low | Low | Low | High | Closed | Cost | Rejected
[6 empty] | Rejected | Health & Safety
Environmental
| Low | Medium | High | Critical