## Table 1 Schools
Term Three 2025
School Name | Category | Roads | Permanent or Variable | Town | Posted Speed | Proposed Speed | Description | Implementation date
Auckland Point School | 1 | HAVEN ROAD (ARTERIAL, SOUTHBOUND) | Variable | Nelson | 50 km/h | 50 km/h with 30km/h variable | starting 20m from southern kerbline of QEII Drive extending for 300m | 2025-07-14
Auckland Point School | 1 | HAVEN ROAD (ARTERIAL, NORTHBOUND) | Variable | Nelson | 50 km/h | 50 km/h with 30km/h variable | starting 20m from sothern kerbline of QEII Drive extending for 300m | 2025-07-14
Auckland Point School | 1 | MAORI ROAD | Variable | Nelson | 50 km/h | 50 km/h with 30km/h variable | starting at Haven Road extending up Maori Road 15m | 2025-07-14
Birchwood School | 1 | HEREFORD STREET | Variable | Nelson | 50 km/h | 50 km/h with 30km/h variable | starting at Durham Street extending south for 50m | 2025-07-14
Birchwood School | 1 | DURHAM STREET | Variable | Nelson | 50 km/h | 50 km/h with 30km/h variable | starting 25m from eastern kerbline of Songer Street extending up Durham Street to Rutland Street | 2025-07-14
Birchwood School | 1 | SEAVIEW ROAD | Variable | Nelson | 50 km/h | 50 km/h with 30km/h variable | starting 20m from eastern kerbline of Songer Street extending up Seaview Road 300m | 2025-07-14
Birchwood School | 1 | ALLPORT PLACE | Variable | Nelson | 50 km/h | 50 km/h with 30km/h variable | starting at Seaview Road extending up Allport Place north for 20m | 2025-07-14
Birchwood School | 1 | RUTLAND STREET | Variable | Nelson | 50 km/h | 50 km/h with 30km/h variable | starting at Durham Street extending south for 35m | 2025-07-14
Clifton Terrace School | 1 | TRESILLIAN AVENUE | Variable | Nelson | 50 km/h | 50 km/h with 30km/h variable | starting at Atawhai Drive ( Tresillian Loop) extending south for 300m | 2025-07-14
Clifton Terrace School | 1 | SEATON STREET | Variable | Nelson | 50 km/h | 50 km/h with 30km/h variable | starting at Tresillian Avenue extending west for 230m | 2025-07-14
Clifton Terrace School | 1 | ATAWHAI DRIVE (TRESILLIAN LOOP) | Variable | Nelson | 50 km/h | 50 km/h with 30km/h variable | Entire Road | 2025-07-14
Clifton Terrace School | 1 | CLIFTON PLACE | Variable | Nelson | 50 km/h | 50 km/h with 30km/h variable | Entire Road | 2025-07-14
Clifton Terrace School | 1 | PENZANCE STREET | Variable | Nelson | 50 km/h | 50 km/h with 30km/h variable | Entire Road | 2025-07-14
Clifton Terrace School | 1 | BODMIN STREET | Variable | Nelson | 50 km/h | 50 km/h with 30km/h variable | Entire Road | 2025-07-14
Enner Glynn School | 1 | THE RIDGEWAY (NORTH) | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting 20m from southern kerbline of Chings Road extending for 300m | 2025-07-14
Enner Glynn School | 1 | BAIGENT ROAD | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting at The Ridgeway extending 40m east | 2025-07-14
Hampden Street School, Nelson College and Nelson College for Girls | 1 | HAMPDEN STREET | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting at Waimea Road extending east for 200m | 2025-07-14
Hampden Street School, Nelson College and Nelson College for Girls | 1 | HAMPDEN STREET | Variable | Nelson | 50 km/h | 50 km/h with 30km/h variable | starting 200m from Waimea Road extending east to outside number 282 Hampden Street | 2025-07-14
Hampden Street School, Nelson College and Nelson College for Girls | 1 | WAIMEA ROAD | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting at Rutherford Street extending south for 1000m | 2025-07-14
Hampden Street School, Nelson College and Nelson College for Girls | 1 | FRANKLYN STREET | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting at the eastern end extending 60m west of Waimea Road | 2025-07-14
Hampden Street School, Nelson College and Nelson College for Girls | 1 | RUTHERFORD STREET | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting 20m from the soutehrn kerbline of Examiner Street extending 260m south | 2025-07-14
Hampden Street School, Nelson College and Nelson College for Girls | 1 | RUTHERFORD STREET | Variable | Nelson | 50 km/h | 50 km/h with 30km/h variable | starting at Van Diemen Street extending north 25m | 2025-07-14
Hampden Street School, Nelson College and Nelson College for Girls | 1 | VAN DIEMEN STREET | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting at Waimea Road extending east for 230m | 2025-07-14
Hampden Street School, Nelson College and Nelson College for Girls | 1 | VAN DIEMEN STREET | Variable | Nelson | 50 km/h | 50 km/h with 30km/h variable | starting 10m west of Rutehrford Street western kerbline extending east for 125m | 2025-07-14
Hampden Street School, Nelson College and Nelson College for Girls | 1 | NGATIAWA STREET | Variable | Nelson | 50 km/h | 50 km/h with 30km/h variable | Entire Road | 2025-07-14
Hampden Street School, Nelson College and Nelson College for Girls | 1 | NGATITAMA STREET | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | Entire Road | 2025-07-14
Hampden Street School, Nelson College and Nelson College for Girls | 1 | BRONTE STREET WEST | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | Entire Road | 2025-07-14
Hampden Street School, Nelson College and Nelson College for Girls | 1 | WELLINGTON STREET | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting at Waimea Road extending 20m west | 2025-07-14
Nayland College, Broadgreen Intermediate, Nayland Primary School | 1 | FERGUSSON STREET | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting at Nayland Road extending 50m east | 2025-07-14
Nayland College, Broadgreen Intermediate, Nayland Primary School | 1 | NAYLAND ROAD | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting 30m north of Exerter Street extending south for 595m | 2025-07-14
Nayland College, Broadgreen Intermediate, Nayland Primary School | 1 | LANGBEIN STREET | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting at Nayland Road extending 35m east | 2025-07-14
Nayland College, Broadgreen Intermediate, Nayland Primary School | 1 | EXETER STREET | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting at Nayland Road extending 50m east | 2025-07-14
Nayland College, Broadgreen Intermediate, Nayland Primary School | 1 | NORWICH STREET | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting at Nayland Road extending 45m east | 2025-07-14
Nelson Central School | 1 | NILE STREET (EAST) | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting 40m west of Tasman Street extending west for 300m | 2025-07-14
Nelson Central School | 1 | ALTON STREET (NORTH) | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting 125m south of Hardy Street extending south for 175m | 2025-07-14
Nelson Central School | 1 | KING STREET | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting at Nile Street East extending south for 10m | 2025-07-14
Nelson Christian Academy | 1 | MARSDEN VALLEY ROAD | Variable | Nelson | 50 km/h | 50 km/h with 30km/h variable | starting10m west of Tussock Place extending west for 300m | 2025-07-14
Nelson College for Girls | 1 | TRAFALGAR STREET (SOUTH) | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting at Examiner Street extending south for 250m | 2025-07-14
Nelson College for Girls | 1 | TRAFALGAR SQUARE WEST | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting at Examiner Street extending north for 90m | 2025-07-14
Nelson College for Girls | 1 | TRAFALGAR SQUARE EAST | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting at Trafalgar Square West extending north for 40m | 2025-07-14
Nelson College for Girls | 1 | EXAMINER STREET | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting at Trafalgar Square West extending west for 80m | 2025-07-14
Nelson College for Girls | 1 | EXAMINER STREET | Variable | Nelson | 50 km/h | 50 km/h with 30km/h variable | starting 80m west of Trafalgar Square West extending west for 130m | 2025-07-14
Nelson College for Girls | 1 | BRONTE STREET (CENTRAL) | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting at the western end of the road extending east for 90m | 2025-07-14
Nelson Intermediate | 1 | TUKUKA STREET | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting at the western end of the road extending east for 185m | 2025-07-14
Nelson Intermediate | 1 | TIPAHI STREET | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting 80m south of Moteuka Street extending south for 300m | 2025-07-14
St Joseph's School | 1 | SCOTLAND STREET | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting at Bronte Street (Central) extending south for 25m | 2025-07-14
St Joseph's School | 1 | MANUKA STREET | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting at Collingwood Street extending east for 340m | 2025-07-14
St Joseph's School | 1 | ERIN STREET | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | Entire Road | 2025-07-14
St Joseph's School | 1 | BRONTE STREET (CENTRAL) | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | staring at the eastern end extending west for 265m | 2025-07-14
St Joseph's School | 1 | ALTON STREET (SOUTH) | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | Entire Road | 2025-07-14
St Joseph's School | 1 | COLLINGWOOD STREET | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting 145m south of Nile Street East extending south for 310m | 2025-07-14
Stoke School | 1 | MAIN ROAD STOKE | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting 35m north of Tainui Street extending north for 370m | 2025-07-14
Stoke School | 1 | RANUI ROAD | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting at Main Road Stoke extending east for 320m | 2025-07-14
Stoke School | 1 | LEMARI AVENUE | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting at Main Road Stoke extending west for 40m | 2025-07-14
Stoke School | 1 | WILLOW AVENUE | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting at Ranui Road extending north for 10m | 2025-07-14
Tahunanui School | 1 | RUI STREET | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | Starting at SH6 extending west for 45m | 14/07/2025 (Tentative subject to co ordination with NZTA for SH6 variable zone)
Tahunanui School | 1 | CENTENNIAL ROAD | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | Starting at Muritai Street extending west for 65m | 14/07/2025 (Tentative subject to co ordination with NZTA for SH6 variable zone)
Tahunanui School | 1 | TOSSWILL ROAD | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | Starting at SH6 extending south for 45m | 14/07/2025 (Tentative subject to co ordination with NZTA for SH6 variable zone)
Tahunanui School | 1 | RAWHITI STREET | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | Entire Road | 14/07/2025 (Tentative subject to co ordination with NZTA for SH6 variable zone)
Tahunanui School | 1 | MURITAI STREET | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting 95m south of Rui Street extending south for 300m | 14/07/2025 (Tentative subject to co ordination with NZTA for SH6 variable zone)
Victory Primary School | 1 | VANGUARD STREET | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting 50m south of Alfred Street extending south for 330m | 2025-07-14
Victory Primary School | 1 | ST VINCENT STREET | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting 35m north of Totara Street extending south for 70m | 2025-07-14
Victory Primary School | 1 | FRANKLYN STREET | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | starting at Vanguard Street extending east for 25m | 2025-07-14
Victory Primary School | 1 | TOTARA STREET | Variable | Nelson | 50 km/h with 40km/h variable | 50 km/h with 30km/h variable | Entire Road | 2025-07-14
Variable

## Table 2 Tortuous Unsealed
Narrow or Winding, Tortuous Unsealed Roads
Road Name | Extent | ONF Category Recommend Change | ONF Category Current | Posted speed | Proposed Speed | SAAS | Explanation of why proposed speed does not match SAAS | Implementation date | Suburb
Nelson
ANISEED VALLEY ROAD | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | Hope

## Table 3 Rural Resi Peri Urban
Rural Residential - Peri Urban Roads
Rural Resi Peri Urban | Town | Ward | Posted Speed | Proposed Speed | Location | Year

## Table 4 Urban Sts No Footpath
Urban Streets with no footpath (Scheduled only if final speed limit setting rule allows)
Road Name | Extent | ONF Category Recommend Change | ONF Category Current | Posted speed | Proposed Speed | SAAS | Explanation of why proposed speed does not match SAAS | Implementation date | Town
Nelson
MATIPO TERRACE (LOOP RD) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | Nelson
MATIPO TERRACE | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | Nelson
ARIESDALE TERRACE | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | Nelson
MURPHY STREET | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | Nelson
THOMPSON TERRACE | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | Nelson
STAFFORD WALK | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | Nelson
HINAU STREET | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | Nelson
MIRO STREET | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | Nelson
WAIMEA ROAD (LOOP ROAD) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | Nelson
KONINI STREET | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | Nelson
MOUNT STREET | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | Nelson
MOUNT STREET (LOOP ROAD) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | Nelson
RENWICK PLACE | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | Nelson
CABLE BAY ROAD (3) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | Cable Bay
KAKENGA ROAD | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | Nelson
LUCAS TERRACE | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | Nelson

## Table 5 Higher Risk Rural Roads
Higher Risk Rural Roads
Road | Town | Ward | Posted Speed | Proposed Speed | Location | Year

## Table 6 Great Taste Trail Roads
On Road Sections of the Great Taste Trail
Road name | Township or Area | Ward | Posted Speed | Proposed Speed | Location | Year | Seal

## Table 7 Specific Roads
Specific Roads
Road Name | Extent | ONF Category Recommend Change | ONF Category Current | Posted speed | Proposed Speed | SAAS | Explanation of why proposed speed does not match SAAS | Implementation date | Town
Nelson
CABLE BAY ROAD (1) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | Nelson
CABLE BAY ROAD (2) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | Nelson
MAORI PA ROAD | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | Nelson
Incorrect speed limit contained within the National Speed Register
Road Name | Extent | ONF Category Recommend Change | ONF Category Current | Posted speed | Proposed Speed | SAAS | Explanation of why proposed speed does not match SAAS | Implementation date | Town
Nelson | #REF!
HAMPDEN STREET | From 282 Hampden Street, extending to Allan Street | Local Streets | Local Streets | 50 | 30 | 30 | Correct NSLR to align with current signed limit | 2025-01-27 | Nelson

## Nelson Base Data
roadName | Extent | ONF Category Proposed | ONF Category | Posted Speed Limit | Proposed Speed Limit | SAAS | Explanation of why proposed speed does not match SAAS | Implementation date | NCCTDC_Reason
HAMPDEN STREET | From 282 Hampden Street, extending to Allan Street | Local Streets | Local Streets | 50 | 30 | 30 | Correct NSLR to align with current signed limit | 2025-01-27