## Monthly review decision report-
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Group Phase | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR
2017-09-14 | September 2017 Review | New approval | Investment management (incl. Transport Planning) | Activity management planning improvement | Auckland Transport | Regional Public Transport Plan Update - 2015-18 | Programme business case |  | HH_ | HH_ | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 507642 | 258898
2017-09-01 | September 2017 Review | New approval | Local road maintenance | Emergency works | Mackenzie District Council | 21/7/2017 - Rainfall and Snow Event | Construction |  | ___ |  | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 271600 | 141232
2017-09-28 | September 2017 Review | New approval | Investment management (incl. Transport Planning) | Programme Business Case Development | Environment Canterbury | Future Christchurch Public Transport Business Case | Programme business case |  | HM_ | HH_ | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 215000 | 109650
2017-09-07 | September 2017 Review | New approval | State highway improvements | Property purchase (State highways) | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec C | Property | SH2 Pokeno to Mangatarata Improvement: Sec C | HH1 | HHL* | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 6182593 | 6182593 |  | 1 | 1 | 1
2017-09-07 | September 2017 Review | New approval | State highway improvements | Property purchase (State highways) | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec E | Property | SH2 Pokeno to Mangatarata Improvement: Sec E | HH2.5 | HML | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 778911 | 778911 |  | 2.5 | 1.3 | 1.3
2017-09-12 | September 2017 Review | New approval | State highway improvements | Property purchase (State highways) | Waikato Highway & Network Operations | SH26 Kirikiri Stream Bridge Replacement | Property | SH26 Kirikiri Stream Bridge Replacement-property | MM99 | HMH | N | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1378087 | 1378087 |  |  | 99 | 99
2017-09-12 | September 2017 Review | New approval | State highway improvements | Replacement of bridges and other structures | Waikato Highway & Network Operations | SH26 Kirikiri Stream Bridge Replacement | Pre-implementation* | SH 26 Kirikiri Stream Bridge Replacement Design | MM99 | HMH | N | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 487674 | 487674 |  |  | 99 | 99
2017-09-13 | September 2017 Review | New approval | State highway improvements | Resilience improvements | West Coast Highway & Network Operations | ENR SH6 Bullock Creek Protection Works | Implementation |  | HMH | HH1-2.9 | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 488965 | 488965
2017-09-04 | September 2017 Review | New approval | State highway improvements | Road improvements | Auckland Highway & Network Operations | SH22: SH1 (Drury) to Paerata Safety Improvements | Detailed Business Case | Single Stage Business Case (IBC/DBC) | HM2 | HH1-2.9 | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1038183 | 1038183 |  | 2 | 2 | 2
2017-09-12 | September 2017 Review | New approval | State highway improvements | Road improvements | BOP Highway & Network Operations | SH2 Wainui Rd to Opotiki, NSRRP | Detailed Business Case | DBC | HM20.9 | HMH | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1187262 | 1187262 |  |  | 20.9 | 20.9
2017-09-12 | September 2017 Review | New approval | State highway improvements | Road improvements | Gisborne Highway & Network Operations | HPMV T2 GIS HNO Napier Port to Gis | Pre-implementation* | Pre Imp | HM3 | HH3-4.9 | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 222908 | 222908 |  | 3 | 1.8 | 1.8
2017-09-12 | September 2017 Review | New approval | State highway improvements | Road improvements | Hawkes Bay Highway & Network Operations | HPMV T2 HB HNO Napier Port to Gisborne | Pre-implementation* | HPMV T2 HB HNO Napier Port to Gisborne | MM1.8 | HHM | N | 7 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 105113 | 105113 |  |  | 1.8 | 1.8
2017-09-12 | September 2017 Review | New approval | State highway improvements | Road improvements | Hawkes Bay Highway & Network Operations | HPMV T2 HB HNO Napier Port to South Boundry | Pre-implementation* | Pre Imp | MM2 | HHM | N | 7 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 114783 | 114783 |  |  | 2 | 2
2017-09-18 | September 2017 Review | New approval | Local road improvements | Road improvements | Kaipara District Council | LED Streetlight Upgrade | Construction | Installation | MH0 | MH5+ | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1200000 | 732000 |  |  | 0 | 0
2017-09-07 | September 2017 Review | New approval | State highway improvements | Road improvements | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec A | Design | SH2 Pokeno-Mangatarata Safe Sys Demo:Sec A | HH1.3 | HML | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 2406028 | 2406028 |  |  | 1.3 | 1.3
2017-09-07 | September 2017 Review | New approval | State highway improvements | Road improvements | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec B | Design | SH2 Pokeno-Mangatarata Safe Sys Demo:Sec B | HH4.6 | HHM | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1148742 | 1148742 |  | 4.6 | 1.3 | 1.3
2017-09-07 | September 2017 Review | New approval | State highway improvements | Road improvements | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec C | Design | Design | HH1 | HHL* | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 962303 | 962303 |  | 1 | 1 | 1
2017-09-07 | September 2017 Review | New approval | State highway improvements | Road improvements | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec D | Design | SH2 Pokeno to Mangatarata Improvement: Sec D | HH1.3 | HHL* | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 3511559 | 3511559 |  |  | 1.3 | 1.3
2017-09-07 | September 2017 Review | New approval | State highway improvements | Road improvements | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec E | Design | SH2 Pokeno to Mangatarata Improvement: Sec E | HH2.5 | HML | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1758571 | 1758571 |  | 2.5 | 1.3 | 1.3
2017-09-04 | September 2017 Review | New Approval Programmes | Road safety promotion | Promotion, education and advertising | NZ Transport Agency | Better conversations on road risk | Implementation |  | HM5+ | HM5+ | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1895000 | 1895000
2017-09-04 | September 2017 Review | Cash flow adjustment | State highway improvements | Minor improvements | Canterbury Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | MHH |  | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0
2017-09-07 | September 2017 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec C | Property | SH2 Pokeno to Mangatarata Improvement: Sec C | HH1 | HHL* | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  | 1 | 1 | 1
2017-09-07 | September 2017 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec E | Property | SH2 Pokeno to Mangatarata Improvement: Sec E | HH2.5 | HML | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 33 | 33 |  | 2.5 | 1.3 | 1.3
2017-09-29 | September 2017 Review | Cash flow adjustment | State highway improvements | Replacement of bridges and other structures | Waikato Highway & Network Operations | SH26 Kirikiri Stream Bridge Replacement | Implementation | SH 26 Kirikiri Stream Bridge Replacement Construct | MM99 | HMH | N | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  |  | 99 | 99
2017-09-29 | September 2017 Review | Cash flow adjustment | Regional Improvements | Replacement of bridges and other structures | West Coast Highway & Network Operations | Taramakau Road Bridge | Construction | 60033092 Construction/Implementation (C) | HM1.9 | HH1.9 | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  |  | 1.9 | 1.9
2017-09-13 | September 2017 Review | Cash flow adjustment | State highway improvements | Resilience improvements | West Coast Highway & Network Operations | ENR SH6 Bullock Creek Protection Works | Implementation |  | HMH | HH1-2.9 | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 13 | 13
2017-09-29 | September 2017 Review | Cash flow adjustment | Regional Improvements | Road improvements | BOP Highway & Network Operations | SH30 Eastern Corridor, Connect Rotorua | Implementation | SH30 Eastern Corridor Connect Rotorua | MH3 | MH3.0 | N | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1 | 1 |  | 3 | 3 | 3
2017-09-12 | September 2017 Review | Cash flow adjustment | State highway improvements | Road improvements | Hawkes Bay Highway & Network Operations | HPMV T2 HB HNO Napier Port to Gisborne | Pre-implementation* | HPMV T2 HB HNO Napier Port to Gisborne | MM1.8 | HHM | N | 7 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 51 | 51 |  |  | 1.8 | 1.8
2017-09-12 | September 2017 Review | Cash flow adjustment | State highway improvements | Road improvements | Hawkes Bay Highway & Network Operations | HPMV T2 HB HNO Napier Port to South Boundry | Pre-implementation* | Pre Imp | MM2 | HHM | N | 7 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 2 | 2 |  |  | 2 | 2
2017-09-29 | September 2017 Review | Cash flow adjustment | Regional Improvements | Road improvements | Hawkes Bay Highway & Network Operations | SH2 Pakipaki to Waipukurau | Implementation | Implementation | HH1.7 | HH1.7 | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  | 1.7 | 1.7 | 1.7
2017-09-04 | September 2017 Review | Cash flow adjustment | Regional Improvements | Road improvements | Northland Highway & Network Operations | SH10 Waipapa Rd Intersection Improvements | Detailed Business Case |  | MM*3.2 | MMM | N | 6 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  |  | 3.2 | 3.2
2017-09-29 | September 2017 Review | Cash flow adjustment | Regional Improvements | Road improvements | Otago Highway & Network Operations | Dunedin - Fairfield Safety Improvements | Implementation | Implementation | HM*1.6 | HM1.6 | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  |  | 1.6 | 1.6
2017-09-04 | September 2017 Review | Cash flow adjustment | Regional Improvements | Road improvements | Otago Highway & Network Operations | Visiting Driver Signature Project Otago | Implementation |  | MH19 | MH6.9 | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  | 19 | 6.9 | 6.9
2017-09-04 | September 2017 Review | Cash flow adjustment | Regional Improvements | Road improvements | Otago Highway & Network Operations | Visiting Driver Signature Project Otago | Implementation |  | MH19 | MH6.9 | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  | 19 | 6.9 | 6.9
2017-09-05 | September 2017 Review | Cash flow adjustment | Regional Improvements | Road improvements | Southland Highway & Network Operations | Visiting Driver Signature Project Sthlnd | Implementation | Implementation | MH19 | MH5.5 | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  | 19 | 5.5 | 5.5
2017-09-07 | September 2017 Review | Cash flow adjustment | State highway improvements | Road improvements | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec A | Design | SH2 Pokeno-Mangatarata Safe Sys Demo:Sec A | HH1.3 | HML | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  |  | 1.3 | 1.3
2017-09-07 | September 2017 Review | Cash flow adjustment | State highway improvements | Road improvements | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec A | Design | SH2 Pokeno-Mangatarata Safe Sys Demo:Sec A | HH1.3 | HML | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  |  | 1.3 | 1.3
2017-09-07 | September 2017 Review | Cash flow adjustment | State highway improvements | Road improvements | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec B | Design | SH2 Pokeno-Mangatarata Safe Sys Demo:Sec B | HH4.6 | HHM | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  | 4.6 | 1.3 | 1.3
2017-09-07 | September 2017 Review | Cash flow adjustment | State highway improvements | Road improvements | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec C | Design | Design | HH1 | HHL* | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  | 1 | 1 | 1
2017-09-07 | September 2017 Review | Cash flow adjustment | State highway improvements | Road improvements | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec C | Design | Design | HH1 | HHL* | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1 | 1 |  | 1 | 1 | 1
2017-09-07 | September 2017 Review | Cash flow adjustment | State highway improvements | Road improvements | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec D | Design | SH2 Pokeno to Mangatarata Improvement: Sec D | HH1.3 | HHL* | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  |  | 1.3 | 1.3
2017-09-07 | September 2017 Review | Cash flow adjustment | State highway improvements | Road improvements | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec E | Design | SH2 Pokeno to Mangatarata Improvement: Sec E | HH2.5 | HML | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  | 2.5 | 1.3 | 1.3
2017-09-05 | September 2017 Review | Cash flow adjustment | Regional Improvements | Road improvements | West Coast Highway & Network Operations | Visitor Driver Signature Project - West Coast | Implementation | Construction/Implementation (C) | MM8 | MH8.0 | N | 7 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 0 | 0 |  |  | 8 | 8
2017-09-18 | September 2017 Review | Cash flow adjustment | Local road maintenance | Sealed road pavement rehabilitation | Kaipara District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | MHH |  | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -1649195 | -1006009
2017-09-18 | September 2017 Review | Cash flow adjustment | Local road maintenance | Sealed road resurfacing | Kaipara District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | MHH |  | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1235747 | 753806
2017-09-18 | September 2017 Review | Cash flow adjustment | Local road maintenance | Unsealed road metalling | Kaipara District Council | Maintenance, Operations and Renewals Programme 2015-18 - AC 8 | Local Roads |  | MHH |  | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 413448 | 252204
2017-09-29 | September 2017 Review | Cost / Scope adjustment | State highway maintenance | Emergency works | Gisborne Highway & Network Operations | EW Gisborne August Storm Event | Construction |  | ___ |  | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -169013 | -169013
2017-09-18 | September 2017 Review | Cost / Scope adjustment | Local road maintenance | Emergency works | Kaipara District Council | E/W KDC Cyclone Cook April 2017 | Construction |  | ___ |  | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 793200 | 483852
2017-09-18 | September 2017 Review | Cost / Scope adjustment | Local road maintenance | Emergency works | Kaipara District Council | E/W KDC Cyclone Debbie April 2017 | Construction |  | ___ |  | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 951000 | 580110
2017-09-04 | September 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | Canterbury Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | MHH |  | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 305696 | 305696
2017-09-25 | September 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | Nelson Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 102600 | 102600
2017-09-20 | September 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | Nelson Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -636120 | -636120
2017-09-05 | September 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | Southland Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | HMH |  | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -174420 | -174420
2017-09-20 | September 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | Tasman Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 533520 | 533520
2017-09-04 | September 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | Tasman Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -305697 | -305697
2017-09-05 | September 2017 Review | Cost / Scope adjustment | State highway improvements | Minor improvements | Wellington Highway & Network Operations | Minor improvements 2015-18 | State Highways |  | HHH |  | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 174420 | 174420
2017-09-29 | September 2017 Review | Cost / Scope adjustment | State highway improvements | New traffic management facilities | Auckland Highway & Network Operations | Improved Incident and Event Management | Indicative Business Case | Indicative Business Case | HL16 | HHH | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -38157 | -38157 |  | 16 | 11 | 11
2017-09-15 | September 2017 Review | Cost / Scope adjustment | Road safety promotion | Promotion, education and advertising | Southland Highway & Network Operations | Community Advertising 12/15 - Southland | Construction |  | MM_ | HMH | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -32011 | -32011 |  |  |  | 99
2017-09-15 | September 2017 Review | Cost / Scope adjustment | Road safety promotion | Promotion, education and advertising | Tasman Highway & Network Operations | Community Advertising 2012/15 - Tasman | Construction |  | HMH | HMH | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -2926 | -2926 |  |  |  | 99
2017-09-07 | September 2017 Review | Cost / Scope adjustment | Regional Improvements | Property purchase (State highways) | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec C | Property | SH2 Pokeno-Mangatarata Safe Sys Demo:Sec C | HH1 | HHL* | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -6182866 | -6182866 |  | 1 | 1 | 1
2017-09-07 | September 2017 Review | Cost / Scope adjustment | State highway improvements | Property purchase (State highways) | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec C | Property | SH2 Pokeno to Mangatarata Improvement: Sec C | HH1 | HHL* | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 273 | 273 |  | 1 | 1 | 1
2017-09-07 | September 2017 Review | Cost / Scope adjustment | Regional Improvements | Property purchase (State highways) | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec E | Property | SH2 Pokeno-Mangatarata Safe System Demo: Section E | HH2.5 | HML | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -778944 | -778944 |  | 2.5 | 1.3 | 1.3
2017-09-12 | September 2017 Review | Cost / Scope adjustment | Regional Improvements | Property purchase (State highways) | Waikato Highway & Network Operations | SH26 Kirikiri Stream Bridge Replacement | Property |  | MM99 | HMH | N | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -1378389 | -1378389 |  |  | 99 | 99
2017-09-12 | September 2017 Review | Cost / Scope adjustment | State highway improvements | Property purchase (State highways) | Waikato Highway & Network Operations | SH26 Kirikiri Stream Bridge Replacement | Property | SH26 Kirikiri Stream Bridge Replacement-property | MM99 | HMH | N | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 302 | 302 |  |  | 99 | 99
2017-09-29 | September 2017 Review | Cost / Scope adjustment | State highway improvements | Replacement of bridges and other structures | Auckland Highway & Network Operations | Punganui Stream Bridge Replacement | Construction |  | HMH | HMH | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -40394 | -40394 |  |  | 5.5
2017-09-12 | September 2017 Review | Cost / Scope adjustment | Regional Improvements | Replacement of bridges and other structures | Waikato Highway & Network Operations | SH26 Kirikiri Stream Bridge Replacement | Pre-implementation* | SH 26 Kirikiri Stream Bridge Replacement Design | MM99 | HMH | N | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -487803 | -487803 |  |  | 99 | 99
2017-09-12 | September 2017 Review | Cost / Scope adjustment | State highway improvements | Replacement of bridges and other structures | Waikato Highway & Network Operations | SH26 Kirikiri Stream Bridge Replacement | Pre-implementation* | SH 26 Kirikiri Stream Bridge Replacement Design | MM99 | HMH | N | 5 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 129 | 129 |  |  | 99 | 99
2017-09-12 | September 2017 Review | Cost / Scope adjustment | Regional Improvements | Resilience improvements | Hawkes Bay Highway & Network Operations | SH2 Raupunga Bluff Enhanced Resilience | Implementation |  | HH5+ | MM5+ | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -923408 | -923408
2017-09-12 | September 2017 Review | Cost / Scope adjustment | State highway improvements | Resilience improvements | Hawkes Bay Highway & Network Operations | SH2 Raupunga Bluff Enhanced Resilience | Implementation |  | HH5+ | MM5+ | N | 1 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 923408 | 923408
2017-09-04 | September 2017 Review | Cost / Scope adjustment | Regional Improvements | Resilience improvements | Wellington Highway & Network Operations | SH2 Rimutaka Hill Underslip Prevention | Implementation |  | HM1-2.9 | HM1-2.9 | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -1080404 | -1080404
2017-09-04 | September 2017 Review | Cost / Scope adjustment | State highway improvements | Resilience improvements | Wellington Highway & Network Operations | SH2 Rimutaka Hill Underslip Prevention | Implementation |  | HM1-2.9 | HM1-2.9 | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1080404 | 1080404
2017-09-04 | September 2017 Review | Cost / Scope adjustment | State highway improvements | Resilience improvements | Wellington Highway & Network Operations | SH2 Te Marua Bank Restoration | Implementation |  | HM1-2.9 | MH1-2.9 | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1346558 | 1346558
2017-09-04 | September 2017 Review | Cost / Scope adjustment | Regional Improvements | Resilience improvements | Wellington Highway & Network Operations | SH2 Te Marua Bank Restoration | Implementation |  | HM1-2.9 | MH1-2.9 | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -1346558 | -1346558
2017-09-13 | September 2017 Review | Cost / Scope adjustment | Regional Improvements | Resilience improvements | West Coast Highway & Network Operations | ENR SH6 Bullock Creek Protection Works | Implementation |  | HMH | HH1-2.9 | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -488978 | -488978
2017-09-04 | September 2017 Review | Cost / Scope adjustment | Regional Improvements | Resilience improvements | West Coast Highway & Network Operations | ENR SH6 Bullock Creek Protection Works | Implementation |  | HMH | HH1-2.9 | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -639635 | -639635
2017-09-29 | September 2017 Review | Cost / Scope adjustment | State highway improvements | Road improvements | Auckland Highway & Network Operations | Newmarket Viaduct to Greenlane Aux | Construction |  | HMM | LLL | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -39895 | -39895 |  |  | 0
2017-09-29 | September 2017 Review | Cost / Scope adjustment | State highway improvements | Road improvements | Auckland Highway & Network Operations | SH20A to Airport | Construction | Construction | HM1.7 | HMM | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 3973738 | 3973738 |  | 1.7 | 3.1 | 3.1
2017-09-29 | September 2017 Review | Cost / Scope adjustment | Debt Funding | Road improvements | Auckland Highway & Network Operations | SH20A to Airport | Implementation | Implementation - Debt Funding | HM1.7 | HMM | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 247571 | 247571 |  | 1.7 | 3.1 | 3.1
2017-09-04 | September 2017 Review | Cost / Scope adjustment | Regional Improvements | Road improvements | Auckland Highway & Network Operations | SH22: SH1 (Drury) to Paerata Safety Improvements | Detailed Business Case | Single Stage Business Case (IBC/DBC) | HM2 | HH2.0 | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -1038693 | -1038693 |  | 2 | 2 | 2
2017-09-04 | September 2017 Review | Cost / Scope adjustment | State highway improvements | Road improvements | Auckland Highway & Network Operations | SH22: SH1 (Drury) to Paerata Safety Improvements | Detailed Business Case | Single Stage Business Case (IBC/DBC) | HM2 | HH2.0 | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 510 | 510 |  | 2 | 2 | 2
2017-09-12 | September 2017 Review | Cost / Scope adjustment | State highway improvements | Road improvements | BOP Highway & Network Operations | SH2 Wainui Rd to Opotiki, NSRRP | Detailed Business Case | DBC | HM20.9 | HMH | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 492 | 492 |  |  | 20.9 | 20.9
2017-09-12 | September 2017 Review | Cost / Scope adjustment | Regional Improvements | Road improvements | BOP Highway & Network Operations | SH2 Wainui Rd to Opotiki, NSRRP | Detailed Business Case | Investigation (DBC) | HM20.9 | HMH | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -1187754 | -1187754 |  |  | 20.9 | 20.9
2017-09-12 | September 2017 Review | Cost / Scope adjustment | Regional Improvements | Road improvements | Gisborne Highway & Network Operations | HPMV T2 GIS HNO Napier Port to Gis | Pre-implementation* | Pre - impl | HM3 | HH1.8 | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -223017 | -223017 |  | 3 | 1.8 | 1.8
2017-09-12 | September 2017 Review | Cost / Scope adjustment | State highway improvements | Road improvements | Gisborne Highway & Network Operations | HPMV T2 GIS HNO Napier Port to Gis | Pre-implementation* | Pre Imp | HM3 | HH1.8 | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 109 | 109 |  | 3 | 1.8 | 1.8
2017-09-04 | September 2017 Review | Cost / Scope adjustment | State highway improvements | Road improvements | Hawkes Bay Highway & Network Operations | Corkscrew Gully Northbound & Southbound Passing Lanes | Design | Corkscrew Gully Northbound Passing Lane | LL3.5 | MLL* | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -2167 | -2167 |  |  | 3.5 | 3.5
2017-09-12 | September 2017 Review | Cost / Scope adjustment | Regional Improvements | Road improvements | Hawkes Bay Highway & Network Operations | HPMV T2 HB HNO Napier Port to Gisborne | Pre-implementation* | Pre Imp | MM1.8 | HHM | N | 7 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -105164 | -105164 |  |  | 1.8 | 1.8
2017-09-12 | September 2017 Review | Cost / Scope adjustment | Regional Improvements | Road improvements | Hawkes Bay Highway & Network Operations | HPMV T2 HB HNO Napier Port to South Boundry | Pre-implementation* | Pre Implementation | MM2 | HHM | N | 7 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -114785 | -114785 |  |  | 2 | 2
2017-09-06 | September 2017 Review | Cost / Scope adjustment | Regional Improvements | Road improvements | Hawkes Bay Highway & Network Operations | SH2 Watchman Rd, HB Airport Intersection | Construction | Construction | HM2.2 | HMM | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -1499263 | -1499263 |  |  | 2.2 | 2.2
2017-09-06 | September 2017 Review | Cost / Scope adjustment | Local road improvements | Road improvements | Kapiti Coast District Council | LED streetlight deployment | Implementation | Implementation | MH99 | MH99.0 | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -1000040 | -970039 |  |  | 99 | 99
2017-09-06 | September 2017 Review | Cost / Scope adjustment | Local road improvements | Road improvements | Nelson City Council | LED Streetlight Upgrade | Construction | Construction | MH5 | HH_ | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -2400000 | -2088000 |  | 5 | 5 | 5
2017-09-29 | September 2017 Review | Cost / Scope adjustment | State highway improvements | Road improvements | Northland Highway & Network Operations | Bulls Gorge Realign | Construction |  | MML | MML | N | 8 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -99317 | -99317 |  |  | 0
2017-09-29 | September 2017 Review | Cost / Scope adjustment | Regional Improvements | Road improvements | Northland Highway & Network Operations | SH10 Kaeo Bridge upgrade | Detailed Business Case |  | HM_ | HML* | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 736795 | 736795 |  | 0.6 | 0.6 | 0.6
2017-09-29 | September 2017 Review | Cost / Scope adjustment | Regional Improvements | Road improvements | Northland Highway & Network Operations | SH10 Kaeo Bridge upgrade | Implementation | Construction | HM_ | HML* | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -736098 | -736098 |  | 0.6 | 0.6 | 0.6
2017-09-29 | September 2017 Review | Cost / Scope adjustment | Regional Improvements | Road improvements | Northland Highway & Network Operations | SH10 Taipa Bridge (No 272) upgrade | Detailed Business Case |  | MH_ | MHL* | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 545443 | 545443 |  | 0.5 | 0.6 | 0.6
2017-09-29 | September 2017 Review | Cost / Scope adjustment | Regional Improvements | Road improvements | Northland Highway & Network Operations | SH10 Taipa Bridge (No 272) upgrade | Implementation |  | MH_ | MHL* | N | 0 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -544839 | -544839 |  | 0.5 | 0.6 | 0.6
2017-09-29 | September 2017 Review | Cost / Scope adjustment | Regional Improvements | Road improvements | Northland Highway & Network Operations | SH12 Matakohe Bridges | Construction |  | HM1.1 | MML | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -816398 | -816398 |  | 1.1 | 1.3 | 1.3
2017-09-29 | September 2017 Review | Cost / Scope adjustment | Regional Improvements | Road improvements | Northland Highway & Network Operations | SH12 Matakohe Bridges | Detailed Business Case | DBC | HM1.1 | MML | N | 4 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 817135 | 817135 |  | 1.1 | 1.3 | 1.3
2017-09-07 | September 2017 Review | Cost / Scope adjustment | State highway improvements | Road improvements | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec A | Design | SH2 Pokeno-Mangatarata Safe Sys Demo:Sec A | HH1.3 | HML | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 495 | 495 |  |  | 1.3 | 1.3
2017-09-06 | September 2017 Review | Cost / Scope adjustment | Regional Improvements | Road improvements | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec A | Design | SH2 Pokeno-Mangatarata Safe Sys Demo:Sec A | HH1.3 | HML | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -2406523 | -2406523 |  |  | 1.3 | 1.3
2017-09-07 | September 2017 Review | Cost / Scope adjustment | Regional Improvements | Road improvements | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec B | Design | SH2 Pokeno-Mangatarata Safe Sys Demo:Sec B | HH4.6 | HHM | N | 2 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -1148802 | -1148802 |  | 4.6 | 1.3 | 1.3
2017-09-07 | September 2017 Review | Cost / Scope adjustment | Regional Improvements | Road improvements | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec C | Design | SH2 Pokeno-Mangatarata Safe Sys Demo:Sec C | HH1 | HHL* | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -962304 | -962304 |  | 1 | 1 | 1
2017-09-07 | September 2017 Review | Cost / Scope adjustment | State highway improvements | Road improvements | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec D | Design | SH2 Pokeno to Mangatarata Improvement: Sec D | HH1.3 | HHL* | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 1085 | 1085 |  |  | 1.3 | 1.3
2017-09-07 | September 2017 Review | Cost / Scope adjustment | Regional Improvements | Road improvements | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec D | Design | Sec D Design | HH1.3 | HHL* | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -3512644 | -3512644 |  |  | 1.3 | 1.3
2017-09-07 | September 2017 Review | Cost / Scope adjustment | Regional Improvements | Road improvements | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec E | Design | SH2 Pokeno-Mangatarata Improvement: Sec E | HH2.5 | HML | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | -1759300 | -1759300 |  | 2.5 | 1.3 | 1.3
2017-09-07 | September 2017 Review | Cost / Scope adjustment | State highway improvements | Road improvements | Waikato Highway & Network Operations | SH2 Pokeno to Mangatarata Improvement: Sec E | Design | SH2 Pokeno to Mangatarata Improvement: Sec E | HH2.5 | HML | N | 3 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 729 | 729 |  | 2.5 | 1.3 | 1.3
2017-09-01 | September 2017 Review | Cost / Scope adjustment | External funding | SuperGold trip payments | Northland Regional Council | SuperGold Card Allocations | Implementation |  | MMM | MMM | N | 6 | Approved | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Investment Transport online or by request | 93621 | 93621 |  |  |  | 99