## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Phase Label | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Decision Status | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR
2018-08-07 | August 2018 Review | New approval | State highway maintenance | Emergency works | NZTA (Northland) | EW Additional slip at Twin Bridges, SH15 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager Systems Management | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 295680 | 295680
2018-08-28 | August 2018 Review | New approval | State highway maintenance | Emergency works | NZTA (Northland) | Pukenui Culvert Wash Out SH 1 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager Systems Management | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 756718 | 756718
2018-08-16 | August 2018 Review | New approval | State highway improvements | New roads | NZTA (Canterbury) | CHCH Northern Arterial Rural with QE2 | Detailed Business Case | System wide TBM & HOV/PT Lane | HHM | HHM | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 650000 | 650000 |  | 4.6 | 2.3 | 2.3
2018-08-17 | August 2018 Review | New approval | State highway improvements | Property purchase (State highways) | NZTA (Canterbury) | SH1 Clarence & Oaro Improvement (NLTF) - Kaikoura Nov 2016 | Property | Property | HHL | VHL | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 2710702 | 2710702 |  | 1.2 | 1.2 | 1.2
2018-08-02 | August 2018 Review | New approval | State highway improvements | Property purchase (State highways) | NZTA (Hawkes Bay) | SH2 Sandy Creek Stream â€“ Resilience | Property |  | HHH | MMH | N | 1 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 13136 | 13136
2018-08-14 | August 2018 Review | New approval | State highway improvements | Resilience improvements | NZTA (Otago) | Katiki Coast Enhanced Resilience Stage 2 | Implementation |  | M_L | MHL* | N | 6 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 3460390 | 3460390
2018-08-08 | August 2018 Review | New approval | Local road improvements | Road improvements | Dunedin City Council | LED Street Light Renewal | Implementation | Implementation | HHH | MHH | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 12245000 | 10408250 |  | 5 | 5 | 5
2018-08-03 | August 2018 Review | New approval | External funding | SuperGold trip payments | Auckland Transport | SuperGold Card Allocation | Construction | SuperGold Card contracted services - rail | MMM | LLL | N | 5 | Approved | Approved by Senior Investment Advisor | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 |  |  | 1 | 0 | 0
2018-08-03 | August 2018 Review | New approval | External funding | SuperGold trip payments | Auckland Transport | SuperGold Card Allocation | Construction | SuperGold Card contracted services â€“ ferry | MMM | LLL | N | 5 | Approved | Approved by Senior Investment Advisor | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 |  |  | 1 | 0 | 0
2018-08-03 | August 2018 Review | New approval | External funding | SuperGold trip payments | Environment Canterbury | SuperGold Card Allocations | Construction | SuperGold Card contracted services - ferry | MM_ | MMM | N |  | Approved | Approved by Senior Investment Advisor | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 |  |  | 1 | 0 | 0
2018-08-03 | August 2018 Review | New approval | External funding | SuperGold trip payments | Greater Wellington | SuperGold Card Allocations | Construction | SuperGold Card contracted service - rail | MML | HMM | N | 6 | Approved | Approved by Senior Investment Advisor | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 |  |  | 1 | 0 | 0
2018-08-03 | August 2018 Review | New approval | External funding | SuperGold trip payments | Greater Wellington | SuperGold Card Allocations | Construction | SuperGold Card contracted service - ferry | MML | HMM | N | 6 | Approved | Approved by Senior Investment Advisor | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 |  |  | 1 | 0 | 0
2018-08-14 | August 2018 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Dunedin City Council | Southern Commuter Route F | Construction | Southern Commuter Route F | HMH | HMM | N | 2 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 3.4 | 3.4
2018-08-13 | August 2018 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | NZTA (Gisborne) | Gisborne - Wainui Cycleway SH 35 | Construction | Gisborne - Wainui Cycleway SH 35 | MMM | MMM | N | 6 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 0 | 2.5
2018-08-08 | August 2018 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | NZTA (Gisborne) | Walking and Cycling connectivity | Implementation | Implementation | HML | HML | N | 5 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 0 | 5.7
2018-08-07 | August 2018 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | NZTA (Gisborne) | Walking and Cycling connectivity | Pre-implementation* | Pre Implementation | HML | HML | N | 5 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 0 | 5.7
2018-08-01 | August 2018 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | NZTA (Marlborough) | Grovetown to Spring Creek Shared pathway | Construction | Construction - NLTF | MMM | MMM | N | 6 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 3.7 | 0 | 3
2018-08-07 | August 2018 Review | Cash flow adjustment | External funding | Cycling facilities | NZTA (Marlborough) | Grovetown to Spring Creek Shared pathway | Design | Design - UCF | MMM | MMM | N | 6 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 3.7 | 0 | 3
2018-08-08 | August 2018 Review | Cash flow adjustment | External funding | Cycling facilities | NZTA (Nelson) | Maitai to Rocks Road Cycle Facility | Implementation | Implementation - Crown Funding | HHH | HHH | N | 1 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 6.1 | 6.1
2018-08-07 | August 2018 Review | Cash flow adjustment | External funding | Cycling facilities | NZTA (Nelson) | Maitai to Rocks Road Cycle Facility | Pre-implementation* | Pre-Implementation - Crown funding | HHH | HHH | N | 1 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 6.1 | 6.1
2018-08-07 | August 2018 Review | Cash flow adjustment | External funding | Cycling facilities | NZTA (Otago) | Dunedin One Way Pair Cycle Lanes | Implementation | UCP construction | HML | HHL | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 2.3 | 0 | 2.3
2018-08-07 | August 2018 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | NZTA (Otago) | Dunedin One Way Pair Cycle Lanes | Implementation | 60029849 Construction/Implementation (C) | HML | HHL | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 2.3 | 0 | 2.3
2018-08-07 | August 2018 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | NZTA (Wellington) | Petone to Melling Walking and Cycling Link Project | Implementation | Implementation - NLTF | HML | HHL | N | 5 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 2.5 | 0 | 2.5
2018-08-07 | August 2018 Review | Cash flow adjustment | External funding | Cycling facilities | NZTA (Wellington) | Petone to Melling Walking and Cycling Link Project | Implementation | Implementation - UCF | HML | HHL | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 2.5 | 0 | 2.5
2018-08-07 | August 2018 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | NZTA (Wellington) | Petone to Melling Walking and Cycling Link Project | Pre-implementation* |  | HML | HHL | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 2.5 | 0 | 2.5
2018-08-07 | August 2018 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | NZTA (Wellington) | Petone to Melling Walking and Cycling Link Project | Pre-implementation* | Pre-implementation phase 2 | HML | HHL | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 2.5 | 0 | 2.5
2018-08-14 | August 2018 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Napier City Council | Cycle Strategy Implementation | Construction | Cycle Strategy Implementation | MM*H | HMH | N | 5 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 5.1 | 5.1
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (BOP) | W2T Katikati Urban (previously called Katikati bypass) | Pre-implementation* | 60203205 | M_L | MML | N |  | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 0 | 2.5
2018-08-13 | August 2018 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Gisborne) | HPMV SH35 Gisborne Route 1- Tolaga Bay/Matawhero to Port | Investigation | Investigation | MMH | MMH | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 4.8 | 4.8
2018-08-13 | August 2018 Review | Cash flow adjustment | Regional Improvements | New roads | NZTA (Gisborne) | SH2 Nth Passing Opportunities -Gisborne | Construction | Construction / Implementation | MLL | MML | N | 0 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1 | 1 | 1
2018-08-14 | August 2018 Review | Cash flow adjustment | Regional Improvements | New roads | NZTA (Hawkes Bay) | Prebensen Hyderabad Intersection upgrade | Construction | Implementation | MMH | MMH | N | 5 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 14.6 | 14.6
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Manawatu/Whanganui) | Wellington RoNS - 9. Otaki to Levin | Investigation |  | HHL | HHL | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 1.4 | 1.4
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Manawatu/Whanganui) | Wellington RoNS - 9. Otaki to Levin | Pre-implementation* | Pre Imp | HHL | HHL | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 1.4 | 1.4
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Manawatu/Whanganui) | Wellington RoNS - 9. Otaki to Levin | Property | Property for Otaki to Levin | HHL | HHL | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 1.4 | 1.4
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Waikato) | SH1 (Cambridge to Piarere) Long Term Improvements | Pre-implementation* | Pre-implementation Long Term Efficiency | HHL | HHL | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 0 | 0.9
2018-08-30 | August 2018 Review | Cash flow adjustment | Regional Improvements | New roads | NZTA (Waikato) | SH29 Piarere to Te Poi | Detailed Business Case | Detailed Business Case | HHL* | HHL | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1.2 | 1.1 | 1.1
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Wellington) | SH1/SH2 Petone to Grenada Link Road | Design |  | HHL* | MHL | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 1.3 | 1.3
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Wellington) | SH1/SH2 Petone to Grenada Link Road | Investigation |  | HHL* | MHL | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 1.3 | 1.3
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Wellington) | SH1/SH2 Petone to Grenada Link Road | Property |  | HHL* | MHL | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -1 | -1 |  |  | 1.3 | 1.3
2018-08-13 | August 2018 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Wellington) | Wellington RoNS (5) - Transmission Gully | Construction | Transmission Gully - PPP component | HHL | HHL | N | 5 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 1.4 | 1.4
2018-08-14 | August 2018 Review | Cash flow adjustment | Local road improvements | New roads | Queenstown-Lakes District Council | Frankton Flats Road 2 | Construction | Frankton Flats Road 2 | HMH | HHH | N | 2 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 4.5 | 3.8
2018-08-17 | August 2018 Review | Cash flow adjustment | Investment management (incl. Transport Planning) | Programme Business Case Development | NZTA (Wellington) | SH2 Ngauranga to Te Marua | Programme business case |  | HM*_ | HH_ | N | 2 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0
2018-08-14 | August 2018 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (BOP) | SH30 Eastern Corridor, Connect Rotorua | Property | Property | MHM | MMM | N | 5 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 3 | 2.7 | 2.7
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (BOP) | Tauranga Northern Link | Property | Property | HHL | HHM | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 2 |  | 2
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (BOP) | W2T Katikati Urban (previously called Katikati bypass) | Property |  | M_L | MML | N |  | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 11 | 11 |  |  | 0 | 2.5
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (BOP) | W2T Omokoroa to Te Puna (Transformed) | Property |  | HHL | HML | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1.2 | 1.3 | 1.3
2018-08-14 | August 2018 Review | Cash flow adjustment | Regional Improvements | Property purchase (State highways) | NZTA (Hawkes Bay) | SH2 Watchman Rd, HB Airport Intersection | Property | Property Purchase | HML | HMM | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 2.2 | 2.2
2018-08-14 | August 2018 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Marlborough) | Dashwood Overbridge | Property | 12766 | HMH | HMM | N | 2 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 2.2 | 0
2018-08-01 | August 2018 Review | Cash flow adjustment | External funding | Property purchase (State highways) | NZTA (Marlborough) | New ÅŒpaoa River Bridge | Property |  | MM_ | MML* | N |  | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1.4 | 0 | 1.4
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Waikato) | SH1 (Cambridge to Piarere) Long Term Improvements | Property | Property Phase C2P | HHL | HHL | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 0 | 0.9
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Waikato) | SH2 Pokeno to Mangatarata Improvement: Sec A | Property | SH2 Pokeno-Mangatarata Safe Sys Demo:Sec A | HHM | HML | N | 2 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 1.3 | 1.3
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Waikato) | SH2 Pokeno to Mangatarata Improvement: Sec C | Property | SH2 Pokeno to Mangatarata Improvement: Sec C | HHL* | HHM | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1 | 1 | 1
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Waikato) | SH2 Pokeno to Mangatarata Improvement: Sec D | Property | SH2 Pokeno-Mangatarata Safe Sys Demo:Sec D | HHL* | HHM | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 1.3 | 1.3
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Waikato) | SH2 Pokeno to Mangatarata Improvement: Sec E | Property | SH2 Pokeno to Mangatarata Improvement: Sec E | HHL | HML | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 2.5 | 1.3 | 1.3
2018-08-14 | August 2018 Review | Cash flow adjustment | Local road improvements | Replacement of bridges and other structures | Gore District Council | Pyramid Bridge Replacement | Detailed Business Case | Pyramid Bridge Detailed Business Case | MML | MHM | N | 7 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1.7 | 0 | 1.7
2018-08-14 | August 2018 Review | Cash flow adjustment | Regional Improvements | Replacement of bridges and other structures | NZTA (Hawkes Bay) | Mangahohi Bridge Replacement | Implementation | Implementation | MMPV_EoL | MMH | N | 2 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 0 | 0
2018-08-15 | August 2018 Review | Cash flow adjustment | Regional Improvements | Replacement of bridges and other structures | NZTA (Manawatu/Whanganui) | Whirokino Trestle and Manawatu River Bridge Replacement | Implementation | Construction | HHL | MHL | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1 | 1 |  | 1.1 | 1.5 | 1.5
2018-08-14 | August 2018 Review | Cash flow adjustment | Local road improvements | Road improvements | Invercargill City Council | 11 Yr Streetlighting Renewal Programme for Invercargill City | Construction |  | MMH | MMH | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 6.2 | 8.7
2018-08-14 | August 2018 Review | Cash flow adjustment | Regional Improvements | Road improvements | NZTA (BOP) | SH30 Eastern Corridor, Connect Rotorua | Detailed Business Case | SH30 Eastern Corridor Connect Rotorua | MHM | MMM | N | 5 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 3 | 2.7 | 2.7
2018-08-14 | August 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (BOP) | SH30 Eastern Corridor, Connect Rotorua | Pre-implementation* | Preimp | MHM | MMM | N | 5 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 3 | 2.7 | 2.7
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (BOP) | TNP SH29 Tauriko West Network Connections | Detailed Business Case | TNP SH29 Tauriko West Network Connections | HHL | HHL | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1.7 | 0 | 1.7
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (BOP) | Tauranga Northern Link | Implementation | Implementation | HHL | HHM | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 2 |  | 2
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (BOP) | Tauranga Northern Link | Pre-implementation* | Pre-implementation - W2T - 1 - TNL | HHL | HHM | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 2 |  | 2
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (BOP) | W2T Katikati Urban (previously called Katikati bypass) | Investigation |  | M_L | MML | N |  | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 0 | 2.5
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (BOP) | W2T Omokoroa to Te Puna (Transformed) | Detailed Business Case | Omokoroa to Te Puna | HHL | HML | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1.2 | 1.3 | 1.3
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (BOP) | W2T Omokoroa to Te Puna (Transformed) | Pre-implementation* | Omokoroa to Te Puna | HHL | HML | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1 | 1 |  | 1.2 | 1.3 | 1.3
2018-08-14 | August 2018 Review | Cash flow adjustment | Regional Improvements | Road improvements | NZTA (Hawkes Bay) | SH2 Napier Road Intersection | Construction | Construction | HMM | HMH | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 0 | 4.5
2018-08-14 | August 2018 Review | Cash flow adjustment | Regional Improvements | Road improvements | NZTA (Hawkes Bay) | SH2 Watchman Rd, HB Airport Intersection | Construction | Construction | HML | HMM | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 2.2 | 2.2
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Northland) | SH1 - Port Marsden Highway to Te Hana | Detailed Business Case | Single stage IBC/DBC | HHL* | HHL* | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1 | 1 |  |  | 0.9 | 0.9
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Northland) | SH1 - Whangarei to Port Marsden Highway | Detailed Business Case | Single stage IBC/DBC | HHL | HHL* | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 1.1 | 1.1
2018-08-14 | August 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Otago) | SH6 Ladies Mile Corridor Imps | Implementation | Implementation - Tucker Beach Rd | M_L | M_M | N |  | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1.7 | 1.7 | 1.7
2018-08-14 | August 2018 Review | Cash flow adjustment | Regional Improvements | Road improvements | NZTA (Southland) | SH1S Bluff Highway/Elles Road I/S Improvement | Detailed Business Case | Detailed business case (I) | MML* | HHL | N | 7 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1.2 | 2.4 | 2.4
2018-08-14 | August 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Southland) | Woodlands Passing Lanes | Construction | Woodlands Passing Lanes | MLM | MMM | N | 8 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 2 | 2
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | SH2 Pokeno to Mangatarata Improvement: Sec A | Design | SH2 Pokeno-Mangatarata Safe Sys Demo:Sec A | HHM | HML | N | 2 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 1.3 | 1.3
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | SH2 Pokeno to Mangatarata Improvement: Sec B | Construction | SH2 Pokeno-Mangatarata Safe Sys Demo:Sec B | HHM | HHM | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 4.6 | 1.3 | 1.3
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | SH2 Pokeno to Mangatarata Improvement: Sec B | Design | SH2 Pokeno-Mangatarata Safe Sys Demo:Sec B | HHM | HHM | N | 2 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 4.6 | 1.3 | 1.3
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | SH2 Pokeno to Mangatarata Improvement: Sec C | Design | Design | HHL* | HHM | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1 | 1 | 1
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | SH2 Pokeno to Mangatarata Improvement: Sec D | Design | SH2 Pokeno to Mangatarata Improvement: Sec D | HHL* | HHM | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 1.3 | 1.3
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | SH2 Pokeno to Mangatarata Improvement: Sec E | Design | SH2 Pokeno to Mangatarata Improvement: Sec E | HHL | HML | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 2.5 | 1.3 | 1.3
2018-08-30 | August 2018 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Wellington) | SH2 Melling Efficiency and Safety Improvements | Indicative Business Case | SH2 Melling Efficiency and Safety Improvements | HML* | MHH | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 0 | 1.3
2018-08-14 | August 2018 Review | Cash flow adjustment | Regional Improvements | Road improvements | NZTA (West Coast) | Visiting Driver Signature Project - West | Implementation | Construction/Implementation (C) | MML* | HHH | N | 7 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 8 | 8
2018-08-01 | August 2018 Review | Cost Decrease | Investment management (incl. Transport Planning) | Activity management planning improvement | NZTA (Auckland) | Activity Management Plan Auckland 15/18 | Programme business case |  | HH_ | HH_ | N | 1 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -23227 | -23227
2018-08-01 | August 2018 Review | Cost Decrease | Investment management (incl. Transport Planning) | Activity management planning improvement | NZTA (Waikato) | Activity Management Plan Waikato 15/18 | Programme business case |  | HM_ | HM_ | N | 2 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -23227 | -23227
2018-08-10 | August 2018 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Kapiti Coast District Council | Urban Cycleway Fund programe | Construction | Construction of UCF projects (NLTF funding) | HHH | HHH | N | 1 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 3752 |  | 10.6 | 0 | 10.6
2018-08-07 | August 2018 Review | Cost Increase | External funding | Cycling facilities | NZTA (Gisborne) | Walking and Cycling connectivity | Detailed Business Case | UCP Detailed Business Case | HML | HML | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 92485 | 92485 |  |  | 0 | 5.7
2018-08-07 | August 2018 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | NZTA (Gisborne) | Walking and Cycling connectivity | Detailed Business Case | DBC | HML | HML | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -92485 | -92485 |  |  | 0 | 5.7
2018-08-07 | August 2018 Review | Cost Decrease | External funding | Cycling facilities | NZTA (Gisborne) | Walking and Cycling connectivity | Implementation | UCP Implementation | HML | HML | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -92485 | -92485 |  |  | 0 | 5.7
2018-08-07 | August 2018 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | NZTA (Marlborough) | Grovetown to Spring Creek Shared pathway | Construction | Construction - NLTF | MMM | MMM | N | 6 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -23552 | -23552 |  | 3.7 | 0 | 3
2018-08-07 | August 2018 Review | Cost Increase | External funding | Cycling facilities | NZTA (Nelson) | Maitai to Rocks Road Cycle Facility | Implementation | Implementation - Crown Funding | HHH | HHH | N | 1 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 153900 | 153900 |  |  | 6.1 | 6.1
2018-08-07 | August 2018 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | NZTA (Nelson) | Maitai to Rocks Road Cycle Facility | Property | Property | HHH | HHH | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -153900 | -153900 |  |  | 6.1 | 6.1
2018-08-27 | August 2018 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Western BoP District Council | Cycling Facilities - Omokoroa to Tauranga City Cycleway | Implementation | Design and construction | HHL | HHL* | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 5300000 | 2703000 |  | 1 | 1.8 | 1.4
2018-08-07 | August 2018 Review | Cost Decrease | Local road maintenance | Emergency works | Hurunui District Council | Kaikoura Earthquake 14 November 2016 | Construction |  | ___ |  | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1544836 | -5400000
2018-08-28 | August 2018 Review | Cost Increase | Local road maintenance | Emergency works | Hurunui District Council | Kaikoura Earthquake 14 November 2016 | Construction |  | ___ |  | N |  | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 6944836
2018-08-28 | August 2018 Review | Cost Increase | Local road maintenance | Emergency works | Kaikoura District Council | Kaikoura Nov 2016 EQ | Construction |  | ___ |  | N |  | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 20369
2018-08-07 | August 2018 Review | Cost Decrease | Local road maintenance | Emergency works | Kaikoura District Council | Kaikoura Nov 2016 EQ | Construction |  | ___ |  | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -579631 | -600000
2018-08-22 | August 2018 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (BOP) | EW BOPE Heavy Rain Event 9â€“12 Feb 2018 | Construction |  | ___ |  | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -3591 | -3591
2018-08-29 | August 2018 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (BOP) | EW BOPE SH5 Tomos | Construction |  | ___ |  | N |  | Declined | Declined by RM P&I | The requirements of section 20 of the Land Transport Management Act 2003 have not been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -2432 | -2432
2018-08-22 | August 2018 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (BOP) | EW BOPE SH5 Tomos | Construction |  | ___ |  | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 2432 | 2432
2018-08-10 | August 2018 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (BOP) | EW BOPE SH5 Tomos | Construction |  | ___ |  | N |  | Approved | Approved by GM P&I | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -2432 | -2432
2018-08-10 | August 2018 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (BOP) | EW SH36 Oropi Gorge Intersection Underslip | Construction |  | ___ |  | N |  | Approved | Approved by GM P&I | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -755114 | -755114
2018-08-01 | August 2018 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (BOP) | EW Waioeka Son of Midway 2.0 | Construction |  | ___ |  | N |  | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 4425 | 4425
2018-08-16 | August 2018 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (BOP) | Waioeka Midway EW (Son of Midway) | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager Systems Management | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 723 | 723
2018-08-10 | August 2018 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (BOP) | Waioeka Midway EW (Son of Midway) | Construction |  | ___ |  | N |  | Approved | Approved by GM P&I | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -57702 | -57702
2018-08-23 | August 2018 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Gisborne) | SH2 Makaratu 21 Sept 2015 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager Systems Management | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 67893 | 67893
2018-08-22 | August 2018 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Manawatu/Whanganui) | MWT June 2015 Rain Manawatu | Construction |  | ___ |  | N |  | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 18086 | 18086
2018-08-13 | August 2018 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Manawatu/Whanganui) | Manawatu Cyclone Debbie EW | Construction |  | ___ |  | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 4538876 | 4538876
2018-08-07 | August 2018 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Northland) | EW Northland 12-3-17 Storm Event | Construction |  | ___ |  | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 323617 | 323617
2018-08-06 | August 2018 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (Northland) | EW Northland 13-04-17 Cyclone Cook | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager Systems Management | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -78968 | -78968
2018-08-29 | August 2018 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (Northland) | Pukenui Culvert Wash Out SH 1 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager Systems Management | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -19402 | -19402
2018-08-10 | August 2018 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (Northland) | SH1-Hautapu Road South Slip | Construction |  | ___ |  | N |  | Approved | Approved by GM P&I | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -27907 | -27907
2018-08-07 | August 2018 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Taranaki) | MWT June 2015 Rain Taranaki | Construction |  | ___ |  | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 138442 | 138442
2018-08-02 | August 2018 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Tasman) | EW Region 10 SH60 Takaka Hill Feb 2018 | Construction |  | ___ |  | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 17744440 | 17744440
2018-08-07 | August 2018 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Waikato) | (EW) Cyclone Debbie/Cook | Construction |  | ___ |  | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 2165243 | 2165243
2018-08-17 | August 2018 Review | Cost Decrease | State highway improvements | Minor improvements | NZTA (BOP) | Minor improvements 2015-18 | State Highways |  | HHM |  | N | 2 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -437452 | -437452
2018-08-13 | August 2018 Review | Cost Increase | State highway improvements | Minor improvements | NZTA (BOP) | Minor improvements 2015-18 | State Highways |  | HHM |  | N | 2 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 437452 | 437452
2018-08-17 | August 2018 Review | Cost Increase | State highway improvements | Minor improvements | NZTA (Northland) | Minor improvements 2015-18 | State Highways |  | HHH |  | N | 1 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 123058 | 123058
2018-08-13 | August 2018 Review | Cost Increase | State highway improvements | Minor improvements | NZTA (Otago) | Minor improvements 2015-18 | State Highways |  | HMH |  | N | 2 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 741044 | 741044
2018-08-01 | August 2018 Review | Cost Increase | State highway improvements | New roads | NZTA (Auckland) | SH1 Puhoi to Warkworth RoNS Detailed Design and Construction | Pre-implementation* | Procurement & Design | HML | HML | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1334 | 1334 |  | 1.1 | 1.1 | 1.1
2018-08-07 | August 2018 Review | Cost Increase | State highway improvements | New roads | NZTA (Otago) | Glenda Drive Intersection and Associated Roads | Construction | Glenda Drive Intersection And Associated Roads | HML | HMM | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 381878 | 381878 |  |  | 4.5 | 4
2018-08-01 | August 2018 Review | Cost Decrease | State highway improvements | New roads | NZTA (Waikato) | SH1 Wex Hamilton Section | Construction | Alliance implementation | HHL | MHL | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -9747000 | -9747000 |  |  | 2.1 | 2.1
2018-08-17 | August 2018 Review | Cost Decrease | Regional Improvements | New traffic management facilities | NZTA (Waikato) | Waikato SEDF | Pre-implementation* |  | MMH | LMPV_EoL | N | 5 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -759 | -759 |  |  | 12 | 12
2018-08-01 | August 2018 Review | Cost Increase | Regional Improvements | New traffic management facilities | NZTA (Waikato) | Waikato SEDF | Pre-implementation* |  | MMH | LMPV_EoL | N | 5 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 738 | 738 |  |  | 12 | 12
2018-08-10 | August 2018 Review | Cost Decrease | Investment management (incl. Transport Planning) | Programme Business Case Development | NZTA (Wellington) | SH2 Ngauranga to Te Marua | Programme business case |  | HM*_ | HH_ | N | 2 | Approved | Approved by GM P&I | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -1662 | -1662
2018-08-06 | August 2018 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Auckland) | SH20A to Airport | Property | Property | HML | HMM | N | 5 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 756100 | 756100 |  | 1.7 | 3.1 | 3.1
2018-08-06 | August 2018 Review | Cost Decrease | Debt Funding | Property purchase (State highways) | NZTA (Auckland) | SH20A to Airport | Property | Property - debt funded | HML | HMM | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -756100 | -756100 |  | 1.7 | 3.1 | 3.1
2018-08-07 | August 2018 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Canterbury) | CHCH Southern Motorway HJR to Rolleston (Stage 2 & 3) | Property |  | HHM | HHL | N | 2 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 3672579 | 3672579 |  |  | 2.4 | 1.5
2018-08-07 | August 2018 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Canterbury) | Harewood Rd to Yaldhurst Rd 4 Laning | Property | Property | HHM | HHM | N | 2 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1769873 | 1769873 |  |  | 1.5 | 1.5
2018-08-29 | August 2018 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Canterbury) | Harewood Rd to Yaldhurst Rd 4 Laning | Property | Property | HHM | HHM | N | 2 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 6539633 | 6539633 |  |  | 1.5 | 1.5
2018-08-17 | August 2018 Review | Cost Decrease | External funding | Property purchase (State highways) | NZTA (Canterbury) | SH1 Clarence & Oaro Improvement (NLTF) - Kaikoura Nov 2016 | Property | Property | HHL | VHL | N | 5 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -2712575 | -2712575 |  | 1.2 | 1.2 | 1.2
2018-08-17 | August 2018 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Canterbury) | SH1 Clarence & Oaro Improvement (NLTF) - Kaikoura Nov 2016 | Property | Property | HHL | VHL | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1873 | 1873 |  | 1.2 | 1.2 | 1.2
2018-08-07 | August 2018 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Canterbury) | Western Belfast By-Pass | Property |  | HHM | MHL | N | 2 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1473650 | 1473650 |  | 4.6 | 2.1 | 2.1
2018-08-13 | August 2018 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Hawkes Bay) | SH2 Sandy Creek Stream â€“ Resilience | Property |  | HHH | MMH | N | 1 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 175 | 175
2018-08-13 | August 2018 Review | Cost Decrease | Regional Improvements | Property purchase (State highways) | NZTA (Hawkes Bay) | SH2 Watchman Rd, HB Airport Intersection | Property | Property Purchase | HML | HMM | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -6550 | -6550 |  |  | 2.2 | 2.2
2018-08-07 | August 2018 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Northland) | SH1 Corridor Improvements - Whangarei | Property | SH1 Corridor Improvement - Whangarei | HMM | HMM | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 270426 | 270426 |  | 2.3 | 0 | 2.3
2018-08-13 | August 2018 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Taranaki) | Normanby Overbridge Realignment | Property | 2649 | LMH | HMH | N | 6 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 853 | 853 |  | 4.1 | 4.1 | 4.1
2018-08-07 | August 2018 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Wellington) | Wellington RoNS (6) - SH1 Mackays to Peka Peka Expressway | Property | Property | HHL | HHL | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 624218 | 624218 |  |  | 1.4 | 0.9
2018-08-23 | August 2018 Review | Cost Decrease | Public transport | Public transport infrastructure and major renewals | Christchurch City Council | CSA Bus interchange construction | Construction | NZTA Grant | HML | HHL | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -511022 | -511022 |  | 1.5 | 1.5 | 1.5
2018-08-20 | August 2018 Review | Cost Increase | Regional Improvements | Replacement of bridges and other structures | NZTA (Manawatu/Whanganui) | Whirokino Trestle and Manawatu River Bridge Replacement | Implementation | Construction | HHL | MHL | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 11183400 | 11183400 |  | 1.1 | 1.5 | 1.5
2018-08-07 | August 2018 Review | Cost Increase | Regional Improvements | Replacement of bridges and other structures | NZTA (Waikato) | HPMV T2 SH30/SH34 Te Kuiti to Whakatane | Implementation |  | HM*L* | HML | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 314531 | 314531 |  |  | 2.2 | 2.2
2018-08-10 | August 2018 Review | Cost Decrease | Regional Improvements | Replacement of bridges and other structures | NZTA (Waikato) | HPMV T2: SH24 Matamata to SH29 IS | Implementation | HPMV T2: SH24 Matamata to SH29 IS | HM*L* | HML | N | 4 | Approved | Approved by GM P&I | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -74177 | -74177 |  |  | 2 | 2
2018-08-10 | August 2018 Review | Cost Decrease | Regional Improvements | Replacement of bridges and other structures | NZTA (Waikato) | HPMV T2: SH24 Matamata to SH29 IS | Pre-implementation* | HPMV T2: SH24 Matamata to SH29 IS | HM*L* | HML | N | 4 | Approved | Approved by GM P&I | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -4540 | -4540 |  |  | 2 | 2
2018-08-07 | August 2018 Review | Cost Increase | Regional Improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH27 Mangawhero Bridge | Detailed Business Case | Single Stage Business Case | HML | HML | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 190822 | 190822 |  | 3.1 | 1.8 | 1.8
2018-08-09 | August 2018 Review | Cost Increase | Regional Improvements | Replacement of bridges and other structures | NZTA (West Coast) | SH6 Taramakau Road Bridge | Construction | Construction/Implementation | HMM | HHL | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1282967 | 1282967 |  |  | 1.9 | 1.9
2018-08-07 | August 2018 Review | Cost Increase | State highway improvements | Resilience improvements | NZTA (Gisborne) | Puketiti Realignment | Implementation |  | HHL* | HHH | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 186612 | 186612
2018-08-10 | August 2018 Review | Cost Decrease | State highway improvements | Resilience improvements | NZTA (Northland) | SH1 Hautapu Slip ( Enhance Res) | Construction |  | HMH | HMH | N | 2 | Approved | Approved by GM P&I | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -66079 | -66079
2018-08-14 | August 2018 Review | Cost Decrease | State highway improvements | Resilience improvements | NZTA (Otago) | Katiki Coast Enhanced Resilience | Implementation |  | HHL | HHL | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -3460390 | -3460390
2018-08-21 | August 2018 Review | Cost Increase | Local road improvements | Road improvements | Christchurch City Council | Accelerated LED Conversion Programme | Implementation |  | M_H | MHH | N |  | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 93610 |  | 5 | 0 | 0
2018-08-10 | August 2018 Review | Cost Increase | Local road improvements | Road improvements | Invercargill City Council | LED Streetlight Upgrade 2017-2018 | Construction |  | MHL | MHL | N | 6 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 656357 |  | 1.7 | 1.4 | 1.4
2018-08-07 | August 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Auckland) | Auck Accelerated Prog: Southern Corridor Improvements | Construction | Construction | HHH | HHH | N | 1 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 36114746 | 36114746 |  | 13 | 0 | 6
2018-08-06 | August 2018 Review | Cost Decrease | Debt Funding | Road improvements | NZTA (Auckland) | Auck Accelerated Prog: Southern Corridor Improvements | Implementation | Construction (Debt Funded) | HHH | HHH | N | 1 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -36114746 | -36114746 |  | 13 | 0 | 6
2018-08-15 | August 2018 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Auckland) | SH20A to Airport | Construction | Construction | HML | HMM | N | 5 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -35900123 | -35900123 |  | 1.7 | 3.1 | 3.1
2018-08-07 | August 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Auckland) | SH20A to Airport | Construction | Construction | HML | HMM | N | 5 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1708836 | 1708836 |  | 1.7 | 3.1 | 3.1
2018-08-06 | August 2018 Review | Cost Increase | Debt Funding | Road improvements | NZTA (Auckland) | SH20A to Airport | Implementation | Implementation - Debt Funding | HML | HMM | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 35900123 | 35900123 |  | 1.7 | 3.1 | 3.1
2018-08-07 | August 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (BOP) | SH2 Wainui Rd to Opotiki, NSRRP | Detailed Business Case | DBC | HMH | HML | N | 2 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 285817 | 285817 |  | 1 | 1 | 1
2018-08-01 | August 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (BOP) | SH2 Wainui Rd to Opotiki, NSRRP | Detailed Business Case | DBC | HMH | HML | N | 2 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 2449 | 2449 |  | 1 | 1 | 1
2018-08-23 | August 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (BOP) | SH2: Baypark to Bayfair Link Upgrade (was MGI) | Construction | Implementation | HHH | HHM | N | 1 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 8930 | 8930 |  | 2.5 | 2.5 | 2.5
2018-08-22 | August 2018 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (BOP) | SH2: Baypark to Bayfair Link Upgrade (was MGI) | Design | Design / PreImplementation | HHH | HHM | N | 1 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -8929 | -8929 |  | 2.5 | 2.5 | 2.5
2018-08-01 | August 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (BOP) | SH30: Owhata to Te Ngae Junction, NSRRP | Detailed Business Case | IBC/DBC - Safe Roads Alliance | HHL | HHL | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 528 | 528 |  |  | 2 | 2
2018-08-07 | August 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (BOP) | SH30: Owhata to Te Ngae Junction, NSRRP | Detailed Business Case | IBC/DBC - Safe Roads Alliance | HHL | HHL | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 499873 | 499873 |  |  | 2 | 2
2018-08-13 | August 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Canterbury) | Harewood Rd to Yaldhurst Rd 4 Laning | Construction | 60034104 Construction SP3 | HHM | HHM | N | 2 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 389 | 389 |  |  | 1.5 | 1.5
2018-08-01 | August 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Canterbury) | Kaikoura Nov 2016 EQ: Lewis Pass Altern Upg Rout - Canterbur | Implementation | Implementation | HML | HML | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 51194 | 51194 |  | 1.4 | 1.4 | 1.4
2018-08-07 | August 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Canterbury) | Kaikoura Nov 2016 EQ: Lewis Pass Altern Upg Rout - Canterbur | Implementation | Implementation | HML | HML | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 513750 | 513750 |  | 1.4 | 1.4 | 1.4
2018-08-07 | August 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Canterbury) | Marshland to Burwood Median Barrier | Detailed Business Case | Detailed Business Case | HMM | HMM | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 215132 | 215132 |  |  | 3.6 | 3.6
2018-08-07 | August 2018 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (Canterbury) | SH7 Waipara to Waikari Safety Improvement | Pre-implementation* | Pre Implementation (D) | HML | HHL | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 249355 | 249355 |  | 1.5 | 1.2 | 1.2
2018-08-01 | August 2018 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (Canterbury) | SH7 Waipara to Waikari Safety Improvement | Pre-implementation* | Pre Implementation (D) | HML | HHL | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1040 | 1040 |  | 1.5 | 1.2 | 1.2
2018-08-07 | August 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Gisborne) | HPMV T2 GIS HNO Napier Port to Gis | Pre-implementation* | Pre Imp | HMM | HHVH | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 158495 | 158495 |  | 2.3 | 0 | 19.2
2018-08-01 | August 2018 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (Gisborne) | HPMV T2 Gis HNO Te Araroa to Tologa | Pre-implementation* | Pre Implementation | MHM | MMM | N | 5 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 2175 | 2175 |  |  | 1.8 | 1.8
2018-08-17 | August 2018 Review | Cost Decrease | Regional Improvements | Road improvements | NZTA (Gisborne) | HPMV T2 Gis HNO Te Araroa to Tologa | Pre-implementation* | Pre Implementation | MHM | MMM | N | 5 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -2367 | -2367 |  |  | 1.8 | 1.8
2018-08-07 | August 2018 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (Hawkes Bay) | SH2 Wairoa to Bay View Safety Improvements | Pre-implementation* | Pre-Implementation | MHL | MHL | N | 6 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 420609 | 420609 |  | 2.4 | 2.4 | 2.4
2018-08-07 | August 2018 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (Hawkes Bay) | SH2 Watchman Rd, HB Airport Intersection | Construction | Construction | HML | HMM | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 771414 | 771414 |  |  | 2.2 | 2.2
2018-08-01 | August 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Manawatu/Whanganui) | Otamaraho Curve P/L Extension | Construction | Otamaraho Curve P/L Extension | HMM | HMH | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 3153 | 3153 |  |  | 2.2 | 2.2
2018-08-17 | August 2018 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Manawatu/Whanganui) | Otamaraho Curve P/L Extension | Construction | Otamaraho Curve P/L Extension | HMM | HMH | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -3972 | -3972 |  |  | 2.2 | 2.2
2018-08-07 | August 2018 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (Manawatu/Whanganui) | SH57: SH1 to Shannon Safety Improvements | Pre-implementation* | Pre-Implementation | HMM | HMM | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 155075 | 155075 |  | 3 | 2.5 | 2.5
2018-08-07 | August 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Marlborough) | Kaikoura Nov 2016 EQ - Lewis Pass Altern Rte Upgr -Marlborou | Implementation | Construction / Implementation | HHL | HML | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 205320 | 205320 |  | 1.5 | 1.4 | 1.4
2018-08-07 | August 2018 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (Marlborough) | SH6 Blenheim to Nelson SSI Rural Roundabout | Detailed Business Case | Single stage business case | M_L | HHL | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 243263 | 243263 |  | 1.9 | 0 | 2
2018-08-07 | August 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Northland) | Delete SH1 Whangarei To Te Hana SI | Detailed Business Case |  | HH_ | HHL | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 356228 | 356228 |  |  | 1.8 | 1.8
2018-08-13 | August 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Northland) | SH1 Corridor Improvements - Whangarei | Construction |  | HMM | HMM | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 768 | 768 |  | 2.3 | 0 | 2.3
2018-08-07 | August 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Northland) | SH1 Corridor Improvements - Whangarei | Design |  | HMM | HMM | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 162400 | 162400 |  | 2.3 | 0 | 2.3
2018-08-07 | August 2018 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (Northland) | SH10 Kaeo Bridge upgrade | Detailed Business Case |  | HM_ | MML | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1340007 | 1340007 |  | 0.6 | 0.6 | 0.6
2018-08-07 | August 2018 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (Northland) | SH10 Taipa Bridge (No 272) upgrade | Pre-implementation* |  | MHL | MHL | N | 6 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1221413 | 1221413 |  | 0.5 | 0.6 | 0.6
2018-08-13 | August 2018 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (Northland) | SH12 Matakohe Bridges | Construction |  | HML | MML | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 6164 | 6164 |  | 1.1 | 1.3 | 1.3
2018-08-07 | August 2018 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (Northland) | SH12 Matakohe Bridges | Pre-implementation* |  | HML | MML | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1744140 | 1744140 |  | 1.1 | 1.3 | 1.3
2018-08-17 | August 2018 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (Otago) | Dunedin - Fairfield Safety Improvements | Pre-implementation* | Pre-Implementation | HM*L | HML | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 101446 | 101446 |  |  | 1.6 | 1.6
2018-08-13 | August 2018 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (Otago) | Dunedin - Fairfield Safety Improvements | Pre-implementation* | Pre-Implementation | HM*L | HML | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 4022 | 4022 |  |  | 1.6 | 1.6
2018-08-07 | August 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Otago) | Dunedin - Port Chalmers Safety Improvements (SH88) | Pre-implementation* | Dunedin - Port Chalmers Pre Implementation | HHL* | HHL | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 193087 | 193087 |  |  | 1.1 | 1.1
2018-08-02 | August 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Otago) | SH6 Ladies Mile Corridor Imps | Implementation | Implementation - Tucker Beach Rd | M_L | M_M | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 991655 | 991655 |  | 1.7 | 1.7 | 1.7
2018-08-01 | August 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Otago) | Stanley St Corridor Improvements(Queenstown Town Centre DBC) | Detailed Business Case | Detailed business case (I) | HML | MM*L | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 279630 | 279630 |  | 1.7 | 1.7 | 1.7
2018-08-07 | August 2018 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (Taranaki) | Waitara to Bell Block Route Imp: SH3/3A to Waitara | Detailed Business Case | Waitara to Bell Block Route Imp: SH3/3A to Waitara | MM*L | HML | N | 7 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 950617 | 950617 |  | 1.5 | 1.1 | 1.1
2018-08-07 | August 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Tasman) | Kaikoura Nov 2016 EQ: Lewis Pass Altern Upg Rout - Tasman | Implementation | Implementation | HML | HML | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 240478 | 240478 |  | 1.4 | 1.4 | 1.4
2018-08-07 | August 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Waikato) | SH1 Bombay- Long Swamp Barrier Infill | Implementation | Pre-implementation & implementation | HHL | HHL | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 2147729 | 2147729 |  | 2.3 | 2.1 | 2.1
2018-08-10 | August 2018 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Waikato) | SH1 Gallagher Drive Intersection Improvements | Implementation | Gallagher IS | HHL | HHL | N | 3 | Approved | Approved by GM P&I | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -10102 | -10102 |  |  | 1.5 | 1.5
2018-08-07 | August 2018 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (Waikato) | SH1B (Taupiri to Gordonton), NSRRP | Pre-implementation* | SH1B (Taupiri to Gordonton), NSRRP | HM*M | HMM | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 179204 | 179204 |  | 4.5 | 0 | 3.2
2018-08-30 | August 2018 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Waikato) | SH2 Pokeno to Mangatarata Improvement: Sec A | Construction | SH2 Pokeno-Mangatarata Safe Sys Demo:Sec A | HHM | HML | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -997526 | -997526 |  |  | 1.3 | 1.3
2018-08-30 | August 2018 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Waikato) | SH2 Pokeno to Mangatarata Improvement: Sec A | Investigation | SH2 Pokeno-Mangatarata Safe Sys Retrofit/Realign:S | HHM | HML | N | 2 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 997526 | 997526 |  |  | 1.3 | 1.3
2018-08-07 | August 2018 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (Waikato) | SH27 (SH26 to SH24), NSRRP | Implementation | SH27 (SH26 to SH24), NSRRP | HM*H | HML | N | 2 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 532646 | 532646 |  | 20.7 | 1.3 | 1.3
2018-08-07 | August 2018 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (Waikato) | SH3 (Hamilton to Ohaupo) Improvements, NSRRP | Detailed Business Case | Single stage business case | HM*H | HHL | N | 2 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 111946 | 111946 |  | 66 | 2 | 2
2018-08-07 | August 2018 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (Waikato) | SH3 Awakino to Mt Messenger Corridor Improvements (Waikato) | Pre-implementation* | Pre-implementation | MM*L* | HHL | N | 7 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 919176 | 919176 |  |  | 1.5 | 1.5
2018-08-10 | August 2018 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (West Coast) | WC Passing Opportunity Improvements | Property | Property | MMH | MMH | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 70105 | 70105 |  | 5.4 | 5.4 | 5.4
2018-08-10 | August 2018 Review | Cost Increase | Local road improvements | Road improvements | Selwyn District Council | LED Upgrade | Implementation | LED Upgrade | MHH | HHL | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 891961 |  |  | 0 | 0
2018-08-24 | August 2018 Review | Cost Decrease | Road policing | Road policing | NZ Transport Agency | Road Policing Programme 2015-18 | Implementation | National Programme | HHL | MMM | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -1277000 | -1277000 |  |  | 0 | 0
2018-08-08 | August 2018 Review | Cost Decrease | Investment management (incl. Transport Planning) | Sector research | NZ Transport Agency | Sector Research | Implementation | 2015-18 NLTP | HHH | MMH | N | 1 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -1141949 | -1141949 |  | 75.3 | 0 | 75.3
2018-08-14 | August 2018 Review | Cost Increase | External funding | SuperGold trip payments | Auckland Transport | SuperGold Card Allocation | Construction | SuperGold Card Exempt Services | MMM | LLL | N | 6 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 2128714 | 2128714 |  | 1 | 0 | 0
2018-08-10 | August 2018 Review | Cost Increase | External funding | SuperGold trip payments | Auckland Transport | SuperGold Card Allocation | Construction | SuperGold Card contracted services - rail | MMM | LLL | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1930342 | 1930342 |  | 1 | 0 | 0
2018-08-10 | August 2018 Review | Cost Increase | External funding | SuperGold trip payments | Auckland Transport | SuperGold Card Allocation | Construction | SuperGold Card contracted services â€“ ferry | MMM | LLL | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 323604 | 323604 |  | 1 | 0 | 0
2018-08-10 | August 2018 Review | Cost Increase | External funding | SuperGold trip payments | Auckland Transport | SuperGold Card Allocation | Construction | SuperGold Card contracted services â€“ bus | MMM | LLL | N | 6 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 10606538 | 10606538 |  | 1 | 0 | 0
2018-08-10 | August 2018 Review | Cost Increase | External funding | SuperGold trip payments | Bay of Plenty Regional Council | SuperGold Card Allocation | Construction | SuperGold Card contracted services - bus | LL_ | LLL | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 737680 | 737680 |  | 0 |  | 0
2018-08-10 | August 2018 Review | Cost Increase | External funding | SuperGold trip payments | Environment Canterbury | SuperGold Card Allocations | Construction | SuperGold Card contracted services - ferry | MM_ | MMM | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 66201 | 66201 |  | 1 | 0 | 0
2018-08-10 | August 2018 Review | Cost Increase | External funding | SuperGold trip payments | Environment Canterbury | SuperGold Card Allocations | Implementation | SuperGold Card contracted services - bus | MM_ | MMM | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 2999553 | 2999553 |  | 1 | 0 | 0
2018-08-10 | August 2018 Review | Cost Increase | External funding | SuperGold trip payments | Gisborne District Council | SuperGold Card Allocations | Implementation | SuperGold Card contracted services - bus | HM_ | MHM | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 15647 | 15647 |  |  |  | 0
2018-08-10 | August 2018 Review | Cost Increase | External funding | SuperGold trip payments | Greater Wellington | SuperGold Card Allocations | Construction | SuperGold Card contracted services - bus | MML | HMM | N | 7 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 4304889 | 4304889 |  | 1 | 0 | 0
2018-08-10 | August 2018 Review | Cost Increase | External funding | SuperGold trip payments | Greater Wellington | SuperGold Card Allocations | Construction | SuperGold Card contracted service - rail | MML | HMM | N | 6 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 2412705 | 2412705 |  | 1 | 0 | 0
2018-08-10 | August 2018 Review | Cost Increase | External funding | SuperGold trip payments | Greater Wellington | SuperGold Card Allocations | Construction | SuperGold Card contracted service - ferry | MML | HMM | N | 6 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 81382 | 81382 |  | 1 | 0 | 0
2018-08-10 | August 2018 Review | Cost Increase | External funding | SuperGold trip payments | Greater Wellington | SuperGold Card Allocations | Implementation | SuperGold Card Exempt services | MML | HMM | N | 8 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 858060 | 858060 |  | 1 | 0 | 0
2018-08-10 | August 2018 Review | Cost Increase | External funding | SuperGold trip payments | Hawkes Bay Regional Council | SuperGold Card Allocations | Implementation | SuperGold Card contracted services - bus | MM_ | MMM | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 240300 | 240300 |  |  |  | 0
2018-08-10 | August 2018 Review | Cost Increase | External funding | SuperGold trip payments | Horizons Manawatu | SuperGold Card Allocation | Implementation | SuperGold Card contracted services - bus | MMM | HHH | N | 6 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 179302 | 179302 |  |  |  | 0
2018-08-10 | August 2018 Review | Cost Increase | External funding | SuperGold trip payments | Invercargill City Council | SuperGold Card Allocations | Implementation | SuperGold Card contracted services - bus | MM_ | MMM | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 23348 | 23348 |  |  |  | 0
2018-08-10 | August 2018 Review | Cost Increase | External funding | SuperGold trip payments | Marlborough District Council | SuperGold Card Allocations | Implementation | SuperGold Card contracted services - bus | MM_ | MMM | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 17413 | 17413 |  |  |  | 0
2018-08-10 | August 2018 Review | Cost Increase | External funding | SuperGold trip payments | Nelson City Council | SuperGold Card Allocations | Implementation | SuperGold Card contracted services - bus | MM_ | HMH | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 118626 | 118626 |  |  |  | 0
2018-08-10 | August 2018 Review | Cost Increase | External funding | SuperGold trip payments | Northland Regional Council | SuperGold Card Allocations | Implementation | SuperGold Card contracted services - bus | MM_ | MMM | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 122530 | 122530 |  |  |  | 0
2018-08-10 | August 2018 Review | Cost Increase | External funding | SuperGold trip payments | Otago Regional Council | SuperGold Card Allocation | Construction | SuperGold Card contracted services - bus | HH_ | HH_ | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 854823 | 854823 |  |  | 1 | 0
2018-08-10 | August 2018 Review | Cost Increase | External funding | SuperGold trip payments | Taranaki Regional Council | SuperGold Card Allocations | Construction | SuperGold Card contracted services - bus | MM_ | HHH | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 104058 | 104058 |  |  |  | 0
2018-08-10 | August 2018 Review | Cost Increase | External funding | SuperGold trip payments | Waikato Regional Council | SuperGold Card Allocation | Construction | SuperGold Card contracted services - bus | MM_ | LLL | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 837754 | 837754 |  |  |  | 0
2018-08-09 | August 2018 Review | Support for strategic case |  |  | Queenstown-Lakes District Council | Ballantyne Road SBC | Support for Strategic Case |  | M__ | H__ | N | 4 | Supported with conditions | Supported with conditions by Senior Manager System Planning |  | 0 |  | In development of the single stage business case that the option analysis clearly define the options and include: o Permanent speed reduction and un-sealed road option; o Status Quo option confirms maintaining 80km speed and unsealed road; o Sealing and improving longitudinal grades and bends, along with mitigation to ensure safety remains the priority outcome; o Sealing and improving longitudinal grades and bends, as well as providing for a higher level of service for access and amenity (Indentified ONRC gaps for amenity and access will need reviewing after the Wider Wanaka Strategic Case and Network Operating Framework for Transport have been developed. Lack of provision for active road users is likely to still be appropriate at this time until the wider network hierachy is defined, however the value of future proofing the road to capture these opportunities will need to be considered in the development of the single staged business case)
2018-08-23 | August 2018 Review | Support for strategic case |  |  | Queenstown-Lakes District Council | Wanaka Strategic Business Case | Support for Strategic Case |  | M__ | H__ | N | 4 | Supported | Supported by Senior Manager System Planning | This is not a funding decision | 0