## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Phase Label | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Decision Status | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR
2019-01-29 | January 2019 Review | New approval | Investment management (incl. Transport Planning) | Activity management planning improvement | Northland Regional Council | Regional Public Transport Plan Programme of Works 2018/21 | Programme business case |  | M__ | M__ | N | 4 | Approved | Approved by Senior Manager System Planning (SP&P) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 52500 | 28350
2019-01-07 | January 2019 Review | New approval | Walking and cycling improvements | Cycling facilities | Auckland Transport | Auckland Cycle Network - Links to Public Transport | Implementation | UCP - ACN Links to PT - NL to Avondale - IMP(NLTF) | HHM | MHM | N | 4 | Approved with conditions precedent | Approved with conditions precedent by GM Investment & Finance | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Transport Investment Online or by request | 40373716 | 20590595 | Clarification of the 95th percentile cost That contribution from 3rd party beneficiaries is explored to the maximum to subsidise local share. Greater clarification of the application of UCF and TEFAR, including resolution of this activity in terms of the agreed funding programme for UCF. | 4.1 | 0 | 4.1
2019-01-18 | January 2019 Review | New approval | External funding | Cycling facilities | NZTA (Northland) | Integrated Northland Cycle Plan | Detailed Business Case | PGF | H_L | H_L | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 263169 | 263169 |  | 2.5 | 2.5 | 2.5
2019-01-10 | January 2019 Review | New approval | Local road maintenance | Emergency works | Auckland Transport | E/W Rural South Auckland 15 July 2018 Storm Event | Construction |  | ___ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (SD&D) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 2424000 | 1236240
2019-01-31 | January 2019 Review | New approval | Local road maintenance | Emergency works | Auckland Transport | E/W Rural South Auckland 29 August 2018 Storm Event | Construction |  | ___ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (SD&D) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 846700 | 431817
2019-01-10 | January 2019 Review | New approval | Local road maintenance | Emergency works | Manawatu District Council | Emergency Works September 2018 Storm | Construction |  | ___ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (SD&D) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1172277 | 855762
2019-01-31 | January 2019 Review | New approval | State highway maintenance | Emergency works | NZTA (West Coast) | EW West Coast, Otira & Westland November 2018 | Construction |  | ___ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (SD&D) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 9971300 | 9971300
2019-01-23 | January 2019 Review | New approval | Local road maintenance | Emergency works | South Wairarapa District Council | Featherston Cloud Burst December 2018 | Construction |  | ___ |  | N |  | Approved | Approved by Manager Systems Management (SD&D) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 307619 | 159962
2019-01-10 | January 2019 Review | New approval | Local road maintenance | Emergency works | Tararua District Council | Event September 2018 | Construction |  | ___ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (SD&D) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 282421 | 186398
2019-01-10 | January 2019 Review | New approval | Local road maintenance | Emergency works | Whanganui District Council | August 2018 Emergency Works | Construction |  | ___ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (SD&D) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 2008065 | 1224920
2019-01-15 | January 2019 Review | New approval | Public transport | Passenger ferry services | Auckland Transport | PT Improvements - Ferry Services | Implementation | Ferry Service Improvements | H_L | H_L | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 5105310 | 3854508 |  | 1.6 | 1.6 | 1.3
2019-01-18 | January 2019 Review | New approval | Public transport | Public transport infrastructure and major renewals | Auckland Transport | ICP - Ellerslie Pakuranga Highway | Detailed Business Case | ICP-Ellerslie Pakuranga-SSBC | H_L | H_L | N | 5 | Approved with conditions | Approved with conditions by GM Investment & Finance | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Transport Investment Online or by request | 1439828 | 734313 | GM I&F approves funding for each of 12 enhanced single stage business cases of AT's Integrated Corridor Programme at a combined cost of $20.6 million (NZTA share $10.47 million) subject to: AT and the Transport Agency holding a workshop or workshops as soon as practicable to: a) Identify all risks with this investment approach b) Identify mitigations against these risks c) Identify opportunities for further innovation d) Establish how best to work together to ensure the success of the overall programme, including the governance and reporting structure and frequency, and escalation of risks or issues to the appropriate levels of senior management; The outcomes of the workshop/s will be reported to GM I&F for endorsement at the first opportunity. | 2.5 | 0 | 2.5
2019-01-18 | January 2019 Review | New approval | Public transport | Public transport infrastructure and major renewals | Auckland Transport | ICP - Gt North Rd - New Lynn to City | Detailed Business Case | ICP-Gt North Rd-New Lynn to City-SSBC | H_L | H_L | N | 5 | Approved with conditions | Approved with conditions by GM Investment & Finance | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Transport Investment Online or by request | 1827520 | 932035 | GM I&F approves funding for each of 12 enhanced single stage business cases of AT's Integrated Corridor Programme at a combined cost of $20.6 million (NZTA share $10.47 million) subject to: AT and the Transport Agency holding a workshop or workshops as soon as practicable to: a) Identify all risks with this investment approach b) Identify mitigations against these risks c) Identify opportunities for further innovation d) Establish how best to work together to ensure the success of the overall programme, including the governance and reporting structure and frequency, and escalation of risks or issues to the appropriate levels of senior management; The outcomes of the workshop/s will be reported to GM I&F for endorsement at the first opportunity. | 1.3 | 0 | 1.3
2019-01-18 | January 2019 Review | New approval | Public transport | Public transport infrastructure and major renewals | Auckland Transport | ICP - Gt North Rd â€“ New Lynn to Henderson | Detailed Business Case | ICP-Gt North Rd-New Lynn to Henderson-SSBC | H_L | H_L | N | 5 | Approved with conditions | Approved with conditions by GM Investment & Finance | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Transport Investment Online or by request | 1475884 | 752701 | GM I&F approves funding for each of 12 enhanced single stage business cases of AT's Integrated Corridor Programme at a combined cost of $20.6 million (NZTA share $10.47 million) subject to: AT and the Transport Agency holding a workshop or workshops as soon as practicable to: a) Identify all risks with this investment approach b) Identify mitigations against these risks c) Identify opportunities for further innovation d) Establish how best to work together to ensure the success of the overall programme, including the governance and reporting structure and frequency, and escalation of risks or issues to the appropriate levels of senior management; The outcomes of the workshop/s will be reported to GM I&F for endorsement at the first opportunity. | 1.2 | 0 | 1.2
2019-01-18 | January 2019 Review | New approval | Public transport | Public transport infrastructure and major renewals | Auckland Transport | ICP - Gt South Rd â€“ Manurewa to Papakura | Detailed Business Case | ICP - Manurewa to Papakura - SSBC | H_L | H_L | N | 5 | Approved with conditions | Approved with conditions by GM Investment & Finance | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Transport Investment Online or by request | 2170247 | 1106826 | GM I&F approves funding for each of 12 enhanced single stage business cases of AT's Integrated Corridor Programme at a combined cost of $20.6 million (NZTA share $10.47 million) subject to: AT and the Transport Agency holding a workshop or workshops as soon as practicable to: a) Identify all risks with this investment approach b) Identify mitigations against these risks c) Identify opportunities for further innovation d) Establish how best to work together to ensure the success of the overall programme, including the governance and reporting structure and frequency, and escalation of risks or issues to the appropriate levels of senior management; The outcomes of the workshop/s will be reported to GM I&F for endorsement at the first opportunity. | 0.2 | 0 | 2.1
2019-01-18 | January 2019 Review | New approval | Public transport | Public transport infrastructure and major renewals | Auckland Transport | ICP - Gt South Rd â€“ Newmarket to Manurewa | Detailed Business Case | ICP - Newmarket to Manurewa - SSBC | H_L | H_L | N | 5 | Approved with conditions | Approved with conditions by GM Investment & Finance | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Transport Investment Online or by request | 2371387 | 1209407 | GM I&F approves funding for each of 12 enhanced single stage business cases of AT's Integrated Corridor Programme at a combined cost of $20.6 million (NZTA share $10.47 million) subject to: AT and the Transport Agency holding a workshop or workshops as soon as practicable to: a) Identify all risks with this investment approach b) Identify mitigations against these risks c) Identify opportunities for further innovation d) Establish how best to work together to ensure the success of the overall programme, including the governance and reporting structure and frequency, and escalation of risks or issues to the appropriate levels of senior management; The outcomes of the workshop/s will be reported to GM I&F for endorsement at the first opportunity. | 2.5 | 0 | 2.5
2019-01-18 | January 2019 Review | New approval | Public transport | Public transport infrastructure and major renewals | Auckland Transport | ICP - Manukau Road | Detailed Business Case | ICP - Manukau Road - SSBC | H_L | H_L | N | 5 | Approved with conditions | Approved with conditions by GM Investment & Finance | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Transport Investment Online or by request | 2426479 | 1237504 | GM I&F approves funding for each of 12 enhanced single stage business cases of AT's Integrated Corridor Programme at a combined cost of $20.6 million (NZTA share $10.47 million) subject to: AT and the Transport Agency holding a workshop or workshops as soon as practicable to: a) Identify all risks with this investment approach b) Identify mitigations against these risks c) Identify opportunities for further innovation d) Establish how best to work together to ensure the success of the overall programme, including the governance and reporting structure and frequency, and escalation of risks or issues to the appropriate levels of senior management; The outcomes of the workshop/s will be reported to GM I&F for endorsement at the first opportunity. | 2.7 | 0 | 2.7
2019-01-18 | January 2019 Review | New approval | Public transport | Public transport infrastructure and major renewals | Auckland Transport | ICP - Mt Eden Road | Detailed Business Case | ICP-Mt.Eden-SSBC | H_M | H_L | N | 4 | Approved with conditions | Approved with conditions by GM Investment & Finance | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Transport Investment Online or by request | 1171834 | 597636 | GM I&F approves funding for each of 12 enhanced single stage business cases of AT's Integrated Corridor Programme at a combined cost of $20.6 million (NZTA share $10.47 million) subject to: AT and the Transport Agency holding a workshop or workshops as soon as practicable to: a) Identify all risks with this investment approach b) Identify mitigations against these risks c) Identify opportunities for further innovation d) Establish how best to work together to ensure the success of the overall programme, including the governance and reporting structure and frequency, and escalation of risks or issues to the appropriate levels of senior management; The outcomes of the workshop/s will be reported to GM I&F for endorsement at the first opportunity. | 4.1 | 0 | 4.1
2019-01-18 | January 2019 Review | New approval | Public transport | Public transport infrastructure and major renewals | Auckland Transport | ICP - New North Road | Detailed Business Case | ICP - New North Road - SSBC | H_M | H_L | N | 4 | Approved with conditions | Approved with conditions by GM Investment & Finance | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Transport Investment Online or by request | 1327813 | 677184 | GM I&F approves funding for each of 12 enhanced single stage business cases of AT's Integrated Corridor Programme at a combined cost of $20.6 million (NZTA share $10.47 million) subject to: AT and the Transport Agency holding a workshop or workshops as soon as practicable to: a) Identify all risks with this investment approach b) Identify mitigations against these risks c) Identify opportunities for further innovation d) Establish how best to work together to ensure the success of the overall programme, including the governance and reporting structure and frequency, and escalation of risks or issues to the appropriate levels of senior management; The outcomes of the workshop/s will be reported to GM I&F for endorsement at the first opportunity. | 4.2 | 0 | 4.2
2019-01-18 | January 2019 Review | New approval | Public transport | Public transport infrastructure and major renewals | Auckland Transport | ICP - Parnell Road | Detailed Business Case | ICP-Parnell Road-SSBC | H_M | H_L | N | 4 | Approved with conditions | Approved with conditions by GM Investment & Finance | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Transport Investment Online or by request | 418735 | 213554 | GM I&F approves funding for each of 12 enhanced single stage business cases of AT's Integrated Corridor Programme at a combined cost of $20.6 million (NZTA share $10.47 million) subject to: AT and the Transport Agency holding a workshop or workshops as soon as practicable to: a) Identify all risks with this investment approach b) Identify mitigations against these risks c) Identify opportunities for further innovation d) Establish how best to work together to ensure the success of the overall programme, including the governance and reporting structure and frequency, and escalation of risks or issues to the appropriate levels of senior management; The outcomes of the workshop/s will be reported to GM I&F for endorsement at the first opportunity. | 3.9 | 0 | 3.9
2019-01-18 | January 2019 Review | New approval | Public transport | Public transport infrastructure and major renewals | Auckland Transport | ICP - Ponsonby Road | Detailed Business Case | ICP_Ponsonby Road-SSBC | H_M | H_L | N | 4 | Approved with conditions | Approved with conditions by GM Investment & Finance | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Transport Investment Online or by request | 838292 | 427529 | GM I&F approves funding for each of 12 enhanced single stage business cases of AT's Integrated Corridor Programme at a combined cost of $20.6 million (NZTA share $10.47 million) subject to: AT and the Transport Agency holding a workshop or workshops as soon as practicable to: a) Identify all risks with this investment approach b) Identify mitigations against these risks c) Identify opportunities for further innovation d) Establish how best to work together to ensure the success of the overall programme, including the governance and reporting structure and frequency, and escalation of risks or issues to the appropriate levels of senior management; The outcomes of the workshop/s will be reported to GM I&F for endorsement at the first opportunity. | 3 | 0 | 3
2019-01-18 | January 2019 Review | New approval | Public transport | Public transport infrastructure and major renewals | Auckland Transport | ICP - Remuera Road | Detailed Business Case | ICP-Remuera Road-SSBC | H_L | H_L | N | 5 | Approved with conditions | Approved with conditions by GM Investment & Finance | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Transport Investment Online or by request | 1898646 | 968310 | GM I&F approves funding for each of 12 enhanced single stage business cases of AT's Integrated Corridor Programme at a combined cost of $20.6 million (NZTA share $10.47 million) subject to: AT and the Transport Agency holding a workshop or workshops as soon as practicable to: a) Identify all risks with this investment approach b) Identify mitigations against these risks c) Identify opportunities for further innovation d) Establish how best to work together to ensure the success of the overall programme, including the governance and reporting structure and frequency, and escalation of risks or issues to the appropriate levels of senior management; The outcomes of the workshop/s will be reported to GM I&F for endorsement at the first opportunity. | 1.5 | 0 | 1.5
2019-01-18 | January 2019 Review | New approval | Public transport | Public transport infrastructure and major renewals | Auckland Transport | ICP - Sandringham Road | Detailed Business Case | ICP - Sandringham - SSBC | H_M | H_L | N | 4 | Approved with conditions | Approved with conditions by GM Investment & Finance | Provided the condition(s) have been satisfied, the requirements of section 20 of the Land Transport Management Act 2003 will be met. Further details regarding the decision can be accessed on Transport Investment Online or by request | 3228632 | 1646603 | GM I&F approves funding for each of 12 enhanced single stage business cases of AT's Integrated Corridor Programme at a combined cost of $20.6 million (NZTA share $10.47 million) subject to: AT and the Transport Agency holding a workshop or workshops as soon as practicable to: a) Identify all risks with this investment approach b) Identify mitigations against these risks c) Identify opportunities for further innovation d) Establish how best to work together to ensure the success of the overall programme, including the governance and reporting structure and frequency, and escalation of risks or issues to the appropriate levels of senior management; The outcomes of the workshop/s will be reported to GM I&F for endorsement at the first opportunity. | 3.1 | 0 | 3.1
2019-01-29 | January 2019 Review | New approval | Investment management (incl. Transport Planning) | Regional land transport planning management | Northland Regional Council | Regional Land Transport Plan 2018/21 W/C 001 | Programme Business Case |  | H__ | H__ | N | 3 | Approved | Approved by Senior Manager System Planning (SP&P) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1025553 | 553798
2019-01-16 | January 2019 Review | New approval | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH30 Kopaki Bridge Replacement | Pre-implementation* |  | H_PV_EoL | HHPV_EoL | N | 2 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 837770 | 837770 |  |  | 99 | 99
2019-01-31 | January 2019 Review | New approval | Local road improvements | Road improvements | Ashburton District Council | Second Ashburton Urban Bridge, Ashburton River | Detailed Business Case | Detailed Business Case | M_H | HHH | N | 4 | Approved | Approved by Senior Manager System Planning (SP&P) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 325000 | 165750 |  | 4 | 4 | 0
2019-01-22 | January 2019 Review | New approval | Regional Improvements | Road improvements | Hastings District Council | Bridge Strengthening Programme 50 Max, HPMV and VDAM 2018-21 | Construction | Construction - HPMV, 50Max & VDAM | MM*M | VM*H | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 4569590 | 2467578 |  | 5 | 0 | 7.4
2019-01-22 | January 2019 Review | New approval | Regional Improvements | Road improvements | Hastings District Council | Bridge Strengthening Programme 50 Max, HPMV and VDAM 2018-21 | Pre-implementation* | Investigation - HPMV, 50Max & VDAM | MM*M | VM*H | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1065920 | 575597 |  | 5 | 0 | 7.4
2019-01-16 | January 2019 Review | New Approval Programmes | External funding | Promotion, education and advertising | Greater Wellington | Road Safety Promotion 2018-21 | Implementation |  | MH | HH | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 68000 | 68000
2019-01-29 | January 2019 Review | Cash flow adjustment | External funding | Cycling facilities | Christchurch City Council | Major Cycleway: Uni-Cycle (University to City) UCF | Construction | Hagley Park to Riccarton Bush Section 2 UCF Fundin | HHH | HHH | N | 1 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 5.9 | 5.9 | 5.9
2019-01-29 | January 2019 Review | Cash flow adjustment | External funding | Cycling facilities | Dunedin City Council | Southern Commuter Route F | Construction | Urban Cycleway Fund | HMH | HMM | N | 2 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 3.4 | 3.4
2019-01-10 | January 2019 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | NZTA (Auckland) | Glen Innes to Tamaki Shared Path - Sections 1 and 2A NZTA | Construction | UCP Glen Innes-Tamaki Dr C/way - Sec 1 CON (NLTF) | HHL | HHM | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 2.3 | 0 | 3.6
2019-01-29 | January 2019 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Waikato District Council | Ngaruawahia to Horotiu shared use walking Cycling Connection | Implementation | Ngaruawahia to Golf Course | MMM | HMM | N | 6 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 0 | 7.9
2019-01-29 | January 2019 Review | Cash flow adjustment | External funding | Cycling facilities | Waikato District Council | Ngaruawahia to Horotiu shared use walking Cycling Connection | Implementation | Urban Cycle Fund Component- Construction for cycle | MMM | HMM | N | 6 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 0 | 7.9
2019-01-25 | January 2019 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Western BoP District Council | Omokoroa Road Corridor Improvements | Construction | RP 160 - 1950 | MHL | HML | N | 6 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1.1 | 0 | 1.1
2019-01-25 | January 2019 Review | Cash flow adjustment | Local road improvements | Low cost / low risk improvements | Hutt City Council | Low cost / low risk improvements 2018-21 | Local Roads |  | __ |  | N | 0 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0
2019-01-25 | January 2019 Review | Cash flow adjustment | Investment management (incl. Transport Planning) | Management of the funding allocation system | NZ Transport Agency | New Zealand Business Number | Implementation | NZ Business Number | HHL | HHL | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1 | 0 | 0
2019-01-24 | January 2019 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (BOP) | TEL Tauranga Eastern Link | Implementation | Tolls Supplement | HHL | HHL | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -12 | -12 |  | 1 | 2 | 2
2019-01-23 | January 2019 Review | Cash flow adjustment | Promotion of road safety and demand management | Promotion, education and advertising | Gisborne District Council | Road Safety Promotion 2018-21 | Implementation |  | MM | MM | N | 5 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0
2019-01-23 | January 2019 Review | Cash flow adjustment | Promotion of road safety and demand management | Promotion, education and advertising | Gisborne District Council | Road Safety Promotion 2018-21 | Implementation |  | MM | MM | N | 5 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0
2019-01-23 | January 2019 Review | Cash flow adjustment | Promotion of road safety and demand management | Promotion, education and advertising | Gisborne District Council | Road Safety Promotion 2018-21 | Implementation |  | HM | HM | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0
2019-01-28 | January 2019 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Auckland) | SH1 Warkworth to Wellsford RoNS - Detailed Design and Const | Property |  | HML | HML | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1.1 | 1.1 | 1.1
2019-01-28 | January 2019 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Waikato) | SH26 Kirikiri Stream Bridge Replacement | Property | SH26 Kirikiri Stream Bridge Replacement-property | MMPV_EoL | MMPV_EoL | N | 2 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 99 | 99
2019-01-28 | January 2019 Review | Cash flow adjustment | Rapid Transit | Rapid Transit Infrastructure | NZTA (Auckland) | City Centre to Mangere Light Rail | Pre-implementation* | Pre-Implementation- RT improvements | HML | HML | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 2 | 2 |  | 2 | 1 | 1
2019-01-29 | January 2019 Review | Cash flow adjustment | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH26 Kirikiri Stream Bridge Replacement | Implementation | SH 26 Kirikiri Stream Bridge Replacement Construct | MMPV_EoL | MMPV_EoL | N | 2 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -1 | -1 |  |  | 99 | 99
2019-01-28 | January 2019 Review | Cash flow adjustment | State highway improvements | Resilience improvements | NZTA (Northland) | SH12 Opononi Foreshore Resilience Improvement | Construction |  | HHH | HHH | N | 1 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0
2019-01-28 | January 2019 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Auckland) | East West Link -part of Auckland Accelerated Programme(AAP) | Pre-implementation* | Design | HHL | HHL | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 1.9 | 1.9
2019-01-28 | January 2019 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Auckland) | East West Link -part of Auckland Accelerated Programme(AAP) | Property | Property | HHL | HHL | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1 | 1 |  |  | 1.9 | 1.9
2019-01-28 | January 2019 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Auckland) | Supporting Growth Route Protection Programme | Detailed Business Case | DBC | HMM | HMM | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -1 | -1 |  | 3.5 | 3.5 | 3.5
2019-01-25 | January 2019 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Canterbury) | SH76 Brougham Street Corridor Imps | Detailed Business Case | Detailed business case (I) | HML | HMM | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 2 | 2 |  |  | 4 | 4
2019-01-28 | January 2019 Review | Cash flow adjustment | Regional Improvements | Road improvements | NZTA (Northland) | SH1 Loop Road North to Smeatons Hill Safety Improvement | Implementation | Implementation | HML | HML | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 1.2 | 0 | 3
2019-01-28 | January 2019 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | SH1 South-East Hamilton Improvements | Construction | SH1 Cobham/Cambridge Improvements Construction | HMM | MMM | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  |  | 5.9 | 5.9
2019-01-28 | January 2019 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | SH1 South-East Hamilton Improvements | Design | SH1 Cobham/Cambridge Improvements Design | HMM | MMM | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1 | 1 |  |  | 5.9 | 5.9
2019-01-28 | January 2019 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | SH25 Coromandel Motorcycle Demonstration Project - stage 2 | Construction | Construction | HHH | HHM | N | 1 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 7.3 | 7.2 | 7.2
2019-01-25 | January 2019 Review | Cash flow adjustment | Local road improvements | Road improvements | Western BoP District Council | District LED upgrade | Implementation | Construction | MHH | MHH | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 0 |  | 5 | 0 | 5
2019-01-29 | January 2019 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Christchurch City Council | Major Cycleway: Uni-Cycle (University to City) UCF | Construction | Hagley Park to Riccarton Bush Section 2 NZTA/Local | HHH | HHH | N | 1 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 3899 | 3900 |  | 5.9 | 5.9 | 5.9
2019-01-30 | January 2019 Review | Cost Decrease | External funding | Cycling facilities | Christchurch City Council | Major Cycleway: Uni-Cycle (University to City) UCF | Construction | Hagley Park to Riccarton Bush Section 2 UCF Fundin | HHH | HHH | N | 1 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | -3899 |  | 5.9 | 5.9 | 5.9
2019-01-29 | January 2019 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Dunedin City Council | Southern Commuter Route F | Construction | Southern Commuter Route F | HMH | HMM | N | 2 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 12824 | 12824 |  |  | 3.4 | 3.4
2019-01-30 | January 2019 Review | Cost Decrease | External funding | Cycling facilities | Dunedin City Council | Southern Commuter Route F | Construction | Urban Cycleway Fund | HMH | HMM | N | 2 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | -12824 |  |  | 3.4 | 3.4
2019-01-07 | January 2019 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Hutt City Council | The Beltway | Pre-implementation* |  | H_M | HMM | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 130498 | 66554 |  | 4.6 | 6.5 | 6.5
2019-01-10 | January 2019 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | NZTA (Auckland) | Glen Innes to Tamaki Shared Path - Sections 1 and 2A NZTA | Construction | UCP Glen Innes-Tamaki Dr C/way - Sec 1 CON (NLTF) | HHL | HHM | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -3809269 | -3809269 |  | 2.3 | 0 | 3.6
2019-01-25 | January 2019 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | NZTA (Wellington) | Wellington to Hutt Valley cycleway/walkway/resilience projct | Design | W2HV Pre-implementation | HHL | HHL | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -1231200 | -1231200 |  |  | 0 | 2.5
2019-01-29 | January 2019 Review | Cost Decrease | External funding | Cycling facilities | Palmerston North City Council | Pioneer Highway Shared Cycle Path to Longburn | Construction | Pioneer Highway shared path to Longburn | HMM | HHH | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -6750 | -6750 |  | 5.3 | 0 | 5.3
2019-01-29 | January 2019 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Palmerston North City Council | Pioneer Highway Shared Cycle Path to Longburn | Construction | NLTF funded phase | HMM | HHH | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 6750 | 3848 |  | 5.3 | 0 | 5.3
2019-01-29 | January 2019 Review | Cost Decrease | External funding | Cycling facilities | Selwyn District Council | Lincoln Rolleston Cyclway | Construction | UCF funded phase of Lincol Rolleston cycleway | MMH | MMH | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -6750 | -6750 |  | 6.3 | 0 | 6.3
2019-01-29 | January 2019 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Selwyn District Council | Lincoln Rolleston Cyclway | Construction | Lincoln Rolleston Cycleway NLTP/Local funding | MMH | MMH | N | 4 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 6750 | 6750 |  | 6.3 | 0 | 6.3
2019-01-25 | January 2019 Review | Cost Decrease | Local road maintenance | Emergency works | Mackenzie District Council | 21/7/2017 - Rainfall and Snow Event | Construction |  | ___ |  | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -268756 | -137066
2019-01-10 | January 2019 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Canterbury) | EW Canterbury Cyclone Gita Feb 2018 | Construction |  | ___ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (SD&D) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 6283200 | 6283200
2019-01-10 | January 2019 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Taranaki) | EW Kent Road and Mangamahoe Culvert Damage | Construction |  | ___ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (SD&D) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 844800 | 844800
2019-01-25 | January 2019 Review | Cost Decrease | Local road maintenance | Emergency works | South Wairarapa District Council | Storm Event Thursday 13 July 2017 | Construction |  | ___ |  | N |  | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -962 | -500
2019-01-31 | January 2019 Review | Cost Decrease | Local road maintenance | Environmental renewals | Kaikoura District Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | Local Roads |  | MM |  | N | 5 | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -7983 | -4071
2019-01-25 | January 2019 Review | Cost Decrease | State highway improvements | Low cost / low risk improvements | NZTA (Auckland) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -3067504 | -3067503
2019-01-25 | January 2019 Review | Cost Decrease | State highway improvements | Low cost / low risk improvements | NZTA (BOP) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -5690534 | -5690534
2019-01-25 | January 2019 Review | Cost Decrease | State highway improvements | Low cost / low risk improvements | NZTA (Canterbury) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -372945 | -372945
2019-01-25 | January 2019 Review | Cost Increase | State highway improvements | Low cost / low risk improvements | NZTA (Gisborne) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 13441686 | 13441685
2019-01-25 | January 2019 Review | Cost Increase | State highway improvements | Low cost / low risk improvements | NZTA (Hawkes Bay) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 333146 | 333146
2019-01-25 | January 2019 Review | Cost Increase | State highway improvements | Low cost / low risk improvements | NZTA (Manawatu/Whanganui) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 10026091 | 10026092
2019-01-25 | January 2019 Review | Cost Decrease | State highway improvements | Low cost / low risk improvements | NZTA (Marlborough) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -2227685 | -2227685
2019-01-25 | January 2019 Review | Cost Increase | State highway improvements | Low cost / low risk improvements | NZTA (Nelson) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 218613 | 218612
2019-01-25 | January 2019 Review | Cost Decrease | State highway improvements | Low cost / low risk improvements | NZTA (Northland) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -1164404 | -1164403
2019-01-25 | January 2019 Review | Cost Decrease | State highway improvements | Low cost / low risk improvements | NZTA (Southland) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -2458885 | -2458884
2019-01-25 | January 2019 Review | Cost Decrease | State highway improvements | Low cost / low risk improvements | NZTA (Taranaki) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -1089048 | -1089049
2019-01-25 | January 2019 Review | Cost Decrease | State highway improvements | Low cost / low risk improvements | NZTA (Tasman) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -1443770 | -1443771
2019-01-25 | January 2019 Review | Cost Decrease | State highway improvements | Low cost / low risk improvements | NZTA (Waikato) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -6303438 | -6303438
2019-01-25 | January 2019 Review | Cost Decrease | State highway improvements | Low cost / low risk improvements | NZTA (Wellington) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -3420369 | -3420369
2019-01-25 | January 2019 Review | Cost Increase | State highway improvements | Low cost / low risk improvements | NZTA (West Coast) | Low cost / low risk improvements 2018-21 | State Highways |  | __ |  | N | 0 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 5657344 | 5657343
2019-01-31 | January 2019 Review | Cost Increase | Local road maintenance | Minor events | Kaikoura District Council | Maintenance, Operations and Renewals Programme 2018-21 - AC 8 | Local Roads |  | MM |  | N | 5 | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 616700 | 314517
2019-01-16 | January 2019 Review | Cost Increase | Local road maintenance | Network and asset management | NZ Transport Agency | National Speed Limit Register | Implementation | maintain register | VHPV_EoL | VH_ | N | 1 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 808300 | 808300 |  |  | 1 | 99
2019-01-15 | January 2019 Review | Cost Increase | State highway improvements | New roads | NZTA (Canterbury) | Mingha Bluff to Rough Creek | Implementation | NLTF Funding | MML | MML | N | 7 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 4109920 | 4109920 |  | 1.1 | 1.1 | 1.1
2019-01-28 | January 2019 Review | Cost Decrease | State highway improvements | New roads | NZTA (Canterbury) | Western Belfast By-Pass | Construction | Construction | HHM | MHL | N | 2 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -5321910 | -5321910 |  | 4.6 | 2.1 | 2.1
2019-01-31 | January 2019 Review | Cost Increase | State highway improvements | New roads | NZTA (Taranaki) | SH3 Mt Messenger Bypass | Construction | Construction | HML | HML | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 1200000 | 1200000 |  | 1.1 | 0.5 | 0.5
2019-01-31 | January 2019 Review | Cost Decrease | External funding | New roads | NZTA (Taranaki) | SH3 Mt Messenger Bypass | Implementation | ARSHP | HML | HML | N | 5 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -1200000 | -1200000 |  | 1.1 | 0.5 | 0.5
2019-01-23 | January 2019 Review | Cost Decrease | State highway improvements | New roads | NZTA (Wellington) | Wellington RoNS (7) - SH1 Peka Peka to Otaki Expressway | Construction |  | HHL | MHM | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -13338000 | -13338000 |  | 1.4 | 0.6 | 0.6
2019-01-31 | January 2019 Review | Cost Increase | State highway improvements | New traffic management facilities | NZTA (Canterbury) | Lyttelton Tunnel Safety Retrofit (Deluge) System | Implementation | Construction | HHPV_EoL | HHVH | N | 2 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 4965659 | 4965659 |  | 0 | 0 | 99
2019-01-28 | January 2019 Review | Cost Decrease | State highway improvements | Property purchase (State highways) | NZTA (Canterbury) | Harewood Rd to Yaldhurst Rd 4 Laning | Property | Property | HHM | HHM | N | 2 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -533078 | -533078 |  |  | 1.5 | 1.5
2019-01-25 | January 2019 Review | Cost Decrease | Public transport | Public transport infrastructure and major renewals | Auckland Transport | Otahuhu Bus Interchange | Construction | Otahuhu Bus Interchange | HHL | HHM | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -578680 | -289340 |  | 1.5 | 3 | 2.7
2019-01-18 | January 2019 Review | Cost Increase | State highway improvements | Resilience improvements | NZTA (Gisborne) | Puketiti Realignment | Implementation |  | HHL* | HHH | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 104236 | 104236
2019-01-28 | January 2019 Review | Cost Decrease | Local road improvements | Resilience improvements | Wellington City Council | Road Resilience Improvement 2015/25 - Ngaio Gorge/Wadestown | Construction |  | HHH | HHH | N | 1 | Declined | Declined by RM P&I | The requirements of section 20 of the Land Transport Management Act 2003 have not been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -208768 | -106472
2019-01-23 | January 2019 Review | Cost Decrease | Local road improvements | Road improvements | Christchurch City Council | Christchurch Northern Corridor - Local Share Activity | Implementation |  | HHL | HHL | N | 5 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -15385456 | -15385456 |  | 1 | 2.3 | 2.3
2019-01-24 | January 2019 Review | Cost Increase | Local road improvements | Road improvements | Matamata-Piako District Council | LED project | Construction | construction | MHH | MHH | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 327660 | 278511 |  |  | 5 | 5
2019-01-28 | January 2019 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Canterbury) | Yaldhurst Rd to Waterloo Rd 4L | Construction | Large | HHM | HHM | N | 2 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -4045 | -4045 |  |  | 2.4 | 4.3
2019-01-31 | January 2019 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (Hawkes Bay) | HB Expressway Safety Treatments | Pre-implementation* | Pre Implementation | HMM | HMM | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 477090 | 477090 |  | 4.5 | 4.5 | 4.5
2019-01-16 | January 2019 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (Hawkes Bay) | SH2 Watchman Rd, HB Airport Intersection | Pre-implementation* |  | HML | HMM | N | 4 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 646 | 646 |  |  | 2.2 | 2.2
2019-01-16 | January 2019 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (Manawatu/Whanganui) | SH57: SH1 to Shannon Safety Improvements | Detailed Business Case | DBC | HMM | HMM | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 25389 | 25389 |  | 3 | 2.5 | 2.5
2019-01-10 | January 2019 Review | Cost Increase | Regional Improvements | Road improvements | NZTA (Manawatu/Whanganui) | SH57: SH1 to Shannon Safety Improvements | Pre-implementation* | Pre-Implementation | HMM | HMM | N | 3 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 416 | 416 |  | 3 | 2.5 | 2.5
2019-01-16 | January 2019 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Waikato) | SH1 Bombay- Long Swamp Barrier Infill | Pre-implementation* |  | HHL | HHL | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 13885 | 13885 |  | 2.3 | 2.1 | 2.1
2019-01-28 | January 2019 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Waikato) | SH1 South-East Hamilton Improvements | Construction | SH1/26 Intersection Improvements Construction | HMM | MMM | N | 3 | Approved | Approved by GM Investment & Finance | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -30585 | -30585 |  |  | 5.9 | 5.9
2019-01-23 | January 2019 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Waikato) | SH3 Awakino Tunnel Bypass | Construction | Construction - NLTF funding | HLL | MML | N | 5 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 214273 | 214273 |  | 2.5 | 2.5 | 2.5
2019-01-23 | January 2019 Review | Cost Decrease | External funding | Road improvements | NZTA (Waikato) | SH3 Awakino Tunnel Bypass | Implementation | Construction implementation | HLL | MML | N | 0 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | -214273 | -214273 |  | 2.5 | 2.5 | 2.5
2019-01-16 | January 2019 Review | Cost Increase | Transitional Rail | Transitional Rail Infrastructure | Auckland Transport | TR - Papakura to Pukekohe Rail Corridor Improvements | Detailed Business Case | TR - P2P DBC - Kiwirail | H_L* | HHL | N | 5 | Approved | Approved by Manager Treasury & Cash Flow (I&F) | The requirements of section 20 of the Land Transport Management Act 2003 have been met. Further details regarding the reasons can be accessed on Transport Investment Online or by request | 0 | 2733270 |  | 3.8 | 0 | 3
2019-01-21 | January 2019 Review | Support for strategic case |  |  | Auckland Transport | Matiatia land-side transport network and infrastructure | Support for Strategic Case |  | M__ | M__ | N | 4 | Supported | Supported by Senior Manager System Planning (SP&P) | This is not a funding decision | 0