## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Phase Label | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Decision Status | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR | Your Phase reference | TIO Phase id | SAP item id | TIO Request id
2022-08-30 | August 2022 Review | New approval | Investment management (incl. Transport Planning) | Activity management planning improvement | Waikato Regional Council | 2024 Regional Public Transport Plan | Implementation |  | VHHH | VHHH | N | 1 | Approved | Approved by Chief Financial Officer (CFO) | These AMPs support the outcomes of the ERP by investigating investment into safe and accessible alternatives to private vehicle travel and emission reduction. | 225000 | 114750 |  |  |  | 99 |  | 277852 |  | 117811
2022-08-01 | August 2022 Review | New approval | Road to Zero | Activity management planning improvement | Wellington City Council | Speed management programme | Single-Stage Business Case | Speed Mgmt Programme | VHHVH | VHHVH | N | 1 | Approved | Approved by Chief Financial Officer (CFO) | WCC are wanting to proceed with their speed programme | 110101 | 56152 |  |  |  |  | Speed Mgmt Programme | 276745 |  | 116814
2022-08-17 | August 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Dunedin City Council | Dunedin Urban Cycleways | Pre-implementation* | Dunedin Tunnels Trail | VHLL | HHL | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | The Tunnels Trails SSBC utilises the Waka Kotahi Business Case Approach. It makes a case for investment in an active mode walking and cycling trail. The proposal utilises a combination of new infrastructure as well as leveraging off existing infrastructure investment to promote and support increased walking and cycling in Otago. The business case meets Waka Kotahi requirements for a single stage business case. | 2433000 | 1261960 |  |  | 1.4 | 1.4 | Tunnels Trail pre-imp | 281960 |  | 118538
2022-08-15 | August 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Hutt City Council | Eastern Bays Shared Path | Implementation | Bays 5-6 | VHHL | VHHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | Adequate information provided to support moving from pre-implementation to implementation for Bays 5-6. Note these have been split out from 1-4 - Implementation of the entire 6 Bays was included in the NLTP, so for phasing purposes only this has been split into two phases in TIO. | 17000000 | 4335000 |  |  | 0 | 1.8 |  | 264396 |  | 120378
2022-08-01 | August 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Wellington City Council | WCC Cycleways - Transformational Programme | Single-Stage Business Case | Tawa Connections - SSBC Lite | HHL | VHHM | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | WCC has resource in the team to do this work, with support from their Council. | 684000 | 348840 |  |  |  | 3.5 | Tawa Connections â€“ SSBC Lite | 281920 |  | 118434
2022-08-09 | August 2022 Review | New approval | Local road maintenance | Emergency works | Rangitikei District Council | Emergency Works December 2021 | Construction | Recover phase for December 2021 weather event | ___ |  | N |  | Approved | Approved by System Manager, Maintenance and Operations (Transport Services) | to undertake initial response and reinstatement for both December 2021 and February 2022 to various road within the district and return those roads to the required pre-event levels of service as approved. | 977071 | 625325 |  |  |  |  | Emergency Works December 2021 | 280799 |  | 116725
2022-08-09 | August 2022 Review | New approval | Local road maintenance | Emergency works | Rangitikei District Council | Emergency Works February 2022 | Construction | Recover phase for February 2022 weather event | ___ |  | N |  | Approved | Approved by National Manager, Maintenance and Operations (Transport Services) | to undertake initial response and reinstatement for both December 2021 and February 2022 to various road within the district and return those roads to the required pre-event levels of service. | 150000 | 96000 |  |  |  |  | Recovery phase | 280822 |  | 117530
2022-08-30 | August 2022 Review | New approval | Local road maintenance | Emergency works | Wairoa District Council | Emergency Works March 2022 | Construction |  | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Fund the request at 95% for current year to ensure Council receives funding. Future years FAR based on EW WK policy 75% | 21435701 | 17505823 |  |  |  |  | RS5619_Emergency Works March 2022 Reinstatement Renewal_Local Roads | 281419 |  | 117546
2022-08-30 | August 2022 Review | New approval | Local road maintenance | Emergency works | Wairoa District Council | Emergency Works March 2022 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | CFO approved Special Purpose Road component at a cost of $649,000 at a funding assistance rate of 100 % | 620000 | 620000 |  |  |  |  | Emergency Works March 2022_Reinstatement Renewal_SPR38 | 281421 |  | 117548
2022-08-18 | August 2022 Review | New approval | Investment management (incl. Transport Planning) | Management of the funding allocation system | NZ Transport Agency | Planning & Investment Evidence Base | Implementation |  | VHHH | VHHH | N | 1 | Approved | Approved by Chief Financial Officer (CFO) |  | 10450000 | 10450000 |  |  |  | 1 |  | 278054 |  | 120586
2022-08-15 | August 2022 Review | New approval | State highway maintenance | Network and asset management | NZTA (Gisborne) | 2021-24 NLTP Funds Management | Repayment | AC-9 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds Management | 7833357 | 7833357 | [5 empty] | 282285 |  | 120513
2022-08-15 | August 2022 Review | New approval | State highway maintenance | Network and asset management | NZTA (Northland) | 2021-24 NLTP funds management | Repayment | AC-9 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds management | 521238 | 521238 | [5 empty] | 282286 |  | 120519
2022-08-15 | August 2022 Review | New approval | State highway maintenance | Network and asset management | NZTA (Otago) | 2021-24 NLTP funds management | Repayment | AC-9 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds management | 110482 | 110482 | [5 empty] | 282287 |  | 120520
2022-08-15 | August 2022 Review | New approval | State highway maintenance | Network and asset management | NZTA (Southland) | 2021-24 NLTP Funds Management | Repayment | AC-9 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds management | 849812 | 849812 | [5 empty] | 282288 |  | 120521
2022-08-15 | August 2022 Review | New approval | State highway maintenance | Network and asset management | NZTA (Taranaki) | 2021-24 NLTP Funds Management | Repayment | AC-9 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds management | 792984 | 792984 | [5 empty] | 282289 |  | 120522
2022-08-29 | August 2022 Review | New approval | State highway improvements | Property purchase (State highways) | NZTA (Auckland) | Legacy Property Acquisition - Auckland | Property |  | HHM | HHM | N | 4 | Approved | Approved by Chief Financial Officer (CFO) |  | 6330000 | 6330000 |  |  | 4 |  |  | 277839 | 60061615 | 118313
2022-08-02 | August 2022 Review | New approval | External funding | Property purchase (State highways) | NZTA (Auckland) | NZUP SH22 (Drury) Corridor Upgrade | Property |  | MML | MML | N | 9 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | NZUP SH22 Property phase 60067769 was created with incorrect Work Category. Request phase be closed and all funding transferred to new Property phase (60067986). | 18000000 | 18000000 |  |  |  | 1.7 |  | 282184 | 60067986 | 120355
2022-08-02 | August 2022 Review | New approval | External funding | Property purchase (State highways) | NZTA (Auckland) | NZUP Waihoehoe Road (Drury) Upgrade | Property |  | MML | MML | N | 9 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This NZUP Waihoehoe Rd Property phase 60067771 was created with incorrect Work Category. Requesting this phase be closed and all funding be transferred to new Property phase (60067985). | 24000000 | 24000000 |  |  |  | 1.8 |  | 282204 | 60067985 | 120354
2022-08-29 | August 2022 Review | New approval | State highway improvements | Property purchase (State highways) | NZTA (Canterbury) | Legacy Property Acquisition - Canterbury | Property |  | HHM | HHM | N | 4 | Approved | Approved by Chief Financial Officer (CFO) |  | 3165000 | 3165000 | [5 empty] | 277874 | 60061628 | 118314
2022-08-24 | August 2022 Review | New approval | Road to Zero | Property purchase (State highways) | NZTA (Northland) | SH1 Whangarei to Wellsford - (Central Section) | Property |  | VHML | HHM | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Property Phase (60066689) created using incorrect Work Category. New phase created (60068287) and all remaining approved Property budget ($2,587,926 excl. admin) to be shifted to new phase. | 2730262 | 2730262 |  |  | 0 | 1.6 |  | 282324 | 60068287 | 120686
2022-08-17 | August 2022 Review | New approval | Road to Zero | Property purchase (State highways) | NZTA (Taranaki) | SH3 - New Plymouth to Egmont Village | Property |  | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) |  | 554001 | 554001 |  |  | 0 | 1.6 |  | 281298 | 60067225 | 120556
2022-08-29 | August 2022 Review | New approval | State highway improvements | Property purchase (State highways) | NZTA (Waikato) | Legacy Property Acquisition Waikato 21-24 | Property |  | HHM | HHM | N | 4 | Approved | Approved by Chief Financial Officer (CFO) |  | 2110000 | 2110000 | [5 empty] | 277605 | 60061512 | 118316
2022-08-29 | August 2022 Review | New approval | State highway improvements | Property purchase (State highways) | NZTA (Wellington) | Legacy Property Acquisition - Wellington | Property |  | HHM | HHM | N | 4 | Approved | Approved by Chief Financial Officer (CFO) |  | 4220000 | 4220000 | [5 empty] | 277389 | 60061250 | 118315
2022-08-31 | August 2022 Review | New approval | Road to Zero | Property purchase (local roads) | Selwyn District Council | Prebbleton Arterial CSM Related Upgrade Packages | Property | Shands/Hamptons Roundabout | HML | HML | N | 6 | Approved | Approved by Chief Financial Officer (CFO) |  | 2800000 | 1428000 |  |  | 1 | 1 | Shands/Hamptons in conjunction with Implementation phase | 282188 |  | 120461
2022-08-25 | August 2022 Review | New approval | State highway improvements | Replacement of bridges and other structures | NZTA (Gisborne) | SH2 Motu Bridge Replacement | Implementation | NLTF Implementation | MHVL | LLL | N | 10 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This PLA is to complete the final stages of Implementation (mainly Second Coat Seal and handover documentation to Maintenance & Operations). Originally this was to be completed within the former Accelerated Regional Roading Programme (Crown funded) but is now sought as NLTP Funding. | 204660 | 204660 |  |  | 1 | 1 | NLTF Implementation | 282085 |  | 120472
2022-08-18 | August 2022 Review | New approval | Local road improvements | Road improvements | Dunedin City Council | Central City Safety and Accessibility Upgrade | Implementation | Retail Quarter Upgrade | VHHL | VHHL | N | 2 | Approved with conditions | Approved with conditions by Chief Financial Officer (CFO) | A DBC has been completed and overall it is sufficiently robust to meet Waka Kotahi requirements as assessed through the IQA process. It follows the principles of the Waka Kotahi Business Case Approach and provides sufficient confidence and alignment to justify funding of the implementation phase. Funding priority and availability is confirmed. Note the 22/23 costs include $8.703m spent in 21/22. The adjusted FAR reflects this, and will be readjusted if necessary at the end of 22/23 depending on 22/23 spend. | 37911000 | 19673204 | Subject to a condition subsequent that Waka Kotahi has capped total cost at P95 ($40.169M) due to the uncertain form and scope of urban realm benefits within the pre-implementation and implementation phases. Condition subsequent to price tension remaining on place components and any future cost/scope adjustment appropriately tensioning that trade-off. |  | 1.3 | 1.3 |  | 230513 |  | 120330
2022-08-04 | August 2022 Review | New approval | Road to Zero | Road improvements | Hastings District Council | Maraekakaho / York Roundabout Construction | Implementation | Maraekakaho / York Roundabout Construction | VHHL | VHHM | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | Existing T-intersection is performing poorly in both safety and efficiency. | 5014000 | 2657420 |  |  |  | 0.5 | Maraekakaho / York Roundabout Construction | 277789 |  | 118187
2022-08-04 | August 2022 Review | New approval | Road to Zero | Road improvements | Hastings District Council | Maraekakaho / York Roundabout Construction | Pre-implementation* | Maraekakaho / York Roundabout Construction | VHHL | VHHM | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | Existing T-intersection is performing poorly in both safety and efficiency. | 329000 | 174370 |  |  |  | 0.5 |  | 281444 |  | 118186
2022-08-04 | August 2022 Review | New approval | Road to Zero | Road improvements | Hastings District Council | Maraekakaho / York Roundabout Construction | Property | Maraekakaho / York Roundabout Construction | VHHL | VHHM | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | Existing T-intersection is performing poorly in both safety and efficiency. | 500000 | 265000 |  |  |  | 0.5 |  | 281445 |  | 118185
2022-08-15 | August 2022 Review | New approval | Road to Zero | Road improvements | NZTA (Auckland) | 2021-24 NLTP funds management | Repayment | AC-23 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds Management | 1442878 | 1442878 | [5 empty] | 282284 |  | 120508
2022-08-15 | August 2022 Review | New approval | State highway improvements | Road improvements | NZTA (Tasman) | CIP SH60 Motueka Project | Implementation | NLTF - SH60 Motueka Investigation Project | MHM | MHM | N | 6 | Approved | Approved by Chief Financial Officer (CFO) |  | 81306 | 81306 |  |  | 3.3 | 3.3 | NLTF | 277098 |  | 120476
2022-08-31 | August 2022 Review | New approval |  | Road improvements | Selwyn District Council | Prebbleton Arterial CSM Related Upgrade Packages | Implementation | Shands/Hamptons Rd Roundabout | HML | HML | N | 6 | Approved | Approved by Chief Financial Officer (CFO) |  | 3800000 | 1938000 |  |  | 1 | 1 | Shands/Hamptons in conjunction with property phase | 260904 |  | 120462
2022-08-30 | August 2022 Review | New approval | Walking and cycling improvements | Walking facilities | Christchurch City Council | Canterbury Multi-Use Arena Support Package | Single-Stage Business Case | SSBC | HHM | MHM | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | See PoE | 80000 | 40800 |  |  |  | 4.1 | 67012 | 277055 |  | 120446
2022-08-19 | August 2022 Review | Cash flow adjustment | Local road maintenance | Bridge and structures renewals | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Redistribution of the carry forward budgets in TIO of $3,581,959 out of WC111 to various wc. Cash neutral amendments. | 919592 | 634518 | [5 empty] | 272536 |  | 120487
2022-08-19 | August 2022 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | NZTA (Otago) | SH6 SH8B SH8 Gibbston to Clyde Corridor Imps | Construction | Nevis Bluff cycle connection - construction | VHML | MML | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow only to match re-forecast of programme | 0 | 0 |  |  | 9.7 | 0.4 | Nevis Bluff cycle connection - construct | 266625 | 60052351 | 120441
2022-08-19 | August 2022 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | NZTA (Otago) | Wakatipu Walking/Cycling Network Improvements | Implementation | NZTA package | HHL | HMM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow only to match reforecast of programme | 0 | 0 |  |  | 2.6 | 2.6 | Implementation - NZTA package | 254416 | 60052906 | 120453
2022-08-19 | August 2022 Review | Cash flow adjustment | Local road maintenance | Drainage renewals | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Redistribution of the carry forward budgets in TIO of $3,581,959 out of WC111 to various wc. Cash neutral amendments. | 225110 | 155326 | [5 empty] | 272533 |  | 120487
2022-08-19 | August 2022 Review | Cash flow adjustment | Local road maintenance | Footpath renewal | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Redistribution of the carry forward budgets in TIO of $3,581,959 out of WC111 to various wc. Cash neutral amendments. | 298857 | 206211 | [5 empty] | 272540 |  | 120487
2022-08-16 | August 2022 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Wellington) | Wellington RoNS (5) - Transmission Gully | Construction | Transmission Gully - PPP component | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move $$ from C-fund to N-funds | 0 | 0 |  |  | 1.4 | 1.4 | 60218421 | 203538 | 60218421 | 120547
2022-08-01 | August 2022 Review | Cash flow adjustment | Public transport infrastructure | Passenger facilities and infrastructure improvements - rail | KiwiRail | Additional Traction feed (West) | Implementation |  | MHL | MHL | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update 2021/22 actuals. Unclaimed funds carried forward. | 0 | 0 |  |  | 1 | 1 |  | 280999 |  | 120367
2022-08-01 | August 2022 Review | Cash flow adjustment | Public transport infrastructure | Passenger facilities and infrastructure improvements - rail | KiwiRail | Infill Signalling | Single-Stage Business Case |  | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update 2021/22 actuals. Unclaimed funds carried forward. | 0 | 0 |  |  |  | 1 |  | 281025 |  | 120368
2022-08-01 | August 2022 Review | Cash flow adjustment | Public transport infrastructure | Passenger facilities and infrastructure improvements - rail | KiwiRail | Integrated rail management centre and emergency management | Implementation |  | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update 2021/22 actuals. Unclaimed funds carried forward. | 0 | 0 |  |  | 1 | 1 |  | 281024 |  | 120369
2022-08-01 | August 2022 Review | Cash flow adjustment | Public transport infrastructure | Passenger facilities and infrastructure improvements - rail | KiwiRail | Progressive fencing and security | Implementation | Progressive Fencing and Security Stage 1 | HHL | MHM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update 2021/22 actuals. Unclaimed funds carried forward. | 0 | 0 |  |  | 1 | 1 | Progressive Fencing and Security Stage 1 - 2021/22 to 2023/24 | 281022 |  | 120370
2022-08-01 | August 2022 Review | Cash flow adjustment | Public transport infrastructure | Passenger facilities and infrastructure improvements - rail | KiwiRail | Strategic Future Planning | Detailed Business Case | Strategic Future Planning | HHL | MMM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update 2021/22 actuals. Unclaimed funds carried forward. | 0 | 0 |  |  |  | 1 | Strategic Future Planning | 281023 |  | 120371
2022-08-01 | August 2022 Review | Cash flow adjustment | Public transport infrastructure | Passenger facilities and infrastructure improvements - rail | KiwiRail | WMUP 5 â€“ Wellington Rail Network Resignalling Renewal | Detailed Business Case |  | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update 2021/22 actuals. Unclaimed funds carried forward. | 0 | 0 |  |  |  | 1.2 |  | 281028 |  | 120372
2022-08-01 | August 2022 Review | Cash flow adjustment | Public transport infrastructure | Passenger facilities and infrastructure improvements - rail | KiwiRail | WMUP 7 â€“ Further capacity improvements beyond current | Single-Stage Business Case | WMUP 7 Capacity Improvements PBC | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update 2021/22 actuals. Unclaimed funds carried forward. | 0 | 0 |  |  |  | 1 |  | 281029 |  | 120373
2022-08-19 | August 2022 Review | Cash flow adjustment | External funding | Property purchase (State highways) | NZTA (Otago) | NZUP Queenstown Package | Property | NZ Upgrade Programme | M_M | MHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow only to match re-forecast of programme | 0 | 0 |  |  | 3.5 | 3.5 | NZ Upgrade Programme | 259376 | 60057045 | 120451
2022-08-19 | August 2022 Review | Cash flow adjustment | Walking and cycling improvements | Property purchase (State highways) | NZTA (Otago) | Wakatipu Walking/Cycling Network Improvements | Property | NZTA Package 331 | HHL | HMM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow only to match reforecast of programme | 0 | 0 |  |  | 2.6 | 2.6 |  | 280902 | 60052907 | 120454
2022-08-16 | August 2022 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Wellington) | Wellington RoNS (5) - Transmission Gully | Property |  | H_L | H_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Restore C-funds to 2020/21 | 0 | 0 |  |  | 1.4 | 1.4 | 60450642 | 194475 | 60450642 | 120546
2022-08-16 | August 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Taranaki/ Wallace/ John Sts | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 0 | 0 |  |  | 1.2 | 1 |  | 280362 | 60066155 | 120568
2022-08-16 | August 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS BPAP Targeted Imp. | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update 3rd Party Contribution for 2021-22. And spent to match SAP-PPM. | 0 | 0 |  |  | 1.2 | 1 |  | 280357 | 60065973 | 120479
2022-08-16 | August 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Newtown to Berhampore | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 0 | 0 |  |  | 1.2 | 1 |  | 280368 | 60066166 | 120565
2022-08-16 | August 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Bus Network Advice | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 0 | 0 |  |  | 1.2 | 1 |  | 280359 | 60065976 | 120558
2022-08-16 | August 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM Early Delivery Thorndon Quay and Hutt Road | Single-Stage Business Case | Thorndon Quay and Hutt Road | VHHL | VHHH | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 0 | 0 |  |  | 1.2 | 1 |  | 282067 | 60067841 | 120571
2022-08-16 | August 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport facilities & infrastructure - renewals | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS CBD to Kilbirnie and Miramar | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 0 | 0 |  |  | 1.2 | 1 |  | 280363 | 60066135 | 120564
2022-08-16 | August 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport facilities & infrastructure - renewals | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Hamilton Rd to Shelly Bay Rd | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 0 | 0 |  |  | 1.2 | 1 |  | 280366 | 60066163 | 120560
2022-08-16 | August 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport facilities & infrastructure - renewals | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Tar St and CBD to Newtown | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update spend for 2021-22. | 0 | 0 |  |  | 1.2 | 1 |  | 280361 | 60066154 | 120478
2022-08-16 | August 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport facilities & infrastructure - renewals | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS General Targeted Imp. | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 0 | 0 |  |  | 1.2 | 1 |  | 280365 | 60066161 | 120566
2022-08-16 | August 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport facilities & infrastructure - renewals | NZTA (Wellington) | LGWM Early Delivery Golden Mile | Pre-implementation* | Golden Mile Pre-Implementation | VHMM | VHHM | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 0 | 0 |  |  | 1.2 | 1 |  | 267815 | 60054793 | 120477
2022-08-19 | August 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport infrastructure and major renewals | Auckland Transport | NCI - Rosedale Station and Assoc. Local Road Improvements | Implementation | NCI - Rosedale PT Components - IMP | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Correcting the cashflow for this activity as an interim change while final cost details are understood and the discussed CSA is actioned. The delays are due to AT now reconsidering the procurement for this activity outside of the NCI Alliance with Waka Kotahi. | 0 | -1 |  |  | 0 | 1.1 | 531.2384 | 238358 |  | 120486
2022-08-05 | August 2022 Review | Cash flow adjustment | External funding | Road improvements | NZTA (BOP) | CIP SH30 Eastern Corridor, Rotorua | Construction | Crown Infrastructure Partners | M_M | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Bringing forward $1.5 M from Y1 to CFY to accomodate Physical works | 0 | 0 |  |  | 0 | 4.1 |  | 271547 | 60059176 | 120309
2022-08-19 | August 2022 Review | Cash flow adjustment | External funding | Road improvements | NZTA (Canterbury) | NZUP SH1 Tinwald Corridor Improvements | Single-Stage Business Case | NZ Upgrade Programme | VHHL | MMM | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  | 4.6 | 4.6 | 60057075 | 246649 | 60057075 | 120384
2022-08-19 | August 2022 Review | Cash flow adjustment | External funding | Road improvements | NZTA (Otago) | NZUP Queenstown Package | Implementation | NZUP Grant Rd to KF Bridge Improvements | M_M | MHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow only to match reforecast of programme | 0 | 0 |  |  | 3.5 | 3.5 | 60057044 | 259377 | 60057044 | 120450
2022-08-19 | August 2022 Review | Cash flow adjustment | External funding | Road improvements | NZTA (Otago) | NZUP Queenstown Package | Implementation |  | M_M | MHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow only to match re-forecast of programme | 0 | 0 |  |  | 3.5 | 3.5 |  | 278964 | 60063228 | 120440
2022-08-19 | August 2022 Review | Cash flow adjustment | External funding | Road improvements | NZTA (Otago) | NZUP Queenstown Package | Pre-implementation* | NZ Upgrade Programme | M_M | MHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow only to match re-forecast of programme | 0 | 0 |  |  | 3.5 | 3.5 | 60057043 | 259356 | 60057043 | 120449
2022-08-19 | August 2022 Review | Cash flow adjustment | External funding | Road improvements | NZTA (Southland) | CIP SH94 Homer Tunnel | Implementation | CIP SH94 Homer Tunnel | H_M | M_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflowing $1809432 from current CY to furture years as per forecasts | 0 | 0 |  |  | 0 | 0 |  | 275306 | 60059181 | 120455
2022-08-31 | August 2022 Review | Cash flow adjustment | External funding | Road improvements | NZTA (Wellington) | NZUP SH2 Melling Efficiency & Safety Imp | Implementation | SH2 Melling Efficiency & Safety Imp NZUP | HMM | MMH | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please move $20 million to 2026 and $20 million to 2027 The reason is delay of physical works | 0 | 0 |  |  | 0 | 1.3 | NZ Upgrade Programme | 270320 | 60218122 | 120787
2022-08-19 | August 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Wellington) | Peka Peka to Otaki Revocation | Implementation | Peka Peka to Otaki Revocation | H_L | M_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please move $5,635,883 from CY to Y1 (2023/24) and $5,800,000 from CY to Y2 (2024/25) to align with the revised construction programme. | 1 | 1 |  |  | 0.6 | 0.6 | 60049936 | 271841 | 60049936 | 120590
2022-08-01 | August 2022 Review | Cash flow adjustment | Coastal shipping | Sea freight operations | NZ Transport Agency | Coastal Shipping - 2021-24 | Implementation | Coastal Shipping - OPEX | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow from 2023/24 to 2022/23. | 0 | 0 |  |  | 1 | 1 | 60067633 | 280818 |  | 120347
2022-08-19 | August 2022 Review | Cash flow adjustment | Local road maintenance | Sealed pavement maintenance | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Redistribution of the carry forward budgets in TIO of $3,581,959 out of WC111 to various wc. Cash neutral amendments. | -3583159 | -2472380 | [5 empty] | 272519 |  | 120487
2022-08-19 | August 2022 Review | Cash flow adjustment | Local road maintenance | Sealed road pavement rehabilitation | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Redistribution of the carry forward budgets in TIO of $3,581,959 out of WC111 to various wc. Cash neutral amendments. | 465141 | 320947 | [5 empty] | 272534 |  | 120487
2022-08-19 | August 2022 Review | Cash flow adjustment | Local road maintenance | Sealed road resurfacing | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Redistribution of the carry forward budgets in TIO of $3,581,959 out of WC111 to various wc. Cash neutral amendments. | 56857 | 39231 | [5 empty] | 272532 |  | 120487
2022-08-19 | August 2022 Review | Cash flow adjustment | Local road maintenance | Structures component replacements | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Redistribution of the carry forward budgets in TIO of $3,581,959 out of WC111 to various wc. Cash neutral amendments. | 898317 | 619839 | [5 empty] | 272535 |  | 120487
2022-08-19 | August 2022 Review | Cash flow adjustment | Local road maintenance | Traffic services renewals | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Redistribution of the carry forward budgets in TIO of $3,581,959 out of WC111 to various wc. Cash neutral amendments. | 64437 | 44462 | [5 empty] | 272538 |  | 120487
2022-08-19 | August 2022 Review | Cash flow adjustment | Local road maintenance | Unsealed road metalling | Far North District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Redistribution of the carry forward budgets in TIO of $3,581,959 out of WC111 to various wc. Cash neutral amendments. | 654848 | 451846 | [5 empty] | 272531 |  | 120487
2022-08-16 | August 2022 Review | Cash flow adjustment | Walking and cycling improvements | Walking facilities | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Featherston St | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -1 | -1 |  |  | 1.2 | 1 |  | 280364 | 60066160 | 120561
2022-08-01 | August 2022 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Christchurch City Council | CCP Lichfield Street (Madras to Manchester) (SfP) | Pre-implementation* | SFP Development of Application | HMM | HHM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update 2022/23 FAR | 0 | 140201 |  |  |  | 4.1 |  | 281399 |  | 120349
2022-08-15 | August 2022 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | NZTA (Canterbury) | 2021-24 NLTP funds management | Repayment | AC3 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds Management | -421279 | -421279 | [5 empty] | 279054 |  | 120512
2022-08-15 | August 2022 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | NZTA (Hawkes Bay) | 2021-24 NLTP funds management | Repayment | AC3 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds management | -1418365 | -1418365 | [5 empty] | 279095 |  | 120514
2022-08-15 | August 2022 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | NZTA (Manawatu/Whanganui) | 2021-24 NLTP funds management | Repayment | AC3 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Remove offset | -1225890 | -1225890 | [5 empty] | 279097 |  | 120516
2022-08-15 | August 2022 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | NZTA (Tasman) | 2021-24 NLTP funds management | Repayment | AC3 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds management | -903152 | -903152 | [5 empty] | 279274 |  | 120525
2022-08-15 | August 2022 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | NZTA (Waikato) | 2021-24 NLTP funds management | Repayment | AC3 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds management | -1552170 | -1552170 | [5 empty] | 279276 |  | 120527
2022-08-15 | August 2022 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | NZTA (Wellington) | 2021-24 NLTP funds management | Repayment | AC3 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds management | -317958 | -317958 | [5 empty] | 279278 |  | 120528
2022-08-11 | August 2022 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | NZTA (Wellington) | Petone to Melling Walking Cycling Link | Implementation | Implementation - NLTF | HHVL | HHL | N | 9 | Approved | Approved by Chief Financial Officer (CFO) | Covid 2021 Claim, Cost increase of $259,310.62 | 280056 | 280056 |  |  | 0 | 2.5 | 60045916 | 250462 | 60045916 | 120381
2022-08-01 | August 2022 Review | Cost Increase | Local road maintenance | Emergency works | DOC (Waikato) | Kauaeranga Road Outlook 76 Slip June 2020 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds to be reinstated that was surplused during annual close. | 171987 | 87713 |  |  |  |  | Design & construction of road reinstatement | 270640 |  | 120366
2022-08-26 | August 2022 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Northland) | EW Northland HR 20220321 | Construction |  | ___ |  | N |  | Approved | Approved by System Manager, Maintenance and Operations (Transport Services) | Structures work was reviewed following investigation and final solution was 50% of original estimate so Application is significantly less than the $1.4M on te initial acceptance form. There are 2 of the roading projects programmed to be completed in 22/23 with est of $150K with the remained for the rail overbridge PM I am content that this application is in line the guidance provided in PIKB and recommend Approval. NAC | 993598 | 993598 | [5 empty] | 281442 | 60067364 | 120687
2022-08-01 | August 2022 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Otago) | EW SH6 Kawarua Gorge Underslip 20210823 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The project spent money after it was closed. It increased from $96,056 to $120,721 | 26639 | 26639 | [5 empty] | 279778 | 60065047 | 120346
2022-08-11 | August 2022 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Tasman) | EW Region 10 SH60 Takaka Hill Feb 2018 | Construction |  | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) |  | 131946 | 131946 |  |  |  |  | 60049083 | 264335 | 60049083 | 120465
2022-08-02 | August 2022 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Waikato) | EW SH30 Whakamaru Hvy Rain 20201221 | Construction |  | ___ |  | N |  | Approved | Approved by National Manager, Maintenance and Operations (Transport Services) | I am content that the event fit the requirements of PIKB and therefore recommend approval. There have been some complications caused by a breakdown in communications between the supplier designer and the project manager which has led to delays in completion. The issues around compliance need to be addressed at the design stage and not post construction. Itâ€™s a shame that we lost the opportunity to influence the outcome and reduce the cost increase. NAC Agree â€“ this meets the conditions for EW on PIKB and it is clear the project had some complications. HH | 828206 | 828206 | [5 empty] | 275425 | 60060023 | 120360
2022-08-19 | August 2022 Review | Cost Decrease | Local road maintenance | Emergency works | Thames-Coromandel District Council | June 2018 Storm Event | Construction | Completion | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2022/23 as activity is claiming complete | -91939 | -46889 |  |  |  |  | Event response and reinstatement (2) (Normal FAR) | 279936 |  | 120583
2022-08-19 | August 2022 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | Manawatu District Council | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Due to community's feedback, the existing walking and cycling programme was on-hold, the only one that continues is the North St section ($300K), to completed the project that started in last financial year. MDC has requested to use Te Araroa Trail Improvement Project as the substitute project, this is estimated $600k, and any surplus will carry over to financial year 23/24, for the walking and cycling projects that yet to be confirmed. | 0 | -940 | [5 empty] | 276219 |  | 120532
2022-08-19 | August 2022 Review | Cost Decrease | Local road improvements | Low cost / low risk improvements | Rangitikei District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The current NZTA approved 2022-23 LCLR budget is $ 6,549,092. The likely expenditure estimated for FY 22/23 is $ 3,449,092. The difference will be part cash forwarded to FY 23/24, $1.1M, and part declared surplus, $2M. The current NZTA approved 2023/24 LCLR budget is $1,875,300 plus the carry forward of $1,100,000 from 2022/23 = $2,975,300. By December 2022 we will assess what the realistic expenditure will be and declare any surplus that is not required in that year. | -2000000 | -1291000 | [5 empty] | 276367 |  | 120474
2022-08-15 | August 2022 Review | Cost Increase | State highway maintenance | Network and asset management | NZTA (Canterbury) | 2021-24 NLTP funds management | Repayment | AC9 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds Management | 3001681 | 3001681 | [5 empty] | 279053 |  | 120511
2022-08-15 | August 2022 Review | Cost Increase | State highway maintenance | Network and asset management | NZTA (Manawatu/Whanganui) | 2021-24 NLTP funds management | Repayment | AC9 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds management | 71829 | 71829 | [5 empty] | 279096 |  | 120517
2022-08-15 | August 2022 Review | Cost Increase | State highway maintenance | Network and asset management | NZTA (Tasman) | 2021-24 NLTP funds management | Repayment | AC9 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds management | 1359029 | 1359029 | [5 empty] | 279273 |  | 120524
2022-08-15 | August 2022 Review | Cost Increase | State highway maintenance | Network and asset management | NZTA (West Coast) | 2021-24 NLTP funds management | Repayment | AC9 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds management | 1328251 | 1328251 | [5 empty] | 279279 |  | 120530
2022-08-19 | August 2022 Review | Cost Decrease | State highway improvements | New roads | NZTA (Auckland) | Hobsonville Deviation | Construction |  | M_M | M_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Completion of the DLP | -297413 | -297413 |  |  | 0 |  | 60201428 | 180375 | 60201428 | 120464
2022-08-19 | August 2022 Review | Cost Decrease | State highway improvements | New roads | NZTA (Canterbury) | CHCH Northern Arterial Rural with QE2 | Detailed Business Case | System wide TBM & HOV/PT Lane | H_M | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | DBC was completed in June 2019, returning surplus $46923 | -50677 | -50677 |  |  | 2.3 | 2.3 |  | 264604 | 60050017 | 120535
2022-08-11 | August 2022 Review | Cost Increase | State highway improvements | New roads | NZTA (Manawatu/Whanganui) | Te Ahu a Turanga; ManawatÅ« Tararua Highway | Implementation | Implementation | H__ | H__ | N | 0 | Approved | Approved by Chief Financial Officer (CFO) |  | 3320719 | 3320719 |  |  | 0 | 1.4 | 60051305 | 258476 | 60051305 | 120383
2022-08-04 | August 2022 Review | Cost Decrease | State highway improvements | New traffic management facilities | NZTA (Auckland) | AKL ITS Improvement Programme (TransportOS) | Implementation |  | H_H | VH_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update remaining funding to match SAP-PPM | -1876918 | -1876918 |  |  | 5.1 | 5.1 |  | 255177 | 60052226 | 120426
2022-08-04 | August 2022 Review | Cost Decrease | State highway improvements | New traffic management facilities | NZTA (BOP) | BOP ITS Improvement Programme (TransportOS) | Implementation | 60052226 | H_H | VH_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update remaining funding to match SAP-PPM | -434011 | -434011 |  |  | 5.1 | 5.1 |  | 254905 |  | 120427
2022-08-04 | August 2022 Review | Cost Decrease | State highway improvements | New traffic management facilities | NZTA (Canterbury) | CAN ITS Improvement Programme (TransportOS) | Implementation |  | H_H | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update remaining funding to match SAP-PPM | -1302032 | -1302032 |  |  | 5.1 | 5.1 | 60052226 | 254804 |  | 120428
2022-08-19 | August 2022 Review | Cost Decrease | State highway improvements | New traffic management facilities | NZTA (Canterbury) | Lyttelton Tunnel Safety Retrofit (Deluge) System | Implementation | Construction | H_PV_EoL | H_VH | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Releasing surplus contingency. | -50092 | -50092 |  |  | 0 | 99 | 60214782 | 199241 | 60214782 | 120447
2022-08-04 | August 2022 Review | Cost Decrease | State highway improvements | New traffic management facilities | NZTA (Otago) | OTA ITS Improvement Programme (TransportOS) | Implementation |  | H_H | VH_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update remaining funding to match SAP-PPM | -434010 | -434010 |  |  | 5.1 | 5.1 | 60052226 | 254839 |  | 120429
2022-08-04 | August 2022 Review | Cost Decrease | State highway improvements | New traffic management facilities | NZTA (Waikato) | WAI ITS Improvement Programme (TransportOS) | Implementation | Implementation | H_H | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update remaining funding to match SAP-PPM | -434011 | -434011 |  |  | 5.1 | 5.1 | 60052226 | 254649 |  | 120430
2022-08-04 | August 2022 Review | Cost Decrease | State highway improvements | New traffic management facilities | NZTA (Wellington) | WGN ITS Improvement Programme (TransportOS) | Implementation |  | H_H | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update remaining funding to match SAP-PPM | -1876917 | -1876917 |  |  | 5.1 | 5.1 |  | 263146 |  | 120431
2022-08-19 | August 2022 Review | Cost Decrease | Public transport services | Passenger services - bus | Otago Regional Council | Wakatipu Basin Public Transport | Implementation | Service Operation | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2022/23 as activity is claiming complete | -166413 | -84871 |  |  | 2.7 | 1 | Year one of service operation | 250476 |  | 120533
2022-08-05 | August 2022 Review | Cost Decrease | State highway improvements | Property purchase (State highways) | NZTA (Canterbury) | Harewood Rd to Yaldhurst Rd 4 Laning | Property | Property | H_M | H_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Returning surplus $8835 b/c release of contingency | -9321 | -9321 |  |  | 1.5 | 1.5 | 60465152 | 212337 | 60465152 | 120357
2022-08-19 | August 2022 Review | Cost Decrease | State highway improvements | Property purchase (State highways) | NZTA (Canterbury) | Mingha Bluff to Rough Creek | Property | Property | M_L | M_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Returning surplus from original survey costs are now funded from a seperate budget | -206450 | -206450 |  |  | 1.1 | 1.1 | 60460952 | 205265 | 60460952 | 120448
2022-08-05 | August 2022 Review | Cost Increase | External funding | Property purchase (State highways) | NZTA (Canterbury) | NZUP SH73 Weedons-Ross Road Intersection | Property | NZ Upgrade Programme | H_L | HML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $48,821 from 60031530 (Pre-Imp) to 60057040 (Property) to cover Property phase shortfall. | 50530 | 50530 |  |  | 1.2 | 1.2 | 60057040 | 270360 | 60057040 | 120435
2022-08-19 | August 2022 Review | Cost Decrease | External funding | Property purchase (State highways) | NZTA (Hawkes Bay) | Waikare Gorge | Property | PGF | H__ | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please move $2,082,956 from 60056381 - Property Phase to 60056380 - Pre-Implementation phase, due to a change in Property strategy from acquisition to designation | -2082956 | -2082956 |  |  | 0 | 1.3 | Property | 269816 | 60056381 | 120589
2022-08-18 | August 2022 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Northland) | SH1N - Brynderwyn North Safe System Project | Property | Large | H_H | HHH | N |  | Approved | Approved by Chief Financial Officer (CFO) |  | 110959 | 110959 |  |  | 4.2 | 7.3 | 60460682 | 215268 | 60460682 | 120470
2022-08-01 | August 2022 Review | Cost Increase | Local road improvements | Property purchase (local roads) | Auckland Transport | Matakana Link Road | Property | Matakana Link Road - PROPERTY | HHH | MHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update 2022/23 FAR | 0 | 5035656 |  |  | 0 | 7.7 | 332.2492 | 249232 |  | 120350
2022-08-05 | August 2022 Review | Cost Decrease | Local road improvements | Property purchase (local roads) | Hamilton City Council | 2018-28 Rototuna Growth - Borman Rd East/Horsham Downs | Property |  | HML | MHM | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2022/23 as activity is claiming complete | -3709 | -1892 |  |  | 1.1 | 1.1 |  | 257329 |  | 120329
2022-08-16 | August 2022 Review | Cost Decrease | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Johnsonville/ Ngauranga | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 0 | -818371 |  |  | 1.2 | 1 |  | 280367 | 60066164 | 120562
2022-08-16 | August 2022 Review | Cost Increase | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS CBD Modelling | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Total includes 3rd party funding. | 117688 | 8717 |  |  | 1.2 | 1 |  | 280360 | 60065977 | 120575
2022-08-16 | August 2022 Review | Cost Increase | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Johnsonville/ Ngauranga | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Correct 3rd party funding | 0 | 818371 |  |  | 1.2 | 1 |  | 280367 | 60066164 | 120572
2022-08-16 | August 2022 Review | Cost Increase | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS CBD Modelling | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 0 | 108971 |  |  | 1.2 | 1 |  | 280360 | 60065977 | 120567
2022-08-16 | August 2022 Review | Cost Increase | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Bus Network Advice | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Correct approved funding | 335686 | 335686 |  |  | 1.2 | 1 |  | 280359 | 60065976 | 120573
2022-08-16 | August 2022 Review | Cost Increase | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Newtown to Berhampore | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Correct total funding. | 1173449 | 1173449 |  |  | 1.2 | 1 |  | 280368 | 60066166 | 120578
2022-08-16 | August 2022 Review | Cost Increase | Public transport infrastructure | Public transport facilities & infrastructure - renewals | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Hamilton Rd to Shelly Bay Rd | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Correct total approved funding. | 169418 | 169418 |  |  | 1.2 | 1 |  | 280366 | 60066163 | 120576
2022-08-16 | August 2022 Review | Cost Decrease | Public transport infrastructure | Public transport infrastructure and major renewals | NZTA (Wellington) | LGWM Early Delivery Golden Mile | Single-Stage Business Case | Golden Mile | VHMM | VHHM | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 0 | -1021096 |  |  | 1.2 | 1 |  | 282066 | 60067843 | 120570
2022-08-22 | August 2022 Review | Cost Decrease | Public transport infrastructure | Public transport infrastructure and major renewals | NZTA (Wellington) | LGWM Early Delivery Golden Mile | Single-Stage Business Case | Golden Mile | VHMM | VHHM | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update 3rd Party for 2021-22. | 0 | -28946 |  |  | 1.2 | 1 |  | 282066 | 60067843 | 120587
2022-08-19 | August 2022 Review | Cost Decrease | Public transport infrastructure | Public transport infrastructure and major renewals | Otago Regional Council | PT - Inter-Regional Ticketing Improvement - Otago | Implementation | Implementation of ticketing | H_PV_EoL | H__ | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2022/23 as activity is claiming complete | -2024135 | -1315688 |  |  | 0 | 0 |  | 235173 |  | 120534
2022-08-01 | August 2022 Review | Cost Decrease | Rail network | Rail network and asset management | KiwiRail | Rail Network Investment Programme 2021-24 Freight & Tourism | Implementation | First RNIP Period | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Remove crown funding from total, remaining is NLTF only. Update 2021/22 actuals. | 0 | -834400000 |  |  | 1 | 1 | National Freight and Tourism Network | 281083 |  | 120374
2022-08-31 | August 2022 Review | Cost Increase | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH26 Kirikiri Stream Bridge Replacement | Implementation | SH 26 Kirikiri Stream Bridge Replacement Construct | M__ | M__ | N | 0 | Approved | Approved by Chief Financial Officer (CFO) |  | 9428328 | 9428328 |  |  | 99 | 99 | 60031830 | 256636 | 60031830 | 120452
2022-08-12 | August 2022 Review | Cost Decrease | Local road improvements | Resilience improvements | Auckland Transport | Kepa Road Slip Remediation Improvements | Single-Stage Business Case | SSBC - Kepa Road Slip Remediation Improvement | LLL | HHH | Y | 4 | Approved | Approved by Auckland Transport Chief Financial Officer |  | -31320 | -15973 |  |  |  | 4.3 | 357.2776 | 277593 |  | 120483
2022-08-19 | August 2022 Review | Cost Decrease | Local road improvements | Road improvements | Auckland Transport | AKL Network Optimisation | Single-Stage Business Case | Auckland Network Optimisation - SSBC | MHM | MHM | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This activity is now complete so declaring balance surplus. | -47727 | -24341 |  |  |  | 3.2 | 324.2692 | 269231 |  | 120485
2022-08-19 | August 2022 Review | Cost Decrease | Local road improvements | Road improvements | Auckland Transport | Auckland Smarter Transport Pricing | Detailed Business Case | Detailed Business Case | H__ | H__ | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This activity is now complete so declaring balance surplus. | -785088 | -400395 |  |  | 0 | 1 | 324.2509 | 250896 |  | 120484
2022-08-19 | August 2022 Review | Cost Decrease | Local road improvements | Road improvements | Auckland Transport | East West Connections | Implementation | Early Works (ii) FN32 (Road Components) | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Auckland Transport does not have local share to complete the final elements of the activity - around the cycling, and these no longer align with the latest cycling network plans and so the balance of this activity is now being declared surplus. | -4134313 | -2108500 |  |  | 1.5 | 1.5 | 324.2492 | 249192 |  | 120481
2022-08-15 | August 2022 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Auckland) | 2021-24 NLTP funds management | Repayment | AC13 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds Management | 2300735 | 2300735 | [5 empty] | 278954 |  | 120507
2022-08-02 | August 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (Auckland) | NZUP SH22 (Drury) Corridor Upgrade | Property |  | MML | MML | N | 9 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This NZUP SH22 Property phase 60067769 was created with incorrect Work Category. Request phase be closed and all funding transferred to new Property phase (60067986). | -18000000 | -18000000 |  |  |  | 1.7 |  | 281987 | 60067769 | 120376
2022-08-02 | August 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (Auckland) | NZUP Waihoehoe Road (Drury) Upgrade | Property |  | MML | MML | N | 9 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This NZUP Waihoehoe Rd Property phase was created with incorrect Work Category. Requesting this phase be closed and all funding be transferred to new Property phase (60067985). | -24000000 | -24000000 |  |  |  | 1.8 |  | 281989 | 60067771 | 120377
2022-08-15 | August 2022 Review | Cost Increase | State highway improvements | Road improvements | NZTA (BOP) | 2021-24 NLTP funds management | Repayment | AC13 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds Management | 1552191 | 1552191 | [5 empty] | 278955 |  | 120509
2022-08-31 | August 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (BOP) | SH2 Waihi - Omokoroa (Katikati-Omokoroa) | Pre-implementation* |  | VHHL | HHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | aligning TIO with SAP & close project | -676181 | -676181 |  |  | 0 | 1.6 |  | 269999 | 60062216 | 120790
2022-08-15 | August 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Canterbury) | 2021-24 NLTP funds management | Repayment | AC13 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds Management | -7960517 | -7960517 | [5 empty] | 279052 |  | 120510
2022-08-05 | August 2022 Review | Cost Increase | External funding | Road improvements | NZTA (Canterbury) | NZUP Brougham St Corridor Improvements | Detailed Business Case | NZ Upgrade Programme | H_L | HMM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $26,819 from 60032126 (Pre-Imp) to 60057015 (DBC) to cover overspend. | 27758 | 27758 |  |  | 4 | 4 | 60057015 | 246831 | 60057015 | 120365
2022-08-05 | August 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (Canterbury) | NZUP Brougham St Corridor Improvements | Pre-implementation* | NZ Upgrade Programme | H_L | HMM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $26,819 from 60032126 (Pre-Imp) to 60057015 (DBC) to cover overspend. | -27758 | -27758 |  |  | 4 | 4 | 60032126 | 231599 | 60032126 | 120361
2022-08-05 | August 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (Canterbury) | NZUP SH73 Weedons-Ross Road Intersection | Detailed Business Case | NZ Upgrade Programme | H_L | HML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $1,250 from 60031529 (DBC) to 60031531 (Imp) to transfer back unused allocation. | -1294 | -1294 |  |  | 1.2 | 1.2 |  | 263131 | 60031529 | 120436
2022-08-05 | August 2022 Review | Cost Increase | External funding | Road improvements | NZTA (Canterbury) | NZUP SH73 Weedons-Ross Road Intersection | Implementation | NZ Upgrade Programme | H_L | HML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $1,250 from 60031529 (DBC) to 60031531 (Imp) to transfer back unused allocation. | 1293 | 1293 |  |  | 1.2 | 1.2 | 60031531 | 239003 | 60031531 | 120438
2022-08-05 | August 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (Canterbury) | NZUP SH73 Weedons-Ross Road Intersection | Pre-implementation* | NZ Upgrade Programme | H_L | HML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $48,821 from 60031530 (Pre-Imp) to 60057040 (Property) to cover Property phase shortfall. | -50530 | -50530 |  |  | 1.2 | 1.2 | 60031530 | 239002 | 60031530 | 120437
2022-08-05 | August 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (Canterbury) | NZUP Walnut Avenue Intersection Improvements | Implementation |  | M_L | MHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $1.1m from 60067420 (Construction - Ops) to 60211591 (Construction) to transfer back allocations from OPEX phase as it will not be used. | -1138500 | -1138500 |  |  | 1.8 | 1.8 |  | 281545 | 60067420 | 120411
2022-08-05 | August 2022 Review | Cost Increase | External funding | Road improvements | NZTA (Canterbury) | NZUP Walnut Avenue Intersection Improvements | Implementation | NZ Upgrade | M_L | MHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $1.1m from 60067420 (Construction - Ops) to 60211591 (Construction) to transfer back allocations from OPEX phase as it will not be used. | 1138500 | 1138500 |  |  | 1.8 | 1.8 | 60211591 | 231796 | 60211591 | 120363
2022-08-05 | August 2022 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (Canterbury) | SH1 Ashley to Belfast - (SH71 to Tram Rd) | Implementation |  | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Returning surplus for 22/23 FY of $118,756 | -128256 | -128256 |  |  | 0 | 1.6 |  | 278552 | 60062296 | 120351
2022-08-05 | August 2022 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (Canterbury) | SH1 Ashley to Belfast SSI (William St to SH71) | Implementation | R2Z | M_L | HHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Returning surplus $100,788 22/23 | -108851 | -108851 |  |  | 0 | 1.6 |  | 278546 | 60062298 | 120352
2022-08-15 | August 2022 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Hawkes Bay) | 2021-24 NLTP funds management | Repayment | AC13 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds management | 114094 | 114094 | [5 empty] | 279094 |  | 120515
2022-08-19 | August 2022 Review | Cost Increase | External funding | Road improvements | NZTA (Hawkes Bay) | Waikare Gorge | Pre-implementation* | PGF | H__ | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please move $2,082,956 from 60056381 - Property Phase to 60056380 - Pre-Implementation phase, due to a change in Property strategy from acquisition to designation | 2082956 | 2082956 |  |  | 0 | 1.3 | Pre-implementation | 265583 | 60056380 | 120588
2022-08-11 | August 2022 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Manawatu/Whanganui) | Otaki to North Levin - SH1/57 - southern section | Implementation |  | VHHL | HHVH | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 142347 | 142347 |  |  | 0 | 1.6 |  | 278530 | 60062283 | 120380
2022-08-23 | August 2022 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Manawatu/Whanganui) | SH1 Bulls to Sanson CI - Pukenui Rd IS | Pre-implementation* |  | MMH | HHL | N | 6 | Approved | Approved by Chief Financial Officer (CFO) |  | 80000 | 80000 |  |  | 0 | 1.6 |  | 278538 | 60062280 | 120559
2022-08-15 | August 2022 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Northland) | 2021-24 NLTP funds management | Repayment | AC13 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds management | 380129 | 380129 | [5 empty] | 279232 |  | 120518
2022-08-22 | August 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (Northland) | RIO SH11 & SH10 Puketona RND | Implementation | Implementation | M_H | HMM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please move $848 from Construction (60055987) to Pre-Imp (60055986) to cover overspend | -848 | -848 |  |  | 1 | 1 | 60055987 | 236536 | 60055987 | 120647
2022-08-22 | August 2022 Review | Cost Increase | External funding | Road improvements | NZTA (Northland) | RIO SH11 & SH10 Puketona RND | Pre-implementation* | Design (Refresh) | M_H | HMM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please move $848 from Construction (60055987) to Pre-Imp (60055986) to cover overspend | 848 | 848 |  |  | 1 | 1 | 60055986 | 236535 | 60055986 | 120646
2022-08-24 | August 2022 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (Northland) | SH1 Whangarei to Wellsford - (Central Section) | Property |  | VHML | HHM | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -2730262 | -2730262 |  |  | 0 | 1.6 |  | 280683 | 60066689 | 120666
2022-08-18 | August 2022 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Northland) | SH1N - Brynderwyn North Safe System Project | Construction | Brynderwyn North SSDP | H_H | HHH | N |  | Approved | Approved by Chief Financial Officer (CFO) |  | 59400 | 59400 |  |  | 4.2 | 7.3 | 60216185 | 214650 | 60216185 | 120469
2022-08-05 | August 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (Southland) | CIP SH94 Homer Tunnel | Implementation | CIP SH94 Homer Tunnel | H_M | M_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer from Imp 60059181 to Pre Imp 60059180 to of $161,883 as addtional work was required in Pre Imp phase. | -161883 | -161883 |  |  | 0 | 0 |  | 275306 | 60059181 | 120386
2022-08-22 | August 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (Southland) | CIP SH94 Homer Tunnel | Implementation | CIP SH94 Homer Tunnel | H_M | M_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer from 60059181 to 60059181 due incresed cost in pre imp due to delays from DoC | -739333 | -739333 |  |  | 0 | 0 |  | 275306 | 60059181 | 120649
2022-08-05 | August 2022 Review | Cost Increase | External funding | Road improvements | NZTA (Southland) | CIP SH94 Homer Tunnel | Pre-implementation* | CIP SH94 Homer Tunnel | H_M | M_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer from Imp 60059181 to Pre Imp 60059180 to of $161,883 as addtional work was required in Pre Imp phase. | 161883 | 161883 |  |  | 0 | 0 | CIP SH94 Homer Tunnel | 275305 | 60059180 | 120385
2022-08-22 | August 2022 Review | Cost Increase | External funding | Road improvements | NZTA (Southland) | CIP SH94 Homer Tunnel | Pre-implementation* | CIP SH94 Homer Tunnel | H_M | M_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer from 60059181 to 60059180 to cover increase costs for Pre Imp, due to delays from DoC | 739333 | 739333 |  |  | 0 | 0 | CIP SH94 Homer Tunnel | 275305 | 60059180 | 120648
2022-08-05 | August 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Taranaki) | SH3 Awakino Gorge to Mt Messenger Corridor | Pre-implementation* | Pre Imp- Mt Messenger to Awakino Gorge Corridor | M_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -363 | -363 |  |  | 1.5 | 1.5 | 60032594 | 234956 | 60032595 | 120382
2022-08-15 | August 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Tasman) | 2021-24 NLTP funds management | Repayment | AC13 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds management | -45717 | -45717 |  |  |  |  | Ac13 | 279272 |  | 120523
2022-08-15 | August 2022 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Waikato) | 2021-24 NLTP funds management | Repayment | AC13 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds management | 19735111 | 19735111 | [5 empty] | 279275 |  | 120526
2022-08-18 | August 2022 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Waikato) | SH1 Taupo Airport to Hatepe | Pre-implementation* |  | VHHL | HHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) |  | 1590000 | 1590000 |  |  | 0 | 1.6 |  | 278495 | 60062215 | 120308
2022-08-05 | August 2022 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (Waikato) | SH27 Mangawhero Bridge | Implementation |  | HML | HHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project under budget | -554023 | -554023 |  |  | 2.1 | 2.1 |  | 278478 | 60062210 | 120434
2022-08-15 | August 2022 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Wellington) | 2021-24 NLTP funds management | Repayment | AC13 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds management | 1785256 | 1785256 | [5 empty] | 279277 |  | 120529
2022-08-05 | August 2022 Review | Cost Decrease | Local road improvements | Road improvements | Waikato District Council | River Rd/Horotiu Bridge Rd Intersection Safety Improvements | Construction | Implementation | H_L | H_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2022/23 as activity is claiming complete | -154334 | -117294 |  |  | 1.5 | 1.7 |  | 269252 |  | 120416
2022-08-05 | August 2022 Review | Cost Decrease | Local road improvements | Road improvements | Waikato District Council | River Rd/Horotiu Bridge Rd Intersection Safety Improvements | Implementation | speed management | H_L | H_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2022/23 as activity is claiming complete | -146085 | -111025 |  |  | 1.5 | 1.7 |  | 269253 |  | 120417
2022-08-05 | August 2022 Review | Cost Decrease | Local road improvements | Road improvements | Waikato District Council | River Rd/Horotiu Bridge Rd Intersection Safety Improvements | Pre-implementation* | detailed design | H_L | H_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2022/23 as activity is claiming complete | -12969 | -9856 |  |  | 1.5 | 1.7 |  | 269251 |  | 120415
2022-08-05 | August 2022 Review | Cost Decrease | Local road improvements | Road improvements | Waikato District Council | Taupiri Mangawara Stream Crossing | Implementation | Indicative, Detailed BC and Implementation | M_M | M_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2022/23 as activity is claiming complete | -86182 | -43953 |  |  | 3.7 | 3.7 |  | 239173 |  | 120418
2022-08-05 | August 2022 Review | Cost Decrease | Investment management (incl. Transport Planning) | Transport model development | NZTA (Waikato) | Rebuild Of Waikato Regional Transport Mo | Programme business case |  | H__ | H__ | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Surplus from last FY $196K | -196400 | -196400 |  |  |  |  | Investment Management activity class - Phase | 280318 | 60066190 | 120353
2022-08-16 | August 2022 Review | Cost Increase | Walking and cycling improvements | Walking facilities | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Featherston St | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Correct total funding. | 1180797 | 1180797 |  |  | 1.2 | 1 |  | 280364 | 60066160 | 120577
2022-08-16 | August 2022 Review | Cost Increase | Walking and cycling improvements | Walking facilities | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS South West CBD | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 1269588 | 689692 |  |  | 1.2 | 1 |  | 280699 | 60066730 | 120569
2022-08-16 | August 2022 Review | Cost Increase | Walking and cycling improvements | Walking facilities | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Bowen St | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Correct spend and approved funds to date. | 322466 | 322466 |  |  | 1.2 | 1 |  | 280358 | 60065975 | 120555
2022-08-16 | August 2022 Review | Cost Increase | Walking and cycling improvements | Walking facilities | NZTA (Wellington) | LGWM ED Central City and SH1 walking cycling and safer speed | Implementation | CCPI | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update 2021/22 to match SAP-PPM actuals. | 1479919 | 1479919 |  |  | 1.2 | 1 |  | 279815 | 60053806 | 120456
2022-08-09 | August 2022 Review | Support for programme business case |  |  | Dunedin City Council | Dunedin City and Hospital PBC | Support for PBC |  | H_L | H_L | N |  | Supported with conditions | Supported with conditions by Manager, Treasury & Cash Flow (Corporate Support) | Endorsed by Waka Kotahi Board on 24/11/2021 | 0 |  | That a review of the governance arrangements for work signalled for the recommended option in the Programme Business Case takes place to the satisfaction of the Waka Kotahi National Manager, System Design. |  |  |  |  | 266723 |  | 120460