## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Phase Label | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Decision Status | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR | Your Phase reference | TIO Phase id | SAP item id | TIO Request id
2022-09-12 | September 2022 Review | New approval | Investment management (incl. Transport Planning) | Activity management planning improvement | Bay of Plenty Regional Council | Activity Management Plan 2021-24 | Improvement to existing AMP |  | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Provision of an RPTP is a statutory requirement. | 400000 | 204000 | [5 empty] | 277898 |  | 117325
2022-09-20 | September 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Auckland Transport | SfP - Funding the Foundations | Implementation | SfP - New Lynn | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The key benefits are: - Develop connected walking and cycling networks faster to increase the uptake and use of active travel modes - Reduce transport related emissions through the increase in walking and cycling - Increase knowledge and build capability across the sector in tactical urbanism, fast delivery, and fail fast delivery/ implementation techniques - Improve road safety for active travel users - The IPM assessment is recorded in TIO as Very High GPS alignment, High scheduling, and Very High efficiency Amount assigned to Auckland Transport has been confirmed by Multimodal & Innovation team | 3670961 | 3303865 |  |  |  | 1 | 452.283 | 283013 |  | 120992
2022-09-20 | September 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Auckland Transport | SfP - Funding the Foundations | Implementation | SfP - Mangere | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The key benefits are: - Develop connected walking and cycling networks faster to increase the uptake and use of active travel modes - Reduce transport related emissions through the increase in walking and cycling - Increase knowledge and build capability across the sector in tactical urbanism, fast delivery, and fail fast delivery/ implementation techniques - Improve road safety for active travel users - The IPM assessment is recorded in TIO as Very High GPS alignment, High scheduling, and Very High efficiency Amount assigned to Auckland Transport has been confirmed by Multimodal & Innovation team | 2923979 | 2631581 |  |  |  | 1 | 452.283 | 283012 |  | 120991
2022-09-09 | September 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Central Hawkes Bay District Council | SFP - CHBDC Streets for people | Implementation | SfP - Main Street Waipawa | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The key benefits are: - Develop connected walking and cycling networks faster to increase the uptake and use of active travel modes - Reduce transport related emissions through the increase in walking and cycling - Increase knowledge and build capability across the sector in tactical urbanism, fast delivery, and fail fast delivery/ implementation techniques - Improve road safety for active travel users - The IPM assessment is recorded in TIO as Very High GPS alignment, High scheduling, and Very High efficiency Amount assigned to Auckland Transport has been confirmed by Multimodal & Innovation team | 1704802 | 1534322 | [5 empty] | 282884 |  | 120826
2022-09-09 | September 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Gisborne District Council | SfP Gisborne Community Trials | Implementation | SfP Gisborne Grey St Community Trials | VHHL | HHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | The key benefits are: - Develop connected walking and cycling networks faster to increase the uptake and use of active travel modes - Reduce transport related emissions through the increase in walking and cycling - Increase knowledge and build capability across the sector in tactical urbanism, fast delivery, and fail fast delivery/ implementation techniques - Improve road safety for active travel users - The IPM assessment is recorded in TIO as Very High GPS alignment, High scheduling, and Very High efficiency Amount assigned to Auckland Transport has been confirmed by Multimodal & Innovation team | 695160 | 625644 |  |  | 1 | 1 |  | 282865 |  | 120907
2022-09-09 | September 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Hutt City Council | SfP Hutt City Suburban Centres Tactical Urbanism | Implementation | SfP Wainuiomata Implementation | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The key benefits are: - Develop connected walking and cycling networks faster to increase the uptake and use of active travel modes - Reduce transport related emissions through the increase in walking and cycling - Increase knowledge and build capability across the sector in tactical urbanism, fast delivery, and fail fast delivery/ implementation techniques - Improve road safety for active travel users - The IPM assessment is recorded in TIO as Very High GPS alignment, High scheduling, and Very High efficiency Amount assigned to Auckland Transport has been confirmed by Multimodal & Innovation team | 1005445 | 904901 |  |  |  |  | C00033.SFP.300 | 282745 |  | 120688
2022-09-27 | September 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | NZTA (Wellington) | LGWM CS Featherson St | Single-Stage Business Case | LGWM CS Featherston St | HHM | VHHH | N | 4 | Approved | Approved by Auckland Transport Chief Financial Officer | Transfer allocation from 60066160. | 2569035 | 1475705 |  |  | 1.2 | 1 |  | 282750 | 60068322 | 121079
2022-09-09 | September 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Tasman District Council | SfP Tasman Towns | Implementation | SfP Mapua Cycle Lanes | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The key benefits are: - Develop connected walking and cycling networks faster to increase the uptake and use of active travel modes - Reduce transport related emissions through the increase in walking and cycling - Increase knowledge and build capability across the sector in tactical urbanism, fast delivery, and fail fast delivery/ implementation techniques - Improve road safety for active travel users - The IPM assessment is recorded in TIO as Very High GPS alignment, High scheduling, and Very High efficiency Amount assigned to Auckland Transport has been confirmed by Multimodal & Innovation team | 933180 | 839862 |  |  |  | 1 |  | 282764 |  | 120909
2022-09-09 | September 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Tasman District Council | SfP Tasman Towns | Implementation | SfP Richmond Cycle Lanes | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The key benefits are: - Develop connected walking and cycling networks faster to increase the uptake and use of active travel modes - Reduce transport related emissions through the increase in walking and cycling - Increase knowledge and build capability across the sector in tactical urbanism, fast delivery, and fail fast delivery/ implementation techniques - Improve road safety for active travel users - The IPM assessment is recorded in TIO as Very High GPS alignment, High scheduling, and Very High efficiency Amount assigned to Auckland Transport has been confirmed by Multimodal & Innovation team | 4234040 | 2406636 |  |  |  | 1 |  | 282763 |  | 120908
2022-09-09 | September 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Wellington City Council | Transitional Cycleways Programme (ex Accelerated)(SfP) | Implementation | SfP Newtown â€“ Island Bay Imp | HHL | VHHM | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The key benefits are: - Develop connected walking and cycling networks faster to increase the uptake and use of active travel modes - Reduce transport related emissions through the increase in walking and cycling - Increase knowledge and build capability across the sector in tactical urbanism, fast delivery, and fail fast delivery/ implementation techniques - Improve road safety for active travel users - The IPM assessment is recorded in TIO as Very High GPS alignment, High scheduling, and Very High efficiency Amount assigned to Auckland Transport has been confirmed by Multimodal & Innovation team | 1716000 | 1544400 |  |  |  | 3.5 | SfP Newtown â€“ Island Bay Imp | 282824 |  | 120910
2022-09-13 | September 2022 Review | New approval | Local road maintenance | Emergency works | Gisborne District Council | Emergency Works: June 2020 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds to move from normal FAR to higher FAR. Adjust emergency works funding (Higher FAR). | 3237144 | 2816315 |  |  |  |  | Construction -Emergency Works: June 2020 Flood Damage (Normal FAR+20%) | 282974 |  | 120940
2022-09-21 | September 2022 Review | New approval | Local road maintenance | Emergency works | Matamata-Piako District Council | EW MPDC July 2022 (Tills Road Slip) | Construction | Tills Road slip repair | ___ |  | N |  | Approved | Approved by System Manager, Maintenance and Operations (Transport Services) | To reduce the risk of significant level of service reduction on a critical (utility lifelines) route. | 400000 | 204000 | [5 empty] | 282219 |  | 120412
2022-09-20 | September 2022 Review | New approval | Local road maintenance | Emergency works | Rotorua Lakes Council | EW - Rotorua LC Storm Damage July 2022 | Construction | Phase 1 - Initial response, investigation & design | ___ |  | N |  | Approved | Approved by National Manager, Maintenance and Operations (Transport Services) | That the Senior Manager System Management: Approves Rotorua Lakes Council Emergency Works at a total cost of $897,901 at 56% FAR (NLTF Share $502,825). No enhanced FAR for this phase. Phase 1 - Initial response, investigation & design. 4 Major sites that need investigation and design. Total road closure at one site and the 3 others are down to 1 lane. On site assessment concluded that 2 other sites were not eligible for E/W's funding. These were removed from the WSP report prior to submitting in TIO. Options for the 4 major sites to be agreed and will be funded through Phase 2. | 897901 | 502825 | [5 empty] | 282765 |  | 120730
2022-09-27 | September 2022 Review | New approval | Local road maintenance | Emergency works | Whanganui District Council | Cyclone Dovi - 13 February 2022 Emergency Works | Construction | Clean up and Minor Repairs | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As recommended by Regional Office. To enable Whanganui District Council to undertake initial response of various roads within the district and return those roads to the required pre-event levels of service. | 128221 | 76933 |  |  |  |  | Clean up and Minor Repairs | 282925 |  | 120869
2022-09-07 | September 2022 Review | New approval | Local road maintenance | Emergency works | Whangarei District Council | EW - Storm event July 2022 | Construction | EW - Storm repairs July 2022 | ___ |  | N |  | Approved | Approved by System Manager, Maintenance and Operations (Transport Services) | refer funding approval document | 414356 | 219609 | [5 empty] | 282786 |  | 120727
2022-09-09 | September 2022 Review | New approval | Investment management (incl. Transport Planning) | Management of the funding allocation system | NZ Transport Agency | Investment in the Funding Allocation System (IFAS) | Implementation | TS assurance and decision making improvements | HHVH | HHVH | N | 3 | Approved | Approved by Chief Financial Officer (CFO) | CFO approved funding to Waka Kotahi national office, for the Transport services operating model programmes funding allocation of $1M from WC911, Investment management activity class | 1000000 | 1000000 |  |  | 1 | 1 | TS Assurance & Decision Making Improve:60068894 | 282948 |  | 120903
2022-09-14 | September 2022 Review | New approval | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | Christchurch City Council | Bus interchange upgrades | Property | 60244 | VHML | VHMM | N | 3 | Approved | Approved by Chief Financial Officer (CFO) | This project is part of the preferred option that was recommended within Greater Christchurch Public Transport Futures Combined Business Cases and is also consistent with the principles of the An Accessible City (AAC) Programme Business Case (which includes for a projected three-fold increase in passenger transport use by 2041 from a 2010 base). Both business cases provide a good overview of and alignment with local, regional and national strategies, especially the Christchurch Central Recovery Plan, its transport chapter An Accessible City and the Regional Public Transport Plan (2018-28). This project is intended to secure the opportunity for the existing interchange to be expanded onto an adjoining block of land to its immediate south (importantly, as designated for bus interchange purposes in the Recovery Plan), in order to accommodate both possible service frequency increases arising from the Public Transport Business Case (ongoing), as well as addressing the existing practical operational improvements to the interchange. | 1400000 | 714000 |  |  |  | 2.1 | 60244 | 277174 |  | 120938
2022-09-16 | September 2022 Review | New approval | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | NZTA (Auckland) | North Western Bus Improvements (ST) | Implementation | NLTF Programme Contingency Transfer | VHHL | VHLL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | INTERPHASE TRANSFER:Moving $3,796,296 contingency allocation from 60067690 into 60062437 as per request to have this consolidated. | 4100000 | 4100000 |  |  | 1.1 | 1.3 | 60062437 AT Transfer #1 | 282992 |  | 120981
2022-09-27 | September 2022 Review | New approval | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | NZTA (Wellington) | LGWM CS BPAP Targeted Improvements | Single-Stage Business Case |  | HHM | HHM | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer allocation from 60065973. | 103816 | 38433 |  |  |  | 3.4 |  | 282746 | 60068268 | 121085
2022-09-27 | September 2022 Review | New approval | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | NZTA (Wellington) | LGWM CS Bus Network Advice | Single-Stage Business Case | LGWM CS Bus Network Advice | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer allocation from 60065976. | 839214 | 528394 |  |  | 1.2 | 1 |  | 282748 | 60068318 | 121083
2022-09-27 | September 2022 Review | New approval | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | NZTA (Wellington) | LGWM CS CBD to Miramar | Single-Stage Business Case |  | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | tranfer allocation from 60066163 & 60066135. | 4643977 | 2894187 |  |  | 1.2 | 1 |  | 282751 | 60068323 | 121090
2022-09-27 | September 2022 Review | New approval | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | NZTA (Wellington) | LGWM CS Tar St and CBD to Newtown | Single-Stage Business Case |  | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer allocation from 60066154. | 5093204 | 3206832 |  |  | 1.2 | 1 |  | 282755 | 60068337 | 121086
2022-09-01 | September 2022 Review | New approval | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Waikato) | SH3 Glenview Bus Hub | Implementation |  | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Recommended as per IPM and Business Case Assessment Fields | 2538000 | 2538000 |  |  |  | 1.9 |  | 282221 | 60068112 | 120468
2022-09-23 | September 2022 Review | New approval | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM CS CBD Modelling | Single-Stage Business Case | LGWM CS CBD Modelling | HHH | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer allocation from 60065977. | 294222 | 185251 |  |  | 1.2 | 1 |  | 282828 | 60068319 | 121048
2022-09-27 | September 2022 Review | New approval | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM CS Johnsonville/ NgÄ Åªranga | Single-Stage Business Case |  | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer allocation from 60066164 | 1911935 | 1093564 |  |  | 1.2 | 1 |  | 282752 | 60068328 | 121077
2022-09-27 | September 2022 Review | New approval | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM CS Newtown to Berhampore | Single-Stage Business Case |  | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer allocation from 60066166 | 2933624 | 1847097 |  |  | 1.2 | 1 |  | 282753 | 60068331 | 121075
2022-09-23 | September 2022 Review | New approval | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM CS Taranaki/ Wallace/ Johns Streets | Single-Stage Business Case |  | HHH | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer allocation from 60066155. | 1987442 | 1148435 |  |  | 1.2 | 1 |  | 282756 | 60068341 | 121050
2022-09-23 | September 2022 Review | New approval | Public transport infrastructure | Public transport facilities & infrastructure - renewals | NZTA (Wellington) | LGWM CS General Targeted Improvements | Single-Stage Business Case |  | HHM | HHM | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer allocation from 60066161. | 103816 | 38433 |  |  |  | 3.4 |  | 282747 | 60068314 | 121058
2022-09-05 | September 2022 Review | New approval | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH25 Pepe Stream Bridge Replacement | Pre-implementation* |  | HHL | HHVH | N | 5 | Approved with conditions | Approved with conditions by Chief Financial Officer (CFO) | â€¢ The benefits of approving this funding request are: - Improved safety and ease of walking and cycling - Reduced risk of severance due to bridge closure - Reduced risk of weight restrictions due to bridge nearing end of life - Impact on travel time during peak summer period â€¢ We note that the BCR is 2.3. â€¢ The requirements of section 20 of the Land Transport Management Act 2003 have been met. | 1825000 | 1825000 | Subject to condition subsequent that those issues identified in the â€œPepe Stream Bridge Replacement Concept Plan Road Safety Audit Version 1 November 2021â€ are resolved during the pre-implementation phase (including consideration of the safe and appropriate speed and walking and cycling safety through Tairua township) Subject to condition precedent activity class manager and Treasury Cashflow confirm priority and availability of funding. |  | 1.3 | 1 |  | 277383 | 60058697 | 117957
2022-09-14 | September 2022 Review | New approval | Road to Zero | Road improvements | Auckland Transport | High Risk Intersections and Corridors | Implementation | HRIC Aviemore Dr & Highland Park Dr SSInt | HHM | VHHL | Y | 2 | Approved | Approved by Auckland Transport Chief Financial Officer |  | 4482444 | 2286046 |  |  |  | 4.5 | 324.2804 | 280418 |  | 120945
2022-09-06 | September 2022 Review | New approval | Road to Zero | Road improvements | NZTA (BOP) | SH2 Omokoroa to Te Puna Safety Improvement | Pre-implementation* | SSI | HHL | HHL | N | 5 | Approved with conditions | Approved with conditions by Chief Financial Officer (CFO) | The problems and benefits considered in the SSI application warrant safety intervention in this high volume (>16,000 vpd) and high safety risk length of SH2. The Short - medium term DSI savings (assumed at least 10 years design life until NZUP project TNL Stage 2 is Implemented) are sufficient to justify as a minimum Wide Centreline Treatment and Intersection Speed Zones at the 2 highest risk intersections where significant turning movements take place. | 725760 | 725760 | close out Feasibility reporting and preliminary option evaluation before Pre-Implementation is completed. This should include as a minimum the following : o Communications and engagement strategy o Design philosophy strategy o Consenting strategy o Procurement and staging strategy o Risk management strategy Either the Regional Manager, System Design or Regional Manager, Infrastructure Delivery should be responsible to sign this off. |  | 10 | 10 |  | 268700 | 60054591 | 120471
2022-09-06 | September 2022 Review | New approval | State highway improvements | Road improvements | NZTA (Hawkes Bay) | SH2 Watchman Rd, HB Airport Intersection | Implementation | Implementation | H_L | HMM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Create a new phase in TIO for the 2021/22 spend which needs to be against SH Improvement. Secondly to move SAP item ID for the Regional Improvements phase to this new phase & action the approval | 1386 | 1386 |  |  | 2.2 | 2.2 |  | 282924 | 60027647 | 120866
2022-09-01 | September 2022 Review | New approval | Road to Zero | Road improvements | NZTA (Otago) | SH6 Wanaka to Luggate Safer Corridor - SH84 IS | Implementation | SH6 Wanaka to Luggate SC - SH84 IS | VHHL | VHML | N | 2 | Approved | Approved by Chief Financial Officer (CFO) |  | 7697160 | 7697160 |  |  | 0 | 1.6 |  | 278559 | 60056855 | 120087
2022-09-30 | September 2022 Review | New approval | Road to Zero | Road improvements | NZTA (Waikato) | Waikato SH Speed Management Guide Implementation | Implementation | Wex 110 Road to Zero | VHHH | VHHL | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer allocation from 60053145. | 19502085 | 19502085 |  |  | 0 | 4.6 | A0152-P-000 | 283076 | 60068670 | 121106
2022-09-09 | September 2022 Review | New approval | Local road improvements | Road improvements | Porirua City Council | Access Kenepuru | Implementation | Stage 2A â€“ Enabling works | HHM | VHHM | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | Enabling works to allow implementation to go ahead | 2200000 | 637200 |  |  | 5.6 | 5.6 | Implementation | 281699 |  | 120348
2022-09-21 | September 2022 Review | New approval | Road to Zero | Road policing | NZ Transport Agency | Drug Driving Testing Support Implementation (DDTSI) | Pre-implementation* | Phase-1 | VHHL | LLVL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) |  | 4582986 | 4582986 |  |  | 0 | 6.8 | SAP ID: 60068855: Old WBS 51000416 | 282187 |  | 120887
2022-09-27 | September 2022 Review | New approval | Walking and cycling improvements | Walking facilities | NZTA (Wellington) | LGWM CS Bowen St | Single-Stage Business Case | LGWM CS Bowen St | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer allocation from 60065975. | 756610 | 458030 |  |  | 1.2 | 1 |  | 282749 | 60068315 | 121081
2022-09-23 | September 2022 Review | New approval | Walking and cycling improvements | Walking facilities | NZTA (Wellington) | LGWM CS South West CBD | Single-Stage Business Case |  | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer allocation from 60066730. | 2608949 | 1433405 |  |  | 1.2 | 1 |  | 282754 | 60068334 | 121049
2022-09-23 | September 2022 Review | New approval | Walking and cycling improvements | Walking facilities | NZTA (Wellington) | LGWM Central City Pedestrian Improvement | Implementation |  | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Allocation transferred from 60053806. | 1783379 | 413084 |  |  | 1.2 | 1 |  | 282759 | 60068425 | 121046
2022-09-29 | September 2022 Review | Cash flow adjustment | Local road maintenance | Bridge and structures renewals | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Changes reflect the updated forecast for the Work Categories to align with target quantities. This is based on discussions held with Tony Lange, Waka Kotahi and Auckland Transport Asset Maintenance and Renewals group on 14 September 2022. The change also reflects the carry over funding for WC 216 from the 2021/22 allocation. | 3990175 | 2034989 | [5 empty] | 272202 |  | 120971
2022-09-27 | September 2022 Review | Cash flow adjustment | Local road maintenance | Bridge and structures renewals | Kaipara District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Rebalance of program for carry forwards from 2021/22 so program monitor can be completed | 1000000 | 620000 | [5 empty] | 272922 |  | 121078
2022-09-29 | September 2022 Review | Cash flow adjustment | Local road maintenance | Cycle path maintenance | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Changes reflect the updated forecast for the Work Categories to align with target quantities. This is based on discussions held with Tony Lange, Waka Kotahi and Auckland Transport Asset Maintenance and Renewals group on 14 September 2022. The change also reflects the carry over funding for WC 216 from the 2021/22 allocation. | -351834 | -179435 | [5 empty] | 272189 |  | 120971
2022-09-05 | September 2022 Review | Cash flow adjustment | Local road maintenance | Cycle path maintenance | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Realignment of cashflows from 2021/22 year end surplus | 13200 | 6732 | [5 empty] | 272822 |  | 120726
2022-09-29 | September 2022 Review | Cash flow adjustment | Local road maintenance | Cycle path renewal | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Changes reflect the updated forecast for the Work Categories to align with target quantities. This is based on discussions held with Tony Lange, Waka Kotahi and Auckland Transport Asset Maintenance and Renewals group on 14 September 2022. The change also reflects the carry over funding for WC 216 from the 2021/22 allocation. | 70040 | 35721 | [5 empty] | 272205 |  | 120971
2022-09-22 | September 2022 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | NZTA (Auckland) | Northern Pathway (Akoranga to Constellation) | Detailed Business Case |  | H_L* | H_L* | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Updating 21/22 to match SAP actual and reducing 22/23 to keep allocation to approved budget of $2,436,648 | 0 | 0 |  |  | 1.9 | 1.9 |  | 257899 | 60052719 | 121038
2022-09-30 | September 2022 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Whangarei District Council | Cycleway Construction 2018/21 | Implementation | Cycleway Construction 2018/21 - Package 1 | H_M | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Delay in Kiwi Rail approval for engineering plan approval of new rail level crossing at Wilkinson Ave. This results in the implementation of the project being deferred. | 0 | 0 |  |  | 0 | 4.6 | Kamo Shared Path - Northern Extension | 260578 |  | 121020
2022-09-29 | September 2022 Review | Cash flow adjustment | Local road maintenance | Drainage renewals | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Changes reflect the updated forecast for the Work Categories to align with target quantities. This is based on discussions held with Tony Lange, Waka Kotahi and Auckland Transport Asset Maintenance and Renewals group on 14 September 2022. The change also reflects the carry over funding for WC 216 from the 2021/22 allocation. | 300861 | 153439 | [5 empty] | 272199 |  | 120971
2022-09-05 | September 2022 Review | Cash flow adjustment | Local road maintenance | Drainage renewals | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Realignment of cashflows from 2021/22 year end surplus | 19976 | 10188 | [5 empty] | 272832 |  | 120726
2022-09-13 | September 2022 Review | Cash flow adjustment | Local road maintenance | Emergency works | Gisborne District Council | 20 June 2021 Weather Event | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Set Normal FAR flag to Yes | 0 | 0 |  |  |  |  | Emergency Works: 20 June 2021 Flood Damage | 279377 |  | 120939
2022-09-19 | September 2022 Review | Cash flow adjustment | Local road maintenance | Emergency works | Porirua City Council | Emergency Works - December 2021 - Heavy Rain Event | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Revised cost FAR amended to normal FAR | 0 | 0 |  |  |  |  | Construction Proposal (Normal FAR+20%) | 281778 |  | 120997
2022-09-01 | September 2022 Review | Cash flow adjustment | Local road maintenance | Emergency works | Wairoa District Council | Emergency Works March 2022 | Construction |  | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Incorrect decision status manager chosen in earlier approval on 30 Aug 22. It should have been CFO and not Mgr T&C. This review is to fix this error. | 0 | 0 |  |  |  |  | Emergency Works March 2022_Reinstatement Renewal_SPR38 | 281421 |  | 120798
2022-09-16 | September 2022 Review | Cash flow adjustment | Local road maintenance | Emergency works | Wellington City Council | Emergency Works Cyclone Dovi Storm Event February 2022 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This review is to override High FAR back to normal. | 0 | 0 |  |  |  |  | Cyclone Dovi - Storm Event Feb. 22 | 281718 |  | 120978
2022-09-16 | September 2022 Review | Cash flow adjustment | Local road maintenance | Emergency works | Wellington City Council | Emergency Works July/August 2017 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This review is to put FAR to normal after higher FAR override. | 0 | 0 |  |  |  |  | EW (Normal FAR+20%) | 264675 |  | 120976
2022-09-29 | September 2022 Review | Cash flow adjustment | Local road maintenance | Environmental maintenance | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Changes reflect the updated forecast for the Work Categories to align with target quantities. This is based on discussions held with Tony Lange, Waka Kotahi and Auckland Transport Asset Maintenance and Renewals group on 14 September 2022. The change also reflects the carry over funding for WC 216 from the 2021/22 allocation. | 2842902 | 1449880 | [5 empty] | 272192 |  | 120971
2022-09-27 | September 2022 Review | Cash flow adjustment | Local road maintenance | Environmental maintenance | Kaipara District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Rebalance of program for carry forwards from 2021/22 so program monitor can be completed | 33122 | 20536 | [5 empty] | 272912 |  | 121078
2022-09-29 | September 2022 Review | Cash flow adjustment | Local road maintenance | Footpath maintenance | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Changes reflect the updated forecast for the Work Categories to align with target quantities. This is based on discussions held with Tony Lange, Waka Kotahi and Auckland Transport Asset Maintenance and Renewals group on 14 September 2022. The change also reflects the carry over funding for WC 216 from the 2021/22 allocation. | -3914228 | -1996257 | [5 empty] | 272190 |  | 120971
2022-09-05 | September 2022 Review | Cash flow adjustment | Local road maintenance | Footpath maintenance | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Realignment of cashflows from 2021/22 year end surplus | 71365 | 36396 | [5 empty] | 272823 |  | 120726
2022-09-27 | September 2022 Review | Cash flow adjustment | Local road maintenance | Footpath maintenance | Kaipara District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Rebalance of program for carry forwards from 2021/22 so program monitor can be completed | 8242 | 5110 | [5 empty] | 272910 |  | 121078
2022-09-29 | September 2022 Review | Cash flow adjustment | Local road maintenance | Footpath renewal | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Changes reflect the updated forecast for the Work Categories to align with target quantities. This is based on discussions held with Tony Lange, Waka Kotahi and Auckland Transport Asset Maintenance and Renewals group on 14 September 2022. The change also reflects the carry over funding for WC 216 from the 2021/22 allocation. | 3862233 | 1969739 | [5 empty] | 272206 |  | 120971
2022-09-05 | September 2022 Review | Cash flow adjustment | Local road maintenance | Footpath renewal | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Realignment of cashflows from 2021/22 year end surplus | 170341 | 86874 | [5 empty] | 272839 |  | 120726
2022-09-30 | September 2022 Review | Cash flow adjustment | Local road improvements | Low cost / low risk improvements | Napier City Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Component projects are fully designed and consented and in a position to be constructed. Two of the projects are close to high schools with limited access and construction in current financial year allows this to be programmed in the 22/23 the summer holiday period. All identified projects present asset and property risk, therefore addressing them at the earliest opportunity is desired. | 0 | 0 | [5 empty] | 276309 |  | 120998
2022-09-16 | September 2022 Review | Cash flow adjustment | Road to Zero | Low cost / low risk improvements | Southland District Council | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Adjusting timing of NLTP period programme for when expected to deliver | 0 | 0 | [5 empty] | 276408 |  | 120791
2022-09-30 | September 2022 Review | Cash flow adjustment | Local road improvements | Low cost / low risk improvements | Whakatane District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Local road improvements programme delivery is behind the NLTP forecast timing due to project development delays. Total NLTP allocation remains unchanged. | 0 | 0 | [5 empty] | 276553 |  | 121052
2022-09-30 | September 2022 Review | Cash flow adjustment | Local road improvements | Low cost / low risk improvements | Whakatane District Council | Low cost / low risk improvements 2021-24 | Local road improvements (SPR) |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Local road (SPR) improvements programme delivery is behind the NLTP forecast timing due to Iwi engagement delays. Total NLTP allocation remains unchanged. | 0 | 0 | [5 empty] | 276554 |  | 121055
2022-09-30 | September 2022 Review | Cash flow adjustment | Road to Zero | Low cost / low risk improvements | Whakatane District Council | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | moving funds from year 2 to year 3 due to delays in delivering the Peace Street design, originally planned for year 2 construction, will now be year 3 construction. | 0 | 0 | [5 empty] | 276557 |  | 121053
2022-09-30 | September 2022 Review | Cash flow adjustment | Road to Zero | Low cost / low risk improvements | Whakatane District Council | Low cost / low risk improvements 2021-24 | Road to Zero (SPR) |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | SPR road to zero programme delivery is behind the NLTP forecast timing due to Iwi engagement delays. Total NLTP allocation remains unchanged. | 0 | 0 | [5 empty] | 276552 |  | 121054
2022-09-30 | September 2022 Review | Cash flow adjustment | Walking and cycling improvements | Low cost / low risk improvements | Whakatane District Council | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Local road improvements programme delivery is behind the NLTP forecast timing due to project development delays. Total NLTP allocation remains unchanged. | 0 | 0 | [5 empty] | 276550 |  | 121051
2022-09-30 | September 2022 Review | Cash flow adjustment | Public transport infrastructure | Low cost / low risk public transport improvements | Whakatane District Council | Low cost / low risk improvements 2021-24 | Public transport infrastructure |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | PT infrastructure programme delivery ahead of NLTP timing, with works originally planned in year 3, now scheduled for completion in year 2. Total NLTP allocation remains unchanged. | 0 | 0 | [5 empty] | 276558 |  | 121057
2022-09-05 | September 2022 Review | Cash flow adjustment | Local road maintenance | Network and asset management | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Realignment of cashflows from 2021/22 year end surplus | 134775 | 68735 | [5 empty] | 272829 |  | 120726
2022-09-27 | September 2022 Review | Cash flow adjustment | Local road maintenance | Network and asset management | Kaipara District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Rebalance of program for carry forwards from 2021/22 so program monitor can be completed | 10000 | 6200 | [5 empty] | 272916 |  | 121078
2022-09-28 | September 2022 Review | Cash flow adjustment | Local road maintenance | Network and asset management | NZ Transport Agency | Asset Management Data Standard- State Highways | Implementation | Roll out of data standard- LR Maintenance | MMM | VHMM | N | 8 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 0 | 0 |  |  |  | 4.4 | LR Maintenance part of funding, SAP item 60067372 | 277727 |  | 121095
2022-09-05 | September 2022 Review | Cash flow adjustment | Local road maintenance | Network operations | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Realignment of cashflows from 2021/22 year end surplus | 4758 | 2427 | [5 empty] | 272827 |  | 120726
2022-09-29 | September 2022 Review | Cash flow adjustment | Local road maintenance | Network service maintenance | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Changes reflect the updated forecast for the Work Categories to align with target quantities. This is based on discussions held with Tony Lange, Waka Kotahi and Auckland Transport Asset Maintenance and Renewals group on 14 September 2022. The change also reflects the carry over funding for WC 216 from the 2021/22 allocation. | -3338639 | -1702706 | [5 empty] | 272193 |  | 120971
2022-09-05 | September 2022 Review | Cash flow adjustment | Local road maintenance | Network service maintenance | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Realignment of cashflows from 2021/22 year end surplus | -82406 | -42027 | [5 empty] | 272826 |  | 120726
2022-09-27 | September 2022 Review | Cash flow adjustment | Local road maintenance | Network service maintenance | Kaipara District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Rebalance of program for carry forwards from 2021/22 so program monitor can be completed | 28165 | 17462 | [5 empty] | 272913 |  | 121078
2022-09-27 | September 2022 Review | Cash flow adjustment | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | NZTA (Wellington) | LGWM CS Tar St and CBD to Newtown | Single-Stage Business Case |  | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer from 60066154. | 0 | 0 |  |  | 1.2 | 1 |  | 282755 | 60068337 | 121088
2022-09-05 | September 2022 Review | Cash flow adjustment | Investment management (incl. Transport Planning) | Programme Business Case Development | NZTA (Canterbury) | Rolleston Transport Improvements | Programme business case |  | H__ | H__ | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -1 | -1 | [5 empty] | 268632 | 60054323 | 120669
2022-09-07 | September 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS BPAP Targeted Imp. | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 0 | 0 |  |  | 1.2 | 1 |  | 280357 | 60065973 | 120874
2022-09-07 | September 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Taranaki/ Wallace/ John Sts | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 0 | 0 |  |  | 1.2 | 1 |  | 280362 | 60066155 | 120876
2022-09-07 | September 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Newtown to Berhampore | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 1 | 1 |  |  | 1.2 | 1 |  | 280368 | 60066166 | 120890
2022-09-07 | September 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Johnsonville/ Ngauranga | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 0 | 0 |  |  | 1.2 | 1 |  | 280367 | 60066164 | 120881
2022-09-07 | September 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS BPAP Targeted Imp. | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 0 | 0 |  |  | 1.2 | 1 |  | 280357 | 60065973 | 120892
2022-09-07 | September 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Bus Network Advice | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 0 | 0 |  |  | 1.2 | 1 |  | 280359 | 60065976 | 120889
2022-09-07 | September 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport facilities & infrastructure - renewals | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Hamilton Rd to Shelly Bay Rd | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 0 | 0 |  |  | 1.2 | 1 |  | 280366 | 60066163 | 120880
2022-09-07 | September 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport facilities & infrastructure - renewals | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS CBD to Kilbirnie and Miramar | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 0 | 0 |  |  | 1.2 | 1 |  | 280363 | 60066135 | 120891
2022-09-05 | September 2022 Review | Cash flow adjustment | Local road maintenance | Rail level crossing warning devices maintenance | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Realignment of cashflows from 2021/22 year end surplus | 979 | 499 | [5 empty] | 272828 |  | 120726
2022-09-27 | September 2022 Review | Cash flow adjustment | Local road maintenance | Rail level crossing warning devices maintenance | Kaipara District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Rebalance of program for carry forwards from 2021/22 so program monitor can be completed | -5000 | -3100 | [5 empty] | 272915 |  | 121078
2022-09-05 | September 2022 Review | Cash flow adjustment | Public transport infrastructure | Rapid Transit Infrastructure | NZTA (Auckland) | North West Rapid Transit Improvements | Detailed Business Case | North West Rapid Transit Improvements | VHHL | HLL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project start delayed. Project timelines now more certain and forecast matches expected project progress | 0 | 0 |  |  | 1.1 | 1.3 |  | 269237 | 60055578 | 120773
2022-09-16 | September 2022 Review | Cash flow adjustment | External funding | Road improvements | NZTA (Auckland) | NZUP SH22 (Drury) Corridor Upgrade | Pre-implementation* |  | MML | MML | N | 9 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move $2,968,127 from FY22/23 to FY23/24 due to origianl funding all sit in one financial year FY22/23. | 0 | 0 |  |  |  | 1.7 |  | 281986 | 60067768 | 120952
2022-09-05 | September 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Canterbury) | Kaikoura Nov 2016 EQ: Lewis Pass Altern Upg Rout - Canterbur | Property | Property | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -1 | -1 |  |  | 1.4 | 1.4 | 60042763 | 249705 | 60042763 | 120668
2022-09-06 | September 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Hawkes Bay) | SH2 Watchman Rd, HB Airport Intersection | Implementation | Implementation | H_L | HMM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Updating actuals for 2021/22 | 0 | 0 |  |  | 2.2 | 2.2 |  | 282924 | 60027647 | 120867
2022-09-15 | September 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Marlborough) | SH6 Blenheim to Nelson - SH6/SH62 | Property | R2Z | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 1 | 1 |  |  | 0 | 1.6 |  | 278556 |  | 120956
2022-09-27 | September 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Wellington) | Peka Peka to Otaki Revocation | Pre-implementation* | Peka Peka to Otaki Revocation | H_L | M_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | this is a test to see if SAP will accept $0 value from TIO | -1 | -1 |  |  | 0.6 | 0.6 | 60049935 | 271842 | 60049935 | 121073
2022-09-30 | September 2022 Review | Cash flow adjustment | Local road improvements | Road improvements | Whangarei District Council | Maunu Road/Central Ave/Walton St/Water St Intersection Imp | Implementation | Maunu/Central Intersection | HMM | HHM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Implementation is deferred to late 2022-23 and into 2023-24. | 0 | 0 |  |  | 0 | 3.8 |  | 260579 |  | 121045
2022-09-29 | September 2022 Review | Cash flow adjustment | Local road maintenance | Routine drainage maintenance | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Changes reflect the updated forecast for the Work Categories to align with target quantities. This is based on discussions held with Tony Lange, Waka Kotahi and Auckland Transport Asset Maintenance and Renewals group on 14 September 2022. The change also reflects the carry over funding for WC 216 from the 2021/22 allocation. | -2550165 | -1300584 | [5 empty] | 272187 |  | 120971
2022-09-05 | September 2022 Review | Cash flow adjustment | Local road maintenance | Routine drainage maintenance | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Realignment of cashflows from 2021/22 year end surplus | 100836 | 51426 | [5 empty] | 272820 |  | 120726
2022-09-27 | September 2022 Review | Cash flow adjustment | Local road maintenance | Routine drainage maintenance | Kaipara District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Rebalance of program for carry forwards from 2021/22 so program monitor can be completed | 60177 | 37310 | [5 empty] | 272907 |  | 121078
2022-09-29 | September 2022 Review | Cash flow adjustment | Local road maintenance | Sealed pavement maintenance | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Changes reflect the updated forecast for the Work Categories to align with target quantities. This is based on discussions held with Tony Lange, Waka Kotahi and Auckland Transport Asset Maintenance and Renewals group on 14 September 2022. The change also reflects the carry over funding for WC 216 from the 2021/22 allocation. | 2022480 | 1031465 | [5 empty] | 272185 |  | 120971
2022-09-05 | September 2022 Review | Cash flow adjustment | Local road maintenance | Sealed pavement maintenance | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Realignment of cashflows from 2021/22 year end surplus | -3056342 | -1558734 | [5 empty] | 272818 |  | 120726
2022-09-27 | September 2022 Review | Cash flow adjustment | Local road maintenance | Sealed pavement maintenance | Kaipara District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Rebalance of program for carry forwards from 2021/22 so program monitor can be completed | -3440460 | -2133085 | [5 empty] | 272905 |  | 121078
2022-09-30 | September 2022 Review | Cash flow adjustment | State highway maintenance | Sealed pavement maintenance | NZTA (Wellington) | Wellington RoNS (5) - Transmission Gully | Implementation | Maintenance and Operations payments | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Maintenance payments haven't started. 2021/22 costs moved to the end. | 0 | 0 |  |  | 1.4 | 1.4 |  | 243429 | 60066242 | 120979
2022-09-30 | September 2022 Review | Cash flow adjustment | Local road maintenance | Sealed pavement maintenance | Taupo District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Resurfacing contract for AC and chipseal has come in over engineers estimate, transferring budget including the underspend in last years sealed pavement maintenance to resurfacing rather than reducing scope of works. Neutral change. | -660000 | -336600 | [5 empty] | 274302 |  | 121072
2022-09-29 | September 2022 Review | Cash flow adjustment | Local road maintenance | Sealed road pavement rehabilitation | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Changes reflect the updated forecast for the Work Categories to align with target quantities. This is based on discussions held with Tony Lange, Waka Kotahi and Auckland Transport Asset Maintenance and Renewals group on 14 September 2022. The change also reflects the carry over funding for WC 216 from the 2021/22 allocation. | -16438746 | -8383761 | [5 empty] | 272200 |  | 120971
2022-09-05 | September 2022 Review | Cash flow adjustment | Local road maintenance | Sealed road pavement rehabilitation | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Realignment of cashflows from 2021/22 year end surplus | 1495659 | 762786 | [5 empty] | 272833 |  | 120726
2022-09-27 | September 2022 Review | Cash flow adjustment | Local road maintenance | Sealed road pavement rehabilitation | Kaipara District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Rebalance of program for carry forwards from 2021/22 so program monitor can be completed | 564300 | 349866 | [5 empty] | 272920 |  | 121078
2022-09-29 | September 2022 Review | Cash flow adjustment | Local road maintenance | Sealed road resurfacing | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Changes reflect the updated forecast for the Work Categories to align with target quantities. This is based on discussions held with Tony Lange, Waka Kotahi and Auckland Transport Asset Maintenance and Renewals group on 14 September 2022. The change also reflects the carry over funding for WC 216 from the 2021/22 allocation. | 4805984 | 2451052 | [5 empty] | 272198 |  | 120971
2022-09-05 | September 2022 Review | Cash flow adjustment | Local road maintenance | Sealed road resurfacing | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Realignment of cashflows from 2021/22 year end surplus | 673261 | 343363 | [5 empty] | 272831 |  | 120726
2022-09-27 | September 2022 Review | Cash flow adjustment | Local road maintenance | Sealed road resurfacing | Kaipara District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Rebalance of program for carry forwards from 2021/22 so program monitor can be completed | 1018000 | 631160 | [5 empty] | 272918 |  | 121078
2022-09-30 | September 2022 Review | Cash flow adjustment | Local road maintenance | Sealed road resurfacing | Taupo District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Resurfacing contract for AC and chipseal has come in over engineers estimate, transferring budget including the underspend in last years sealed pavement maintenance to resurfacing rather than reducing scope of works. Neutral change. | 660000 | 336600 | [5 empty] | 274315 |  | 121072
2022-09-29 | September 2022 Review | Cash flow adjustment | Local road maintenance | Structures component replacements | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Changes reflect the updated forecast for the Work Categories to align with target quantities. This is based on discussions held with Tony Lange, Waka Kotahi and Auckland Transport Asset Maintenance and Renewals group on 14 September 2022. The change also reflects the carry over funding for WC 216 from the 2021/22 allocation. | 1144750 | 583822 | [5 empty] | 272201 |  | 120971
2022-09-27 | September 2022 Review | Cash flow adjustment | Local road maintenance | Structures component replacements | Kaipara District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Rebalance of program for carry forwards from 2021/22 so program monitor can be completed | 572510 | 354956 | [5 empty] | 272921 |  | 121078
2022-09-29 | September 2022 Review | Cash flow adjustment | Local road maintenance | Structures maintenance | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Changes reflect the updated forecast for the Work Categories to align with target quantities. This is based on discussions held with Tony Lange, Waka Kotahi and Auckland Transport Asset Maintenance and Renewals group on 14 September 2022. The change also reflects the carry over funding for WC 216 from the 2021/22 allocation. | -592454 | -302152 | [5 empty] | 272188 |  | 120971
2022-09-05 | September 2022 Review | Cash flow adjustment | Local road maintenance | Structures maintenance | Hutt City Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Realignment of cashflows from 2021/22 year end surplus | 453598 | 231335 | [5 empty] | 272821 |  | 120726
2022-09-27 | September 2022 Review | Cash flow adjustment | Local road maintenance | Structures maintenance | Kaipara District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Rebalance of program for carry forwards from 2021/22 so program monitor can be completed | 32951 | 20429 | [5 empty] | 272908 |  | 121078
2022-09-29 | September 2022 Review | Cash flow adjustment | Local road maintenance | Traffic services renewals | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Changes reflect the updated forecast for the Work Categories to align with target quantities. This is based on discussions held with Tony Lange, Waka Kotahi and Auckland Transport Asset Maintenance and Renewals group on 14 September 2022. The change also reflects the carry over funding for WC 216 from the 2021/22 allocation. | 4411497 | 2249864 | [5 empty] | 272204 |  | 120971
2022-09-27 | September 2022 Review | Cash flow adjustment | Local road maintenance | Traffic services renewals | Kaipara District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Rebalance of program for carry forwards from 2021/22 so program monitor can be completed | 9296 | 5763 | [5 empty] | 272924 |  | 121078
2022-09-29 | September 2022 Review | Cash flow adjustment | Local road maintenance | Unsealed pavement maintenance | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Changes reflect the updated forecast for the Work Categories to align with target quantities. This is based on discussions held with Tony Lange, Waka Kotahi and Auckland Transport Asset Maintenance and Renewals group on 14 September 2022. The change also reflects the carry over funding for WC 216 from the 2021/22 allocation. | 1396026 | 711973 | [5 empty] | 272186 |  | 120971
2022-09-27 | September 2022 Review | Cash flow adjustment | Local road maintenance | Unsealed pavement maintenance | Kaipara District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Rebalance of program for carry forwards from 2021/22 so program monitor can be completed | 108697 | 67392 | [5 empty] | 272906 |  | 121078
2022-09-29 | September 2022 Review | Cash flow adjustment | Local road maintenance | Unsealed road metalling | Auckland Transport | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Changes reflect the updated forecast for the Work Categories to align with target quantities. This is based on discussions held with Tony Lange, Waka Kotahi and Auckland Transport Asset Maintenance and Renewals group on 14 September 2022. The change also reflects the carry over funding for WC 216 from the 2021/22 allocation. | 2339118 | 1192950 | [5 empty] | 272197 |  | 120971
2022-09-07 | September 2022 Review | Cash flow adjustment | Walking and cycling improvements | Walking facilities | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS South West CBD | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -1 | -1 |  |  | 1.2 | 1 |  | 280699 | 60066730 | 120877
2022-09-07 | September 2022 Review | Cash flow adjustment | Walking and cycling improvements | Walking facilities | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Featherston St | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 0 | 0 |  |  | 1.2 | 1 |  | 280364 | 60066160 | 120878
2022-09-07 | September 2022 Review | Cash flow adjustment | Walking and cycling improvements | Walking facilities | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Bowen St | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 1 | 1 |  |  | 1.2 | 1 |  | 280358 | 60065975 | 120875
2022-09-30 | September 2022 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Hutt City Council | Hutt City Cycling & Micromobility Connectivity Assessment | Single-Stage Business Case |  | HHM | VHHM | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2022/23 as activity is claiming complete | -378301 | -192934 |  |  | 3.4 | 3.4 |  | 269172 |  | 120973
2022-09-30 | September 2022 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | NZTA (Auckland) | Northern Pathway (Akoranga to Constellation) | Detailed Business Case |  | H_L* | H_L* | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update actual for 21/22 to match SAP | -212 | -212 |  |  | 1.9 | 1.9 |  | 257899 | 60052719 | 121104
2022-09-30 | September 2022 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | NZTA (Auckland) | Northern Pathway (Akoranga to Constellation) | Detailed Business Case |  | H_L* | H_L* | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -908980 | -908980 |  |  | 1.9 | 1.9 |  | 257899 | 60052719 | 121042
2022-09-21 | September 2022 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | NZTA (Otago) | Dunedin - Port Chalmers Safety Improvements (SH88) | Implementation |  | H__ | HHL | N | 0 | Approved | Approved by Chief Financial Officer (CFO) |  | 4914002 | 4914002 |  |  | 1.1 | 1.1 | 60049448 | 263919 | 60049448 | 120767
2022-09-16 | September 2022 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | NZTA (Otago) | SH6 SH8B SH8 Gibbston to Clyde Corridor Imps | Detailed Business Case | Nevis Bluff Cycle Connection SSBC | VHML | MML | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | declaring surplus remaining allocation in this SSBC phase. The Implementation phase has since been funded | -34706 | -34706 |  |  | 9.7 | 0.4 | Nevis Bluff Cycle Connection SSBC | 266624 | 60052350 | 120902
2022-09-30 | September 2022 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Taupo District Council | SfP - Safer connections to Taupo Schools | Pre-implementation* | SfP - Safer connections to Schools in Taupo | HHL | HHH | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Withdrew for Streets for People package due to resourcing. | -80137 | -72123 |  |  |  | 1 |  | 281378 |  | 121071
2022-09-01 | September 2022 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Wellington City Council | Wellington Cycle Network - Eastern Package | Implementation | Miramar - UCP Implementation - NLTF | VHHL | VHHM | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | Final claim/washup of project | 142400 | 72624 |  |  | 0 | 2.5 |  | 249029 |  | 120310
2022-09-21 | September 2022 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Western BoP District Council | Cycling Facilities - Omokoroa to Tauranga City Cycleway | Implementation | Design and construction | H_L | H_L | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Request aligns with cost scope adjustment request submitted to delegations for approval at the meeting on 8/9/22. | 2249216 | 1147100 |  |  | 1.8 | 1.4 | Staged design and construction | 233825 |  | 120786
2022-09-09 | September 2022 Review | Cost Increase | Local road maintenance | Emergency works | Gisborne District Council | 20 June 2021 Weather Event | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update FAR as per EW policy | 0 | 1049668 |  |  |  |  | Emergency Works: 20 June 2021 Flood Damage | 279377 |  | 120915
2022-09-05 | September 2022 Review | Cost Decrease | Local road maintenance | Emergency works | Gisborne District Council | Emergency Works: June 2020 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Held collaborative meeting with Senior Investment Advisor concerning realistic delivery of programme and contingencies factors. Agreed that both parties would take a more considered approach around risk and instead of adding contingencies to the overall programme to mitigate this there would be opportunities to revisit specific sites with an options report for further consideration. Council staff believe this is a transparent process and after reviewing the programme with its professional services providers has taken an aggressive approach to its programme by reducing it by $2M. The risk for Council is we are unsure of inflation levels in 2023/24 and would like to keep the door open for a cost/scope increase if we were too optimistic. This would be signaled early to our Senior Investment Advisor. | -2003740 | -1382506 |  |  |  |  | Construction -Emergency Works: June 2020 Flood Damage | 278152 |  | 120715
2022-09-13 | September 2022 Review | Cost Decrease | Local road maintenance | Emergency works | Gisborne District Council | Emergency Works: June 2020 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -3237144 | -2168886 |  |  |  |  | Construction -Emergency Works: June 2020 Flood Damage | 278152 |  | 120941
2022-09-30 | September 2022 Review | Cost Decrease | Local road maintenance | Emergency works | Grey District Council | EW Atarau Rd Rough River Flood Damage 2021-Jul-17 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2022/23 as activity is claiming complete | -12572 | -7920 |  |  |  |  | Construction | 279133 |  | 121098
2022-09-09 | September 2022 Review | Cost Increase | Local road maintenance | Emergency works | Napier City Council | November 2020 Napier Rain Event | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Budget to be set at normal FAR threshold Phase 279020 will be reduced and set at higher Far rate | 174560 | 89026 |  |  |  |  | Construction of permanent works (2) | 278318 |  | 120917
2022-09-09 | September 2022 Review | Cost Increase | Local road maintenance | Emergency works | Napier City Council | November 2020 Napier Rain Event | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | moving funds to normal FAR phase. Set this phase to higher FAR | -174560 | 47923 |  |  |  |  | Construction of permanent works (+20%) | 279020 |  | 120918
2022-09-19 | September 2022 Review | Cost Decrease | Local road maintenance | Emergency works | Porirua City Council | Emergency Works - December 2021 - Heavy Rain Event | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Budget to be reset at as per NZTA FAR policy. Phase 281778 budget decreased from $1,236,623 to $814,666 and reset at higher FAR of 74% | -421957 | -64923 |  |  |  |  | Construction Proposal (Normal FAR+20%) | 281778 |  | 120996
2022-09-19 | September 2022 Review | Cost Increase | Local road maintenance | Emergency works | Porirua City Council | Emergency Works - December 2021 - Heavy Rain Event | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Budget to be reset at as per NZTA FAR policy. Phase 280415 budget increased to $679,615 from $257,658 | 421957 | 227857 |  |  |  |  | Construction Proposal | 280415 |  | 120995
2022-09-16 | September 2022 Review | Cost Decrease | Local road maintenance | Emergency works | Tararua District Council | Event November 2020 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Original application was only 1.65mil . TIO approval 2.34mil. Majority repairs completed less Mangahei Road $220K | -900031 | -621021 |  |  |  |  | Event November 2020 - Cost Scope Adjustm | 280825 |  | 120768
2022-09-05 | September 2022 Review | Cost Decrease | Local road maintenance | Emergency works | Wairoa District Council | Emergency Work Event 1 SP38 04/09/2018 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Works Completed | -160380 | -160380 |  |  |  |  | EW E1 SP38 04/09/2018 | 266084 |  | 120650
2022-09-13 | September 2022 Review | Cost Increase | Local road maintenance | Emergency works | Wairoa District Council | Emergency Works March 2022 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 3851931 | 3659335 |  |  |  |  | RS5619_Emergency Works March 2022 Reinstatement Renewal_Local Roads | 281419 |  | 120943
2022-09-13 | September 2022 Review | Cost Decrease | Local road maintenance | Emergency works | Wairoa District Council | Emergency Works March 2022 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -3851931 | -2888949 |  |  |  |  | RS5618_Emergency Works March 2022 Response & Clean-up_Local Roads | 281418 |  | 120944
2022-09-16 | September 2022 Review | Cost Increase | Local road maintenance | Emergency works | Wellington City Council | Emergency Works Cyclone Dovi Storm Event February 2022 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Budget to be set at higher FAR for phase 281718 as per NZTA EW policy | 0 | 139000 |  |  |  |  | Cyclone Dovi - Storm Event Feb. 22 | 281718 |  | 120977
2022-09-16 | September 2022 Review | Cost Decrease | Local road maintenance | Emergency works | Wellington City Council | Emergency Works July/August 2017 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Budget to be set at higher FAR as per NZTA EW policy. Phase 264675 set at higher FAR | -756084 | -196158 |  |  |  |  | EW (Normal FAR+20%) | 264675 |  | 120975
2022-09-16 | September 2022 Review | Cost Increase | Local road maintenance | Emergency works | Wellington City Council | Emergency Works July/August 2017 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Budget to be set a normal FAR as per NZTA EW policy. Phase 268054 has been increased from $3,198,045 to $3,954,129 | 756084 | 385603 |  |  |  |  | EW | 268054 |  | 120974
2022-09-30 | September 2022 Review | Cost Decrease | Local road maintenance | Emergency works | Whangarei District Council | EW - Storm event July 2022 | Construction | EW - Storm repairs July 2022 (Normal FAR+20%) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -220384 | -160880 |  |  |  |  | (Normal FAR+20%) | 282944 |  | 121110
2022-09-30 | September 2022 Review | Cost Increase | Local road maintenance | Emergency works | Whangarei District Council | EW - Storm event July 2022 | Construction | EW - Storm repairs July 2022 | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 220384 | 116803 | [5 empty] | 282786 |  | 121109
2022-09-27 | September 2022 Review | Cost Decrease | Local road maintenance | Emergency works | Whangarei District Council | EW Storm Event 17 July 2020 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Final Slip tender awarded for Anzac Road intersection. No funding required for Dundas Road slip | -900182 | -477096 | [5 empty] | 271440 |  | 121044
2022-09-27 | September 2022 Review | Cost Decrease | Local road maintenance | Emergency works | Whangarei District Council | EW Storm Events June 2020 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Due to high costs for original solution a low-cost higher risk solution has been adopted for the High Street Slip Site 1. | -557581 | -295518 | [5 empty] | 270904 |  | 121043
2022-09-19 | September 2022 Review | Cost Increase | Local road improvements | Low cost / low risk improvements | DOC (Otago) | Low cost / low risk improvements 2021-24 | Local road improvements (SPR) |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 170000 | 86700 | [5 empty] | 276078 |  | 120999
2022-09-30 | September 2022 Review | Cost Increase | External funding | New roads | NZTA (Nelson) | Nelson Future Access | Detailed Business Case | DBC - Nelson Future Access | VHHL | VHHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project closed. | 1768 | 1768 |  |  | 2.2 | 2.2 | 60032525 | 234004 | 60032525 | 121113
2022-09-01 | September 2022 Review | Cost Increase | State highway improvements | New roads | NZTA (Waikato) | SH1 Wex Long Swamp Section | Construction |  | H_L | MML | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | PLA for 4 lane upgrades of $505K | 546468 | 546468 |  |  | 1.3 | 1.3 |  | 270039 | 60210358 | 120362
2022-09-16 | September 2022 Review | Cost Decrease | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | NZTA (Auckland) | North Western Bus Improvements (ST) | Implementation | NLTF Programme Contingency moved to 60062437 | VHHL | VHLL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | INTERPHASE TRANSFER : Moving $3,796,296 contingency allocation from 60067690 into 60062437 as per request to have this consolidated. | -4100000 | -4100000 |  |  | 1.1 | 1.3 | NLTF Programme Contingency | 281901 | 60067690 | 120980
2022-09-01 | September 2022 Review | Cost Increase | Investment management (incl. Transport Planning) | Programme Business Case Development | Hamilton City Council | Hamilton Waikato Metro Spatial Plan | Programme business case |  | V_L* | V_H | N | 1 | Approved | Approved by Chief Financial Officer (CFO) | Accelerating mode shift and emission reduction, as well as land use and transport integration. | 92201 | 47022 | [5 empty] | 278093 |  | 120379
2022-09-16 | September 2022 Review | Cost Increase | External funding | Property purchase (State highways) | NZTA (BOP) | NZUP Takitimu North Link Stage 1 | Property | NZ Upgrade Programme | H_L | HHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | nterphase transfer of $1,835,000 from 60057025 (Imp: -$1,835,000) to 60057020 (Pre-Imp: +$1,080,00) and 60057024 (Property: +$755,000) to re-distribute contingency drawdown. | 781425 | 781425 |  |  | 2 | 2 | 60057024 | 270279 | 60057024 | 120900
2022-09-01 | September 2022 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Waikato) | SH1 Wex Long Swamp Section | Property | 16837 | H_L | MML | N |  | Approved | Approved by Chief Financial Officer (CFO) | PLA for $325k to close out outstanding property | 343402 | 343402 |  |  | 1.3 | 1.3 | 60404372 | 194966 | 60404372 | 120356
2022-09-27 | September 2022 Review | Cost Decrease | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Bus Network Advice | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer allocation to 60068318. | -839214 | -528394 |  |  | 1.2 | 1 |  | 280359 | 60065976 | 121082
2022-09-27 | September 2022 Review | Cost Decrease | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Johnsonville/ Ngauranga | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer to Item 60068328. | -1911935 | -1093564 |  |  | 1.2 | 1 |  | 280367 | 60066164 | 121017
2022-09-23 | September 2022 Review | Cost Decrease | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS CBD Modelling | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -294222 | -185251 |  |  | 1.2 | 1 |  | 280360 | 60065977 | 121047
2022-09-27 | September 2022 Review | Cost Decrease | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Newtown to Berhampore | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer allocation to 60068331. | -2933624 | -1847097 |  |  | 1.2 | 1 |  | 280368 | 60066166 | 121074
2022-09-27 | September 2022 Review | Cost Decrease | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS BPAP Targeted Imp. | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer to Item 60067268. | -103816 | -38433 |  |  | 1.2 | 1 |  | 280357 | 60065973 | 121012
2022-09-23 | September 2022 Review | Cost Decrease | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Taranaki/ Wallace/ John Sts | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer to Item 60068341. | -1987441 | -1148434 |  |  | 1.2 | 1 |  | 280362 | 60066155 | 121013
2022-09-27 | September 2022 Review | Cost Decrease | Public transport infrastructure | Public transport facilities & infrastructure - renewals | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS CBD to Kilbirnie and Miramar | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -4300890 | -2707968 |  |  | 1.2 | 1 |  | 280363 | 60066135 | 121089
2022-09-23 | September 2022 Review | Cost Increase | Public transport infrastructure | Public transport facilities & infrastructure - renewals | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS General Targeted Imp. | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move to 60068314 | 0 | 65383 |  |  | 1.2 | 1 |  | 280365 | 60066161 | 121056
2022-09-23 | September 2022 Review | Cost Decrease | Public transport infrastructure | Public transport facilities & infrastructure - renewals | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS General Targeted Imp. | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move $36,770 from 2022/23 to 2023/24 | -103816 | -103816 |  |  | 1.2 | 1 |  | 280365 | 60066161 | 120879
2022-09-27 | September 2022 Review | Cost Decrease | Public transport infrastructure | Public transport facilities & infrastructure - renewals | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Tar St and CBD to Newtown | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer allocation to 60068337. | -5093204 | -3206832 |  |  | 1.2 | 1 |  | 280361 | 60066154 | 120888
2022-09-27 | September 2022 Review | Cost Decrease | Public transport infrastructure | Public transport facilities & infrastructure - renewals | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Hamilton Rd to Shelly Bay Rd | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -343087 | -186219 |  |  | 1.2 | 1 |  | 280366 | 60066163 | 121016
2022-09-08 | September 2022 Review | Cost Decrease | Public transport services | Public transport operations and management | Bay of Plenty Regional Council | Government reduced public transport fares scheme (Crown) | Implementation | PT Ops and Man - Reduced Fares | VHHL | VHHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | Cost-neutral rebalancing of funding between phases. Sub-delegated to the Activity Class Manager for public transport. | -37500 | -37500 | [5 empty] | 281225 |  | 120894
2022-09-30 | September 2022 Review | Cost Decrease | State highway improvements | Replacement of bridges and other structures | NZTA (BOP) | HPMV SH2 Opotiki to Gisborne boundary | Implementation | NLTF commitment to Tpackage - PGF | H_M | H_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Physical works complete, $2,336,664 of surplus funds to be returned as per the forcast spend. | -2523576 | -2523576 |  |  | 0 | 2.4 | 60051622 | 265922 | 60051622 | 121059
2022-09-05 | September 2022 Review | Cost Increase | State highway improvements | Replacement of bridges and other structures | NZTA (Northland) | SH10 Kaeo Bridge upgrade | Implementation | NLTF-SH Improvements | HHL | MHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Pre-Implementation phase (60038590) completed with $46754 underspend. Additional allocation to be transferred to this Implementation phase. Minor cashflow transfer between years, to shift some spending into future years. | 50493 | 50493 |  |  | 0.6 | 0.6 | 60038592 | 269811 | 60038592 | 120710
2022-09-05 | September 2022 Review | Cost Decrease | State highway improvements | Replacement of bridges and other structures | NZTA (Northland) | SH10 Kaeo Bridge upgrade | Pre-implementation* | NLTF-SH Improvements | HHL | MHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Pre-Implementation phase completed. Surplus $46,754 budget to be transferred to Implementation Phase (60038591). | -50494 | -50494 |  |  | 0.6 | 0.6 | 60038591 | 278788 | 60038591 | 120709
2022-09-01 | September 2022 Review | Cost Increase | Road to Zero | Road improvements | Auckland Transport | Safe Speeds - Phases 1-3 | Implementation | Safe Speeds - Phases 1-3 - Imp | VH_VH | VHHVH | N | 0 | Approved with conditions | Approved with conditions by Chief Financial Officer (CFO) | The cost increase is due to cost escalation and detailed design changes needed following public consultation - there is no change of scope. More detail is provided in the CSA funding request memo to Delegations which is attached to the supporting documents section of TIO. | 6367602 | 3247477 | that the funding decision by the Chief Financial Officer is noted to the Waka Kotahi Board in the Transport Services funding decision report, given that the total approved cost of the programme is increased from $49,297,544 to $56,118,752. |  | 0 | 12 | 324.2647 | 278712 |  | 120312
2022-09-01 | September 2022 Review | Cost Increase | Road to Zero | Road improvements | Auckland Transport | Safe Speeds - Phases 1-3 | Pre-implementation* | Safe Speeds - Phases 1-3 - Pre-Imp | VH_VH | VHHVH | N | 0 | Approved with conditions | Approved with conditions by Chief Financial Officer (CFO) | The cost increase is due to cost escalation and detailed design changes needed following public consultation - there is no change of scope. More detail is provided in the CSA funding request memo to Delegations which is attached to the supporting documents section of TIO. | 453606 | 231339 | that the funding decision by the Chief Financial Officer is noted to the Waka Kotahi Board in the Transport Services funding decision report, given that the total approved cost of the programme is increased from $49,297,544 to $56,118,752. |  | 0 | 12 | 324.2696 | 279201 |  | 120311
2022-09-05 | September 2022 Review | Cost Decrease | External funding | Road improvements | Gisborne District Council | Tairawhiti Roading - LOS improvements (PGF2) East Cape Road | Construction | PGF2 Route 3 Tiniroto/Wharekopae Roads | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2022/23 as activity is claiming complete | -1080 | -1080 |  |  | 1 | 1 | PGF2 Route 3 Tiniroto/Wharekopae Roads | 269598 |  | 120770
2022-09-30 | September 2022 Review | Cost Decrease | Local road improvements | Road improvements | Hamilton City Council | Bankwood Comries Intersection Safety Improvements SSI | Implementation | construction | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2022/23 as activity is claiming complete | -32759 | -24733 |  |  | 0 | 1.6 | implementation | 269901 |  | 121025
2022-09-05 | September 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (Auckland) | NZUP Mill Road Corridor | Implementation | Mill Road Corridor NZUP | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | NZUP Mill Rd budget to be reduced by $52.2M to fund SH22 (155112022) and Waihoehoe Rd (155122022) NZUP projects. Mill Rd Pre-Imp phase to be reduced by $8.5M, and Implementation by $43.6M. Total South Auckland Package appropriation is $403M incl. admin. | -45167659 | -45167659 |  |  | 1.2 | 1.2 | NZ Upgrade Programme | 269744 | 60056119 | 120789
2022-09-05 | September 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (Auckland) | NZUP Mill Road Corridor | Pre-implementation* | NZ Upgrade Programme | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | NZUP Mill Rd budget to be reduced by $52.2M to fund SH22 (155112022) and Waihoehoe Rd (155122022) NZUP projects. Mill Rd Pre-Imp phase to be reduced by $8.5M, and Implementation by $43.6M. Total South Auckland Package appropriation is $403M incl. admin. | -8834323 | -8834323 |  |  | 1.2 | 1.2 |  | 269742 | 60056117 | 120788
2022-09-05 | September 2022 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Auckland) | SH22: SH1 Drury to Paerata (Glenbrook RAB) | Implementation | R2Z | HHL | HHH | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Covid Claim approved $496,102 | 535789 | 535789 |  |  | 0 | 1.6 | R2Z | 278492 | 60062180 | 120606
2022-09-16 | September 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (BOP) | NZUP Takitimu North Link Stage 1 | Implementation | NZ Upgrade Programme | H_L | HHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $1,835,000 from 60057025 (Imp: -$1,835,000) to 60057020 (Pre-Imp: +$1,080,00) and 60057024 (Property: +$755,000) to re-distribute contingency drawdown | -1899223 | -1899223 |  |  | 2 | 2 | 60057025 | 270272 | 60057025 | 120901
2022-09-19 | September 2022 Review | Cost Increase | External funding | Road improvements | NZTA (BOP) | NZUP Takitimu North Link Stage 1 | Pre-implementation* | NZ Upgrade Programme | H_L | HHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer outstanding balance of $79,290 for Pre-Implemenation that did not happen in previous review that was to (Transfer outstanding balance of $79,290 for Pre-Implemenation. Interphase transfer of $1,835,000 from 60057025 (Imp: -$1,835,000) to 60057020 (Pre-Imp: +$1,080,00) and 60057024 (Property: +$755,000) to re-distribute contingency drawdown) | 82065 | 82065 |  |  | 2 | 2 | 60057020 | 173210 | 60057020 | 120994
2022-09-16 | September 2022 Review | Cost Increase | External funding | Road improvements | NZTA (BOP) | NZUP Takitimu North Link Stage 1 | Pre-implementation* | NZ Upgrade Programme | H_L | HHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $1,835,000 from 60057025 (Imp: -$1,835,000) to 60057020 (Pre-Imp: +$1,080,00) and 60057024 (Property: +$755,000) to re-distribute contingency drawdown. | 1035735 | 1035735 |  |  | 2 | 2 | 60057020 | 173210 | 60057020 | 120899
2022-09-15 | September 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (BOP) | SH2: Baypark to Bayfair Link Upgrade (was MGI) | Investigation | New Works | H_H | H_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Surplus unused funds. | -118908 | -118908 |  |  | 2.5 | 2.5 | 60215477 | 194041 | 60215477 | 120955
2022-09-16 | September 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Canterbury) | Groynes to Sawyers Arms 4L | Construction | Construction - 324 | H_M | H_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Defect notification period over, surplus the remaining allocation of the project | -8180 | -8180 |  |  | 1.4 | 1.4 |  | 270268 | 60210492 | 120898
2022-09-08 | September 2022 Review | Cost Increase | External funding | Road improvements | NZTA (Canterbury) | NZUP Brougham St Corridor Improvements | Detailed Business Case | NZ Upgrade Programme | H_L | HMM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $23,445 from WC 60056968 (Imp) to WC 6005701 (DBC) to close out DBC phase. | 24266 | 24266 |  |  | 4 | 4 | 60057015 | 246831 | 60057015 | 120777
2022-09-08 | September 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Canterbury) | NZUP Brougham St Corridor Improvements | Implementation | NZUP Brougham St Corridor Improvements | H_L | HMM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $23,445 from WC 60056968 (Imp) to WC 6005701 (DBC) to close out DBC phase. | -24266 | -24266 |  |  | 4 | 4 | 60056968 | 231610 | 60056968 | 120778
2022-09-30 | September 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (Canterbury) | NZUP Walnut Avenue Intersection Improvements | Implementation | NZ Upgrade | M_L | MHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $24,233 from (Imp) 60211591 to (Pre-Imp) 60057031 to close-off the Pre-Imp phase. | -25082 | -25082 |  |  | 1.8 | 1.8 | 60211591 | 231796 | 60211591 | 121092
2022-09-30 | September 2022 Review | Cost Increase | External funding | Road improvements | NZTA (Canterbury) | NZUP Walnut Avenue Intersection Improvements | Pre-implementation* | NZ Upgrade Programme | M_L | MHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $24,233 from (Imp) 60211591 to (Pre-Imp) 60057031 to close-off the Pre-Imp phase. | 25081 | 25081 |  |  | 1.8 | 1.8 | 60057031 | 270287 | 60057031 | 121091
2022-09-15 | September 2022 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (Marlborough) | SH6 Blenheim to Nelson - SH6/SH62 | Property | R2Z | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -90425 | -90425 |  |  | 0 | 1.6 |  | 278556 |  | 120957
2022-09-05 | September 2022 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (Waikato) | SH1 and Grey St IS | Pre-implementation* |  | VHHM | VHHL | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | scope change to cheaper more suitable option | -402019 | -402019 |  |  | 10 | 10 | 22903 | 277334 | 60061021 | 120749
2022-09-30 | September 2022 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Waikato) | SH3 Awakino Tunnel Bypass | Construction | Construction - NLTF funding | H_L | M_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow Crown Funding allocation to Construction Phase - NLTF funding. | 1577541 | 1577541 |  |  | 0.8 | 0.8 | Construction-60038686 | 263999 |  | 121112
2022-09-30 | September 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (Waikato) | SH3 Awakino Tunnel Bypass | Implementation | Construction implementation | H_L | M_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -1577541 | -1577541 |  |  | 0.8 | 0.8 | 60038686 | 246371 | 60038686 | 121111
2022-09-06 | September 2022 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Waikato) | Waikato SH Speed Management Guide Implementation | Implementation | Waikato SH Speed Management Implementation | VHHH | VHHL | N | 1 | Approved | Approved by Chief Financial Officer (CFO) |  | 19574623 | 19574623 |  |  | 0 | 4.6 |  | 264443 | 60053145 | 120711
2022-09-30 | September 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Waikato) | Waikato SH Speed Management Guide Implementation | Implementation | Waikato SH Speed Management Implementation | VHHH | VHHL | N | 1 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -19502085 | -19502085 |  |  | 0 | 4.6 |  | 264443 | 60053145 | 121108
2022-09-14 | September 2022 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Wellington) | SH58 Safety Improvements | Implementation |  | VHHL | HML | N | 2 | Approved | Approved by Chief Financial Officer (CFO) |  | 280955 | 280955 |  |  | 1.3 | 1.3 |  | 279258 | 60064033 | 120873
2022-09-05 | September 2022 Review | Cost Decrease | External funding | Road improvements | Wairoa District Council | PGF Wairoa High Productivity Motor Vehicle Upgrades | Implementation | HPMV upgrades | M__ | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | project complete | -37328 | -37328 |  |  | 1 | 5.5 |  | 269312 |  | 120706
2022-09-09 | September 2022 Review | Cost Increase | Public transport services | Total Mobility wheelchair hoists and ramps | Invercargill City Council | Public Transport Programme 2021-24 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reinstate WC519 funding which was accidently surplused during EOY processing | 4500 | 2700 | [5 empty] | 272871 |  | 120922
2022-09-09 | September 2022 Review | Cost Increase | Public transport services | Total Mobility wheelchair hoists and ramps | Marlborough District Council | Public Transport Programme 2021-24 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reinstate WC519 funding which was accidently surplused during EOY processing | 24000 | 14400 | [5 empty] | 273081 |  | 120921
2022-09-06 | September 2022 Review | Cost Increase | Public transport services | Total Mobility wheelchair hoists and ramps | Northland Regional Council | Public Transport Programme 2021-24 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reinstate WC519 funding which was accidently surplused during EOY processing | 50000 | 30000 | [5 empty] | 273671 |  | 120872
2022-09-08 | September 2022 Review | Cost Increase | Public transport services | Total mobility operations | Bay of Plenty Regional Council | Government reduced public transport fares scheme (Crown) | Implementation | Total Mobility - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | Cost-neutral rebalancing of funding between phases. Sub-delegated to the Activity Class Manager for public transport. | 37500 | 37500 | [5 empty] | 281224 |  | 120895
2022-09-09 | September 2022 Review | Cost Decrease | Walking and cycling improvements | Walking facilities | NZ Transport Agency | Innovating Streets Programme 2021-24 | Implementation | Implementation - Funding allocated to AOs | HHL | VHHVH | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Move funding for CHNDC, Gisborne DC, Hutt City CC, Tasman DC and Wellington CC | -7855765 | -7855765 |  |  | 1 | 1 |  | 279202 |  | 120911
2022-09-20 | September 2022 Review | Cost Decrease | Walking and cycling improvements | Walking facilities | NZ Transport Agency | Innovating Streets Programme 2021-24 | Implementation | Implementation - Funding allocated to AOs | HHL | VHHVH | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Funds moving to Auckland Transport SfP | -5935446 | -5935446 |  |  | 1 | 1 |  | 279202 |  | 121011
2022-09-06 | September 2022 Review | Cost Increase | Walking and cycling improvements | Walking facilities | NZTA (Waikato) | SH1 Tamahere Interchange Ped/Cycle | Single-Stage Business Case | SH1 Tamahere Interchange Ped/Cycle | HMH | H_H | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 3186 | 3186 |  |  | 0 | 0 |  | 275486 | 60060050 | 120868
2022-09-16 | September 2022 Review | Cost Decrease | Walking and cycling improvements | Walking facilities | NZTA (Waikato) | SH1 Tamahere Interchange Ped/Cycle | Single-Stage Business Case | SH1 Tamahere Interchange Ped/Cycle | HMH | H_H | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -3186 | -3186 |  |  | 0 | 0 |  | 275486 | 60060050 | 120885
2022-09-27 | September 2022 Review | Cost Decrease | Walking and cycling improvements | Walking facilities | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Bowen St | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer allocation to 60068315. | -756610 | -458030 |  |  | 1.2 | 1 |  | 280358 | 60065975 | 121080
2022-09-23 | September 2022 Review | Cost Decrease | Walking and cycling improvements | Walking facilities | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS South West CBD | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer to Item 60068334. | -2608949 | -1433405 |  |  | 1.2 | 1 |  | 280699 | 60066730 | 121014
2022-09-01 | September 2022 Review | Cost Increase | Walking and cycling improvements | Walking facilities | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS South West CBD | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Correct 3rd Party contribution. | 0 | 579896 |  |  | 1.2 | 1 |  | 280699 | 60066730 | 120799
2022-09-27 | September 2022 Review | Cost Decrease | Walking and cycling improvements | Walking facilities | NZTA (Wellington) | LGWM City Streets | Single-Stage Business Case | LGWM CS Featherston St | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transfer to Item 60068322. | -2569035 | -1475705 |  |  | 1.2 | 1 |  | 280364 | 60066160 | 121015
2022-09-23 | September 2022 Review | Cost Decrease | Walking and cycling improvements | Walking facilities | NZTA (Wellington) | LGWM ED Central City and SH1 walking cycling and safer speed | Implementation | CCPI | HHM | VHHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow allocation from 2022/23 to 60068425. | -1783379 | -413084 |  |  | 1.2 | 1 |  | 279815 | 60053806 | 120884