## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Phase Label | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Decision Status | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR | Your Phase reference | TIO Phase id | SAP item id | TIO Request id
2022-11-01 | November 2022 Review | New approval | Investment management (incl. Transport Planning) | Activity management planning improvement | Clutha District Council | Activity Management Plan 2021-24 | Improvement to existing AMP |  | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The funding enables an AMP/RPTP to be developed and contribute to the priority outcomes of the relevant GPS, and the long term outcomes of the community. | 236800 | 153920 |  |  |  |  | CDC WC003 | 277470 |  | 115302
2022-11-04 | November 2022 Review | New approval | Investment management (incl. Transport Planning) | Activity management planning improvement | NZ Transport Agency | 2021-24 NLTP Funds Management | Repayment | AC1 - Admin | LLVL | LLVL | N | 12 | Approved | Approved by Chief Financial Officer (CFO) | Required to reflect actual spend as recommended by Snr Mgr OPPP, Investment and Finance | 1019600 | 1019600 | [5 empty] | 283273 |  | 121430
2022-11-28 | November 2022 Review | New approval | Road to Zero | Activity management planning improvement | NZ Transport Agency | State Highway Speed Management Plan | Implementation | 60069223 | VHHL | VHHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | High alignment to strategic priorities of the GPS and is a critical component of the Road to Zero programme. Under the Road to Zero Strategy, Land Transport Rule: Setting of Speed Limits 2022, Waka Kotahi as an RCA is required to produce a Speed Management Plan (SMP). The decision is neutral in relation to the climate change strategic priority set out in the GPS and the proposal is consistent with the GPS as a whole. | 3562300 | 3562300 |  |  |  | 2.1 | SAP-PPM Item Id 60069223 | 283272 |  | 121476
2022-11-01 | November 2022 Review | New approval | Investment management (incl. Transport Planning) | Activity management planning improvement | Opotiki District Council | Activity Management Plan 2021-24 | Improvement to existing AMP |  | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The funding enables an AMP/RPTP to be developed and contribute to the priority outcomes of the relevant GPS, and the long term outcomes of the community. | 100000 | 75000 | [5 empty] | 277675 |  | 120804
2022-11-01 | November 2022 Review | New approval | Investment management (incl. Transport Planning) | Activity management planning improvement | Porirua City Council | Activity Management Plan 2021-24 | Improvement to existing AMP |  | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The funding enables an AMP/RPTP to be developed and contribute to the priority outcomes of the relevant GPS, and the long term outcomes of the community. | 280000 | 147800 | [5 empty] | 275304 |  | 120972
2022-11-01 | November 2022 Review | New approval | Investment management (incl. Transport Planning) | Activity management planning improvement | Rotorua Lakes Council | Activity Management Plan 2021-24 | Improvement to existing AMP |  | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The funding enables an AMP/RPTP to be developed and contribute to the priority outcomes of the relevant GPS, and the long term outcomes of the community. | 100000 | 56000 | [5 empty] | 282864 |  | 121215
2022-11-01 | November 2022 Review | New approval | Investment management (incl. Transport Planning) | Activity management planning improvement | Waitaki District Council | Activity Management Plan 2021-24 | Improvement to existing AMP |  | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The funding enables an AMP/RPTP to be developed and contribute to the priority outcomes of the relevant GPS, and the long term outcomes of the community. | 200000 | 114000 |  |  |  |  | Activity Management Planning | 275961 |  | 116687
2022-11-04 | November 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Gisborne District Council | SfP Gisborne Community Trials | Implementation | SfP Gisborne Uawa Community Trials Implementation | VHHL | HHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | The key benefits are: - Develop connected walking and cycling networks faster to increase the uptake and use of active travel modes - Reduce transport related emissions through the increase in walking and cycling - Increase knowledge and build capability across the sector in tactical urbanism, fast delivery, and fail fast delivery/ implementation techniques - Improve road safety for active travel users - The IPM assessment is recorded in TIO as Very High GPS alignment, High scheduling, and Very High efficiency Funds have been moved from Grey St Community Trials | 347580 | 312822 |  |  | 1 | 1 |  | 283257 |  | 121438
2022-11-22 | November 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Hamilton City Council | Biking & Micro-mobility citywide programme | Pre-implementation* | Design | HHH | HHM | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | Primary benefit is Impact on mode choice. Encouraging people to use alternative modes other than private vehicle. This will also contribute towards the Emission Reduction Plan targets. | 1900000 | 969000 |  |  | 3 | 3 |  | 262664 |  | 120581
2022-11-04 | November 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | NZ Transport Agency | 2021-24 NLTP Funds Management | Repayment | AC3 | LLVL | LLVL | N | 12 | Approved | Approved by Chief Financial Officer (CFO) | Required to reflect actual spend as recommended by Snr Mgr OPPP, Investment and Finance | 1478000 | 1478000 | [5 empty] | 283278 |  | 121434
2022-11-02 | November 2022 Review | New approval | Walking and cycling improvements | Cycling facilities | Timaru District Council | SfP Timaru District Council 2021-24 | Implementation | SfP - Timaru Port Loop Trial | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The key benefits are: - Develop connected walking and cycling networks faster to increase the uptake and use of active travel modes - Reduce transport related emissions through the increase in walking and cycling - Increase knowledge and build capability across the sector in tactical urbanism, fast delivery, and fail fast delivery/ implementation techniques - Improve road safety for active travel users - The IPM assessment is recorded in TIO as Very High GPS alignment, High scheduling, and Very High efficiency Amount assigned to Timaru DC has been confirmed by Multimodal & Innovation team | 1150000 | 1035000 |  |  |  | 1 |  | 283235 |  | 121396
2022-11-17 | November 2022 Review | New approval | Local road maintenance | Emergency works | Dunedin City Council | E/W July 2022 Rain and Wind Damage | Construction | Response and reinstatement of damaged sites | ___ |  | N |  | Approved | Approved by National Manager, Maintenance and Operations (Transport Services) | 5 months of rainfall in one month culminating in event | 2026892 | 1053984 | [5 empty] | 282977 |  | 120951
2022-11-28 | November 2022 Review | New approval | Local road maintenance | Emergency works | Far North District Council | EW - Far North DC August 2022 | Construction | Phase 1 - Initial Response - EW August 2022 | ___ |  | N |  | Approved | Approved by National Manager, Programmes and Standards (Transport Services) | 1. Addresses the initial response / investigation which enables the reinstatement of levels of service that have been impacted as a result of this significant event; 2. Maintains appropriate customer levels of service, to provide safe and resilient access to social and economic opportunities | 152177 | 105002 |  |  |  |  | EW August 2022 | 282954 |  | 121334
2022-11-01 | November 2022 Review | New approval | Local road maintenance | Emergency works | Far North District Council | EW FNDC July 2022 | Construction | Initial Response - EW July 2022 | ___ |  | N |  | Approved | Approved by System Manager, Maintenance and Operations (Transport Services) | refer supporting docs | 1146355 | 790985 |  |  |  |  | EW July 2022 | 282953 |  | 120953
2022-11-21 | November 2022 Review | New approval | Local road maintenance | Emergency works | Kapiti Coast District Council | Emergency Works August Storm Event 2022 | Construction | Initial Response - Maungakotukutuku Road | ___ |  | N |  | Approved | Approved by System Manager, Maintenance and Operations (Transport Services) | That the Regional Manager Maintenance and Operations (Transport Services): Approves Kapiti Coast Emergency Works at a total cost of $139,130 and a FAR of 51% (NLTF Share $70,956). | 139130 | 70956 | [5 empty] | 283098 |  | 121146
2022-11-15 | November 2022 Review | New approval | State highway maintenance | Emergency works | NZTA (BOP) | EW BOPE RW July HR from 20220708 | Construction |  | ___ |  | N |  | Approved | Approved by System Manager, Maintenance and Operations (Transport Services) | I am comfortable that this application qualifies for Emergency Works funding as it will be used to recover the network to the same level of service that it was at before this storm event occurred. Resilience improvements to be funded separately and if deemed appropriate, should be delivered at the same time as the Emergency Works. (MF) I am content that this event sits with the current PIKB guidance for emergency works and I recommend approval NAC | 540000 | 540000 | [5 empty] | 282157 | 60067964 | 121531
2022-11-01 | November 2022 Review | New approval | State highway maintenance | Emergency works | NZTA (BOP) | EW SH2-294/2.4 Waiotahe Slip 20221019 | Construction |  | ___ |  | N |  | Approved | Approved by System Manager, Maintenance and Operations (Transport Services) | I am content that this event fits within the current PIKB guidance for emergency works funding. I recommend approval NAC | 540000 | 540000 | [5 empty] | 283201 | 60068953 | 121425
2022-11-18 | November 2022 Review | New approval | State highway maintenance | Emergency works | NZTA (Gisborne) | EW SH2 Matawai HRE 20220715 | Construction |  | ___ |  | N |  | Approved | Approved by National Manager, Maintenance and Operations (Transport Services) | I am content that this event fits within the current PIKB funding guidance for emergency works funding. I recommend approval (NAC). | 1792800 | 1792800 | [5 empty] | 282156 | 60067958 | 121574
2022-11-02 | November 2022 Review | New approval | State highway maintenance | Emergency works | NZTA (Manawatu/Whanganui) | EW Saddle/Pahitaua HR 20220713 | Construction |  | ___ |  | N |  | Approved | Approved by System Manager, Maintenance and Operations (Transport Services) | I support this application and recommend approval NAC | 864000 | 864000 | [5 empty] | 282154 | 60067931 | 121427
2022-11-28 | November 2022 Review | New approval | State highway maintenance | Emergency works | NZTA (Nelson) | EW Nelson Severe HR 20220820 | Construction |  | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | The key benefit in approving this funding request is returning the road network to a pre storm level of service | 24589250 | 24589250 | [5 empty] | 282726 | 60068405 | 121420
2022-11-02 | November 2022 Review | New approval | State highway maintenance | Emergency works | NZTA (Northland) | EW Mangamuku/Kaeo HR 20220818 | Construction |  | ___ |  | N |  | Approved with conditions | Approved with conditions by National Manager, Programmes and Standards (Transport Services) | This funding enables works to facilitate early recovery for the Mangamuka corridor. Emerging options for this state highway corridor will be advised to the Waka Kotahi Board in November 2022 and that Board will be informed of this approval. See condition attached to this approval. | 14040000 | 14040000 | CFO will need to report this approval (by National Manager, Prog & Standards) of $14.4M to the Board |  |  |  |  | 282705 | 60068350 | 121335
2022-11-04 | November 2022 Review | New approval | State highway maintenance | Emergency works | NZTA (Otago) | EW Otago RW Coast & Central HR 20220718 | Construction |  | ___ |  | N |  | Approved | Approved by National Manager, Maintenance and Operations (Transport Services) | I support Rogers comments and recommend approval. Note: This is very close to the delegation limit for Wayne. $5M. If the cost increases as the recovery develops, it will need to go back through the delegation committee for Vanessa endorsement. I am content that this event sits within the current PIKB guidance for emergency works funding. I recommend approval NAC | 4996176 | 4996176 | [5 empty] | 282167 | 60068017 | 121442
2022-11-25 | November 2022 Review | New approval | State highway maintenance | Emergency works | NZTA (Waikato) | EW Desert Road RS763 HR 20220819 | Construction |  | ___ |  | N |  | Approved | Approved by National Manager, Maintenance and Operations (Transport Services) | Commentary supporting the decision to recommend approval: This has been a change in step for the delivery of EW works. This project has been delivered outside the NOC contract. The design and build elements have been provided by GSI. The progression of this project has been outstanding I commend the network team and the geotechnical SME support. I hope we can continue to build on the experience gained on this project. I am content that this sits within the current PIKB guidance for emergency works funding and I recommend approval NAC | 2156992 | 2156992 | [5 empty] | 282724 | 60068383 | 121623
2022-11-25 | November 2022 Review | New approval | Local road maintenance | Emergency works | Rotorua Lakes Council | EW - Rotorua LC Storm Damage July 2022 | Construction | Phase 2 - Construction | ___ |  | N |  | Approved | Approved by National Manager, Maintenance and Operations (Transport Services) | That the Senior Manager System Management: Approves the Recovery Phase (Phase 2) of Rotorua Lakes Council Emergency Works at a total cost of $2,020,544 (NLTF Share $1,443,436). The enhanced FAR is triggered for this phase and equates to $1,185,337. Phase 1 - Initial response, investigation & design funding was approved In September 2022. Phase 2 â€“ This application is for the recovery of the 4 Major sites eligible for E/W's funding. All work in this application complies with PIKB. Sites that didn't were removed from the application and will be monitored and/or funded via another work category. | 460890 | 258098 | [5 empty] | 282766 |  | 120731
2022-11-29 | November 2022 Review | New approval | Local road maintenance | Emergency works | Tararua District Council | EW Event March 2022 | Construction |  | ___ |  | N |  | Approved | Approved by National Manager, Maintenance and Operations (Transport Services) | As per Regional Office recommendation | 4364850 | 3771747 |  |  |  |  | Event March 2022 | 281738 |  | 118130
2022-11-16 | November 2022 Review | New approval | Local road maintenance | Emergency works | Thames-Coromandel District Council | EW TCDC July 2022 | Construction | Initial Response, Investigation an Design | ___ |  | N |  | Approved | Approved by National Manager, Maintenance and Operations (Transport Services) | Investment required to repair storm damage / return LoS that existed prior to this weather event and complete site investigation and reinstatement option assessment for those sites requiring slope stability improvements / retaining structures. | 551000 | 391210 | [5 empty] | 282904 |  | 120847
2022-11-14 | November 2022 Review | New approval | Local road maintenance | Emergency works | Waitomo District Council | EW - Waitomo DC February 2022 Cyclone Dovi | Construction | Construction & MSQA Of Permanent Construction Site | ___ |  | N |  | Approved | Approved by National Manager, Programmes and Standards (Transport Services) | Permanent reinstatement works approval of $6.38M for 22-23. See attached doc for details. | 240737 | 180553 | [5 empty] | 282952 |  | 120914
2022-11-04 | November 2022 Review | New approval | Local road maintenance | Network and asset management | NZ Transport Agency | 2021-24 NLTP Funds Management | Repayment | AC8 | LLVL | LLVL | N | 12 | Approved | Approved by Chief Financial Officer (CFO) | Required to reflect actual spend as recommended by Snr Mgr OPPP, Investment and Finance | 80000 | 80000 | [5 empty] | 283274 |  | 121429
2022-11-04 | November 2022 Review | New approval | State highway maintenance | Network and asset management | NZ Transport Agency | 2021-24 NLTP Funds Management | Repayment | AC9 | LLVL | LLVL | N | 12 | Approved | Approved by Chief Financial Officer (CFO) | Required to reflect actual spend as recommended by Snr Mgr OPPP, Investment and Finance | 15573300 | 15573300 | [5 empty] | 283279 |  | 121436
2022-11-28 | November 2022 Review | New approval | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | Christchurch City Council | PT Future Infrastructure Works | Detailed Business Case | PT Futures Infrastructure Capital Work | VHHL | VHML | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | Waka Kotahi endorse PT Futures Business Case (IBC) in May'21. The POE as attached in supporting document is prepared to carry out a Detailed Business Case for the recommended Infrastructure works. It is expected IQA will be completed after completion of Business Case. approval will enable improving mode shift from private passenger vehicle based trips to public transport. | 400000 | 204000 |  |  | 2.1 | 2.1 | 914 | 277095 |  | 121481
2022-11-01 | November 2022 Review | New approval | Investment management (incl. Transport Planning) | Programme Business Case Development | NZ Transport Agency | Innovation Programme | Programme business case |  | HHL | VHHM | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | This funding approval enables improved value for money and future performance of the land transport system. | 15000000 | 15000000 |  |  |  |  | 60069122 | 277975 |  | 118621
2022-11-25 | November 2022 Review | New approval | Road to Zero | Property purchase (State highways) | NZTA (Canterbury) | SH1 Rakaia to Ashburton CI - Stage 2 | Property |  | VHHL | HHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) |  | 1688000 | 1688000 |  |  | 0 | 1.6 |  | 277997 | 60061650 | 117947
2022-11-25 | November 2022 Review | New approval | Road to Zero | Property purchase (State highways) | NZTA (Canterbury) | SH1 Templeton to Selwyn River | Property | SH1 Templeton to Selwyn River | VHHL | VHHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) |  | 896750 | 896750 |  |  | 10 | 10 | 41 | 277305 | 60060947 | 121482
2022-11-25 | November 2022 Review | New approval | Road to Zero | Property purchase (State highways) | NZTA (Canterbury) | SH1 Timaru to St Andrews | Property | SH1 Timaru to St Andrews | VHHL | VHHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) |  | 1962300 | 1962300 |  |  | 10 | 10 | 293 | 277339 | 60061001 | 121551
2022-11-25 | November 2022 Review | New approval | Road to Zero | Property purchase (State highways) | NZTA (Canterbury) | SH71 Rangiora to SH1 | Property | SH71 Rangiora to SH1 | VHHL | VHHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) |  | 1633140 | 1633140 |  |  | 10 | 10 | 641 | 277327 | 60060995 | 121483
2022-11-30 | November 2022 Review | New approval | Road to Zero | Property purchase (State highways) | NZTA (Canterbury) | SH73 West Melton to Yaldhurst | Property | SH73 West Melton to Yaldhurst | VHHL | VHHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) |  | 1055000 | 1055000 |  |  | 10 | 10 | 353 | 277343 | 60061029 | 121635
2022-11-04 | November 2022 Review | New approval | Public transport infrastructure | Public transport facilities & infrastructure - renewals | NZ Transport Agency | 2021-24 NLTP Funds Management | Repayment | AC5 | LLVL | LLVL | N | 12 | Approved | Approved by Chief Financial Officer (CFO) | Required to reflect actual spend as recommended by Snr Mgr OPPP, Investment and Finance | 1447900 | 1447900 | [5 empty] | 283275 |  | 121431
2022-11-04 | November 2022 Review | New approval | Public transport services | Public transport operations and management | NZ Transport Agency | 2021-24 NLTP Funds Management | Repayment | AC4 | LLVL | LLVL | N | 12 | Approved | Approved by Chief Financial Officer (CFO) | Required to reflect actual spend as recommended by Snr Mgr OPPP, Investment and Finance | 15000 | 15000 | [5 empty] | 283280 |  | 121435
2022-11-04 | November 2022 Review | New approval | State highway improvements | Road improvements | NZ Transport Agency | 2021-24 NLTP Funds Management | Repayment | AC13 | LLVL | LLVL | N | 12 | Approved | Approved by Chief Financial Officer (CFO) | Required to reflect actual spend as recommended by Snr Mgr OPPP, Investment and Finance | 18814900 | 18814900 | [5 empty] | 283277 |  | 121433
2022-11-04 | November 2022 Review | New approval | Road to Zero | Road improvements | NZ Transport Agency | 2021-24 NLTP Funds Management | Repayment | AC23 | LLVL | LLVL | N | 12 | Approved | Approved by Chief Financial Officer (CFO) | Required to reflect actual spend as recommended by Snr Mgr OPPP, Investment and Finance | 12971300 | 12971300 | [5 empty] | 283276 |  | 121432
2022-11-01 | November 2022 Review | New approval | State highway improvements | Road improvements | NZTA (Auckland) | ANO TIBC Projects | Implementation |  | MHM | MHM | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | INTERPHASE TRANSFER: Please move $7,547,104 from 60056368(construction) to 60067926(construction). Request email attached in supporting doc | 8150872 | 8150872 |  |  |  | 3 |  | 282145 | 60067926 | 121416
2022-11-30 | November 2022 Review | New approval | Road to Zero | Road improvements | NZTA (Canterbury) | SH1 Rakaia to Ashburton CI - Stage 2 | Implementation | SH1 Rakaia to Ashburton CI - Stg 1 | VHHL | HHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) |  | 6480000 | 6480000 |  |  | 0 | 1.6 | R2A St 2 (Construction) | 231725 | 60056840 | 121558
2022-11-30 | November 2022 Review | New approval | Road to Zero | Road improvements | NZTA (Canterbury) | SH1 Templeton to Selwyn River | Implementation | SH1 Telegraph Rd to Rolleston Dr - Stg 1 | VHHL | VHHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) |  | 4536000 | 4536000 |  |  | 10 | 10 | 1301 | 277308 | 60060960 | 121559
2022-11-28 | November 2022 Review | New approval | Road to Zero | Road improvements | NZTA (Canterbury) | SH71 Rangiora to SH1 | Implementation | SH71 Rangiora to SH1 - Stg 1 | VHHL | VHHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) |  | 1000000 | 1000000 |  |  | 10 | 10 | 641 | 277326 | 60060994 | 121560
2022-11-30 | November 2022 Review | New approval | Road to Zero | Road improvements | NZTA (Hawkes Bay) | SH51 Napier to Hastings | Implementation | SH51 Elliston St to Tutaekuri Bridge - Stg 1 | VHHL | VHHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) |  | 5400000 | 5400000 |  |  | 10 | 10 | 84 | 277273 | 60060914 | 121654
2022-11-16 | November 2022 Review | New approval | Road to Zero | Road improvements | NZTA (Northland) | SH1 Whangarei to Wellsford - (Northern Section) | Implementation | RTZ SH1 Whangarei to Wellsford SSI (Northern | VHMVH | HHVH | N | 1 | Approved | Approved by Chief Financial Officer (CFO) |  | 2421730 | 2421730 |  |  | 1.8 | 1.8 | RTZ | 278484 | 60068071 | 120958
2022-11-08 | November 2022 Review | New approval | Road to Zero | Road improvements | NZTA (Waikato) | SH1 Cambridge to Piarere online safety improvements | Implementation | Stg 3B | VHML | VHLL | N | 3 | Approved | Approved by Chief Financial Officer (CFO) |  | 1050840 | 1050840 |  |  | 0 | 1.6 |  | 283101 | 60068790 | 121421
2022-11-30 | November 2022 Review | New approval | Road to Zero | Road improvements | NZTA (Waikato) | SH29 Piarere to SH28 | Implementation | SH29 SH1 to SH28 - Stg 1 | VHHM | VHHL | N | 1 | Approved | Approved by Chief Financial Officer (CFO) |  | 7355000 | 7355000 |  |  | 10 | 10 | 601 | 277248 | 60060861 | 121658
2022-11-30 | November 2022 Review | New approval | Road to Zero | Road improvements | NZTA (Waikato) | SH5 Tirau to Tarukenga Marae Rd | Implementation | SH5 Tirau to Tarukenga Marae Rd - Stg 1 | VHHM | VHHL | N | 1 | Approved | Approved by Chief Financial Officer (CFO) |  | 5000000 | 5000000 |  |  | 10 | 10 | 434 | 277265 | 60060895 | 121659
2022-11-11 | November 2022 Review | New approval | Road to Zero | Road policing | NZ Transport Agency | Drug Driving Testing Support Implementation (DDTSI) | Implementation | implementation | VHHL | LLVL | N | 2 | Approved | Approved by Auckland Transport Chief Financial Officer | phase transfer, moving $3.8m from pre imp to imp for better financial control | 4150986 | 4150986 |  |  | 0 | 6.8 | 60069092 | 283292 |  | 121472
2022-11-04 | November 2022 Review | Cash flow adjustment | Investment management (incl. Transport Planning) | Activity management planning improvement | NZ Transport Agency | 2021-24 NLTP Funds Management | Repayment | AC1 - Admin | LLVL | LLVL | N | 12 | Approved | Approved by Chief Financial Officer (CFO) | Moving funds into Year 1 | 0 | 0 | [5 empty] | 283273 |  | 121443
2022-11-25 | November 2022 Review | Cash flow adjustment | Local road maintenance | Cycle path maintenance | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reallocation between categories to suit new contract rates | -10393 | -6652 | [5 empty] | 274016 |  | 121569
2022-11-25 | November 2022 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Cycling Investment - Central Isthmus & Sandringham | Detailed Business Case | Cycling Investment - Central & Sandringham - DBC | HHM | HMM | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Further to the Sep22 Programme Monitor, this is a cost neutral cashflow to reflect the current proposed delivery for these improvements. There is a likelihood that the activity will be complete early FY24 so some may be declared surplus in the future, but will continue to be monitored. | 0 | 0 |  |  | 0 | 3.2 | 452.2613 | 261280 |  | 121546
2022-11-25 | November 2022 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Cycling Investment - City Centre & Fringe | Detailed Business Case | Cycling Investment - City Centre and Fringe - DBC | HHM | HMM | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Further to the Sep22 Programme Monitor, this is a cost neutral cashflow to reflect the current proposed delivery for these improvements. There is a likelihood that the activity will be complete early FY24 so some may be declared surplus in the future, but will continue to be monitored. | 0 | 0 |  |  | 0 | 3.2 | 452.2613 | 261263 |  | 121545
2022-11-25 | November 2022 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Urban Cycleways Programme - Glen Innes to Tamaki Drive | Implementation | UCP - Glen Innes-Tamaki Dr C/way - Sec 4 (NLTF) | VHHVL | VHHVL | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Further to the Sep22 Programme Monitor, this is a cost neutral cashflow to reflect the current proposed delivery for these improvements. | 0 | 0 |  |  | 0 | 0.7 | 452.2465 | 246508 |  | 121527
2022-11-28 | November 2022 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Urban Cycleways Programme - Great North Road Cycleway | Implementation | UCP - Wst Connx - Great North Road | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Further to the Sep22 Programme Monitor, this is a cost neutral cashflow to reflect the current proposed delivery for these improvements. | 0 | 0 |  |  |  | 2.6 | 452.2777 | 277747 |  | 121528
2022-11-04 | November 2022 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | NZ Transport Agency | 2021-24 NLTP Funds Management | Repayment | AC3 | LLVL | LLVL | N | 12 | Approved | Approved by Chief Financial Officer (CFO) | Moving funds into Year 1 | 0 | 0 | [5 empty] | 283278 |  | 121448
2022-11-25 | November 2022 Review | Cash flow adjustment | Local road maintenance | Drainage renewals | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reallocation between categories to suit new contract rates | 362530 | 232019 | [5 empty] | 274026 |  | 121569
2022-11-25 | November 2022 Review | Cash flow adjustment | Local road maintenance | Environmental maintenance | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reallocation between categories to suit new contract rates | 100518 | 64332 | [5 empty] | 274019 |  | 121569
2022-11-25 | November 2022 Review | Cash flow adjustment | Local road maintenance | Footpath maintenance | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reallocation between categories to suit new contract rates | 194000 | 124160 | [5 empty] | 274017 |  | 121569
2022-11-25 | November 2022 Review | Cash flow adjustment | Local road maintenance | Minor events | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reallocation between categories to suit new contract rates | -70100 | -44864 | [5 empty] | 274018 |  | 121569
2022-11-04 | November 2022 Review | Cash flow adjustment | State highway maintenance | Network and asset management | NZ Transport Agency | 2021-24 NLTP Funds Management | Repayment | AC9 | LLVL | LLVL | N | 12 | Approved | Approved by Chief Financial Officer (CFO) | Moving funds into Year 1 | 0 | 0 | [5 empty] | 283279 |  | 121445
2022-11-04 | November 2022 Review | Cash flow adjustment | Local road maintenance | Network and asset management | NZ Transport Agency | 2021-24 NLTP Funds Management | Repayment | AC8 | LLVL | LLVL | N | 12 | Approved | Approved by Chief Financial Officer (CFO) | Moving funds into Year 1 | 0 | 0 | [5 empty] | 283274 |  | 121444
2022-11-25 | November 2022 Review | Cash flow adjustment | Local road maintenance | Network service maintenance | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reallocation between categories to suit new contract rates | -13457 | -8612 | [5 empty] | 274020 |  | 121569
2022-11-25 | November 2022 Review | Cash flow adjustment | Public transport infrastructure | Passenger facilities and infrastructure improvements - rail | Auckland Transport | AKL Metro Train Capacity - Tranche 3 | Implementation | EMU Rolling Stock (Tranche 3) - IMP | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Further to the Sep22 Programme Monitor, this is a cost neutral cashflow to reflect the current proposed delivery for these improvements. | 0 | 0 |  |  |  | 2.1 | 563.2605 | 260527 |  | 121525
2022-11-25 | November 2022 Review | Cash flow adjustment | Public transport infrastructure | Passenger facilities and infrastructure improvements - rail | Auckland Transport | AKL Pedestrian Level Crossing Removal | Implementation | Pedestrian Level Crossing Removal | MHL | MHL | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Further to the Sep22 Programme Monitor, this is a cost neutral cashflow to reflect the current proposed delivery for these improvements. | 0 | -1 |  |  |  | 1.5 | 563.2647 | 264701 |  | 121526
2022-11-25 | November 2022 Review | Cash flow adjustment |  | Property purchase (local roads) | Auckland Transport | Lincoln Road Corridor Improvement | Property | Lincoln Road Corridor Imp-Property | HHVH | HHVH | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Further to the Sep22 Programme Monitor, this is a cost neutral cashflow to reflect the current proposed delivery for these improvements. | 0 | 0 |  |  | 7.5 | 7.5 | 332.219 | 218995 |  | 121543
2022-11-04 | November 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport facilities & infrastructure - renewals | NZ Transport Agency | 2021-24 NLTP Funds Management | Repayment | AC5 | LLVL | LLVL | N | 12 | Approved | Approved by Chief Financial Officer (CFO) | Moving funds into Year 1 | 0 | 0 | [5 empty] | 283275 |  | 121450
2022-11-25 | November 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport infrastructure and major renewals | Auckland Transport | AMETI - Eastern Busway 1 (Previously part of AMETI Stage 2A) | Construction | AMETI Eastern Busway 1 (Panmure-Pakuranga) | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Further to the Sep22 Programme Monitor, this is a cost neutral cashflow to reflect the current proposed delivery for these improvements. | 0 | 0 |  |  | 0 | 1.1 | 531.228 | 227971 |  | 121524
2022-11-25 | November 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport infrastructure and major renewals | Auckland Transport | Connected Communities - Gt North Rd (NL to City Corridor) | Detailed Business Case | CC-Gt North Rd-New Lynn to City-SSBC | HHM | HHM | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As per the Sep22 Programme Monitor, a number of corridors within the Connected Communities programme are on hold while a review is being completed. While the final review will be confirmed in June 2023, the current priority is on New North Road, so at this time, this is a cost neutral cashflow, however once the review is complete cashflows / timing will be confirmed. | 0 | 0 |  |  | 0 | 3.2 | 531.2663 | 266291 |  | 121514
2022-11-25 | November 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport infrastructure and major renewals | Auckland Transport | Connected Communities - Gt North Rd â€“ New Lynn to Henderso | Detailed Business Case | CC - Gt North Rd - New Lynn to Henderson - SSBC | H_L | HHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As per the Sep22 Programme Monitor, a number of corridors within the Connected Communities programme are on hold while a review is being completed. While the final review will be confirmed in June 2023, the current priority is on New North Road, so at this time, this is a cost neutral cashflow, however once the review is complete cashflows / timing will be confirmed. | 0 | 0 |  |  | 0 | 1.2 | 531.2663 | 266295 |  | 121515
2022-11-25 | November 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport infrastructure and major renewals | Auckland Transport | Connected Communities - Gt South Rd â€“ Manurewa to Papakura | Detailed Business Case | CC - Manurewa to Papakura - SSBC | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As per the Sep22 Programme Monitor, a number of corridors within the Connected Communities programme are on hold while a review is being completed. While the final review will be confirmed in June 2023, the current priority is on New North Road, so at this time, this is a cost neutral cashflow, however once the review is complete cashflows / timing will be confirmed. | 0 | 0 |  |  | 0 | 2.1 | 531.2663 | 266278 |  | 121516
2022-11-25 | November 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport infrastructure and major renewals | Auckland Transport | Connected Communities - Gt South Rd â€“ Newmarket to Manurew | Detailed Business Case | CC - Newmarket to Manurewa - SSBC | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As per the Sep22 Programme Monitor, a number of corridors within the Connected Communities programme are on hold while a review is being completed. While the final review will be confirmed in June 2023, the current priority is on New North Road, so at this time, this is a cost neutral cashflow, however once the review is complete cashflows / timing will be confirmed. | 0 | 0 |  |  | 0 | 2.5 | 531.2663 | 266275 |  | 121517
2022-11-25 | November 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport infrastructure and major renewals | Auckland Transport | Connected Communities - Manukau Road | Detailed Business Case | CC - Manukau Road - SSBC | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As per the Sep22 Programme Monitor, a number of corridors within the Connected Communities programme are on hold while a review is being completed. While the final review will be confirmed in June 2023, the current priority is on New North Road, so at this time, this is a cost neutral cashflow, however once the review is complete cashflows / timing will be confirmed. | 0 | 0 |  |  | 0 | 2.7 | 531.2663 | 266272 |  | 121518
2022-11-25 | November 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport infrastructure and major renewals | Auckland Transport | Connected Communities - Parnell Road | Detailed Business Case | CC - Parnell Road - SSBC | H_M | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As per the Sep22 Programme Monitor, a number of corridors within the Connected Communities programme are on hold while a review is being completed. While the final review will be confirmed in June 2023, the current priority is on New North Road, so at this time, this is a cost neutral cashflow, however once the review is complete cashflows / timing will be confirmed. | 0 | 0 |  |  | 0 | 3.9 | 531.2663 | 266287 |  | 121519
2022-11-25 | November 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport infrastructure and major renewals | Auckland Transport | Connected Communities - Remuera Road | Detailed Business Case | CC - Remuera Road - SSBC | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As per the Sep22 Programme Monitor, a number of corridors within the Connected Communities programme are on hold while a review is being completed. While the final review will be confirmed in June 2023, the current priority is on New North Road, so at this time, this is a cost neutral cashflow, however once the review is complete cashflows / timing will be confirmed. | 0 | 0 |  |  | 0 | 1.5 | 531.2663 | 266269 |  | 121521
2022-11-25 | November 2022 Review | Cash flow adjustment | Public transport infrastructure | Public transport infrastructure and major renewals | Auckland Transport | Connected Communities - Sandringham Road (Corridor) | Detailed Business Case | CC - Sandringham - SSBC | HHM | HHM | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As per the Sep22 Programme Monitor, a number of corridors within the Connected Communities programme are on hold while a review is being completed. While the final review will be confirmed in June 2023, the current priority is on New North Road, so at this time, this is a cost neutral cashflow, however once the review is complete cashflows / timing will be confirmed. | 0 | 0 |  |  | 0 | 3.2 | 531.2647 | 264660 |  | 121512
2022-11-04 | November 2022 Review | Cash flow adjustment | Public transport services | Public transport operations and management | NZ Transport Agency | 2021-24 NLTP Funds Management | Repayment | AC4 | LLVL | LLVL | N | 12 | Approved | Approved by Chief Financial Officer (CFO) | Moving funds into Year 1 | 0 | 0 | [5 empty] | 283280 |  | 121449
2022-11-25 | November 2022 Review | Cash flow adjustment | Local road maintenance | Rail level crossing warning devices maintenance | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reallocation between categories to suit new contract rates | -443 | -283 | [5 empty] | 274022 |  | 121569
2022-11-25 | November 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | Auckland Transport | High Risk Intersections and Corridors | Implementation | HRIC Ash St & Rata St SSC | HHM | VHHL | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Further to the Sep22 Programme Monitor, this is a cost neutral cashflow to reflect the current proposed delivery for these improvements. | 0 | 0 |  |  |  | 4.5 | 324.2804 | 280416 |  | 121530
2022-11-25 | November 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | Auckland Transport | High Risk Intersections and Corridors | Implementation | HRIC Atkinson Ave SSC | HHM | VHHL | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Further to the Sep22 Programme Monitor, this is a cost neutral cashflow to reflect the current proposed delivery for these improvements. | 0 | 0 |  |  |  | 4.5 | 324.2804 | 280417 |  | 121529
2022-11-25 | November 2022 Review | Cash flow adjustment | Local road improvements | Road improvements | Auckland Transport | TNFG - North West,, | Pre-implementation* | TNFG - North West | VHHVL | VHHVL | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This is for the Notice of Requirement (NOR) post-lodgement costs associated with Auckland Transport's NoR elements in relation to the recommended network identified at the DBC level for the North West growth area. These values include AT's indirect admin fee of 5.7%. | 0 | 0 |  |  |  | 0.7 | 324.2505 | 250457 |  | 121547
2022-11-04 | November 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZ Transport Agency | 2021-24 NLTP Funds Management | Repayment | AC23 | LLVL | LLVL | N | 12 | Approved | Approved by Chief Financial Officer (CFO) | Moving funds into Year 1 | 0 | 0 | [5 empty] | 283276 |  | 121446
2022-11-04 | November 2022 Review | Cash flow adjustment | State highway improvements | Road improvements | NZ Transport Agency | 2021-24 NLTP Funds Management | Repayment | AC13 | LLVL | LLVL | N | 12 | Approved | Approved by Chief Financial Officer (CFO) | Moving funds into Year 1 | 0 | 0 | [5 empty] | 283277 |  | 121447
2022-11-04 | November 2022 Review | Cash flow adjustment | Local road improvements | Road improvements | NZ Transport Agency | Safe Network Programme 2018-21 NLTP | Pre-implementation* | SNP-Programme Management (Local Roads) | HHL | VHHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Udating TIO to align with SAP | 0 | 0 |  |  | 0 | 1.6 | 60052632/80002478 | 267001 |  | 121441
2022-11-25 | November 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Canterbury) | SH1 Ashley to Belfast - (William St to Saltwater Creek) | Pre-implementation* | SH1 Ashley to Belfast Saltwater-William | HHL | HHH | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Transferring $94,926 (excl admin) from FY 23/24 to FY 22/23 | 0 | 0 |  |  | 0 | 1.6 |  | 278548 | 60062295 | 121533
2022-11-24 | November 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Wellington) | SH2 Masterton to Carterton - Ngaumutawa Intersection | Pre-implementation* | R2Z | VHHL | MHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  | 0 | 1.6 | R2Z | 278537 | 60062287 | 121536
2022-11-24 | November 2022 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (Wellington) | SH2 Masterton to Carterton - Norfolk Rd Roundabout | Pre-implementation* | R2Z | VHHL | HHM | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project close | 0 | 0 |  |  | 0 | 1.6 |  | 279255 | 60064035 | 121534
2022-11-25 | November 2022 Review | Cash flow adjustment | Local road maintenance | Routine drainage maintenance | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reallocation between categories to suit new contract rates | -42827 | -27409 | [5 empty] | 274014 |  | 121569
2022-11-08 | November 2022 Review | Cash flow adjustment | Road to Zero | Safety promotion, education and advertising | NZ Transport Agency | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update 2021/22 actual spend to reflect finance figure. | 0 | 0 | [5 empty] | 278432 |  | 121478
2022-11-25 | November 2022 Review | Cash flow adjustment | Local road maintenance | Sealed pavement maintenance | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reallocation between categories to suit new contract rates | -257765 | -164970 | [5 empty] | 274012 |  | 121569
2022-11-25 | November 2022 Review | Cash flow adjustment | Local road maintenance | Sealed road pavement rehabilitation | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reallocation between categories to suit new contract rates | -901275 | -576816 | [5 empty] | 274027 |  | 121569
2022-11-25 | November 2022 Review | Cash flow adjustment | Local road maintenance | Sealed road resurfacing | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reallocation between categories to suit new contract rates | 678598 | 434303 | [5 empty] | 274025 |  | 121569
2022-11-25 | November 2022 Review | Cash flow adjustment | Local road maintenance | Structures maintenance | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reallocation between categories to suit new contract rates | -1460 | -934 | [5 empty] | 274015 |  | 121569
2022-11-25 | November 2022 Review | Cash flow adjustment | Local road maintenance | Traffic services renewals | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reallocation between categories to suit new contract rates | -56113 | -35912 | [5 empty] | 274031 |  | 121569
2022-11-25 | November 2022 Review | Cash flow adjustment | Local road maintenance | Unsealed pavement maintenance | South Waikato District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reallocation between categories to suit new contract rates | 18187 | 11640 | [5 empty] | 274013 |  | 121569
2022-11-04 | November 2022 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Gisborne District Council | SfP Gisborne Community Trials | Implementation | SfP Gisborne Grey St Community Trials | VHHL | HHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds moving to Uawa Community Trials | -347580 | -312822 |  |  | 1 | 1 |  | 282865 |  | 121439
2022-11-25 | November 2022 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | NZTA (Gisborne) | Walking and Cycling connectivity | Implementation | Implementation | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project close. | -34504 | -34504 |  |  | 0 | 5.7 | 60045957 | 232811 | 60045957 | 121573
2022-11-29 | November 2022 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | NZTA (Waikato) | 2021-24 NLTP funds management | Repayment | AC3 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds management | -3441 | -3441 | [5 empty] | 279276 |  | 121651
2022-11-01 | November 2022 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Wellington City Council | Wellington Cycle Network - Eastern Package | Implementation | Evans Bay - UCP Implementation - NLTF | VHHL | VHHM | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | This is the final piece of the Cycleway for Evans Bay Stage 1 and will see all the benefits of this section realised. WCC have undertaken a QS exercise to bring down costs as much as possible with a slightly enhanced contingency to account for the complex marine environment and inflationary pressure | 10620469 | 5416439 |  |  | 0 | 2.5 |  | 249017 |  | 120552
2022-11-14 | November 2022 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Taranaki) | EW SH3 Awakino Dropout 20220611 | Construction |  | ___ |  | N |  | Approved | Approved by National Manager, Programmes and Standards (Transport Services) | Approved by acting Mgr on behalf of Programme & Standards Mgr. Total approval is $7,176,227 inc admin | 7176226 | 7176226 | [5 empty] | 281880 | 60067683 | 121365
2022-11-28 | November 2022 Review | Cost Increase | State highway maintenance | Emergency works | NZTA (Taranaki) | EW SH4 Taranaki Culvert 20220602 | Construction |  | ___ |  | N |  | Approved | Approved by National Manager, Programmes and Standards (Transport Services) | This funding approval enables reinstatement of a road whilst complying with environmental and freshwater regulations. | 7141511 | 7141511 | [5 empty] | 281680 | 60067618 | 121419
2022-11-25 | November 2022 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (West Coast) | EW West Coast Bonar Crk HR 20211205 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -1154369 | -1154369 | [5 empty] | 280575 | 60066516 | 121554
2022-11-25 | November 2022 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (West Coast) | EW West Coast March 20190326 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -953841 | -953841 | [5 empty] | 267974 | 60053007 | 121557
2022-11-28 | November 2022 Review | Cost Increase | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Hawkes Bay) | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Incorrect actual amount entered in TIO. Needs fixing but was awaiting TIO fix so can change historic data for 21-22 | 96220 | 96220 | [5 empty] | 276260 | 60061859 | 121636
2022-11-28 | November 2022 Review | Cost Increase | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Otago) | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Incorrect actual amount entered in TIO. Needs fixing but was awaiting TIO fix so can change historic data for 21-22 | 1285200 | 1285200 | [5 empty] | 276279 | 60061868 | 121637
2022-11-28 | November 2022 Review | Cost Increase | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Southland) | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Incorrect actual amount entered in TIO. Needs fixing but was awaiting TIO fix so can change historic data for 21-22 | 777600 | 777600 | [5 empty] | 276286 | 60061871 | 121638
2022-11-11 | November 2022 Review | Cost Increase | Local road improvements | Low cost / low risk improvements | Waipa District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funding moved from R2Z to Local Rd imps, as issues at Achilles Bridge do not fit into R2Z framework. | 300000 | 153000 | [5 empty] | 276495 |  | 121403
2022-11-11 | November 2022 Review | Cost Decrease | Road to Zero | Low cost / low risk improvements | Waipa District Council | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Move $300k into local Rd Imps to fund Archilles Br. | -300000 | -153000 | [5 empty] | 276496 |  | 121404
2022-11-11 | November 2022 Review | Cost Decrease | Public transport infrastructure | Low cost / low risk public transport improvements | Greater Wellington | Low cost / low risk improvements 2021-24 | Public transport infrastructure |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As per Metlink August 2022 re-forecast. | -7243279 | -3694072 | [5 empty] | 276141 |  | 121367
2022-11-28 | November 2022 Review | Cost Increase | Public transport infrastructure | Low cost / low risk public transport improvements | NZTA (Waikato) | Low cost / low risk improvements 2021-24 | Public transport infrastructure |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Incorrect actual amount entered in TIO. Needs fixing but was awaiting TIO fix so can change historic data for 21-22 | 1989998 | 1989998 | [5 empty] | 276298 | 60064560 | 121639
2022-11-28 | November 2022 Review | Cost Decrease | State highway maintenance | Network and asset management | NZTA (Gisborne) | 2021-24 NLTP Funds Management | Repayment | AC-9 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds management. | -7818492 | -7818492 | [5 empty] | 282285 |  | 121642
2022-11-29 | November 2022 Review | Cost Decrease | State highway maintenance | Network and asset management | NZTA (Northland) | 2021-24 NLTP funds management | Repayment | AC-9 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds management | -452998 | -452998 | [5 empty] | 282286 |  | 121649
2022-11-29 | November 2022 Review | Cost Decrease | State highway maintenance | Network and asset management | NZTA (Tasman) | 2021-24 NLTP funds management | Repayment | AC9 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds management | -144695 | -144695 | [5 empty] | 279273 |  | 121647
2022-11-25 | November 2022 Review | Cost Decrease | Public transport services | New activities influencing users of the transport system | Auckland Transport | Airport Access - Short-term Improvements | Implementation | Airport Access - TDM & Customer Experience - PT | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Further to the Sep22 Programme Monitor, AT are looking to declare a partial surplus for this activity while final costs are confirmed. | -1240957 | -632888 |  |  | 1.3 | 1.3 | 421.2687 | 278749 |  | 121544
2022-11-25 | November 2022 Review | Cost Decrease | Local road improvements | New roads | Auckland Transport | Medallion Drive Upgrade | Implementation | Medallion Drive Upgrade - Implementation | H_L | M_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Further to the Sep22 programme monitor, this activity is nearing completion (with close of defect period expected soon). As such, a partial surplus is being declared while final costs are being confirmed. | -2719172 | -1386778 |  |  | 0 | 2.4 | 323.2383 | 238306 |  | 121552
2022-11-25 | November 2022 Review | Cost Decrease | Local road improvements | New roads | Hamilton City Council | 2015 Resolution Drive | Implementation | 2015 Resolution Drive | H_L* | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2022/23 as activity is claiming complete | -25469 | -12989 |  |  | 0 | 2.3 |  | 232532 |  | 121611
2022-11-16 | November 2022 Review | Cost Decrease | External funding | New roads | NZTA (Manawatu/Whanganui) | NZUP Otaki to North of Levin | Detailed Business Case | NZ Upgrade Programme | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Moving $98,313 from 60057046 to 60057047 as DBC phase is now closed and any surplus is getting transferred to the current phase of the project. | -101754 | -101754 |  |  | 1.4 | 1.4 | 60057046 | 270297 | 60057046 | 121537
2022-11-16 | November 2022 Review | Cost Increase | External funding | New roads | NZTA (Manawatu/Whanganui) | NZUP Otaki to North of Levin | Pre-implementation* | NZ Upgrade Programme | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reinstating $250k in 25/26 that was reduced in error | 101754 | 101754 |  |  | 1.4 | 1.4 | 60057047 | 254803 | 60057047 | 121549
2022-11-16 | November 2022 Review | Cost Increase | External funding | New roads | NZTA (Manawatu/Whanganui) | NZUP Otaki to North of Levin | Pre-implementation* | NZ Upgrade Programme | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Moving $98,313 from 60057046 to 60057047 as DBC phase is now closed and any surplus is getting transferred to the current phase of the project. | 101754 | 101754 |  |  | 1.4 | 1.4 | 60057047 | 254803 | 60057047 | 121550
2022-11-16 | November 2022 Review | Cost Decrease | External funding | New roads | NZTA (Manawatu/Whanganui) | NZUP Otaki to North of Levin | Pre-implementation* | NZ Upgrade Programme | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Moving $98,313 from 60057046 to 60057047 as DBC phase is now closed and any surplus is getting transferred to the current phase of the project. | -101754 | -101754 |  |  | 1.4 | 1.4 | 60057047 | 254803 | 60057047 | 121538
2022-11-04 | November 2022 Review | Cost Decrease | State highway improvements | New traffic management facilities | NZTA (BOP) | Weigh Right Paengaroa | Implementation |  | HHH | HMH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Correcting the 2019/20 actual spend | -616 | -616 |  |  | 14 | 14 | 60048361 | 262618 | 60048361 | 121451
2022-11-14 | November 2022 Review | Cost Increase | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | Auckland Transport | Carrington Road Upgrade | Detailed Business Case | Carrington Road Upgrade DBC | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | The revised cost to develop the Carrington Road DBC is a result of more detailed scoping at the project setup and procurement stages. The updated costs reflects the professional services based on price responses during the tender phase that was subsequently negotiated with the preferred supplier. The cost also reflects the higher internal staff cost that will allow greater Subject Matter Expert input and the need to appoint external consultants to key project team roles (project manager, engagement lead) due to Auckland Transport under-resourcing. | 1253900 | 639489 |  |  |  | 2.1 | 561.2778 | 277802 |  | 121102
2022-11-02 | November 2022 Review | Cost Increase | Public transport services | Passenger services - bus | Bay of Plenty Regional Council | Public Transport Programme 2021-24 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Driver wages increase has been endorsed at delegations and funding priority and availability has been confirmed. | 1701298 | 867663 | [5 empty] | 272210 |  | 121237
2022-11-08 | November 2022 Review | Cost Increase | Investment management (incl. Transport Planning) | Programme Business Case Development | Porirua City Council | Eastern Porirua Regeneration PBC | Programme business case |  | VHHL | VHHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | The Porirua Eastern Regeneration Project is a partnership approach between KÄinga Ora, as the lead agency, PCC, Greater Wellington, Waka Kotahi, and NgÄti Toa, this PBC aims to achieve transport related outcomes that are necessary to support urban form and density changes that are proposed to improve the lives of those people who live and visit to Eastern Porirua. In October 2021, an estimated budget of $150,000 was approved in the PoE for the Eastern Porirua â€“ Transport Works, for the preparation of the PBC. The $150,000 budget provided for the preparation of the PBC covers: a) $70,000 for the writing of the PBC and project management b) $50,000 for further base line data including traffic counts (pre and post Transmission Gully) to cover the findings of the Integrated Transport Assessment which identified 12 intersections that will be under pressure from the development c) $30,000 for other, such as further modelling etc. In March 2022, in undertaking the procurement to identify the appropriate consultant to write the PBC and in reviewing the original scope provided in the PoE, the partners identified that the costs of the development of the PBC will likely exceed the approved budget of $150,000 and that additional work will also be required. To ensure there is certainty in the cost of the development of the PBC, the partners agreed to undertake a two-stage approach to the development of the PBC, which allows a more fit-for-purpose requirement and accurate costing of the remaining stage of the PBC. The stages are: â€¢ Stage 1 â€“ develop the strategic case and jointly define and agree the scope and cost to complete the PBC â€“ costing $59,500 â€¢ Stage 2 â€“ complete the remainder of the PBC. A consultant was selected to undertake Stage 1 with a fee of $59,500 to develop the strategic case and review the scope requirements for completing the remainder of the PBC. | 300000 | 162000 | [5 empty] | 279777 |  | 121154
2022-11-30 | November 2022 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Canterbury) | Groynes to Sawyers Arms 4L | Property |  | H_M | H_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project closed and write off $338 as agreed with DG & HB. | 337 | 337 |  |  | 1.4 | 1.4 | 60436252 | 200230 | 60436252 | 121671
2022-11-14 | November 2022 Review | Cost Increase | External funding | Property purchase (State highways) | NZTA (Canterbury) | NZUP SH73 Weedons-Ross Road Intersection | Property | NZ Upgrade Programme | H_L | HML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $49,053 from (Imp) 60031531 to (Property) 60057040 to cover for Property overspent. | 50770 | 50770 |  |  | 1.2 | 1.2 | 60057040 | 270360 | 60057040 | 121485
2022-11-14 | November 2022 Review | Cost Increase | Road to Zero | Property purchase (State highways) | NZTA (Canterbury) | SH1 Ashley to Belfast - (William St to Saltwater Creek) | Property | SH1 Ashley to Belfast Saltwater-William | HHL | HHH | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Requesting additional $434,722 (excl admin) in FY 21/22. See Price level adjustment memo. | 458632 | 458632 |  |  | 0 | 1.6 |  | 278316 | 60060542 | 121327
2022-11-30 | November 2022 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Northland) | SH1 Corridor Improvements - Whangarei | Property | SH1 Corridor Improvement - Whangarei | H_M | HMM | N |  | Approved | Approved by Chief Financial Officer (CFO) |  | 1618 | 1618 |  |  | 0 | 2.3 | 60471902 | 224010 | 60471902 | 121633
2022-11-25 | November 2022 Review | Cost Decrease | Local road improvements | Replacement of bridges and other structures | Auckland Transport | NCI - Rosedale Station and Assoc. Local Road Improvements | Implementation | NCI - Rosedale LR Components - IMP | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | This surplus is the result of reduced phase costs to Auckland Transport following a Board of Enquiry report on the NCI programme. Auckland Council was required to contribute 25% of the cost. This was provided to Auckland Transport in the last financial year. Adjustment reflects the expected remaining cost to close out the completed works on Motorway Bridge replacement and Alexandra Underpass. Supporting information is included in the Supporting Documents section for all the project phases. | -2007390 | -1023769 |  |  | 0 | 1.1 | 322.2665 | 266505 |  | 121494
2022-11-30 | November 2022 Review | Cost Increase | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH30 Kopaki Bridge Replacement | Implementation |  | H__ | H__ | N | 0 | Approved | Approved by Chief Financial Officer (CFO) |  | 1260360 | 1260360 |  |  | 99 | 99 |  | 254885 | 60052983 | 121452
2022-11-16 | November 2022 Review | Cost Decrease | Local road improvements | Road improvements | Auckland Transport | Great North Road Slip Remediation | Single-Stage Business Case | SSBC - Great North Road Slip Remediation | HLL | HHM | Y | 4 | Approved | Approved by Auckland Transport Chief Financial Officer |  | -1031543 | -526087 |  |  |  | 4.1 | 324.2774 | 277430 |  | 121548
2022-11-25 | November 2022 Review | Cost Decrease | Local road improvements | Road improvements | Hurunui District Council | Street Lighting Renewal - LED Conversion | Implementation | present | M_H | M__ | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2022/23 as activity is claiming complete | -107550 | -55926 |  |  | 4 | 4 |  | 262721 |  | 121565
2022-11-28 | November 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Auckland) | 2021-24 NLTP funds management | Repayment | AC13 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds management. | -170425 | -170425 | [5 empty] | 278954 |  | 121644
2022-11-28 | November 2022 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (Auckland) | 2021-24 NLTP funds management | Repayment | AC-23 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds management. | -642669 | -642669 | [5 empty] | 282284 |  | 121643
2022-11-01 | November 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Auckland) | Auckland Network Optimisation (ANO) Programme | Implementation | Auckland System Optimisation SH - Stage 1 | MHM | MHM | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | INTERPHASE TRANSFER: Please move 7547104 from 60056368(construction) to 60067926(construction) | -8150873 | -8150873 |  |  |  | 3.2 | InfoHub ID 28116348 ¦ SAP 60056368 | 254840 | 60056368 | 121417
2022-11-28 | November 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (BOP) | 2021-24 NLTP funds management | Repayment | AC13 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds management | -136398 | -136398 | [5 empty] | 278955 |  | 121645
2022-11-28 | November 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Canterbury) | 2021-24 NLTP funds management | Repayment | AC13 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds Management | -2093729 | -2093729 | [5 empty] | 279052 |  | 121641
2022-11-14 | November 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (Canterbury) | NZUP SH73 Weedons-Ross Road Intersection | Implementation | NZ Upgrade Programme | H_L | HML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $49,053 from (Imp) 60031531 to (Property) 60057040 to cover for Property overspent. | -50772 | -50772 |  |  | 1.2 | 1.2 | 60031531 | 239003 | 60031531 | 121488
2022-11-29 | November 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Hawkes Bay) | 2021-24 NLTP funds management | Repayment | AC13 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds management | -70892 | -70892 | [5 empty] | 279094 |  | 121648
2022-11-25 | November 2022 Review | Cost Increase | External funding | Road improvements | NZTA (Otago) | NZUP Queenstown Package | Detailed Business Case | NZ Upgrade Programme | M_M | MHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $8,061 from (Pre-Imp) 60057043 to (DBC) 60057042 to close-out DBC phase. | 8343 | 8343 |  |  | 3.5 | 3.5 | 60057042 | 270361 | 60057042 | 121555
2022-11-14 | November 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (Otago) | NZUP Queenstown Package | Implementation | NZUP Grant Rd to KF Bridge Improvements | M_M | MHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $8,400,000 from (Imp) 60057044 to (Pre-Imp) 60057043 to cover for Pre-Imp costs that will be journaled from the Imp to Pre-Imp phase. | -8694001 | -8694001 |  |  | 3.5 | 3.5 | 60057044 | 259377 | 60057044 | 121487
2022-11-14 | November 2022 Review | Cost Increase | External funding | Road improvements | NZTA (Otago) | NZUP Queenstown Package | Pre-implementation* | NZ Upgrade Programme | M_M | MHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $8,400,000 from (Imp) 60057044 to (Pre-Imp) 60057043 to cover for Pre-Imp costs that will be journaled from the Imp to Pre-Imp phase. | 8600849 | 8600849 |  |  | 3.5 | 3.5 | 60057043 | 259356 | 60057043 | 121486
2022-11-14 | November 2022 Review | Cost Increase | External funding | Road improvements | NZTA (Otago) | NZUP Queenstown Package | Pre-implementation* | NZ Upgrade Programme | M_M | MHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | $90k reinstated in 24/25 as instructed by Norcel Vitalez due to an error in previous review. | 93150 | 93150 |  |  | 3.5 | 3.5 | 60057043 | 259356 | 60057043 | 121511
2022-11-25 | November 2022 Review | Cost Decrease | External funding | Road improvements | NZTA (Otago) | NZUP Queenstown Package | Pre-implementation* | NZ Upgrade Programme | M_M | MHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase transfer of $8,061 from (Pre-Imp) 60057043 to (DBC) 60057042 to close-out DBC phase. | -8344 | -8344 |  |  | 3.5 | 3.5 | 60057043 | 259356 | 60057043 | 121556
2022-11-29 | November 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Waikato) | 2021-24 NLTP funds management | Repayment | AC13 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds management | -1538315 | -1538315 | [5 empty] | 279275 |  | 121650
2022-11-11 | November 2022 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Waikato) | SH1 Cambridge to Piarere online safety improvements | Implementation | Stg 1 and 2 | VHML | VHLL | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | transfer $973K excl admin from 60068790 to 60062182 - because it a stage under the project | 1050839 | 1050839 |  |  | 0 | 1.6 |  | 278490 | 60062182 | 121489
2022-11-11 | November 2022 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (Waikato) | SH1 Cambridge to Piarere online safety improvements | Implementation | Stg 3B | VHML | VHLL | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | transfer $973K excl admin from 60068790 to 60062182 - because it a stage under the project | -1050840 | -1050840 |  |  | 0 | 1.6 |  | 283101 | 60068790 | 121490
2022-11-01 | November 2022 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Waikato) | SH1 Cambridge to Piarere online safety improvements | Implementation | Stg 1 and 2 | VHML | VHLL | N | 3 | Approved | Approved by Chief Financial Officer (CFO) |  | 1721520 | 1721520 |  |  | 0 | 1.6 |  | 278490 | 60062182 | 121326
2022-11-25 | November 2022 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Waikato) | SH1 South-East Hamilton improvements | Construction | SH1 Cobham/Cambridge Improvements Construction | H_M | MMM | N | 0 | Approved | Approved by Chief Financial Officer (CFO) |  | 856755 | 856755 |  |  | 5.9 | 5.9 | 60033606 | 239051 | 60033606 | 121477
2022-11-01 | November 2022 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Waikato) | SH3 and SH4 IS | Pre-implementation* |  | VHHM | VHHL | N | 1 | Approved | Approved by Chief Financial Officer (CFO) |  | 115160 | 115160 |  |  | 10 | 10 | 20621 | 277354 | 60061064 | 121216
2022-11-29 | November 2022 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Wellington) | 2021-24 NLTP funds management | Repayment | AC13 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds management | -132241 | -132241 | [5 empty] | 279277 |  | 121652
2022-11-24 | November 2022 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Wellington) | SH2 Masterton to Carterton (corridor improvements) | Implementation | R2Z | VHMM | HHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer, Txf $6,914,007 from 144052020/60056825 Imp to143502020/60056536 Imp and Txf $7,304,897 from 143402020/60062285 Imp to143502020/60056536 Imp, Projects are contiguous, Implementation Phases merged for Reporting efficiency | 15073025 | 15073025 |  |  | 0 | 1.6 | SNP-SSI | 278436 | 60056536 | 121619
2022-11-24 | November 2022 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (Wellington) | SH2 Masterton to Carterton - Ngaumutawa Intersection | Implementation |  | VHHL | MHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer, Txf $6,914,007 from 144052020/60056825 Imp to143502020/60056536 Imp, Projects are contiguous, Implementation Phases merged for Reporting efficiency | -7467128 | -7467128 |  |  | 0 | 1.6 |  | 269964 | 60056825 | 121621
2022-11-24 | November 2022 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (Wellington) | SH2 Masterton to Carterton - Norfolk Rd Roundabout | Implementation |  | VHHL | HHM | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer, Txf $7,304,897 from 143402020/60062285 Imp to143502020/60056536 Imp, Projects are contiguous, Implementation Phases merged for Reporting efficiency | -7605898 | -7605898 |  |  | 0 | 1.6 |  | 278534 | 60062285 | 121620
2022-11-11 | November 2022 Review | Cost Decrease | Road to Zero | Road policing | NZ Transport Agency | Drug Driving Testing Support Implementation (DDTSI) | Pre-implementation* | Phase-1 | VHHL | LLVL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | phase transfer, moving $3.8m from pre imp to imp for better financial control | -4150986 | -4150986 |  |  | 0 | 6.8 | SAP ID: 60068855: Old WBS 51000416 | 282187 |  | 121471
2022-11-15 | November 2022 Review | Cost Decrease | Road to Zero | Safety promotion, education and advertising | NZ Transport Agency | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The RSP team have advised that they would like to surplus most of their unspent 2021/22 allocation that has been carried forward into 2022/23. | 0 | -5630776 | [5 empty] | 278432 |  | 121513
2022-11-11 | November 2022 Review | Cost Increase | Public transport infrastructure | Transitional Rail Infrastructure | Greater Wellington | TR: Unlocking Capacity & Improving Resilience-Infrastructure | Implementation | Infrastructure improvements (GW) | VH_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Changes to the WMUP IV Programme | 43334 | 43334 |  |  | 1.8 | 1.8 |  | 275954 |  | 121232
2022-11-11 | November 2022 Review | Cost Decrease | Public transport infrastructure | Transitional Rail Infrastructure | Greater Wellington | TR: Unlocking Capacity & Improving Resilience-Infrastructure | Implementation | Infrastructure improvements | VH_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cost Escalation Release of P95 Removal of substations from scope Merging the management of WMUP III and IV together Note $4m contingency in both FY23 and FY24 | -48989 | -48989 |  |  | 1.8 | 1.8 | Infrastructure improvements | 263978 |  | 121231
2022-11-21 | November 2022 Review | Cost Decrease | Walking and cycling improvements | Walking facilities | NZ Transport Agency | Innovating Streets Programme 2021-24 | Implementation | Implementation - Funding allocated to AOs | HHL | VHHVH | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Funds being moved to Hastings DC | -1320807 | -1320807 |  |  | 1 | 1 |  | 279202 |  | 121591
2022-11-04 | November 2022 Review | Cost Decrease | Walking and cycling improvements | Walking facilities | NZ Transport Agency | Innovating Streets Programme 2021-24 | Implementation | Implementation - Funding allocated to AOs | HHL | VHHVH | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Funds being moved to Timaru DC | -1035000 | -1035000 |  |  | 1 | 1 |  | 279202 |  | 121426
2022-11-03 | November 2022 Review | Cost Increase | Walking and cycling improvements | Walking facilities | NZTA (Waikato) | SH1 Tamahere Interchange Ped/Cycle | Single-Stage Business Case | SH1 Tamahere Interchange Ped/Cycle | HMH | H_H | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | 3186 | 3186 |  |  | 0 | 0 |  | 275486 | 60060050 | 121424
2022-11-01 | November 2022 Review | Support for activity management plan |  |  | Queenstown-Lakes District Council | Activity Management Plan 2021-24 | Support for AMP |  | ___ |  | N |  | Endorsed | Endorsed by Chief Financial Officer (CFO) |  | 0 | [6 empty] | 273791 |  | 121228