## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Phase Label | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Decision Status | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR | Your Phase reference | TIO Phase id | SAP item id | TIO Request id
2023-01-17 | January 2023 Review | New approval | Walking and cycling improvements | Cycling facilities | Auckland Transport | Cycling Investment - Other AKL Focus Areas | Single-Stage Business Case | Other AKL Focus Area - SSBCs | VHML | VHML | N | 3 | Approved | Approved by Chief Financial Officer (CFO) | As the next investigation and design phase of the Auckland Cycling and Micromobility programme, this will enable AT to plan the delivery of cycling networks and supporting interventions in priority areas. Progression is critical to make the required contribution to Auckland's climate objectives (7% cycling mode share by distance by 2031). | 6014330 | 3067309 | That AT confirm the list of projects to be delivered under the activity, and represent them appropriately within Transport Investment Online. |  | 2.8 | 2.8 | 452.2778 | 277804 |  | 117834
2023-01-26 | January 2023 Review | New approval | Local road maintenance | Emergency works | Grey District Council | EW - Grey DC December 2021 Rutherglen Road Slip | Construction |  | ___ |  | N |  | Approved | Approved by System Manager, Maintenance and Operations (Transport Services) | Recommendation That the Regional Manager - Maintenance and Operations: Approves Grey District Councilâ€™s Emergency Works request for the December 2021 event at a total gross cost of $183,359 for Financial Year 22/23. | 1 | 1 |  |  |  |  | Construction 63% | 282010 |  | 120419
2023-01-26 | January 2023 Review | New approval | Local road maintenance | Emergency works | Grey District Council | EW - Grey DC December 2021 Rutherglen Road Slip | Construction |  | ___ |  | N |  | Approved | Approved by System Manager, Maintenance and Operations (Transport Services) | Recommendation That the Regional Manager - Maintenance and Operations: Approves Grey District Councilâ€™s Emergency Works request for the December 2021 event at a total gross cost of $183,359 for Financial Year 22/23. | 28359 | 23538 |  |  |  |  | Initial Response/Reinstatement 2021/22 | 282009 |  | 120420
2023-01-13 | January 2023 Review | New approval | Local road maintenance | Emergency works | Kaipara District Council | EW July 2022 Event | Construction | EW Response | ___ |  | N |  | Approved | Approved by System Manager, Maintenance and Operations (Transport Services) | refer paper in supporting docs. | 199416 | 123638 |  |  |  |  | EW Response | 283077 |  | 121099
2023-01-10 | January 2023 Review | New approval | Local road maintenance | Emergency works | Manawatu District Council | EW July 2022 Events | Repayment | Recover phase for July 2022 weather event1 | ___ |  | N |  | Approved | Approved by System Manager, Maintenance and Operations (Transport Services) | As recommended by regional office. To enable Manawatu DC to undertake initial response and permanent repairs to return those roads within the district to thee required pre-event level of service | 295647 | 153736 |  |  |  |  | MDC: July 2022 Emergency works event1 | 282215 |  | 120409
2023-01-19 | January 2023 Review | New approval | State highway maintenance | Emergency works | NZTA (Manawatu/Whanganui) | EW Otanga Road Slip 20220226 | Construction |  | ___ |  | N |  | Approved | Approved by National Manager, Maintenance and Operations (Transport Services) | Iâ€™m not sure if the team fully understand the emergency works process as it should not have taken this long to provide an application or develop a recovery option. A workshop is planned for February 2023 to step the team through the process. This should ensure we get a better outcome next time. I am now content that this event fits within the current PIKB guidance and I recommend approval. NAC | 1107000 | 1107000 | [5 empty] | 282908 | 60068503 | 121905
2023-01-19 | January 2023 Review | New approval | State highway maintenance | Emergency works | NZTA (Wellington) | EW SH59 Pukerua Bay Slips 20220818 | Construction |  | ___ |  | N |  | Approved | Approved by National Manager, Maintenance and Operations (Transport Services) | I am content that this event fits within the current PIKB guidance for emergency works funding and I recommend approval NAC | 4927608 | 4927608 | [5 empty] | 282909 | 60068509 | 121896
2023-01-27 | January 2023 Review | New approval | Local road maintenance | Emergency works | Stratford District Council | EW 2022 - Mangaehu and Whangamomona | Construction | 2022 Emergency Works - Mangaehu/Whangamomona | ___ |  | N |  | Approved | Approved by System Manager, Maintenance and Operations (Transport Services) | The weather event between 19 May 2022 and 13 July 2022 had a detrimental effect on the routes within the district. Localised damage occurred to the network and resulted in closures to the Upper Mangaehu Road for a period of 24 hours and restrictions to others. Immediate emergency response (road closure) was required to maintain the safety of general road users and maintenance contractors. | 285749 | 174307 | [5 empty] | 283334 |  | 121592
2023-01-18 | January 2023 Review | New approval | Local road maintenance | Emergency works | Whangarei District Council | EW - Whangarei DC November 2022 Storm event | Construction | EW - Storm repairs July 2022 | ___ |  | N |  | Approved | Approved by National Manager, Maintenance and Operations (Transport Services) | EW - Whangarei DC November 2022 Storm Event - approved by Senior Manager, Maintenance and Operations and saved in TIO. | 1068137 | 566113 | [5 empty] | 283393 |  | 121808
2023-01-09 | January 2023 Review | New approval | Road to Zero | Road improvements | NZTA (Manawatu/Whanganui) | Otaki to North of Levin - SH1/SH57 - northern section | Implementation | Foxton to Whirokino - Stg 1 | HHL | HHH | N | 5 | Approved | Approved by Chief Financial Officer (CFO) |  | 6804000 | 6804000 |  |  | 0 | 1.6 |  | 278532 | 60062281 | 114870
2023-01-09 | January 2023 Review | New approval | Road to Zero | Safety promotion, education and advertising | NZ Transport Agency | RtZ Work-Related Road Safety | Implementation | RtZ Work-Related Road Safety | MHM | MHM | N | 6 | Approved | Approved by Chief Financial Officer (CFO) |  | 24449625 | 24449625 |  |  | 5.6 | 5.6 | SAP 60068924 | 283054 |  | 121617
2023-01-20 | January 2023 Review | Cash flow adjustment | Local road maintenance | Emergency works | Grey District Council | EW Atarau Rd Rough River Flood Damage 2021-Jul-17 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2022/23 as activity is claiming complete | -1 | -1 |  |  |  |  | Construction | 279133 |  | 121902
2023-01-20 | January 2023 Review | Cash flow adjustment | Local road maintenance | Emergency works | Kaikoura District Council | Kaikoura Nov 2016 EQ | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Extension requested for end of Financial Year 2024/2025 due to delays regarding to the COVID, consent processing and negotiations processes with the different parties. This has pushed the start of the physical construction to the FY 2023/2024. | 0 | 0 |  |  |  |  | Clarence Valley Access | 266303 |  | 121856
2023-01-20 | January 2023 Review | Cash flow adjustment | Road to Zero | Road improvements | NZ Transport Agency | SIP - Programme Management | Pre-implementation* | SIP Programme Management | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow, but will need to consider additional funds for Admin. | 0 | 0 |  |  | 2.2 | 2.2 | 60063778 Jamie K | 277979 |  | 121860
2023-01-04 | January 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Christchurch City Council | EW - Earthquake Events - NLTP funding | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | FAR needed to be added. | 0 | -446910 |  |  |  |  | 721* | 211617 |  | 121834
2023-01-20 | January 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Far North District Council | EW February 2022 Cyclone Dovi | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2022/23 as activity is claiming complete | -39519 | -27268 |  |  |  |  | EW February 2022 Cyclone Dovi | 280979 |  | 121899
2023-01-20 | January 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Far North District Council | EW March 2022 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Automatic reconciliation of approved costs with claimed costs for 2022/23 as activity is claiming complete | -132163 | -91192 |  |  |  |  | EW March 2022 | 281400 |  | 121900
2023-01-20 | January 2023 Review | Cost Decrease | Local road maintenance | Emergency works | Gisborne District Council | 20 June 2021 Weather Event | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | 4 contracts that were tendered in November were below the engineers estimates have reduced overall funding requirements to release savings | -448343 | -390058 |  |  |  |  | Emergency Works: 20 June 2021 Flood Damage | 279377 |  | 121857
2023-01-20 | January 2023 Review | Cost Decrease | Road to Zero | Low cost / low risk improvements | Dunedin City Council | Low cost / low risk improvements 2021-24 | Road to Zero |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Not able to deliver full programme. Surplus declared to reallocate elsewhere. Further surplus may be declared in June/July once more of the programme is committed. | -6053409 | -3142862 | [5 empty] | 276116 |  | 121861
2023-01-20 | January 2023 Review | Cost Decrease | Local road maintenance | Network and asset management | NZ Transport Agency | Asset Management Data Standard- State Highways | Implementation | Roll out of data standard- LR Maintenance | MMM | VHMM | N | 8 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update to match SAP-PPM total. NB Admin is zero for this phase. | -18215270 | -18215270 |  |  |  | 4.4 | LR Maintenance part of funding, SAP item 60067372 | 277727 |  | 121862
2023-01-20 | January 2023 Review | Cost Increase | Local road maintenance | Network and asset management | NZ Transport Agency | Asset Management Data Standard- State Highways | Implementation | Roll out of data standard- LR Maintenance | MMM | VHMM | N | 8 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Earlier review was not correct and this is a fix as discussed with GH, HB, MR & MJ. The only change is in year 23/24. Moved funds from 22/23 | 1082278 | 18215278 |  |  |  | 4.4 | LR Maintenance part of funding, SAP item 60067372 | 277727 |  | 121912
2023-01-30 | January 2023 Review | Cost Increase | State highway improvements | New roads | NZTA (Wellington) | Wellington RoNS (5) - Transmission Gully | Construction | Construction - enabling | H_L | H_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Receive $1,846,863 from Pre Imp phase to rebalance financials | 1994612 | 1994612 |  |  | 1.4 | 1.4 | 60216287 | 226528 | 60216287 | 121922
2023-01-30 | January 2023 Review | Cost Decrease | State highway improvements | New roads | NZTA (Wellington) | Wellington RoNS (5) - Transmission Gully | Design |  | H_L | H_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Contribute $3,151,610 to Const & Prop phases to rebalance financials- $1,486,863 to Const; $1,664,747 to Property | -3403739 | -3403739 |  |  | 1.4 | 1.4 | 60214139 | 173335 | 60214139 | 121924
2023-01-20 | January 2023 Review | Cost Decrease | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | NZTA (Auckland) | North Western Bus Improvements (ST) | Implementation | Implementation - NLTF Programme Contingency #2 | VHHL | VHLL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | INTERPHASE TRANSFER: Moving $9,671,389 contingency allocation from 60069260 into 60062437 as per request to have this consolidated. (Move in TIO the $9.7m from 283374 to 282992, in SAP it should be manual entry to 60062437) | -10445100 | -10445100 |  |  | 1.1 | 1.3 | AT Transfer #2 Moved to 60062437 (move from 283374 to 282992) | 283374 | 60069260 | 121821
2023-01-20 | January 2023 Review | Cost Increase | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | NZTA (Auckland) | North Western Bus Improvements (ST) | Implementation | NLTF Programme Contingency Transfer & Covid Claims | VHHL | VHLL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | INTERPHASE TRANSFER: Moving $9,671,389 contingency allocation from 60069260 into 60062437 as per request to have this consolidated. (Move in TIO the $9.7m from 283374 to 282992, in SAP it should be manual entry to 60062437) | 10445100 | 10445100 |  |  | 1.1 | 1.3 | 60062437 AT Transfer contingency #1 & #2 (3,796,296 + 9,671,389) + Covid Claims | 282992 | 60062437 | 121898
2023-01-10 | January 2023 Review | Cost Increase | Public transport services | Payments for Total Mobility wheelchair hoists and ramps | West Coast Regional Council | Public Transport Programme 2021-24 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | This increase is well evidenced through actual demand values presented. | 43609 | 43609 | [5 empty] | 274692 |  | 121571
2023-01-10 | January 2023 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Nelson) | SH6 Rai Saddle Second Curve Realignment | Property |  | H_L* | HHL | N |  | Approved | Approved by Chief Financial Officer (CFO) |  | 94044 | 94044 |  |  | 2.6 | 2.6 | 60451872 | 247511 | 60451872 | 121722
2023-01-30 | January 2023 Review | Cost Increase | State highway improvements | Property purchase (State highways) | NZTA (Wellington) | Wellington RoNS (5) - Transmission Gully | Property |  | H_L | H_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Receive $1,664,747 from PreImp phase to rebalance and cover costs of Silverwood Court settlement | 1930519 | 1930519 |  |  | 1.4 | 1.4 | 60450642 | 194475 | 60450642 | 121923
2023-01-16 | January 2023 Review | Cost Increase | Public transport infrastructure | Rapid Transit Infrastructure | NZTA (Canterbury) | PT Futures MRT | Indicative Business Case |  | VHLL | HHL | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | This funding approval enables the IBC to be completed by mid-2023 to meet Ministerial expectations. Furthermore, it will provide residents of Christchurch, businesses and local authorities some certainty over the preferred direction for transport investment in authority investment and central government policy direction. | 1103258 | 1103258 |  |  | 1 | 1 |  | 268114 | 60054249 | 121699
2023-01-06 | January 2023 Review | Cost Increase | Road to Zero | Road improvements | NZ Transport Agency | Tackling Unsafe Speeds | Implementation | Safer Speeds around Schools (SSAS) State Highways | HHL | VHHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) | Correct the FAR to 100% | 0 | 9907637 |  |  |  | 1.1 | 60068444 | 282804 |  | 121835
2023-01-19 | January 2023 Review | Cost Decrease | Road to Zero | Road improvements | NZ Transport Agency | Tackling Unsafe Speeds | Implementation | Safer Speeds around schools (SSAS) Local Roads | HHL | VHHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -50100000 | -50100000 |  |  |  | 1.1 | WBS 80002362 - Mike Creamer | 270260 |  | 121775
2023-01-31 | January 2023 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Auckland) | Northern Corridor Improvements (NCI) | Construction | Construction - Main | H_M | H_M | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Escalation Relief prolongation claim: $7,759,355 for NCI Alliance. This will be an adjustment to the TOC to June 2022 | 8380103 | 8380103 |  |  | 3 | 3 | 60027507 | 254897 | 60027507 | 121934
2023-01-10 | January 2023 Review | Cost Increase | Road to Zero | Road improvements | NZTA (BOP) | SH2 Wainui Rd to Opotiki, NSRRP | Implementation |  | HHL | HHL | N | 5 | Approved | Approved by Chief Financial Officer (CFO) |  | 61820 | 61820 |  |  | 1 | 1 |  | 278518 | 60062263 | 121809
2023-01-16 | January 2023 Review | Cost Decrease |  | Road improvements | NZTA (Canterbury) | NZUP Rolleston Access Improvements | Implementation |  | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | $6M interphase transfer from another project and WBS. 1) Interphase transfer of $650,000 from Weedons Imp-Contg (60063225) to Weedons Imp (60031531). 2) Interphase transfer of $5.35M from Rolleston Imp-Contg (60063221) to Weedons Imp (60031531). | -5537250 | -5537250 |  |  | 1.2 | 1.2 |  | 278981 | 60063221 | 121815
2023-01-16 | January 2023 Review | Cost Decrease | External funding | Road improvements | NZTA (Canterbury) | NZUP SH73 Weedons-Ross Road Intersection | Implementation | NZUP Weedons-Ross Road Int.- Contingency | H_L | HML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | $6M interphase transfer from another project and WBS. 1) Interphase transfer of $650,000 from Weedons Imp-Contg (60063225) to Weedons Imp (60031531). 2) Interphase transfer of $5.35M from Rolleston Imp-Contg (60063221) to Weedons Imp (60031531). | -672750 | -672750 |  |  | 1.2 | 1.2 | NZUP Weedons-Ross Road Int.- Contingency | 279213 | 60063225 | 121817
2023-01-16 | January 2023 Review | Cost Increase | External funding | Road improvements | NZTA (Canterbury) | NZUP SH73 Weedons-Ross Road Intersection | Implementation | NZ Upgrade Programme | H_L | HML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | $6M interphase transfer from another project and WBS. 1) Interphase transfer of $650,000 from Weedons Imp-Contg (60063225) to Weedons Imp (60031531). 2) Interphase transfer of $5.35M from Rolleston Imp-Contg (60063221) to Weedons Imp (60031531). | 6210000 | 6210000 |  |  | 1.2 | 1.2 | 60031531 | 239003 | 60031531 | 121816
2023-01-20 | January 2023 Review | Cost Increase | External funding | Road improvements | NZTA (Taranaki) | SH43 Forgotten World Highway-Tangarakau Gorge Seal Extension | Implementation | PGF | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please reallocate $2,200,000 surplused from 142662020 - 60056022 Implementation on 7-Jun-22 to 135342018 - 60053425 Implementation. MOT/Ministers approval received to transfer funds within SRP Programme | 2200000 | 2200000 |  |  | 0.7 | 0.7 |  | 255076 | 60053425 | 121901
2023-01-20 | January 2023 Review | Cost Decrease | Road to Zero | Safety promotion, education and advertising | Gisborne District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 23 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Due to COVID the full program will not be able to be delivered this year | -100000 | -67000 | [5 empty] | 272566 |  | 121736