## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Phase Label | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Decision Status | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR | Your Phase reference | TIO Phase id | SAP item id | TIO Request id
2024-01-19 | January 2024 Review | New approval | Local road maintenance | Emergency works | Carterton District Council | EW Carterton District Council Cyclone Gabrielle 2023 | Construction | Permanent Repairs/Network reinstatement | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | Recommendation That the Senior Manager, Maintenance & Operations, Transport Services: Approves emergency works funding to Carterton District Council for EW Carterton District Council Cyclone Gabrielle 2023 at a cost of $602,286 at a funding assistance rate of 51% ($307,166 out of the NLTF) for Recovery from activity class 8, work category 141. | 602286 | 427623 | [5 empty] | 283721 |  | 122158
2024-01-09 | January 2024 Review | New approval | Local road maintenance | Emergency works | Central Otago District Council | EW CODC - September 2023 | Construction | Response | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | qualifying event | 25953 | 13236 | [5 empty] | 290366 |  | 126300
2024-01-09 | January 2024 Review | New approval | Local road maintenance | Emergency works | Central Otago District Council | EW CODC - September 2023 | Construction | Repair and Recovery | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | qualifying event | 157302 | 80224 | [5 empty] | 290367 |  | 126301
2024-01-23 | January 2024 Review | New approval | Local road maintenance | Emergency works | Hurunui District Council | EW Hurunui DC July 2022 | Construction | Repair badly damaged roads | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | That the Regional Manager, Maintenance & Operations, Transport Services: â€¢ Approves emergency works funding to Hurunui District Council â€¢ for the EW Hurunui DC July 2022 event â€¢ at a cost of $433,600 (including 0% admin) â€¢ at a normal funding assistance rate of 52% ($225,472 out of the NLTF) â€¢ for 282217 and 282218 â€¢ from activity class 8, work category 141. | 348000 | 180960 | [5 empty] | 282218 |  | 126595
2024-01-23 | January 2024 Review | New approval | Local road maintenance | Emergency works | Hurunui District Council | EW Hurunui DC July 2022 | Construction | Initial response | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | That the Regional Manager, Maintenance & Operations, Transport Services: â€¢ Approves emergency works funding to Hurunui District Council â€¢ for the EW Hurunui DC July 2022 event â€¢ at a cost of $433,600 (including 0% admin) â€¢ at a normal funding assistance rate of 52% ($225,472 out of the NLTF) â€¢ for 282217 and 282218 â€¢ from activity class 8, work category 141. | 85600 | 44512 | [5 empty] | 282217 |  | 126594
2024-01-11 | January 2024 Review | New approval | Rail network | Emergency works | KiwiRail | EW Cyclone Gabrielle Recovery 2023 | Construction | - | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) |  | 40000000 | 40000000 |  |  |  |  | Weather Recovery 2023 | 290841 |  | 126847
2024-01-23 | January 2024 Review | New approval | Local road maintenance | Emergency works | Selwyn District Council | EW Selwyn DC October 2023 | Construction | Selwyn DC High Wind Event Oct 2023 | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | That the Regional Manager, Maintenance & Operations, Transport Services: â€¢ Approves emergency works funding to Selwyn District Council â€¢ for the EW Selwyn DC October 2023 event â€¢ at a cost of $390,100 (including 0% admin) â€¢ at a normal funding assistance rate of 51% ($198,951 out of the NLTF) â€¢ for TIO Phase ID 290388 â€¢ from activity class 8, work category 141. | 390100 | 198951 |  |  |  |  | Initial response. clearance of debris and delivery of repairs to signage/assets. | 290388 |  | 126675
2024-01-17 | January 2024 Review | New approval | Local road maintenance | Emergency works | South Wairarapa District Council | EW South Wairarapa District Council Cyclone Gabrielle 2023 | Construction | Permanent Repairs/Network reinstatement | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | The Senior Manager, Maintenance & Operations, Transport Services approves emergency works funding to South Wairarapa District Council for Emergency Works - South Wairarapa District Council Cyclone Gabrielle 2023 (160893/283722) project at a cost of $525,687 at a funding assistance rate of 71% ($373,238 out of the NLTF) for Recovery from activity class 8, work category 141. | 525687 | 373238 |  |  |  |  | Permanent repairs. | 283722 |  | 122160
2024-01-12 | January 2024 Review | New approval | Local road maintenance | Emergency works | Waimakariri District Council | EW Waimakariri DC July 2023 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | That the Senior Manager, Maintenance & Operations, Transport Services: â€¢ Approves emergency works funding to Waimakariri District Council â€¢ for the EW Waimakariri DC July 2023 event â€¢ at a cost of $1,947,826 (including 0% admin) â€¢ at a normal funding assistance rate of 51% ($580,851 out of the NLTF) and at an enhanced funding assistance rate of 71% ($574,320 out of the NLTF) â€¢ for 288962 and 288963 â€¢ from activity class 8, work category 141. | 999620 | 509806 | [5 empty] | 288963 |  | 125701
2024-01-12 | January 2024 Review | New approval | Local road maintenance | Emergency works | Waimakariri District Council | EW Waimakariri DC July 2023 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | That the Senior Manager, Maintenance & Operations, Transport Services: â€¢ Approves emergency works funding to Waimakariri District Council â€¢ for the EW Waimakariri DC July 2023 event â€¢ at a cost of $1,947,826 (including 0% admin) â€¢ at a normal funding assistance rate of 51% ($580,851 out of the NLTF) and at an enhanced funding assistance rate of 71% ($574,320 out of the NLTF) â€¢ for 288962 and 288963 â€¢ from activity class 8, work category 141. | 139304 | 71045 | [5 empty] | 288962 |  | 125700
2024-01-15 | January 2024 Review | New approval | Local road maintenance | Emergency works | Waimakariri District Council | EW Waimakariri DC October 2023 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | That the Regional Manager, Maintenance & Operations, Transport Services: â€¢ Approves emergency works funding to Waimakariri District Council â€¢ for the EW Waimakariri DC October 2023 event â€¢ at a cost of $195,073 (including 0% admin) â€¢ at an enhanced funding assistance rate of 71% ($138,502 out of the NLTF) â€¢ for 290437 â€¢ from activity class 8, work category 141. | 195073 | 138502 | [5 empty] | 290437 |  | 126535
2024-01-26 | January 2024 Review | New approval | Local road maintenance | Emergency works | Waitomo District Council | EW - Waitomo DC September 2023 | Construction | Mangarino Road - I, D, DP, MSQA & Physical Works | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | Mangarino Road sustained substantial damage following a rain event, making it eligible for work category 141 funding. | 1420000 | 1349000 |  |  |  |  | Mangarino - Physical Works, Design and MSQA | 290630 |  | 126523
2024-01-29 | January 2024 Review | New approval | Local road maintenance | Emergency works | Westland District Council | EW Westland DC February 2023 | Construction | Response & Reinstatement | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | That the Regional Manager, Maintenance & Operations, Transport Services: â€¢ Approves emergency works funding to Westland District Council â€¢ for the EW Westland DC February 2023 event â€¢ at a cost of $229,971 (including 0% admin) â€¢ at a normal funding assistance rate of 62% ($127,334 out of the NLTF) and at an enhanced funding assistance rate of 82% ($20,167 out of the NLTF) â€¢ for TIO Phase ID 284530 â€¢ from activity class 8, work category 141. | 205378 | 127334 | [5 empty] | 284530 |  | 125750
2024-01-26 | January 2024 Review | New approval | State highway improvements | Property purchase (State highways) | NZTA (Auckland) | SH1 Papakura to Bombay | Property | Stage 2 property NLTF funded - Drury South to Bomb | H_M | VHHM | N | 0 | Approved | Approved by Chief Financial Officer (CFO) |  | 5300000 | 5300000 |  |  | 2.5 |  | Property Stage 2 SH1 Drury to Bombay - NLTF funded | 289266 | 60072763 | 126882
2024-01-17 | January 2024 Review | New approval | Road to Zero | Road improvements | Auckland Transport | High Risk Intersections and Corridors | Implementation | HRIC Opaheke Rd & Chapel St SSInt | HHM | VHHL | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Changing Activity class to R2Z. New phase created and claim moved from 283823 to 290860. | 2400024 | 1224012 |  |  |  | 4.5 | 324.2909 | 290860 |  | 126883
2024-01-05 | January 2024 Review | New approval | Road to Zero | Road improvements | NZTA (Tasman) | SH60 Ruby Bay Bypass | Pre-implementation* |  | HMM | HMM | N | 5 | Approved | Approved by Chief Financial Officer (CFO) |  | 457800 | 457800 |  |  |  | 5 |  | 288454 | 60071510 | 126775
2024-01-11 | January 2024 Review | Cash flow adjustment | Rail network | Emergency works | KiwiRail | EW Cyclone Gabrielle Recovery 2023 | Construction | - | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) |  | 0 | 0 |  |  |  |  | Weather Recovery 2023 | 290841 |  | 126849
2024-01-04 | January 2024 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (BOP) | Minden Te Puna Intersection Improvements | Property |  | H_M | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  | 2.5 | 2.5 | 60467682 | 232655 | 60467682 | 126765
2024-01-04 | January 2024 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Marlborough) | Lions Back Safety Improvements | Property |  | M_H | M_H | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  | 4.4 | 0 | NB Includes pre-2013 costs which are missing in SAP | 200422 | 60439372 | 126770
2024-01-04 | January 2024 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Taranaki) | SH3 Vickers Road to City Upgrade | Property | Property 331 | M_H | M_H | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  | 0 | 3.7 |  | 270322 | 60460252 | 126780
2024-01-04 | January 2024 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Wellington) | Weigh Right MacKay's | Property |  | H_H | MMM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  | 14 | 14 | 60048365 | 262617 | 60048365 | 126781
2024-01-04 | January 2024 Review | Cash flow adjustment | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH25 Pepe Stream Bridge Replacement | Single-Stage Business Case | Single Stage Business Case | HHL | HHVH | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  | 1.3 | 1 |  | 270922 | 60058458 | 126767
2024-01-04 | January 2024 Review | Cash flow adjustment | State highway improvements | Replacement of bridges and other structures | NZTA (West Coast) | SH7 Ahaura River Bridge Replacement | Implementation | Construction | H__ | H__ | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  | 0 | 0 | 60030967 | 232575 | 60030967 | 126782
2024-01-04 | January 2024 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Auckland) | Auckland Network Optimisation (ANO) Programme | Single-Stage Business Case | AKL Opt SSBC | MHM | MHM | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  |  | 3.2 | InfoHub ID 28116348 ¦ SAP 60056366 | 254837 | 60056366 | 126758
2024-01-04 | January 2024 Review | Cash flow adjustment | Road to Zero | Road improvements | NZTA (BOP) | SH33 (Te Ngae Junction to Paengaroa) - TNJ intersection | Pre-implementation* |  | VHMVL | VHHL | N | 8 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  | 0 | 1.6 |  | 278539 | 60062266 | 126766
2024-01-16 | January 2024 Review | Cash flow adjustment | External funding | Road improvements | NZTA (Northland) | NZUP SH1 Whangarei to Port Marsden H'way | Detailed Business Case | NZ Upgrade Programme | H_L | HML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  | 1.1 | 1.1 | External Funding 60057017 | 270290 | 60057017 | 126778
2024-01-11 | January 2024 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | NZTA (Gisborne) | Gisborne - Wainui Cycleway SH 35 | Construction | Gisborne - Wainui Cycleway SH 35 | M_M | M_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please transfer $4,350 from 60039128 - Property to 60214504 - Implementation, this will alow the Porperty Phase to be closed followed by the Implementation phase with an over spend of $912 | 4741 | 4741 |  |  | 0 | 2.5 | 60214504 | 213804 | 60214504 | 126801
2024-01-11 | January 2024 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | NZTA (Gisborne) | Gisborne - Wainui Cycleway SH 35 | Construction | Gisborne - Wainui Cycleway SH 35 | M_M | M_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Write off $993 increase. | 993 | 993 |  |  | 0 | 2.5 | 60214504 | 213804 | 60214504 | 126846
2024-01-11 | January 2024 Review | Cost Decrease | Local road maintenance | Emergency works | KiwiRail | EW Cyclone Gabrielle Recovery 2023 | Construction | Jan/Feb Weather Events - wrong activity class | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) |  | -40000000 | -40000000 |  |  |  |  | Weather Recovery 2023 | 284026 |  | 126848
2024-01-04 | January 2024 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (Taranaki) | EW Gabrielle Taranaki RW 20230214 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Project Close | -151745 | -151745 | [5 empty] | 283657 | 60069818 | 126803
2024-01-11 | January 2024 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (Wellington) | EW SH59 Pukerua Bay Footpath 22020818 | Construction |  | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | AIA (Ting) request to close and surplus $228,342 | -248893 | -248893 | [5 empty] | 282979 | 60068588 | 126851
2024-01-11 | January 2024 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (Wellington) | EW SH59 Pukerua Bay Slips 20220818 | Construction |  | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | AIA (Ting) request to close and surplus $93,691 | -102123 | -102123 | [5 empty] | 282909 | 60068509 | 126839
2024-01-18 | January 2024 Review | Cost Decrease | State highway maintenance | Emergency works | NZTA (West Coast) | EW West Coast SH7 Omoto East Slumping 20190811 | Construction |  | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | Closure requested by Brittany Williams | -244737 | -244737 | [5 empty] | 268831 | 60054638 | 126886
2024-01-04 | January 2024 Review | Cost Decrease | Local road maintenance | Emergency works | Wellington City Council | Emergency Works Cyclone Dovi Storm Event February 2022 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Project Close | -513218 | -261741 |  |  |  |  | Cyclone Dovi - Storm Event Feb. 22 | 281718 |  | 126764
2024-01-04 | January 2024 Review | Cost Decrease | State highway maintenance | Network and asset management | NZTA (Canterbury) | 2021-24 NLTP funds management | Repayment | AC9 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Fix offset | -7858518 | -7858518 | [5 empty] | 279053 |  | 126819
2024-01-04 | January 2024 Review | Cost Decrease | State highway maintenance | Network and asset management | NZTA (Tasman) | 2021-24 NLTP funds management | Repayment | AC9 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reduce offset. | -994008 | -994008 | [5 empty] | 279273 |  | 126820
2024-01-18 | January 2024 Review | Cost Decrease | Local road improvements | New roads | Porirua City Council | PCC Link Roads | Construction | Construction | VHHL | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | FAR change to correct FAR for the 23/24 year | 0 | -29829 |  |  | 1 | 1 |  | 224001 |  | 126842
2024-01-04 | January 2024 Review | Cost Decrease | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | NZTA (Waikato) | Hamilton Urban Improvements - Bus priority hotspots | Single-Stage Business Case | Single Stage Business Case | HHM | HHM | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reduced scope. | -54948 | -54948 | [5 empty] | 258356 | 60052751 | 126776
2024-01-04 | January 2024 Review | Cost Decrease | Public transport services | Passenger services - bus | Gisborne District Council | Government reduced public transport fares scheme (Crown) | Implementation | Bus Services - Reduced fares | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -3883 | -3883 | [5 empty] | 281227 |  | 126804
2024-01-11 | January 2024 Review | Cost Decrease | State highway improvements | Property purchase (State highways) | NZTA (Gisborne) | Gisborne - Wainui Cycleway SH 35 | Property | Wainui stage II Property | M_M | M_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please transfer $4,350 from 60039128 - Property to 60214504 - Implementation, this will alow the Porperty Phase to be closed followed by the Implementation phase with an over spend of $911 | -4611 | -4611 |  |  | 0 | 2.5 | 60039128 | 246493 | 60039128 | 126802
2024-01-29 | January 2024 Review | Cost Increase | External funding | Property purchase (State highways) | NZTA (Wellington) | NZUP SH2 Melling Efficiency & Safety Imp | Property | NZ Upgrade Programme | HMM | MMH | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please transfer $43,961,000 from 60063250 Implementation Contingency to 60471352 Property | 45719440 | 45719440 |  |  | 0 | 1.3 |  | 270321 | 60471352 | 126926
2024-01-04 | January 2024 Review | Cost Decrease | Public transport infrastructure | Rapid Transit Infrastructure | NZTA (Auckland) | City Centre to Mangere | Indicative Business Case | Establishment Unit RT | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -279141 | -279141 |  |  | 1 | 1 | Establishment Unit RTN | 277180 | 60061106 | 126759
2024-01-09 | January 2024 Review | Cost Decrease | Public transport infrastructure | Rapid Transit Infrastructure | NZTA (Auckland) | City Centre to Mangere | Indicative Business Case | Establishment Unit RT | H_L | H_L | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Update to match SAP item which is marked as "Complete" | -428 | -428 |  |  | 1 | 1 | Establishment Unit RTN | 277180 | 60061106 | 126838
2024-01-04 | January 2024 Review | Cost Decrease | State highway improvements | Replacement of bridges and other structures | NZTA (BOP) | HPMV SH2 Opotiki to Gisborne boundary | Implementation | NLTF commitment to Tpackage - PGF | H_M | H_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -41121 | -41121 |  |  | 0 | 2.4 | 60051622 | 265922 | 60051622 | 126760
2024-01-16 | January 2024 Review | Cost Increase | State highway improvements | Resilience improvements | NZTA (Southland) | SH94 Milford Road to Te Anau Downs | Single-Stage Business Case |  | HHL | HMM | N | 5 | Approved | Approved by Chief Financial Officer (CFO) |  | 150000 | 150000 |  |  |  | 2.4 |  | 277422 | 60069346 | 126529
2024-01-17 | January 2024 Review | Cost Decrease | Local road improvements | Road improvements | Auckland Transport | High Risk Intersections and Corridors | Implementation | HRIC Opaheke Rd & Chapel St SSInt | HHM | VHHL | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Changing Activity class to R2Z. New phase created and claim removed to 290860. | -2400024 | -1224012 |  |  |  | 4.5 | 324.2838 | 283823 |  | 126723
2024-01-04 | January 2024 Review | Cost Decrease | Local road improvements | Road improvements | Kaikoura District Council | LED Streetlight Renewal Programme | Implementation | Implementation Phase | M_H | M_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -26551 | -13541 |  |  | 0 | 0 |  | 271984 |  | 126773
2024-01-05 | January 2024 Review | Cost Decrease | Road to Zero | Road improvements | NZ Transport Agency | SIP - Programme Management | Pre-implementation* | SIP Programme Management | VHHL | VHHL | N | 2 | Approved | Approved by Chief Financial Officer (CFO) |  | -457800 | -457800 |  |  | 2.2 | 2.2 | 60063778 Jamie K | 277979 |  | 126822
2024-01-10 | January 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Auckland) | Northern Corridor Improvements (NCI) | Construction | Construction - Main | H_M | HHM | N | 0 | Approved | Approved by Chief Financial Officer (CFO) | Claims for unforeseen escalation costs resulting from the COVID-19 pandemic. all escalation claims up to and including June 2023 have now been settled and one further claim is expected, for which an allowance ($2.5M) has been included in the forecasted cost. | 4244517 | 4244517 |  |  | 3 | 3 | 60027507 | 254897 | 60027507 | 126700
2024-01-04 | January 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (BOP) | Minden Te Puna Intersection Improvements | Construction | Construction | H_M | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -235578 | -235578 |  |  | 2.5 | 2.5 | 60217896 | 231383 | 60217896 | 126762
2024-01-18 | January 2024 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (Hawkes Bay) | SH51 Napier to Hastings | Implementation | SH51 Elliston St to Tutaekuri Bridge - Stg 1 | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please transfer $150,000 from 60060914 Implementation to 60060890 Pri-Implementation to cover overspend and additional cost | -163500 | -163500 |  |  | 2.1 | 2.1 | 84 | 277273 | 60060914 | 126858
2024-01-18 | January 2024 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Hawkes Bay) | SH51 Napier to Hastings | Pre-implementation* | SH51 Napier to Hastings | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please transfer $150,000 from 60060914 Implementation to 60060890 Pri-Implementation to cover overspend and additional cost | 163500 | 163500 |  |  | 2.1 | 2.1 | 11 | 277266 | 60060890 | 126859
2024-01-10 | January 2024 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Manawatu/Whanganui) | Otaki to North Levin - SH1/57 - southern section | Implementation |  | VHHL | HHVH | N | 2 | Approved | Approved by Chief Financial Officer (CFO) | Covid Claim: Covid19 claim approved by Claims Handling Group 8-Dec-23 for $1,642,579. | 1790395 | 1790395 |  |  | 0 | 1.6 |  | 278530 | 60062283 | 126706
2024-01-04 | January 2024 Review | Cost Decrease | External funding | Road improvements | NZTA (Northland) | RIO SH12 & Rawene Rd IS IMPR | Pre-implementation* | Design | L_H | L_H | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -2887 | -2887 |  |  | 1 | 1 | 60055992 | 269693 | 60055992 | 126779
2024-01-15 | January 2024 Review | Cost Decrease | External funding | Road improvements | NZTA (Tasman) | CIP SH60 Motueka Project | Implementation | CIP SH60 Motueka Investigation Project | MHM | MHM | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please transfer $7,087 from 60059407 - Implementation to 60059406 - Pre-Implementation, Pre-Imp and Imp phases can then be closed. | -7087 | -7087 |  |  | 3.3 | 3.3 |  | 276583 | 60059407 | 126845
2024-01-15 | January 2024 Review | Cost Increase | External funding | Road improvements | NZTA (Tasman) | CIP SH60 Motueka Project | Pre-implementation* | CIP SH60 Motueka Project | MHM | MHM | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please transfer $7,087 from 60059407 - Implementation to 60059406 - Pre-Implementation, Pre-Imp and Imp phases can then be closed. | 7087 | 7087 |  |  | 3.3 | 3.3 |  | 271780 | 60059406 | 126844
2024-01-04 | January 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Waikato) | 2021-24 NLTP funds management | Repayment | AC13 | LHVL | LHVL | N | 12 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Reduce offset. | -42582 | -42582 | [5 empty] | 279275 |  | 126821
2024-01-04 | January 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Waikato) | SH3/37 Waitomo Road Intersection | Implementation | Construction | H_H | H_H | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -23014 | -23014 |  |  | 4.5 | 4.5 | 60026516 | 231798 | 60026516 | 126768
2024-01-29 | January 2024 Review | Cost Decrease | External funding | Road improvements | NZTA (Wellington) | NZUP SH2 Melling Efficiency & Safety Imp | Implementation |  | HMM | MMH | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please transfer $43,961,000 from 60063250 Implementation Contingency to 60471352 Property | -45719440 | -45719440 |  |  | 0 | 1.3 |  | 278984 | 60063250 | 126925
2024-01-17 | January 2024 Review | Cost Increase | External funding | Road improvements | NZTA (Wellington) | NZUP SH2 Melling Efficiency & Safety Imp | Implementation | SH2 Melling Efficiency & Safety Imp NZUP | HMM | MMH | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please transfer $6,177.164 from 60057014 Pre-Implementation to 60218122 Implementation, Pre-Imp phase can then be closed | 6424251 | 6424251 |  |  | 0 | 1.3 | NZ Upgrade Programme | 270320 | 60218122 | 126885
2024-01-25 | January 2024 Review | Cost Decrease | External funding | Road improvements | NZTA (Wellington) | NZUP SH2 Melling Efficiency & Safety Imp | Implementation |  | HMM | MMH | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please transfer $174,743,000 from 60063250 Implementation Contingency to 60218122 Implementation | -181732720 | -181732720 |  |  | 0 | 1.3 |  | 278984 | 60063250 | 126904
2024-01-25 | January 2024 Review | Cost Increase | External funding | Road improvements | NZTA (Wellington) | NZUP SH2 Melling Efficiency & Safety Imp | Implementation | SH2 Melling Efficiency & Safety Imp NZUP | HMM | MMH | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please transfer $174,743,000 from 60063250 Implementation Contingency to 60218122 Implementation | 181732720 | 181732720 |  |  | 0 | 1.3 | NZ Upgrade Programme | 270320 | 60218122 | 126905
2024-01-17 | January 2024 Review | Cost Decrease | External funding | Road improvements | NZTA (Wellington) | NZUP SH2 Melling Efficiency & Safety Imp | Pre-implementation* | NZ Upgrade Programme | HMM | MMH | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please transfer $6,177.164 from 60057014 Pre-Implementation to 60218122 Implementation, Pre-Imp phase can then be closed | -6424251 | -6424251 |  |  | 0 | 1.3 | 60057014 | 270285 | 60057014 | 126887
2024-01-04 | January 2024 Review | Cost Decrease | Road to Zero | Safety promotion, education and advertising | NZTA (Auckland) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Surplus funds not required. Confirmed by RSP team. | 0 | -118150 |  |  |  |  | 60065061 | 273190 | 60065061 | 126799
2024-01-04 | January 2024 Review | Cost Decrease | Road to Zero | Safety promotion, education and advertising | NZTA (Canterbury) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Surplus funds not required. Confirmed by RSP team. | 0 | -216146 |  |  |  |  | 60065103 | 273398 | 60065103 | 126798
2024-01-04 | January 2024 Review | Cost Decrease | Road to Zero | Safety promotion, education and advertising | NZTA (Manawatu/Whanganui) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Surplus funds not required. Confirmed by RSP team. | 0 | -45400 |  |  |  |  | 60065081 | 273346 | 60065081 | 126800
2024-01-04 | January 2024 Review | Cost Decrease | Road to Zero | Safety promotion, education and advertising | NZTA (Otago) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Surplus funds not required. Confirmed by RSP team. | 0 | -122803 |  |  |  |  | 60065111 | 273450 | 60065111 | 126704