## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Phase Label | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Decision Status | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR | Your Phase reference | TIO Phase id | SAP item id | TIO Request id
2024-02-02 | February 2024 Review | New approval | External funding | Cycling facilities | Wellington City Council | CERF-TC WCC Transport package | Implementation | Thorndon to Wadestown Transitional Cycleway | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | CERF activities | 1000000 | 900000 |  |  |  | 0 |  | 290898 |  | 126917
2024-02-02 | February 2024 Review | New approval | External funding | Cycling facilities | Wellington City Council | CERF-TC WCC Transport package | Implementation | Karori to Botanic Garden transitional cycleway | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | CERF activities | 1316100 | 1184490 |  |  |  | 0 |  | 290897 |  | 126916
2024-02-02 | February 2024 Review | New approval | External funding | Cycling facilities | Wellington City Council | CERF-TC WCC Transport package | Pre-implementation* | North Western suburbs - Transitional Cycleway | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | CERF activities | 210000 | 189000 |  |  |  | 0 |  | 290899 |  | 126918
2024-02-26 | February 2024 Review | New approval | Local road maintenance | Emergency works | Far North District Council | EW - Far North DC August 2022 | Construction | Phase 2&3 - Major Remedial Works - EW August 2022 | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | CFO approval from activity class 8, Refer to supporting docs. | 23919860 | 17734781 | [5 empty] | 283200 |  | 126850
2024-02-20 | February 2024 Review | New approval | Local road maintenance | Emergency works | Far North District Council | EW Far North DC October 2023 | Construction | Phase 1 - Initial Response - EW October 2023 | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | Refer to funding approval document under supporting documents. | 200297 | 178264 |  |  |  |  | Phase 1 - Initial Response - EW October 2023 | 290477 |  | 126978
2024-02-20 | February 2024 Review | New approval | Local road maintenance | Emergency works | Far North District Council | EW Far North DC October 2023 | Construction | Phase 2 - Minor Remedial Works - EW October 2023 | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | Refer to funding approval document under supporting documents in TIO. | 234300 | 208527 |  |  |  |  | Phase 2 - Minor Remedial Works - EW October 2023 | 290906 |  | 127002
2024-02-26 | February 2024 Review | New approval | Local road maintenance | Emergency works | Kaikoura District Council | EW Kaikoura DC April 2023 (Blue Duck Valley Road) | Construction | Blue Duck - Emergency Slope Stabilisation | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | That the Regional Manager, Maintenance & Operations, Transport Services: â€¢ Approves emergency works funding to Kaikoura District Council â€¢ for the EW Kaikoura DC April 2023 (Blue Duck Valley Road) event â€¢ at a cost of $239,715 (including 0% admin) â€¢ at an enhanced funding assistance rate of 71% ($170,198 out of the NLTF) â€¢ for TIO Phase ID 290684 â€¢ from activity class 8, work category 141. | 239715 | 170198 | [5 empty] | 290684 |  | 126982
2024-02-14 | February 2024 Review | New approval | Local road maintenance | Emergency works | Kaikoura District Council | EW Kaikoura DC April 2023 (Puhi Puhi Road) | Construction | Puhi Puhi Road | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | That the Regional Manager, Maintenance & Operations, Transport Services: â€¢ Approves emergency works funding to Kaikoura District Council â€¢ for the EW Kaikoura DC April 2023 (Puhi Puhi Road) event â€¢ at a cost of $560,285 (including 0% admin) â€¢ at a normal funding assistance rate of 51% ($89,423 out of the NLTF) and at an enhanced funding assistance rate of 71% ($273,311 out of the NLTF) â€¢ for TIO Phase ID 284505 â€¢ from activity class 8, work category 141. | 175340 | 89423 | [5 empty] | 284505 |  | 123186
2024-02-12 | February 2024 Review | New approval | Local road maintenance | Emergency works | Kapiti Coast District Council | Emergency Works August Storm Event 2022 | Construction | Build permanent rock wall | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | That the Regional Manager Maintenance & Operations, Wellington approves: $600,000 (NLTF $306,000) at a FAR of 51% for the Recovery phase of the Kapiti Coast District Council Emergency Works Storm Event August 2022 from Activity Class 08 Work Category 141. Notes that this brings the total cost of the activity from $289,130 to $889,130. | 600000 | 306000 | [5 empty] | 284158 |  | 126878
2024-02-20 | February 2024 Review | New approval | Local road maintenance | Emergency works | Masterton District Council | MDC Jan Flooding Event 2023 | Construction | Recovery | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | The Senior Manager, Maintenance & Operations, Transport Services approves emergency works funding to Masterton District Council for Emergency Works Masterton District Council Recovery Phaseâ€“ Jan Flooding Event 2023 (160785/ 283834) project at a cost of $2,824,362 at a funding assistance rate of 56%/76% ($2,067,272 out of the NLTF) for Recovery from activity class 8, work category 141. | 1472916 | 824833 | [5 empty] | 283834 |  | 122237
2024-02-12 | February 2024 Review | New approval | State highway maintenance | Emergency works | NZTA (Waikato) | EW Waikato East Cyclone Lola 20231030 | Construction |  | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | We need TCDC to carry out the works on the storm water pipes before we reconstruct the pavement. Please keep the pressure on the council as this pavement will continue to deteriorate and consume reactive spend. We really donâ€™t want to consume more reactive spend than the cost to reconstruct pavement. And we donâ€™t want to reconstruct the pavement until the pipes have been fixed. | 500000 | 500000 | [5 empty] | 290457 | 60073924 | 127001
2024-02-09 | February 2024 Review | New approval | Local road maintenance | Emergency works | New Plymouth District Council | EW - May 2023 Rain Event (NPDC) | Construction | Planned Restoration | ___ |  | N |  | Approved | Approved by National Manager, Programmes and Standards (Transport Services) | As recommended by Regional Office. To enable New Plymouth District Council to undertake initial response and recovery of Ngamotu Rd in New Plymouth and return this section to the required pre-event level of service. | 468500 | 238935 |  |  |  |  | Planned Restoration | 284149 |  | 123317
2024-02-08 | February 2024 Review | New approval | Local road maintenance | Emergency works | Rotorua Lakes Council | EW - Rotorua LC Storm Damage May 2023 | Construction | Phase 2 - Construction | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | That the Senior Manager, Maintenance & Operations Transport Services: â€¢ Approves emergency works funding to Rotorua LC Storm Damage May 2023 (Phase 2) at a cost of $2,950,000 (including 0% Admin) â€¢ at a funding assistance rate of 76% $2,242,000 out of the NLTF â€¢ for phase 284390 â€¢ from activity class 8, work category 141 â€¢ thereby increasing the approved total cost from $750,000 to $3,700,000 (including 0% Admin) | 2950000 | 2242000 | [5 empty] | 284390 |  | 126757
2024-02-21 | February 2024 Review | New approval | Local road maintenance | Emergency works | Selwyn District Council | EW Selwyn DC July 2023 | Construction | EW Selwyn DC Heavy Rain Event July 23 | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | That the Senior Manager, Maintenance & Operations, Transport Services: â€¢ Approves emergency works funding to Selwyn District Council â€¢ for the EW Selwyn DC July 2023 event â€¢ at a cost of $3,986,257 (including 0% admin) â€¢ at a normal funding assistance rate of 51% ($658,516 out of the NLTF) and at an enhanced funding assistance rate of 71% ($1,913,485 out of the NLTF) â€¢ for TIO phase ID 290387 â€¢ from activity class 8, work category 141. | 1291208 | 658516 |  |  |  |  | EW Selwyn DC Heavy Rain Event July 23 | 290387 |  | 126673
2024-02-20 | February 2024 Review | New approval | Local road maintenance | Emergency works | South Wairarapa District Council | Emergency Works Cyclone Hale Storm Event 2023 | Construction | Network reinstatement | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | The Senior Manager, Maintenance & Operations, Transport Services approves emergency works funding to South Wairarapa District Council for Emergency Works - South Wairarapa District Council Cyclone Hale storm event 2023 (160645/283605) project at a cost of $$1,328,316 at a funding assistance rate of 51%/71% ($877,441 out of the NLTF) for Recovery from activity class 8, work category 141. | 1328316 | 877441 | [5 empty] | 283605 |  | 121984
2024-02-20 | February 2024 Review | New approval | Local road maintenance | Emergency works | Thames-Coromandel District Council | EW - Thames-Coromandel DC July 2023 | Construction | Permanent Reinstatement MSQA and Construction | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | Investment required to construct permanent reinstatement structures / works. | 1840500 | 938655 | [5 empty] | 289670 |  | 126019
2024-02-20 | February 2024 Review | New approval | Local road maintenance | Emergency works | Thames-Coromandel District Council | EW - Thames-Coromandel DC July 2023 | Construction | Initial Response, Investigation and Design | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | Investment required to respond to storm damage / return LoS that existed prior to this weather event and complete site investigation and design of permanent reinstatement works, planned for construction as part of the second EW phase. | 408994 | 208587 | [5 empty] | 289669 |  | 126018
2024-02-19 | February 2024 Review | New approval | Local road maintenance | Emergency works | Waitomo District Council | EW - Waitomo DC February 2022 Cyclone Dovi | Construction | 23/24 - Professional Services and Physical Works | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | This emergency works funding application meets Waka Kotahi investment requirements as assessed against the Planning and Investment Knowledge Base guidance. Investment required to complete permanent reinstatement works to restore LoS that existed prior to the weather event as detailed in the attached funding approval paper. | 2235000 | 2123250 | [5 empty] | 290769 |  | 126724
2024-02-02 | February 2024 Review | New approval | Investment management (incl. Transport Planning) | Management of the funding allocation system | NZ Transport Agency | Infrastructure Procurement Strategy | Implementation | SAP 60074414 | HHH | HHH | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | 1. The key benefit of this funding is to implement the Board endorsed Waka Kotahi Infrastructure Procurement Strategy. 2. The requirements of section 20 of the Land Transport Management Act 2003 have been met. 3. The decision is neutral in relation to the climate change strategic priority set out in the GPS (including impacts on relevant transport emission reduction targets and consistency with the ERP) and the proposal is consistent with the GPS as a whole. | 1065000 | 1065000 |  |  |  | 1 | 60074414 | 290857 |  | 126946
2024-02-27 | February 2024 Review | New approval | External funding | New activities influencing users of the transport system | Otago Regional Council | CERF-TC- Superstops facilities | Implementation | Superstop imp -- Union St | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | Part of the Budget 2022 Cabinet approved initiatives with funding under the Climate Emergency response Fund (CERF) programme. CERF-TC projects do not follow the same NLTF business case assessment pathway. The business case assessment has been replaced with a bespoke application, assessment, monitoring process as detailed in Transport Choices Funding Agreement Guidance Notes. | 753122 | 585900 |  |  | 0 | 0 |  | 284248 |  | 127059
2024-02-19 | February 2024 Review | New approval | Public transport services | New activities influencing users of the transport system | Queenstown-Lakes District Council | Travel Demand Management | Implementation | Implementation Phase | HHH | VHHVH | N | 4 | Approved | Approved by Chief Financial Officer (CFO) | The TDM package will optimise use of Queenstownâ€™s limited existing network and committed investment in infrastructure and services through travel planning, activation events, promotion and wayfinding, helping to maximise alternative mode share and maintain a functional transport network | 500000 | 255000 |  |  |  | 8.5 |  | 277213 |  | 121428
2024-02-23 | February 2024 Review | New approval | External funding | Passenger services - bus | Greater Wellington | CERF-Decarbonising the PT Bus Fleet - Lyall Bay Stage 1 | Implementation | funding depot stage 1 | HHH | VHHM | N | 4 | Approved | Approved by Minister for Crown Appropriation | This has a signed agreement as per the process for the CERF Bus Decarbonisation Contestable Fund | 21250981 | 10838000 |  |  |  |  | Funding depot stage 1 | 291079 |  | 127164
2024-02-16 | February 2024 Review | New approval | Public transport infrastructure | Public transport facilities & infrastructure - operations and maintenance | NZTA (Waikato) | Hamilton Urban Improvements - Bus priority hotspots | Indicative Business Case |  | HHM | HHM | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Suprlus transfer funds of $499,844.00 from DBC 60052751 to newly created IBC item 60073997. Cost neutral transfer. | 544830 | 544830 | [5 empty] | 290879 | 60073997 | 126922
2024-02-09 | February 2024 Review | New approval | External funding | Resilience improvements | NZ Transport Agency | Modern Bailey bridge stock purchase | Implementation | 60074533 | LHL | LHL | N | 12 | Approved | Approved by Chief Financial Officer (CFO) | To enhance national resilience in response to civil defence emergencies through the purchase of modern Bailey bridge stocks to supplement the existing stocks that are now almost fully in use. | 15000000 | 15000000 |  |  | 0 | 0 | 60074533 | 290977 |  | 127008
2024-02-16 | February 2024 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | NZTA (BOP) | SH2: Baypark to Bayfair Link Upgrade (was MGI) | Implementation | construction of walking and cycling | H_H | H_M | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  | 2.5 | 2.5 | walking and cycling variation | 266124 | 60051841 | 127060
2024-02-02 | February 2024 Review | Cash flow adjustment | External funding | New roads | NZTA (Auckland) | NZUP Penlink | Implementation | NZ Upgrade Programme | H_L | HML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Please cashflow $672,291 (2024); -$4,653,357 (2025); $55,395,696 (2026) & -$51,414,631 (2027) | 1 | 1 |  |  | 13.4 | 7.8 |  | 269747 | 60056122 | 126910
2024-02-16 | February 2024 Review | Cash flow adjustment | Investment management (incl. Transport Planning) | Programme Business Case Development | NZ Transport Agency | One Network Framework | Programme business case |  | HHL | HHL | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Revised programme timeframe - pause to check alignment with PIF outcomes, internal resourcing availability, but most importantly roll out staged appropriately in time for year 1 start of of 24 -27 NLTP and sector next phase of programming and planning. | 0 | 0 |  |  |  |  | 80002709 - plus Business Change Enterprise resource | 280299 |  | 127058
2024-02-16 | February 2024 Review | Cash flow adjustment | State highway improvements | Property purchase (State highways) | NZTA (Waikato) | Atiamuri Bridge Replacement | Property |  | H_PV_EoL | H_H | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  | 0 | 1 | 60461092 | 247893 | 60461092 | 126843
2024-02-16 | February 2024 Review | Cash flow adjustment | State highway improvements | Resilience improvements | NZTA (Wellington) | SH2 Remutaka Hill Underslip Prevention | Implementation |  | HML | HML | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -1 | -1 |  |  |  |  | 60042585 | 249674 | 60042585 | 126942
2024-02-02 | February 2024 Review | Cash flow adjustment | External funding | Road improvements | NZTA (Auckland) | NZUP Penlink | Implementation |  | H_L | HML | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cashflow all allocation to 2027. This is contingencies and is normal to have it out as far as possible. | 0 | 0 |  |  | 13.4 | 7.8 |  | 278976 | 60063233 | 126909
2024-02-16 | February 2024 Review | Cash flow adjustment | External funding | Road improvements | NZTA (Northland) | SH10 Waipapa Corridor Improvements | Implementation | PGF | M_M | MHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Additional costs related to service relocations and pavement defects outside of the contractor responsibility. PLA for $771,531 (excluding admin) submitted and awaiting approval | 0 | 0 |  |  | 3.2 | 3.2 | PGF - Implementation | 241049 | 60214480 | 126980
2024-02-02 | February 2024 Review | Cost Decrease | Local road maintenance | Bridge and structures renewals | Buller District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Buller DC has declared a surplus from WC 216. | -250000 | -180000 | [5 empty] | 272263 |  | 126939
2024-02-04 | February 2024 Review | Cost Increase | External funding | Cycling facilities | Waitaki District Council | CERF-TC Oamaru SH 1, safe crossings upgrades | Pre-implementation* | Stage 1 - SH1 Safe Crossings Upgrades | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | Approved by the Transport Choices Review Forum in September 23 and factored into final TC budget post Minister announcement to pause TC. | 49900 | 49900 |  |  |  | 0 | Sharepoint Contract 900 Transport Choices Programme - Profesional Services | 284538 |  | 126391
2024-02-02 | February 2024 Review | Cost Increase | External funding | Cycling facilities | Wellington City Council | CERF-TC WCC Transport package | Implementation | TC Aro Valley Transitional Cycleways | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | Projects cost revised and approved in October 23. Memo attached | 492134 | 442920 |  |  |  | 0 |  | 284367 |  | 126911
2024-02-02 | February 2024 Review | Cost Increase | External funding | Cycling facilities | Wellington City Council | CERF-TC WCC Transport package | Implementation | TC Kilbirne Connection Transitional Cycleway | HHH | HHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Projects cost revised and approved in October 23. Memo attached This activity includes the Kilbirne Transitional Cycleway and the Kilbirne Walkable Neighborhoods | 824096 | 741686 |  |  |  | 0 |  | 284369 |  | 126913
2024-02-02 | February 2024 Review | Cost Increase | External funding | Cycling facilities | Wellington City Council | CERF-TC WCC Transport package | Implementation | TC Ngaio Connection Transitional Cycleway | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | Projects cost revised and approved in October 23. Memo attached | 427612 | 384851 |  |  |  | 0 |  | 284368 |  | 126912
2024-02-02 | February 2024 Review | Cost Decrease | External funding | Cycling facilities | Wellington City Council | CERF-TC WCC Transport package | Implementation | TC Thorndon Connection Transitional Cycleway | HHH | HHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Projects cost revised and approved in October 23. Memo attached | -876274 | -788647 |  |  |  | 0 |  | 284370 |  | 126914
2024-02-02 | February 2024 Review | Cost Decrease | External funding | Cycling facilities | Wellington City Council | CERF-TC WCC Transport package | Pre-implementation* | TC Ngaio to Karori Transitional Cycleway | HHH | HHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cost reduction approved in October 23 | -347490 | -347490 |  |  |  | 0 |  | 284535 |  | 126920
2024-02-02 | February 2024 Review | Cost Decrease | External funding | Cycling facilities | Wellington City Council | CERF-TC WCC Transport package | Pre-implementation* | TC Salamanca Road to Northland Transitional Cly | HHH | HHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cost reduction approved in October 23 | -209880 | -209880 |  |  |  | 0 |  | 284536 |  | 126921
2024-02-02 | February 2024 Review | Cost Decrease | External funding | Cycling facilities | Wellington City Council | CERF-TC WCC Transport package | Pre-implementation* | TC Ngaio to Johnsonville | HHH | HHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cost reduction approved in October 23 | -347490 | -347490 |  |  |  | 0 |  | 284534 |  | 126919
2024-02-02 | February 2024 Review | Cost Increase | External funding | Cycling facilities | Wellington City Council | CERF-TC WCC Transport package | Pre-implementation* | Karori to Botanic Garden transitional cycleway | HHH | HHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Projects cost revised and approved in October 23 | 10000 | 9000 |  |  |  | 0 |  | 284532 |  | 126915
2024-02-15 | February 2024 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Wellington City Council | Transitional Cycleways Programme (ex Accelerated)(SfP) | Implementation | SfP Newtown â€“ Island Bay Imp | HHL | VHHM | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Moving $220k from NZTA contingency for Four permanent raised crossings as approved in the variation agreement signed on 25/07/2023. Authorised by SfP Programme Lead, Geoff. Cost neutral transfer from 279202 to 282824. | 220000 | 198000 |  |  |  | 3.5 | SfP Newtown â€“ Island Bay Imp | 282824 |  | 126888
2024-02-02 | February 2024 Review | Cost Decrease | External funding | Cycling facilities | Whangarei District Council | CERF-TC - WDC Transport Choices Package | Implementation | WDC01 Raumanga Shared Path and CBD cycle parking | HHH | HHH | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Correcting error in total value. Value too high. | -115000 | -115000 |  |  |  | 0 |  | 284202 |  | 126938
2024-02-29 | February 2024 Review | Cost Decrease | Local road maintenance | Drainage renewals | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | National office have prioritised the requests for bridge maintenance and renewals as they are highest risk and also the surplus is coming from WC216. The request for funding has been recommended | -400000 | -236000 | [5 empty] | 272310 |  | 126944
2024-02-02 | February 2024 Review | Cost Decrease | Local road maintenance | Environmental maintenance | Buller District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Buller DC has declared a surplus from WC 216. | -75383 | -54276 | [5 empty] | 272253 |  | 126939
2024-02-02 | February 2024 Review | Cost Decrease | Local road improvements | Low cost / low risk improvements | Chatham Islands Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | As per discussions with Council's Network Engineer - CIC has declared a surplus for Local Road Improvements AC. | -799767 | -703795 | [5 empty] | 276022 |  | 126924
2024-02-16 | February 2024 Review | Cost Decrease | Local road improvements | Low cost / low risk improvements | Western BoP District Council | Low cost / low risk improvements 2021-24 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The 2023/24 LRI allocation was approved prior to the joint (NZTA/WBOPDC) One Network Maintenance Contract extension being declined. This request is supported given the uncertainty regarding delivery of the local road improvements programme, now that new supply arrangements need to be established before the programme of improvement works can be delivered. | -5241000 | -2672910 | [5 empty] | 276538 |  | 127039
2024-02-29 | February 2024 Review | Cost Increase | Local road maintenance | Minor events | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | National office have prioritised the requests for bridge maintenance and renewals as they are highest risk and also the surplus is coming from WC216. The request for funding has been recommended | 400000 | 236000 | [5 empty] | 272302 |  | 126944
2024-02-29 | February 2024 Review | Cost Decrease | Local road maintenance | Network and asset management | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | National office have prioritised the requests for bridge maintenance and renewals as they are highest risk and also the surplus is coming from WC216. The request for funding has been recommended | -100000 | -59000 | [5 empty] | 272307 |  | 126944
2024-02-05 | February 2024 Review | Cost Decrease | Public transport services | Operations & maintenance of real-time and ticketing systems | Taranaki Regional Council | Public Transport Programme 2021-24 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | That the National Manager, Programme and Standards, Transport Services: â€¢ Endorse the price level adjustment & recommend that the Senior Manager I&F - Operational Policy & Performance approve funding o to Taranaki Regional Council (TRC) o for Public Transport Programme 2021-24 (PT continuous programme) o a total amount of $1,839,153 made up of: ï‚§ WC 511: $1,855,683 at a FAR of 51% ï‚§ WC 517: $185,237 at a FAR of 60% ï‚§ A decrease of ($201,767) from work categories 519, 521 and 525 at various FARs. o A total NLTF amount of $912,152 made up of: ï‚§ WC 511: $946,398 ï‚§ WC 517: $111,142 ï‚§ A decrease of ($145,388) o From AC 4 - Public Transport Services Activity Class. The overall approved total cost of the PT continuous programme that aligns to the Public Transport Services Activity Class increases from $12,329,884 to $14,169,037. | -57916 | -29537 | [5 empty] | 274188 |  | 126042
2024-02-16 | February 2024 Review | Cost Decrease | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | NZTA (Waikato) | Hamilton Urban Improvements - Bus priority hotspots | Single-Stage Business Case | Single Stage Business Case | HHM | HHM | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Surplus transfer funds of $499,844.00 from DBC 60052751 to newly created IBC item 60073997 | -544832 | -544832 | [5 empty] | 258356 | 60052751 | 126923
2024-02-20 | February 2024 Review | Cost Increase | External funding | Passenger facilities and infrastructure improvements - bus | Timaru District Council | CERF - TC - Pre Implementation Timaru | Implementation | MyWay into Stafford Street - Implementation | HHH | HHH | N | 4 | Approved | Approved by Minister for Crown Appropriation | Correct error in original approval. This is now consistent with Schedule 2. | 155200 | 155200 | [5 empty] | 284217 |  | 126381
2024-02-05 | February 2024 Review | Cost Increase | Public transport services | Passenger services - bus | Taranaki Regional Council | Public Transport Programme 2021-24 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | That the National Manager, Programme and Standards, Transport Services: â€¢ Endorse the price level adjustment & recommend that the Senior Manager I&F - Operational Policy & Performance approve funding o to Taranaki Regional Council (TRC) o for Public Transport Programme 2021-24 (PT continuous programme) o a total amount of $1,839,153 made up of: ï‚§ WC 511: $1,855,683 at a FAR of 51% ï‚§ WC 517: $185,237 at a FAR of 60% ï‚§ A decrease of ($201,767) from work categories 519, 521 and 525 at various FARs. o A total NLTF amount of $912,152 made up of: ï‚§ WC 511: $946,398 ï‚§ WC 517: $111,142 ï‚§ A decrease of ($145,388) o From AC 4 - Public Transport Services Activity Class. The overall approved total cost of the PT continuous programme that aligns to the Public Transport Services Activity Class increases from $12,329,884 to $14,169,037. | 1855683 | 946398 | [5 empty] | 274181 |  | 126042
2024-02-05 | February 2024 Review | Cost Decrease | Public transport services | Payments for Total Mobility wheelchair hoists and ramps | Taranaki Regional Council | Public Transport Programme 2021-24 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | That the National Manager, Programme and Standards, Transport Services: â€¢ Endorse the price level adjustment & recommend that the Senior Manager I&F - Operational Policy & Performance approve funding o to Taranaki Regional Council (TRC) o for Public Transport Programme 2021-24 (PT continuous programme) o a total amount of $1,839,153 made up of: ï‚§ WC 511: $1,855,683 at a FAR of 51% ï‚§ WC 517: $185,237 at a FAR of 60% ï‚§ A decrease of ($201,767) from work categories 519, 521 and 525 at various FARs. o A total NLTF amount of $912,152 made up of: ï‚§ WC 511: $946,398 ï‚§ WC 517: $111,142 ï‚§ A decrease of ($145,388) o From AC 4 - Public Transport Services Activity Class. The overall approved total cost of the PT continuous programme that aligns to the Public Transport Services Activity Class increases from $12,329,884 to $14,169,037. | -73851 | -73851 | [5 empty] | 274186 |  | 126042
2024-02-02 | February 2024 Review | Cost Decrease | External funding | Programme Business Case Development | Waikato Regional Council | CERF-VKT Reduction Waikato | Programme business case |  | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | The new government paused the funding in the late 2023. No further funding beyond the $200k establishing funding will be available. | -1360000 | -1360000 | [5 empty] | 284492 |  | 126945
2024-02-02 | February 2024 Review | Cost Decrease | External funding | Property purchase (State highways) | NZTA (Tasman) | CIP SH60 Motueka Project | Property | CIP SH60 Motueka Project | MHM | MHM | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -40716 | -40716 |  |  | 3.3 | 3.3 | Property Purchase | 271800 | 60059421 | 126943
2024-02-12 | February 2024 Review | Cost Increase | External funding | Resilience improvements | NZTA (Otago) | RIO SH01S Kakanui Rvr Flood Mitigation | Pre-implementation* | DO NOT USE | H_L | HHL | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Not a new project but moving funds from activity ID 132976, phase Id 269725. Moving because it is now a mixture of funding from RIO and Crown Resilience (TRF) which old template can not accommodate - (Removing fund as in incorrect funding source. Should have been RIO - Crown - 12/2/24) | 16895 | 16895 |  |  | 1 | 1 |  | 290580 |  | 126554
2024-02-12 | February 2024 Review | Cost Increase | External funding | Resilience improvements | NZTA (Otago) | RIO SH01S Kakanui Rvr Flood Mitigation | Pre-implementation* |  | H_L | M_L | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funding removed in expectation of transferring the $200,000 to a new TIO activity with Improvement template (activity ID 171941 & phase ID 290580). This mapping issue is still to be actioned by the TIO team. We are returning this $200,000 as the new TIO activity cannot be set up yet until the mapping issue is resolved (as timeline for fix is not yet confirmed). The total budget approved of $200,000 is a temporary lump sum in 2023/24 but spanning historical years. The historical costs will be allocated to the correct years once the new mapping issue is fixed. | 200000 | 200000 |  |  |  |  | Design | 269725 | 60056073 | 127021
2024-02-28 | February 2024 Review | Cost Decrease | External funding | Resilience improvements | NZTA (West Coast) | Crown Resilience Programme LCLR WTCT | Implementation |  | VH_H | VHHH | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | To move $4,380,000 allocation from WBS 60071767 (Surplus) to WBS 60074623 (New approval) as the SH6 Meybille Bay Slip project is more than the $2m limit and should now be removed from the Crown Resilience LCLR programme and be set up as a standalone project. This is a cost neutral cashflow from LCLR to Meybille. | -4664699 | -4664699 |  |  |  | 4 |  | 290390 | 60071767 | 127242
2024-02-28 | February 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Auckland) | ANO SH1 NB Silverdale Bus Priority | Pre-implementation* |  | MHM | MHM | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | INTERPHASE TRANSFER: Transfer $1,090,493 from 60056368 to 6007975 | 1188636 | 1188636 |  |  | 3.6 | 3.6 |  | 282149 | 60067975 | 127240
2024-02-28 | February 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Auckland) | ANO SH16 Te Atatu Interchange EB On Ramp | Implementation |  | MHM | MHM | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | INTERPHASE TRANSFER Moving 1.9m of Surplus from 60056368 to 60070105 to complete construction Approved by Sponsor | 2071000 | 2071000 |  |  | 5.3 | 5.3 |  | 283887 | 60070105 | 127241
2024-02-28 | February 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Auckland) | Auckland Network Optimisation (ANO) Programme | Implementation | Auckland System Optimisation SH - Stage 1 | MHM | MHM | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | INTERPHASE TRANSFER: Transfer $2,990,493 from 60056368 to 60070105 & $1,090,493 from 60056368 to 60067975 - $1,900,000 | -3259637 | -3259637 |  |  |  | 3.2 | InfoHub ID 28116348 ¦ SAP 60056368 | 254840 | 60056368 | 127243
2024-02-16 | February 2024 Review | Cost Decrease | External funding | Road improvements | NZTA (BOP) | NZUP Takitimu North Link Stage 1 | Implementation |  | H_L | HHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Surplus $263,137 from 60067403 and transfer to 60063230 | -273662 | -273662 |  |  | 2 | 2 |  | 281500 | 60067403 | 126950
2024-02-16 | February 2024 Review | Cost Increase | External funding | Road improvements | NZTA (BOP) | NZUP Takitimu North Link Stage 1 | Implementation |  | H_L | HHM | N | 0 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Surplus $263,137 from 60067403 and transfer to 60063230 | 273662 | 273662 |  |  | 2 | 2 |  | 278963 | 60063230 | 126951
2024-02-16 | February 2024 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Manawatu/Whanganui) | Otaki to North of Levin - SH1/SH57 - northern section | Implementation | Foxton to Whirokino - Stg 1 | HHL | HHH | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please transfer $2,801 from 60062282 Pre-Implementation to 60062281 Implementation, Pre-Imp phase can then be closed | 3052 | 3052 |  |  | 0 | 1.6 |  | 278532 | 60062281 | 126958
2024-02-16 | February 2024 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (Manawatu/Whanganui) | Otaki to North of Levin - SH1/SH57 - northern section | Pre-implementation* | R2Z | HHL | HHH | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Interphase Transfer: Please transfer $2,801 from 60062282 Pre-Implementation to 60062281 Implementation, Pre-Imp phase can then be closed | -3052 | -3052 |  |  | 0 | 1.6 |  | 278533 | 60062282 | 126959
2024-02-27 | February 2024 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Manawatu/Whanganui) | SH1 Bulls to Sanson CI - Pukenui Rd IS | Implementation |  | VHMVL | HHL | N | 8 | Approved | Approved by Chief Financial Officer (CFO) |  | 392401 | 392401 |  |  | 0 | 1.6 |  | 269996 | 60056875 | 127004
2024-02-27 | February 2024 Review | Cost Increase | Road to Zero | Road improvements | NZTA (Otago) | SH6 Wanaka to Luggate Safer Corridor - SH84 IS | Implementation | SH6 Wanaka to Luggate SC - SH84 IS | VHHL | VHML | N | 2 | Approved | Approved by Chief Financial Officer (CFO) |  | 718311 | 718311 |  |  | 0 | 1.6 |  | 278559 | 60056855 | 127019
2024-02-02 | February 2024 Review | Cost Decrease | Road to Zero | Road improvements | NZTA (Wellington) | SH2 Masterton to Carterton - Norfolk Rd Roundabout | Implementation |  | VHHL | HHM | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -286015 | -286015 |  |  | 0 | 1.6 |  | 278534 | 60062285 | 126890
2024-02-02 | February 2024 Review | Cost Increase | Local road maintenance | Routine drainage maintenance | Buller District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Buller DC has declared a surplus from WC 216. | 53527 | 38539 | [5 empty] | 272248 |  | 126939
2024-02-29 | February 2024 Review | Cost Increase | Local road maintenance | Routine drainage maintenance | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | National office have prioritised the requests for bridge maintenance and renewals as they are highest risk and also the surplus is coming from WC216. The request for funding has been recommended | 200000 | 118000 | [5 empty] | 272298 |  | 126944
2024-02-02 | February 2024 Review | Cost Decrease | Local road maintenance | Sealed pavement maintenance | Buller District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Buller DC has declared a surplus from WC 216. | -262500 | -189000 | [5 empty] | 272246 |  | 126939
2024-02-02 | February 2024 Review | Cost Increase | Local road maintenance | Sealed road pavement rehabilitation | Buller District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Buller DC has declared a surplus from WC 216. | 13970 | 10058 | [5 empty] | 272261 |  | 126939
2024-02-02 | February 2024 Review | Cost Decrease | Local road maintenance | Sealed road resurfacing | Buller District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Buller DC has declared a surplus from WC 216. | -109828 | -79076 | [5 empty] | 272259 |  | 126939
2024-02-02 | February 2024 Review | Cost Increase | Local road maintenance | Structures component replacements | Buller District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Buller DC has declared a surplus from WC 216. | 23086 | 16622 | [5 empty] | 272262 |  | 126939
2024-02-29 | February 2024 Review | Cost Increase | Local road maintenance | Structures component replacements | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | National office have prioritised the requests for bridge maintenance and renewals as they are highest risk and also the surplus is coming from WC216. The request for funding has been recommended | 1500000 | 885000 | [5 empty] | 272312 |  | 126944
2024-02-02 | February 2024 Review | Cost Decrease | Local road maintenance | Structures maintenance | Buller District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Buller DC has declared a surplus from WC 216. | -68255 | -49144 | [5 empty] | 272249 |  | 126939
2024-02-05 | February 2024 Review | Cost Decrease | Public transport services | Total Mobility wheelchair hoists and ramps | Taranaki Regional Council | Public Transport Programme 2021-24 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | That the National Manager, Programme and Standards, Transport Services: â€¢ Endorse the price level adjustment & recommend that the Senior Manager I&F - Operational Policy & Performance approve funding o to Taranaki Regional Council (TRC) o for Public Transport Programme 2021-24 (PT continuous programme) o a total amount of $1,839,153 made up of: ï‚§ WC 511: $1,855,683 at a FAR of 51% ï‚§ WC 517: $185,237 at a FAR of 60% ï‚§ A decrease of ($201,767) from work categories 519, 521 and 525 at various FARs. o A total NLTF amount of $912,152 made up of: ï‚§ WC 511: $946,398 ï‚§ WC 517: $111,142 ï‚§ A decrease of ($145,388) o From AC 4 - Public Transport Services Activity Class. The overall approved total cost of the PT continuous programme that aligns to the Public Transport Services Activity Class increases from $12,329,884 to $14,169,037. | -70000 | -42000 | [5 empty] | 274185 |  | 126042
2024-02-05 | February 2024 Review | Cost Increase | Public transport services | Total mobility operations | Taranaki Regional Council | Public Transport Programme 2021-24 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | That the National Manager, Programme and Standards, Transport Services: â€¢ Endorse the price level adjustment & recommend that the Senior Manager I&F - Operational Policy & Performance approve funding o to Taranaki Regional Council (TRC) o for Public Transport Programme 2021-24 (PT continuous programme) o a total amount of $1,839,153 made up of: ï‚§ WC 511: $1,855,683 at a FAR of 51% ï‚§ WC 517: $185,237 at a FAR of 60% ï‚§ A decrease of ($201,767) from work categories 519, 521 and 525 at various FARs. o A total NLTF amount of $912,152 made up of: ï‚§ WC 511: $946,398 ï‚§ WC 517: $111,142 ï‚§ A decrease of ($145,388) o From AC 4 - Public Transport Services Activity Class. The overall approved total cost of the PT continuous programme that aligns to the Public Transport Services Activity Class increases from $12,329,884 to $14,169,037. | 185237 | 111142 | [5 empty] | 274184 |  | 126042
2024-02-02 | February 2024 Review | Cost Increase | Local road maintenance | Unsealed pavement maintenance | Buller District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Buller DC has declared a surplus from WC 216. | 75383 | 54276 | [5 empty] | 272247 |  | 126939
2024-02-29 | February 2024 Review | Cost Decrease | Local road maintenance | Unsealed pavement maintenance | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2021-24 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Snr Mgr Operational Policy, Planning and Performance (Corporate Support) | National office have prioritised the requests for bridge maintenance and renewals as they are highest risk and also the surplus is coming from WC216. The request for funding has been recommended | -100000 | -59000 | [5 empty] | 272297 |  | 126944
2024-02-16 | February 2024 Review | Cost Increase | Walking and cycling improvements | Walking facilities | NZ Transport Agency | Innovating Streets Programme 2021-24 | Implementation | Green Bond Project- Imp Funding allocated to AOs | HHL | VHHVH | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | $95,952 (281381) and the reason is â€œproject $ surplused in error by TCC in Oct 23. The surplus should have gone to NZTA Contingency (279202) Implement â€“ green bond project - Imp funding alloc to AOsâ€ - cost neutral transfer | 95952 | 95952 |  |  | 1 | 1 | Green Bond Project-Implementation - Funding allocated to AOs | 279202 |  | 127101
2024-02-15 | February 2024 Review | Cost Decrease | Walking and cycling improvements | Walking facilities | NZ Transport Agency | Innovating Streets Programme 2021-24 | Implementation | Green Bond Project- Imp Funding allocated to AOs | HHL | VHHVH | N | 5 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Moving $220k to WCC for 4 permanent raised pedestrian crossings. As agreed with SfP Programme Lead, Geoff and his team. Cost neutral transfer from 279202 to 282824. | -220000 | -220000 |  |  | 1 | 1 | Green Bond Project-Implementation - Funding allocated to AOs | 279202 |  | 127079