## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Phase Label | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Decision Status | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR | Your Phase reference | TIO Phase id | SAP item id | TIO Request id
2024-08-28 | August 2024 Review | New approval | Local road operations | Emergency works | South Wairarapa District Council | Emergency Works Cyclone Hale Storm Event 2023 | Construction | Network reinstatement @ High FAR | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation in line with NZTA EW policy | 520194 | 369338 | [5 empty] | 293058 |  | 131445
2024-08-29 | August 2024 Review | New approval | External funding | Emergency works | Tararua District Council | EW Cyclone Gabrielle | Construction | Cyclone Gabrielle - Recovery Phase - Normal FAR | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation to align with NZTA EW policy | 484112 | 353402 | [5 empty] | 292699 |  | 129099
2024-08-28 | August 2024 Review | New approval | External funding | Emergency works | Thames-Coromandel District Council | EW - Thames-Coromandel DC January 2023 (NIWE) | Construction | Permanent Reinstatement MSQA & Cons (NIWE) @71% | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Splitting phase 160986 into normal FAR @ $1,064,646 and moving $1,481,437 to High FAR | 1481437 | 1051820 |  |  |  |  | Permanent Reinstatement MSQA & Cons (NIWE) extra Higher FAR | 293056 |  | 131418
2024-08-22 | August 2024 Review | New approval | Local road operations | Emergency works | Waikato District Council | EW - Waikato DC Storm Damage Jan-Feb 2023 | Construction | 23/24 Phase 2 - I&D (NIWE) @ High FAR | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Amend allocation to align with NZTA EW policy | 66278 | 47057 | [5 empty] | 293002 |  | 131368
2024-08-22 | August 2024 Review | New approval | Local road operations | Emergency works | Waikato District Council | EW - Waikato District Severe Wind event | Construction | Response to event | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | Recommendation: - Approves emergency works funding to Waikato District Council - For EW - Waikato District Severe Wind event May 2024 - At a total cost of $299,420 (including 0% Admin) - at a funding assistance rate of 71% ($212,588 NLTF share) - for response and recovery phase - from activity class 8, work category 141 Reason for Recommendation: This funding approval enables the appropriate level of service to be restored to the Waikato District transport network. The requirements of section 20 (4) of the Land Transport Management Act 2003 have been met. | 299420 | 212588 | [5 empty] | 292688 |  | 131138
2024-08-27 | August 2024 Review | New approval | Public transport services |  | Auckland Transport | Community Connect - Auckland Trial | Implementation |  | ___ | MHL | N |  | Approved | Approved by Minister for Crown Appropriation | This funding recognises the shortfall in local share funding to pay for Total Mobility services during the 223/24FY | 1026604 | 1026604 |  |  |  |  | 517.293 | 293038 |  | 131395
2024-08-27 | August 2024 Review | New approval | Public transport services |  | Invercargill City Council | CERF-CC Community Connect Scheme | Implementation |  | ___ | MHL | N |  | Approved | Approved by Minister for Crown Appropriation | This funding recognises the shortfall in local share funding to pay for Total Mobility services during the 223/24FY | 20114 | 20114 | [5 empty] | 293040 |  | 131397
2024-08-27 | August 2024 Review | New approval | Public transport services |  | Marlborough District Council | CERF-CC Community Connect Scheme | Implementation |  | ___ | MHL | N |  | Approved | Approved by Minister for Crown Appropriation | This funding recognises the shortfall in local share funding to pay for Total Mobility services during the 223/24FY | 28287 | 28287 | [5 empty] | 293042 |  | 131399
2024-08-22 | August 2024 Review | New approval | Safety |  | NZ Transport Agency | Drug Driving Testing Support Implementation (DDTSI) | Implementation |  | ___ | LLVL | N |  | Approved | Approved by Chief Financial Officer | This project will support the introduction of random roadside drug testing legislative compliance and will support NZ Police in their deployment of the Oral Fluid Testing (OFT) Delivering the Drug Driving educational campaign to ensure strong driver awareness of the changes relating to Drug Driving and the introduction of the OFT testing; â€¢ Support NZP by accepting their new Drug Driving sanctions of Infringement penalties for drug driving offences in the form of Driver licence Demerit warning and suspension letters; â€¢ Support Ministry of Justice (MoJ) by accepting their new Drug Driving sanctions of criminal penalties for drug driving offences; â€¢ Assist in the reporting for Road to Zero about the effectiveness of the enhancement to Drug Driving testing. | 1900000 | 1900000 |  |  | 0 | 6.8 | 60083383 | 292995 |  | 131361
2024-08-08 | August 2024 Review | New approval | Safety |  | NZ Transport Agency | SIP - Programme Management | Pre-implementation* |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Transfer from R2Z to SH1 | 3815103 | 3815103 |  |  | 2.2 | 2.2 | 60079525 - Louise Capes | 292841 |  | 131201
2024-08-01 | August 2024 Review | New approval | State highway improvements |  | NZTA (Hawkes Bay) | Napier Port Access | Detailed Business Case |  | ___ | HMM | N |  | Approved | Approved by Chief Financial Officer | The work will enable completing investment case for the Stage 1 - RoNs Hawkes Bay Expressway Improvement. | 2799834 | 2799834 |  |  | 3.9 | 3.9 |  | 292703 | 60082021 | 131067
2024-08-26 | August 2024 Review | New approval | State highway improvements |  | NZTA (Southland) | TRF-STLD-SH1 Ocean Beach, Bluff | Single-Stage Business Case |  | ___ | LLVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | 1) To transfer $459,000 from Imp (60074848) to Pre-imp (60074847), and 2) to transfer $551,000 from Imp (60074848) to create a new SSBC phase (60083027). This is to match estimated work for SSBC and Pre-imp phases. | 586815 | 586815 |  |  |  | 0 |  | 292953 | 60083027 | 131351
2024-08-08 | August 2024 Review | New approval | State highway improvements |  | NZTA (Waikato) | SH23 and SH39 IS | Pre-implementation* |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow $25,349 from 60061054 to 60082413. | 25349 | 25349 |  |  | 2.1 | 2.1 |  | 292758 | 60082413 | 131204
2024-08-08 | August 2024 Review | New approval | State highway improvements |  | NZTA (Waikato) | SH3 Awakino to Mt Messenger Corridor Improvements (Waikato) | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow $581,222 from 60062213 to 60082552. | 581222 | 581222 |  |  | 1.5 | 1.5 |  | 292772 | 60082552 | 131205
2024-08-08 | August 2024 Review | New approval | State highway improvements |  | NZTA (Waikato) | SH3 Awakino to Mt Messenger Corridor Improvements (Waikato) | Property |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow $95,933 from 60062214 to 60082553. | 95933 | 95933 |  |  | 1.5 | 1.5 |  | 292773 | 60082553 | 131206
2024-08-09 | August 2024 Review | New approval | Walking and cycling improvements |  | NZTA (Waikato) | SH3 Awakino to Mt Messenger Corridor Improvements (Waikato) | Property |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | RTZ closed and moved to SHI. | 95933 | 95933 |  |  | 1.5 | 1.5 |  | 292774 | 60082703 | 131229
2024-08-07 | August 2024 Review | New approval | Safety |  | Selwyn District Council | Prebbleton Arterial CSM Related Upgrade Packages | Implementation |  | ___ | HML | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Funds moved form the corresponding R2Z phase what was surplused during 2023/24 EOY processing. | 2715655 | 1384984 |  |  | 1 | 1 |  | 292723 |  | 131184
2024-08-07 | August 2024 Review | New approval | Safety |  | Selwyn District Council | Prebbleton Arterial CSM Related Upgrade Packages | Implementation |  | ___ | HML | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Funds moved form the corresponding R2Z phase what was surplused during 2023/24 EOY processing. | 2162018 | 1102629 |  |  | 1 | 1 | Shands/Hamptons in conjunction with property phase | 292722 |  | 131183
2024-08-07 | August 2024 Review | New approval | Safety |  | Selwyn District Council | Prebbleton Arterial CSM Related Upgrade Packages | Property |  | ___ | HML | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Funds moved form the corresponding R2Z phase what was surplused during 2023/24 EOY processing. | 1047183 | 534063 |  |  | 1 | 1 |  | 292725 |  | 131186
2024-08-07 | August 2024 Review | New approval | Safety |  | Selwyn District Council | Prebbleton Arterial CSM Related Upgrade Packages | Property |  | ___ | HML | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Funds moved form the corresponding R2Z phase what was surplused during 2023/24 EOY processing. | 1212020 | 618130 |  |  | 1 | 1 | Shands/Hamptons in conjunction with Implementation phase | 292724 |  | 131185
2024-08-27 | August 2024 Review | New approval | Public transport services |  | Taranaki Regional Council | CERF-CC Community Connect Scheme | Implementation |  | ___ | MHL | N |  | Approved | Approved by Minister for Crown Appropriation | This funding recognises the shortfall in local share funding to pay for Total Mobility services during the 223/24FY | 46819 | 46819 | [5 empty] | 293039 |  | 131396
2024-08-27 | August 2024 Review | New approval | Public transport services |  | Tasman District Council | CERF-CC Community Connect Scheme | Implementation |  | ___ | MHL | N |  | Approved | Approved by Minister for Crown Appropriation | This funding recognises the shortfall in local share funding to pay for Total Mobility services during the 223/24FY | 4157 | 4157 | [5 empty] | 293041 |  | 131398
2024-08-07 | August 2024 Review | New approval | Safety |  | Wellington City Council | Speed management programme | Single-Stage Business Case |  | ___ | VHHVH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Funds moved from the corresponding R2Z phase that was surplused during 2023/24 EOY processing. | 773404 | 394436 | [5 empty] | 292726 |  | 131188
2024-08-27 | August 2024 Review | New approval | Public transport services |  | West Coast Regional Council | CERF-CC Community Connect Scheme | Implementation |  | ___ | MHL | N |  | Approved | Approved by Minister for Crown Appropriation | This funding recognises the shortfall in local share funding to pay for Total Mobility services during the 223/24FY | 17782 | 17782 | [5 empty] | 293043 |  | 131400
2024-08-26 | August 2024 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | NZTA (Manawatu/Whanganui) | Manawatu River Bridge SH3 Ashhurst Cycle/walkway | Pre-implementation* |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Net change is 0 | 0 | 0 |  |  | 1.7 | 1.7 |  | 221912 | 60215140 | 131192
2024-08-26 | August 2024 Review | Cash flow adjustment | State highway operations | Emergency works | NZTA (Manawatu/Whanganui) | EW Otanga Road Slip 20220226 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Project Close | 1 | 1 | [5 empty] | 282908 | 60068503 | 131285
2024-08-06 | August 2024 Review | Cash flow adjustment |  | Emergency works | NZTA (Northland) | EW Mangamuka/Kaeo HR 20220818 | Construction | Construction Recovery (closed) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Opened in error | 0 | 0 | [5 empty] | 283740 | 60069662 | 131174
2024-08-06 | August 2024 Review | Cash flow adjustment | State highway maintenance | Emergency works | NZTA (Waikato) | EW Waikato East/West July HR 20220712 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Project Complete and to be closed | 0 | 0 | [5 empty] | 282153 | 60067914 | 131173
2024-08-19 | August 2024 Review | Cash flow adjustment | State highway maintenance | Emergency works | NZTA (Wellington) | EW Wgtn EQ & Storm 20161114 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Project Closing | 0 | 0 |  |  |  |  | 60042375 | 250432 | 60042375 | 131277
2024-08-26 | August 2024 Review | Cash flow adjustment | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Marlborough) | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 | [5 empty] | 276269 | 60061865 | 131373
2024-08-26 | August 2024 Review | Cash flow adjustment | State highway improvements | Low cost / low risk improvements | NZTA (Nelson) | Low cost / low risk improvements 2021-24 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 | [5 empty] | 276272 | 60061776 | 131265
2024-08-26 | August 2024 Review | Cash flow adjustment | State highway improvements | Low cost / low risk improvements | NZTA (Otago) | Low cost / low risk improvements 2021-24 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 | [5 empty] | 276282 | 60061867 | 131262
2024-08-26 | August 2024 Review | Cash flow adjustment | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Otago) | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 | [5 empty] | 276279 | 60061868 | 131263
2024-08-26 | August 2024 Review | Cash flow adjustment | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Southland) | Low cost / low risk improvements 2021-24 | Walking and cycling improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | HJJB MRR - 26/8/24 | 0 | 0 | [5 empty] | 276286 | 60061871 | 131264
2024-08-26 | August 2024 Review | Cash flow adjustment | State highway improvements | Low cost / low risk improvements | NZTA (Taranaki) | Low cost / low risk improvements 2021-24 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 | [5 empty] | 276290 | 60061861 | 131261
2024-08-26 | August 2024 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (BOP) | Hairini Link - Stage 4 | Construction |  | ___ | H_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow | 90k from future years to CY | 0 | 0 |  |  | 2.1 | 2.5 | 60217219 | 194905 | 60217219 | 131301
2024-08-26 | August 2024 Review | Cash flow adjustment | Walking and cycling improvements | Property purchase (State highways) | NZTA (Canterbury) | Mingha Bluff to Rough Creek | Property |  | ___ | M_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow | project closure | 0 | 0 |  |  | 1.1 | 1.1 | 60460952 | 205265 | 60460952 | 131382
2024-08-26 | August 2024 Review | Cash flow adjustment | Walking and cycling improvements | Property purchase (State highways) | NZTA (Southland) | CIP SH94 Homer Tunnel | Property |  | ___ | MHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | project closed | 0 | 0 |  |  | 0 | 0 |  | 288447 | 60070446 | 131379
2024-08-14 | August 2024 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Auckland) | RoRS Waihoehoe Road (Drury) Upgrade | Implementation |  | ___ | MML | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflowing $5,194,770 from Year2 2025/26 to next FY 2024/25 | 0 | 0 |  |  |  | 1.8 | MCIP 60073510 | 290571 | 60073510 | 131275
2024-08-14 | August 2024 Review | Cash flow adjustment | State highway pothole prevention | Sealed pavement maintenance | NZTA (Auckland) | SH1 Puhoi to Warkworth RoNS Detailed Design and Construction | Construction |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow phasing update as at 14/08/2024 | 0 | 0 |  |  | 1.1 | 1.1 | Construction | 263236 | 60075902 | 131271
2024-08-28 | August 2024 Review | Cash flow adjustment | Safety |  | NZ Transport Agency | Vehicle Impoundment Programme 24-27 | Implementation |  | ___ | HHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | to enable automatic approval of allocations in SAP | 0 | 0 |  |  | 0 | 0 | 60083513 | 290594 |  | 131413
2024-08-14 | August 2024 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | NZTA (Auckland) | Northern Pathway (Westhaven to Akoranga) | Detailed Business Case |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Surplus - project closed. | -3479 | -3479 |  |  | 1.3 | 1.3 | MCIP 60066010 Ex-NZUP | 280036 | 60066010 | 131178
2024-08-01 | August 2024 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | NZTA (Auckland) | Northern Pathway (Westhaven to Akoranga) | Pre-implementation* |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow funds from 60059443 to cover 2023/24 spend of $994 (incl. admin). | 994 | 994 |  |  | 1.3 | 1.3 | MCIP 60056054 Ex-NZUP | 269719 | 60056054 | 131123
2024-08-13 | August 2024 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | Whangarei District Council | CERF-TC - WDC Transport Choices Package | Implementation |  | ___ | HHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase transfer - The Kamo shared path Imp budget reduced by $560,000 from $$4,340,000 to $3,780,000 . The Raumanaga shared path Imp budget increased by $560,000 from $3,358,000 to $3,918,000 | 560000 | 560000 |  |  |  | 0 | WHGR03: Raumanga Shared Path Extension and CBD Cycle Parking | 284202 |  | 131238
2024-08-22 | August 2024 Review | Cost Decrease | External funding | Emergency works | Auckland Transport | EW - AT Anniversary Weekend & Cyclone Gabrielle 2023 | Construction | E/W - Reinstatement @ 51% (NIWE) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Fixing AT to align with NZTA EW policy | -10597688 | -5404821 |  |  |  |  | 141.2838 | 291176 |  | 131366
2024-08-09 | August 2024 Review | Cost Increase | External funding | Emergency works | Auckland Transport | EW - AT Anniversary Weekend & Cyclone Gabrielle 2023 | Construction | E/W - Reinstatement @ 51% (NIWE) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Correcting earlier calculation to fix FAR calculations | 3966225 | 2022775 |  |  |  |  | 141.2838 | 291176 |  | 131227
2024-08-07 | August 2024 Review | Cost Increase | External funding | Emergency works | Auckland Transport | EW - AT Anniversary Weekend & Cyclone Gabrielle 2023 | Construction | E/W - Reinstatement @ 51% (NIWE) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Transfer from phase ID 291177 @ 51% rather than 71% | 62378648 | 31813110 |  |  |  |  | 141.2838 | 291176 |  | 131193
2024-08-09 | August 2024 Review | Cost Decrease | External funding | Emergency works | Auckland Transport | EW - AT Anniversary Weekend & Cyclone Gabrielle 2023 | Construction | E/W - Reinstatement @ 71% (NIWE) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Total funding of $62,378,648 from phase ID 291177 split and moved to phase ID 291176 for $39,924,687 @ FAR 51% and balance of $22,453,961 retained at 71% in phase ID 291177 | -39924687 | -28346528 |  |  |  |  | 141.2901 | 291177 |  | 131194
2024-08-22 | August 2024 Review | Cost Increase | External funding | Emergency works | Auckland Transport | EW - AT Anniversary Weekend & Cyclone Gabrielle 2023 | Construction | E/W - Reinstatement @ 71% (NIWE) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Fixing AT to align with NZTA EW policy | 10597688 | 7524358 |  |  |  |  | 141.2901 | 291177 |  | 131279
2024-08-09 | August 2024 Review | Cost Decrease | External funding | Emergency works | Auckland Transport | EW - AT Anniversary Weekend & Cyclone Gabrielle 2023 | Construction | E/W - Reinstatement @ 71% (NIWE) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Correcting earlier calculation to fix FAR calculations | -3966225 | -2816019 |  |  |  |  | 141.2901 | 291177 |  | 131228
2024-08-09 | August 2024 Review | Cost Decrease | External funding | Emergency works | Auckland Transport | EW - AT Anniversary Weekend & Cyclone Gabrielle 2023 | Construction | E/W - Reinstatement @ 51% (NIWE) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Total funding of $62,378,648 from phase ID 291177 split and moved to phase ID 291176 for $39,924,687 @ FAR 51% and balance of $22,453,961 retained at 71% in phase ID 291177 | -22453961 | -11451520 |  |  |  |  | 141.2838 | 291176 |  | 131226
2024-08-22 | August 2024 Review | Cost Decrease | Local road operations | Emergency works | Auckland Transport | EW - AT Storm Event 9 May 2023 | Construction | E/W - Storm Event 9 May | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Fixing AT to align with NZTA EW policy | 0 | -799245 |  |  |  |  | 141.2846 | 284581 |  | 131365
2024-08-09 | August 2024 Review | Cost Increase | Local road operations | Emergency works | Auckland Transport | EW - AT Storm Event 9 May 2023 | Construction | E/W - Storm Event 9 May | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Storm Event May to have higher FAR | 0 | 799245 |  |  |  |  | 141.2846 | 284581 |  | 131236
2024-08-20 | August 2024 Review | Cost Increase | External funding | Emergency works | NZTA (Auckland) | EW Auckland Extreme HR 20230127 | Construction | Anniversary Weekend (SH Recovery) | ___ |  | N |  | Approved with conditions | Approved with conditions by National Manager, Programmes and Standards (Transport Services) | Lonely Track SE Pond site was not identified when the original funding application for Auckland Extreme Heavy Rainfall Emergency Works event was submitted. Condition in place to enable more timely application for future. | 1911859 | 1911859 | Recovery Manager is required to consider the advice from Manager Tactical Asset Investment around improvement in the process and discuss with ASM if required. Please email VOS support upon completion by 16 September 2024. |  |  |  |  | 292469 | 60069693 | 131165
2024-08-13 | August 2024 Review | Cost Increase | State highway operations | Emergency works | NZTA (BOP) | EW BOPE RW late Sept HR 20230922 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | When TREC was set up it was agreed that all recovery work with the TREC zones not under construction would be passed to TREC for completion. As this was considered to be the most efficient delivery model. Unfortunately, it hasnâ€™t turn out that way. I support Sandraâ€™s comments and recommend approval. Nick Cook (NMR) | 1177710 | 1177710 | [5 empty] | 289960 | 60073395 | 131139
2024-08-28 | August 2024 Review | Cost Increase | State highway operations | Emergency works | NZTA (Canterbury) | EW Nth Canty HR July 20230709 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | PLA $310,488 to close project | 338432 | 338432 | [5 empty] | 288458 | 60071504 | 131384
2024-08-05 | August 2024 Review | Cost Decrease | External funding | Emergency works | NZTA (Hawkes Bay) | EW Gabrielle Hawkes Bay 20230214 | Construction | Construction NIWE Recovery | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Close Project | -782042 | -782042 | [5 empty] | 291171 | 60069825 | 131168
2024-08-13 | August 2024 Review | Cost Increase | State highway operations | Emergency works | NZTA (Taranaki) | EW Uruti Valley Slip 20211212 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | professional services and design errors have resulting in the increase of costs associated with this project | 1035501 | 1035501 | [5 empty] | 280655 | 60066585 | 131097
2024-08-13 | August 2024 Review | Cost Increase | State highway operations | Emergency works | NZTA (Tasman) | EW SH60 Takaka Hill HR 20240626 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | Initial Application $4.5M August 24 | 4905000 | 4905000 | [5 empty] | 292680 | 60081797 | 131140
2024-08-05 | August 2024 Review | Cost Decrease | State highway operations | Emergency works | NZTA (Waikato) | EW Waikato East/West July HR 20220712 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Project Close | -60545 | -60545 | [5 empty] | 282153 | 60067914 | 131087
2024-08-12 | August 2024 Review | Cost Increase | External funding | Emergency works | NZTA (Waikato) | EW Waikato Region Extreme HR 20230127 | Construction | Waikato Region Extreme HR Response-NIWE Recovery | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Reinstating $3,893,588 that was zeroed during EOY processing and came up as surplus during cashflow. | 4244011 | 4244011 | [5 empty] | 292682 | 60069712 | 131266
2024-08-13 | August 2024 Review | Cost Increase | State highway operations | Emergency works | NZTA (Wellington) | EW Wgtn EQ & Storm 20161114 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | This project has taken a long time to deliver, which is not in line with the concept of emergency works. 2018-2024. In the interest of closing this project out. I support the application. I also recommend a lesson learned workshop is carried out. Nick Cook NMR PLA $575,090 to close June 24 | 575091 | 575091 |  |  |  |  | 60042375 | 250432 | 60042375 | 131088
2024-08-13 | August 2024 Review | Cost Increase | State highway operations | Emergency works | NZTA (Wellington) | EW Wgtn SH53 Wards Line HR 20220921 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | PLA $390,961 June 24 | 390962 | 390962 | [5 empty] | 283112 | 60068833 | 131069
2024-08-28 | August 2024 Review | Cost Decrease | Local road operations | Emergency works | South Wairarapa District Council | Emergency Works Cyclone Hale Storm Event 2023 | Construction | Network reinstatement | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation in line with NZTA EW policy | -520194 | -265299 | [5 empty] | 283605 |  | 131441
2024-08-28 | August 2024 Review | Cost Increase | External funding | Emergency works | Tararua District Council | EW Cyclone Gabrielle | Construction | Cyclone Gabrielle - Recovery Phase (NIWE) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation to align with NZTA EW policy | 484140 | 353422 |  |  |  |  | Draft Recovery | 284325 |  | 131438
2024-08-28 | August 2024 Review | Cost Decrease | External funding | Emergency works | Tararua District Council | EW Cyclone Gabrielle | Construction | Cyclone Gabrielle- Recovery Phase (NIWE) FAR +20% | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation to align with NZTA EW policy | -484140 | -450250 | [5 empty] | 292679 |  | 131439
2024-08-28 | August 2024 Review | Cost Decrease | External funding | Emergency works | Thames-Coromandel District Council | EW - Thames-Coromandel DC January 2023 (NIWE) | Construction | Permanent Reinstatement MSQA & Construction (NIWE) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Splitting this phase into normal FAR @ $1,064,646 and moving $1,481,437 @ 71 High FAR | -1481437 | -755533 | [5 empty] | 283778 |  | 131417
2024-08-22 | August 2024 Review | Cost Increase | External funding | Emergency works | Waikato District Council | EW - Waikato DC Storm Damage Jan-Feb 2023 | Construction | Phase 3-Construction & MSQA -NIWE (Normal FAR+20%) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Amend allocation to align with NZTA EW policy | 0 | 800098 | [5 empty] | 292305 |  | 131372
2024-08-22 | August 2024 Review | Cost Increase | External funding | Emergency works | Waikato District Council | EW - Waikato DC Storm Damage Jan-Feb 2023 | Construction | Phase 3 - Cons & MSQA of Critical Sites - NIWE | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Amend allocation to align with NZTA EW policy | 0 | 398207 |  |  |  |  | Phase 3 - Construction & MSQA of Critical Sites | 292304 |  | 131371
2024-08-22 | August 2024 Review | Cost Decrease | External funding | Emergency works | Waikato District Council | EW - Waikato DC Storm Damage Jan-Feb 2023 | Construction | Phase 2 - Invest & Design - NIWE | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Amend allocation to align with NZTA EW policy | -66278 | -33802 |  |  |  |  | Investigation and Design | 292303 |  | 131369
2024-08-07 | August 2024 Review | Cost Decrease | Investment management (incl. Transport Planning) | Management of the funding allocation system | NZ Transport Agency | Investment in the Funding Allocation System (IFAS) | Implementation |  | ___ | HHVH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | New allocation will be set up for 2024-27 NLTP | -10385369 | -10385369 |  |  | 1 | 1 |  | 278317 |  | 131191
2024-08-20 | August 2024 Review | Cost Decrease | State highway improvements | New traffic management facilities | NZTA (Auckland) | Weigh Right Bombay | Implementation |  | ___ | HMVH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Inter Programme Transfer: Please Transfer $409,236 from 60047943 Implementation to 60030985 Implementation. | -446066 | -446066 |  |  | 14 | 14 | 60047943 | 234230 | 60047943 | 131308
2024-08-26 | August 2024 Review | Cost Decrease | State highway improvements | New traffic management facilities | NZTA (Auckland) | Weigh Right Stanley Street | Implementation |  | ___ | HMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Inter Prog. Txf: Transfer $1,705,518 fr 60047939 Imp. $784,503 - 60030985 Imp, $188,885 - 60070915 Imp, $260,808 - 60032036 Imp, $20,000 - 60047946 Prop, $61,035 - 60031962 Imp, $30167 - 60047923 Prop, $185,411- 60048361 Imp, $174,709 - 60044273 Imp. | -1859015 | -1859015 |  |  | 14 | 14 | 60047939 | 250253 | 60047939 | 131345
2024-08-26 | August 2024 Review | Cost Increase | State highway improvements | New traffic management facilities | NZTA (BOP) | Weigh Right Paengaroa | Implementation |  | ___ | HMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Inter Prog. Txf: Transfer $1,705,518 fr 60047939 Imp. $784,503 - 60030985 Imp, $188,885 - 60070915 Imp, $260,808 - 60032036 Imp, $20,000 - 60047946 Prop, $61,035 - 60031962 Imp, $30167 - 60047923 Prop, $185,411- 60048361 Imp, $174,709 - 60044273 Imp. | 202098 | 202098 |  |  | 14 | 14 | 60048361 | 262618 | 60048361 | 131347
2024-08-20 | August 2024 Review | Cost Increase | State highway improvements | New traffic management facilities | NZTA (Canterbury) | Weigh Right Rakaia | Implementation |  | ___ | HHVH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Inter Programme Transfer: Please Transfer $1,800,000 from 60070922 Property to 60044273 Implementation. | 1961999 | 1961999 |  |  | 14 | 14 |  | 250273 | 60044273 | 131307
2024-08-26 | August 2024 Review | Cost Increase | State highway improvements | New traffic management facilities | NZTA (Canterbury) | Weigh Right Rakaia | Implementation |  | ___ | HHVH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Inter Prog. Txf: Transfer $1,705,518 fr 60047939 Imp. $784,503 - 60030985 Imp, $188,885 - 60070915 Imp, $260,808 - 60032036 Imp, $20,000 - 60047946 Prop, $61,035 - 60031962 Imp, $30167 - 60047923 Prop, $185,411- 60048361 Imp, $174,709 - 60044273 Imp. | 190433 | 190433 |  |  | 14 | 14 |  | 250273 | 60044273 | 131343
2024-08-26 | August 2024 Review | Cost Increase | State highway improvements | New traffic management facilities | NZTA (Hawkes Bay) | Weigh Right Napier Port | Implementation |  | ___ | MMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Inter Prog. Txf: Transfer $1,705,518 fr 60047939 Imp. $784,503 - 60030985 Imp, $188,885 - 60070915 Imp, $260,808 - 60032036 Imp, $20,000 - 60047946 Prop, $61,035 - 60031962 Imp, $30167 - 60047923 Prop, $185,411- 60048361 Imp, $174,709 - 60044273 Imp. | 284281 | 284281 |  |  | 14 | 14 | 60032036 | 250274 | 60032036 | 131342
2024-08-26 | August 2024 Review | Cost Increase | State highway improvements | New traffic management facilities | NZTA (Manawatu/Whanganui) | Weigh Right Ohakea | Implementation |  | ___ | HHVH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Inter Prog. Txf: Transfer $1,705,518 fr 60047939 Imp. $784,503 - 60030985 Imp, $188,885 - 60070915 Imp, $260,808 - 60032036 Imp, $20,000 - 60047946 Prop, $61,035 - 60031962 Imp, $30167 - 60047923 Prop, $185,411- 60048361 Imp, $174,709 - 60044273 Imp. | 66527 | 66527 |  |  | 14 | 14 | 60031962 | 231335 | 60031962 | 131341
2024-08-05 | August 2024 Review | Cost Decrease | Public transport services | Operations & maintenance of real-time and ticketing systems | Gisborne District Council | CERF-CC Community Connect Scheme | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Project funds no longer required and declared surplus | -400 | -400 | [5 empty] | 289025 |  | 131118
2024-08-05 | August 2024 Review | Cost Decrease | Public transport infrastructure | Passenger facilities and infrastructure improvements - rail | Auckland Transport | AKL Metro Train Capacity - Tranche 3 | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | This has been discussed with NZTA as an offset to enable the Paint Booth phase to be put in. | -6870500 | -3503955 |  |  |  | 2.1 | 563.2647 | 264721 |  | 131079
2024-08-05 | August 2024 Review | Cost Decrease | Public transport services | Passenger services - bus | Environment Canterbury | PT Futures enhanced frequency | Implementation |  | ___ | VHHVH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -2332773 | -1189714 |  |  | 1.7 | 1 | implementation | 278078 |  | 131096
2024-08-05 | August 2024 Review | Cost Decrease | Public transport services | Passenger services - bus | Gisborne District Council | CERF-CC Community Connect Scheme | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Project funds no longer required and declared surplus | -4603 | -4603 | [5 empty] | 288529 |  | 131119
2024-08-01 | August 2024 Review | Cost Increase | Walking and cycling improvements | Property purchase (State highways) | NZTA (Auckland) | Northern Pathway (Westhaven to Akoranga) | Property |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow funds from 60059443 to cover 2023/24 spend of $259,785 (incl. admin). | 259785 | 259785 |  |  | 1.3 | 1.3 | MCIP 60056053 Ex-NZUP | 269721 | 60056053 | 131124
2024-08-20 | August 2024 Review | Cost Decrease | Walking and cycling improvements | Property purchase (State highways) | NZTA (Auckland) | Weigh Right Albany | Property |  | ___ | MMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Inter Programme Transfer: Please Transfer $1,800,000 from 60070922 Property to 60044273 Implementation. | -1908000 | -1908000 |  |  |  | 4.4 |  | 284547 | 60070922 | 131306
2024-08-05 | August 2024 Review | Cost Increase | Walking and cycling improvements | Property purchase (State highways) | NZTA (Canterbury) | RoRS SH73 Weedons-Ross Road Intersection | Property |  | ___ | HML | N |  | Approved | Approved by Manager, Treasury & Cash Flow | To cover overspend of $27,643 | 72331 | 72331 |  |  | 1.2 | 1.2 | MCIP 60057040 | 270360 | 60057040 | 131159
2024-08-26 | August 2024 Review | Cost Increase | Walking and cycling improvements | Property purchase (State highways) | NZTA (Hawkes Bay) | Weigh Right Napier Port | Property |  | ___ | MMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Inter Prog. Txf: Transfer $1,705,518 fr 60047939 Imp. $784,503 - 60030985 Imp, $188,885 - 60070915 Imp, $260,808 - 60032036 Imp, $20,000 - 60047946 Prop, $61,035 - 60031962 Imp, $30167 - 60047923 Prop, $185,411- 60048361 Imp, $174,709 - 60044273 Imp. | 21200 | 21200 |  |  | 14 | 14 | 60047946 | 260279 | 60047946 | 131346
2024-08-26 | August 2024 Review | Cost Increase | Walking and cycling improvements | Property purchase (State highways) | NZTA (Manawatu/Whanganui) | Weigh Right Ohakea | Property |  | ___ | HHVH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Inter Prog. Txf: Transfer $1,705,518 fr 60047939 Imp. $784,503 - 60030985 Imp, $188,885 - 60070915 Imp, $260,808 - 60032036 Imp, $20,000 - 60047946 Prop, $61,035 - 60031962 Imp, $30167 - 60047923 Prop, $185,411- 60048361 Imp, $174,709 - 60044273 Imp. | 31977 | 31977 |  |  | 14 | 14 |  | 260278 | 60047923 | 131344
2024-08-16 | August 2024 Review | Cost Decrease | Walking and cycling improvements | Property purchase (State highways) | NZTA (Southland) | CIP SH94 Homer Tunnel | Property |  | ___ | MHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | To transfer $26,899 from Property (60070446) to Imp (60059181) phase and close the Property phase. 60070446 has an admin rate of 3.5% & 60059181 has an admin rate of 0% | -27840 | -27840 |  |  | 0 | 0 |  | 288447 | 60070446 | 131290
2024-08-26 | August 2024 Review | Cost Decrease | Walking and cycling improvements | Property purchase (State highways) | NZTA (Southland) | Edendale Realignment | Property |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | project closed | -53246 | -53246 |  |  | 1.2 | 1.2 | 60441622 | 246993 | 60441622 | 131380
2024-08-05 | August 2024 Review | Cost Decrease | Public transport infrastructure | Public transport improvements, major renewals and minor improvements | Environment Canterbury | Electronic Ticketing System Enhancement | Implementation |  | ___ | H_H | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -427611 | -218082 |  |  | 5.3 | 5.3 | Implementation | 248032 |  | 131082
2024-08-26 | August 2024 Review | Cost Decrease | Public transport infrastructure | Public transport infrastructure and major renewals | Waikato Regional Council | Regional Consortium Interim Ticketing Solution | Implementation |  | ___ | H_L | N |  | Declined | Declined by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -9336 | -6068 |  |  | 1.2 | 1.2 |  | 260056 |  | 131177
2024-08-26 | August 2024 Review | Cost Decrease | Local road improvements | Replacement of bridges and other structures | Gore District Council | Pyramid Bridge Replacement | Construction |  | ___ | M_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -37723 | -27775 |  |  | 0 | 1.7 |  | 237211 |  | 131359
2024-08-26 | August 2024 Review | Cost Decrease | State highway improvements | Replacement of bridges and other structures | NZTA (Marlborough) | New ÅŒpaoa River Bridge | Implementation |  | ___ | MLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | project closure | -12808 | -12808 |  |  | 0 | 1.4 |  | 270298 | 60032206 | 131317
2024-08-26 | August 2024 Review | Cost Increase | State highway improvements | Replacement of bridges and other structures | NZTA (Northland) | Weigh Right Marsden | Implementation |  | ___ | MMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Inter Prog. Txf: Transfer $1,705,518 fr 60047939 Imp. $784,503 - 60030985 Imp, $188,885 - 60070915 Imp, $260,808 - 60032036 Imp, $20,000 - 60047946 Prop, $61,035 - 60031962 Imp, $30167 - 60047923 Prop, $185,411- 60048361 Imp, $174,709 - 60044273 Imp. | 205885 | 205885 |  |  | 5.6 | 4.4 |  | 284548 | 60070915 | 131348
2024-08-05 | August 2024 Review | Cost Decrease | Local road improvements | Replacement of bridges and other structures | Rangitikei District Council | Mangaweka Bridge Replacement - Detailed Business Case | Implementation |  | ___ | HHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -36357 | -23996 |  |  | 1 | 1 |  | 278747 |  | 131127
2024-08-26 | August 2024 Review | Cost Decrease | Local road improvements | Resilience improvements | NZ Transport Agency | Crown Resilience Programme Management | Implementation |  | ___ | VHHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | COST NEUTRAL - To transfer $216,267 from Crown Resilience Programme Management (60071697) to Crown Resilience Programme LCLR WTCT (60071767) for approved Change Requests as of 01/08/2024, and to transfer $100,000 to SH73 Kellys Creek Bridge (60082738). | -316267 | -316267 |  |  |  | 4 | SAP Initiative: 162602023; SAP Item: 60071697 | 288961 |  | 131122
2024-08-26 | August 2024 Review | Cost Decrease | State highway improvements | Resilience improvements | NZTA (Canterbury) | Crown Resilience Programme LCLR CAN | Implementation |  | ___ | VHHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | COST NEUTRAL - To transfer $44,733 from Crown Resilience Programme LCLR CAN (60071724) to Crown Resilience Programme LCLR WTCT (60071767) for approved Change Requests as of 01/08/2024 | -47641 | -47641 |  |  |  | 4 |  | 290389 | 60071724 | 131132
2024-08-26 | August 2024 Review | Cost Decrease | State highway improvements | Resilience improvements | NZTA (Southland) | TRF-STLD-SH1 Ocean Beach, Bluff | Implementation |  | ___ | LLVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | 1) To transfer $459,000 from Imp (60074848) to Pre-imp (60074847), and 2) to transfer $551,000 from Imp (60074848) to create a new SSBC phase (60083027). This is to match estimated work for SSBC and Pre-imp phases. | -1075650 | -1075650 |  |  |  | 0 |  | 291457 | 60074848 | 131339
2024-08-26 | August 2024 Review | Cost Increase | State highway improvements | Resilience improvements | NZTA (Southland) | TRF-STLD-SH1 Ocean Beach, Bluff | Pre-implementation* |  | ___ | LLVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | To transfer $459,000 from Imp (60074848) to Pre-imp (60074847) to match estimated work for Pre-imp phase. | 488835 | 488835 |  |  |  | 0 |  | 291459 | 60074847 | 131338
2024-08-26 | August 2024 Review | Cost Increase | State highway improvements | Resilience improvements | NZTA (West Coast) | Crown Resilience Programme LCLR WTCT | Implementation |  | ___ | VHHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | COST NEUTRAL - To transfer $261,000 from Crown Resilience Programme LCLR CAN (60071724) and Programme Management (60071697) to Crown Resilience Programme LCLR WTCT (60071767) for approved Change Requests as of 01/08/2024 | 277965 | 277965 |  |  |  | 4 |  | 290390 | 60071767 | 131133
2024-08-26 | August 2024 Review | Cost Decrease | Safety | Road improvements | DOC (West Coast) | Franz Josef Glacier Access Resilience | Single-Stage Business Case |  | ___ | HLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -43717 | -22296 | [5 empty] | 278614 |  | 131287
2024-08-14 | August 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Auckland) | ANO SH1 Papakura to Manukau Managed Lane | Single-Stage Business Case |  | ___ | MHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer - Project 60067980 is closed so moving surplus allocation of $770,186 back into ANO bucket WBS 60056410 | -839503 | -839503 |  |  | 6.4 | 6.4 |  | 282151 | 60067980 | 131272
2024-08-15 | August 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Auckland) | ANO SH16 Royal Road Active Improvements | Implementation |  | ___ | MHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer - Moving $89k from 60056368 to 60070095 | 97010 | 97010 |  |  | 2.9 | 2.9 |  | 283885 | 60070095 | 131283
2024-08-16 | August 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Auckland) | ANO SH16 Royal Road Active Improvements | Pre-implementation* |  | ___ | MHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer - Transferring $116,018 from 60056410 ANO Pre imp to 60070094 ANO SH16 Royal Road pre-imp | 126460 | 126460 |  |  | 2.9 | 2.9 |  | 283884 | 60070094 | 131293
2024-08-15 | August 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Auckland) | ANO SH16 The Strand Upgrades W&C | Pre-implementation* |  | ___ | MHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer - Moving $130k from 60056410 ANO pre-imp to 60067970 The Strand Pre-imp | 141700 | 141700 |  |  |  | 3 |  | 282147 | 60067970 | 131281
2024-08-16 | August 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Auckland) | ANO VMS Infrastructure Expansion | Implementation |  | ___ | MHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer - Moving $450k from ANO Implementation WBS 60056368 to Ano VMS projects Implementation WBS 60081821 | 490500 | 490500 |  |  | 3.2 | 3.2 |  | 292685 | 60081821 | 131296
2024-08-16 | August 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Auckland) | Auckland Network Optimisation (ANO) Programme | Implementation |  | ___ | HHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer - Moving $450k from ANO Implementation WBS 60056368 to Ano VMS projects Implementation WBS 60081821 | -490500 | -490500 |  |  |  | 3.2 | InfoHub ID 28116348 ¦ SAP 60056368 | 254840 | 60056368 | 131294
2024-08-15 | August 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Auckland) | Auckland Network Optimisation (ANO) Programme | Implementation |  | ___ | HHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer - Moving $89k from 60056368 to 60070095 | -97010 | -97010 |  |  |  | 3.2 | InfoHub ID 28116348 ¦ SAP 60056368 | 254840 | 60056368 | 131284
2024-08-16 | August 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Auckland) | Auckland Network Optimisation (ANO) Programme | Pre-implementation* |  | ___ | HHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer - Transferring $116,018 from 60056410 ANO Pre imp to 60070094 ANO SH16 Royal Road pre-imp | -126459 | -126459 |  |  |  | 3.2 | InfoHub ID 28116348 ¦ SAP 60056410 | 254838 | 60056410 | 131292
2024-08-15 | August 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Auckland) | Auckland Network Optimisation (ANO) Programme | Pre-implementation* |  | ___ | HHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer - Moving $130k from 60056410 ANO pre-imp to 60067970 The Strand Pre-imp | -141700 | -141700 |  |  |  | 3.2 | InfoHub ID 28116348 ¦ SAP 60056410 | 254838 | 60056410 | 131282
2024-08-14 | August 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Auckland) | Auckland Network Optimisation (ANO) Programme | Pre-implementation* |  | ___ | HHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer - Project 60067980 is closed so moving surplus allocation of $770,186 back into ANO bucket WBS 60056410. | 839502 | 839502 |  |  |  | 3.2 | InfoHub ID 28116348 ¦ SAP 60056410 | 254838 | 60056410 | 131273
2024-08-08 | August 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (BOP) | SH2 Omokoroa to Te Puna Safety Improvement | Implementation |  | ___ | HMM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow $63,055 incl. admin from 60054591 to 60076216 | 63055 | 63055 |  |  | 2.1 | 2.1 |  | 292483 | 60076216 | 131202
2024-08-26 | August 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Canterbury) | Weigh Right Glasnevin | Implementation |  | ___ | M__ | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Inter Prog. Txf: Transfer $1,705,518 fr 60047939 Imp. $784,503 - 60030985 Imp, $188,885 - 60070915 Imp, $260,808 - 60032036 Imp, $20,000 - 60047946 Prop, $61,035 - 60031962 Imp, $30167 - 60047923 Prop, $185,411- 60048361 Imp, $174,709 - 60044273 Imp. | 855108 | 855108 |  |  | 14 | 14 | 60030985 | 246469 | 60030985 | 131340
2024-08-20 | August 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Canterbury) | Weigh Right Glasnevin | Implementation |  | ___ | M__ | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Inter Programme Transfer: Please Transfer $409,236 from 60047943 Implementation to 60030985 Implementation. | 446067 | 446067 |  |  | 14 | 14 | 60030985 | 246469 | 60030985 | 131309
2024-08-26 | August 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Gisborne) | SH35 and connecting routes: Passing Opportunities | Implementation |  | ___ | H_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer: Please transfer $140,330 from 60051616 Pre-Implementation to 60051617 Implementation, Pre-Imp project can then be closed | 140330 | 140330 |  |  | 1 | 0.8 | PGF | 264801 | 60051617 | 131364
2024-08-26 | August 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Gisborne) | SH35 and connecting routes: Passing Opportunities | Pre-implementation* |  | ___ | H_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer: Please transfer $140,330 from 60051616 Pre-Implementation to 60051617 Implementation, Pre-Imp project can then be closed | -140330 | -140330 |  |  | 1 | 0.8 | PGF Only | 264798 | 60051616 | 131363
2024-08-16 | August 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Marlborough) | SH1 Picton Port Access Improvements | Implementation |  | ___ | VHHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer: Please transfer $251,905 from 60061007 Implementation to 60056643 Single Stage Business Case to cover overspend in 2023-24, SSBC project can then be closed | -274576 | -274576 |  |  | 2 | 2 |  | 276608 | 60061007 | 131289
2024-08-16 | August 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Marlborough) | SH1 Picton Port Access Improvements | Single-Stage Business Case |  | ___ | VHHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer: Please transfer $251,905 from 60061007 Implementation to 60056643 Single Stage Business Case to cover overspend in 2023-24, SSBC project can then be closed | 274576 | 274576 |  |  | 2 | 2 |  | 269351 | 60056643 | 131288
2024-08-12 | August 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Northland) | SH1N Port Marsden Highway to Te Hana improvements | Detailed Business Case |  | ___ | VHML | N |  | Approved | Approved by Chief Financial Officer | PLA for Northland Share RoNS Project Development approved as additional funding of $1,219,153 (inc admin) | 1219153 | 1219153 |  |  | 0.9 | 0.9 | 60042313 | 249234 | 60042313 | 131258
2024-08-16 | August 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Southland) | CIP SH94 Homer Tunnel | Implementation |  | ___ | MHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | To transfer $26,899 from Property (60070446) to Imp (60059181) phase and close the Property phase. 60070446 has an admin rate of 3.5% & 60059181 has an admin rate of 0% | 26899 | 26899 |  |  | 0 | 0 |  | 275306 | 60059181 | 131291
2024-08-26 | August 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Tasman) | SH60 Redwood to Mapua | Pre-implementation* |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | project close | -453076 | -453076 |  |  |  | 2.5 |  | 292424 | 60076166 | 131370
2024-08-08 | August 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Waikato) | SH1 Tokoroa to Taupo Safer Corridor | Implementation |  | ___ | MHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow from ($38,269 incl of admin) 60062208 to 60076254. | 38268 | 38268 |  |  | 0 | 1.6 |  | 292523 | 60076254 | 131203
2024-08-01 | August 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Waikato) | SH3/21 Intersection Improvements, NSRRP | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | total costs increase PLA approved for $83,085 additional funds required | 90562 | 90562 |  |  | 1.7 | 1.7 | 60215945 | 278786 | 60215945 | 131128
2024-08-01 | August 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Wellington) | NZUP Programme Contingency | Implementation |  | ___ | M_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow $ 260,779 from 60059443 to - $994 to 60056054 & $259,785 to 60056053 | -260779 | -260779 |  |  | 0 | 0 |  | 271843 | 60059443 | 131125
2024-08-26 | August 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Wellington) | Wellington Port Access Improvements | Indicative Business Case |  | ___ | VHML | N |  | Approved | Approved by Manager, Treasury & Cash Flow | project closed as per PM request | -562755 | -562755 |  |  | 1 | 1 | 60027702 | 231317 | 60027702 | 131305
2024-08-26 | August 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (West Coast) | RIO West Coast SL Bridge SFT IMPR | Pre-implementation* |  | ___ | M_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow | project closed | -19352 | -19352 |  |  | 1 | 1 | 60056045 | 269714 | 60056045 | 131381
2024-08-22 | August 2024 Review | Cost Decrease | Safety | Road policing | NZ Transport Agency | Drug Driving Testing Support Implementation (DDTSI) | Implementation |  | ___ | LLVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Funds surplused as requested by Mark Weeds. See attached email message. | -3680656 | -3680656 |  |  | 0 | 6.8 | 60069092 | 283292 |  | 131360
2024-08-16 | August 2024 Review | Cost Increase | Safety | Road policing | NZ Transport Agency | Drug Driving Testing Support Implementation (DDTSI) | Implementation |  | ___ | LLVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Reinstating funds of $3,680,656 taken off in last review | 3680656 | 3680656 |  |  | 0 | 6.8 | 60069092 | 283292 |  | 131286
2024-08-07 | August 2024 Review | Cost Decrease | Safety | Road policing | NZ Transport Agency | Road Safety Partnership Programme - NZ Police Appropriation | Implementation |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | 2021-24 NLTP claiming complete. | -2277000 | -2277000 |  |  | 1 | 1 |  | 270363 |  | 131190
2024-08-12 | August 2024 Review | Cost Decrease | Coastal shipping | Sea freight operations | NZ Transport Agency | Coastal Shipping - 2021-24 | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | no further funding required. All activities are complete | -6241626 | -6241626 |  |  | 1 | 1 | 60067633 | 280818 |  | 131259
2024-08-14 | August 2024 Review | Cost Decrease | Investment management (incl. Transport Planning) | Sector research | NZ Transport Agency | Sector Research Programme 2021-24 | Implementation |  | ___ | HHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Annual Close. | -1687685 | -1687685 |  |  |  | 5.9 | 80002107 | 277935 |  | 131276
2024-08-09 | August 2024 Review | Cost Increase | Public transport services | Super gold card | Auckland Transport | SuperGold Card Allocation | Construction |  | ___ | LHL | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2024/25 | 2893402 | 2893402 |  |  | 0 | 0 | 522.9005 | 217751 |  | 131215
2024-08-09 | August 2024 Review | Cost Increase | Public transport services | Super gold card | Bay of Plenty Regional Council | SuperGold Card Allocation | Construction |  | ___ | L_L | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2024/25 | 1085330 | 1085330 |  |  |  | 0 | Supergold | 220569 |  | 131221
2024-08-09 | August 2024 Review | Cost Increase | Public transport services | Super gold card | Environment Canterbury | SuperGold Card Allocations | Implementation |  | ___ | M_M | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2024/25 | 3803468 | 3803468 |  |  | 0 | 0 |  | 221849 |  | 131214
2024-08-09 | August 2024 Review | Cost Increase | Public transport services | Super gold card | Gisborne District Council | SuperGold Card Allocations | Implementation |  | ___ | M_M | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2024/25. | 32632 | 32632 |  |  |  | 0 |  | 221845 |  | 131233
2024-08-09 | August 2024 Review | Cost Increase | Public transport services | Super gold card | Greater Wellington | SuperGold Card Allocations | Implementation |  | ___ | H_M | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2024/25 | 108819 | 108819 |  |  | 0 | 0 |  | 221846 |  | 131216
2024-08-09 | August 2024 Review | Cost Increase | Public transport services | Super gold card | Hawkes Bay Regional Council | SuperGold Card Allocations | Implementation |  | ___ | M_M | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2024/25. | 168284 | 168284 |  |  |  | 0 |  | 220130 |  | 131230
2024-08-09 | August 2024 Review | Cost Increase | Public transport services | Super gold card | Horizons Manawatu | SuperGold Card Allocation | Implementation |  | ___ | H_H | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2024/25 | 307985 | 307985 |  |  |  | 0 |  | 218548 |  | 131222
2024-08-09 | August 2024 Review | Cost Increase | Public transport services | Super gold card | Invercargill City Council | SuperGold Card Allocations | Implementation |  | ___ | M_M | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2024/25 | 71458 | 71458 |  |  |  | 0 |  | 221850 |  | 131224
2024-08-09 | August 2024 Review | Cost Increase | Public transport services | Super gold card | Marlborough District Council | SuperGold Card Allocations | Implementation |  | ___ | M_M | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2024/25 | 37288 | 37288 |  |  |  | 0 |  | 221848 |  | 131225
2024-08-09 | August 2024 Review | Cost Increase | Public transport services | Super gold card | Nelson City Council | SuperGold Card Allocations | Implementation |  | ___ | H_H | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2024/25 | 191706 | 191706 |  |  |  | 0 |  | 221847 |  | 131223
2024-08-09 | August 2024 Review | Cost Increase | Public transport services | Super gold card | Northland Regional Council | SuperGold Card Allocations | Implementation |  | ___ | M_M | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2024/25. | 67510 | 67510 |  |  |  | 0 |  | 221852 |  | 131232
2024-08-09 | August 2024 Review | Cost Increase | Public transport services | Super gold card | Otago Regional Council | SuperGold Card Allocation | Construction |  | ___ | H__ | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2024/25 | 1222530 | 1222530 |  |  | 1 | 0 | SGC | 218695 |  | 131218
2024-08-09 | August 2024 Review | Cost Increase | Public transport services | Super gold card | Taranaki Regional Council | SuperGold Card Allocations | Construction |  | ___ | H_H | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2024/25. | 74951 | 74951 |  |  |  | 0 | SGC Taranaki 2012/15 | 215365 |  | 131231
2024-08-09 | August 2024 Review | Cost Increase | Public transport services | Super gold card | Waikato Regional Council | SuperGold Card Allocation | Construction |  | ___ | LML | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2024/25 | 1090185 | 1090185 |  |  | 0 | 0 | Supergold | 215358 |  | 131219
2024-08-09 | August 2024 Review | Cost Increase | Public transport services | SuperGold trip payments | Auckland Transport | SuperGold Card Allocation | Construction |  | ___ | LHL | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2024/25 | 2773979 | 2773979 |  |  | 0 | 0 | 522.9035 | 264917 |  | 131209
2024-08-09 | August 2024 Review | Cost Increase | Public transport services | SuperGold trip payments | Auckland Transport | SuperGold Card Allocation | Construction |  | ___ | LHL | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2024/25 | 1125704 | 1125704 |  |  | 0 | 0 | 522.9025 | 264916 |  | 131210
2024-08-09 | August 2024 Review | Cost Increase | Public transport services | SuperGold trip payments | Auckland Transport | SuperGold Card Allocation | Construction |  | ___ | LHL | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2024/25 | 14083321 | 14083321 |  |  | 0 | 0 | 522.9015 | 251616 |  | 131208
2024-08-09 | August 2024 Review | Cost Increase | Public transport services | SuperGold trip payments | Environment Canterbury | SuperGold Card Allocations | Construction |  | ___ | M_M | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2024/25 | 79497 | 79497 |  |  | 0 | 0 |  | 264915 |  | 131217
2024-08-09 | August 2024 Review | Cost Increase | Public transport services | SuperGold trip payments | Greater Wellington | SuperGold Card Allocations | Construction |  | ___ | H_M | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2024/25 | 6291370 | 6291370 |  |  | 0 | 0 |  | 251617 |  | 131211
2024-08-09 | August 2024 Review | Cost Increase | Public transport services | SuperGold trip payments | Greater Wellington | SuperGold Card Allocations | Construction |  | ___ | H_M | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2024/25 | 2813606 | 2813606 |  |  | 0 | 0 |  | 264914 |  | 131213
2024-08-09 | August 2024 Review | Cost Increase | Public transport services | SuperGold trip payments | Greater Wellington | SuperGold Card Allocations | Construction |  | ___ | H_M | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2024/25 | 89987 | 89987 |  |  | 0 | 0 |  | 264913 |  | 131212
2024-08-09 | August 2024 Review | Cost Increase | Public transport services | SuperGold trip payments | Waikato Regional Council | SuperGold Card Allocation | Implementation |  | ___ | LML | N |  | Approved | Approved by Minister for Crown Appropriation | Ministry approved funding for 2024/25 | 2808 | 2808 |  |  | 0 | 0 | 522 | 290233 |  | 131220
2024-08-05 | August 2024 Review | Cost Increase | Public transport services | Total mobility operations | Auckland Transport | Community Connect - Auckland Trial | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Fix the FAR | 0 | 4331616 |  |  |  |  | 517.9105 | 284619 |  | 131158
2024-08-13 | August 2024 Review | Cost Decrease | Walking and cycling improvements | Walking facilities | Whangarei District Council | CERF-TC - WDC Transport Choices Package | Implementation |  | ___ | HHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase transfer - The Kamo shared path Imp budget reduced by $560,000 from $$4,340,000 to $3,780,000 . The Raumanaga shared path Imp budget increased by $560,000 from $3,358,000 to $3,918,000 | -560000 | -560000 |  |  |  | 0 | WHGR02 - Kamo Shared Path Connections | 284204 |  | 131237