## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Phase Label | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Decision Status | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR | Your Phase reference | TIO Phase id | SAP item id | TIO Request id
2024-09-12 | August 2024 Review | New approval | External funding | Emergency works | Gisborne District Council | EW Cyclone Gabrielle Recovery | Construction | Bridge repair-programme (red/orange bridges) | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | This funding approval enables the transport network at this location to be reinstated to the appropriate levels of service. | 11399631 | 10031675 |  |  |  |  | Bridge repair -programme (red/orange bridges) - 6032XX | 291503 |  | 128440
2024-09-13 | August 2024 Review | New approval | Local road operations | Emergency works | Tararua District Council | EW - Tararua DC June 2023 | Construction | Initial Response & Recovery | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | As recommended by regional office. To enable Tararua DC to undertake initial response and recovery to various roads within the district and return those roads to the required pre-event level of service. | 2023109 | 1881491 | [5 empty] | 290944 |  | 127007
2024-09-04 | September 2024 Review | New approval | External funding | Emergency works | Carterton District Council | EW Carterton District Council Cyclone Gabrielle 2023 | Construction | Permant Repairs/Network Reinstat (NIWE) @ High FAR | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | amending allocation to align with NZTA EW policy | 352345 | 250165 | [5 empty] | 293117 |  | 132179
2024-09-04 | September 2024 Review | New approval | External funding | Emergency works | Central Hawkes Bay District Council | EW Cyclone Gabrielle | Construction | Recovery (NIWE) High FAR | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Amending allocation to align with NZTA EW policy | 1699462 | 1342575 | [5 empty] | 293118 |  | 132183
2024-09-04 | September 2024 Review | New approval | Local road operations | Emergency works | Far North District Council | EW - Far North DC August 2022 | Construction | Phase 2&3-Major Remedial Wks-EW Aug 22 (FAR+20%) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation to align with NZTA EW policy | 7026844 | 6394428 | [5 empty] | 293125 |  | 132229
2024-09-04 | September 2024 Review | New approval | Local road operations | Emergency works | Gisborne District Council | EW 20 June 2021 Weather Event | Construction | EW: 20 June 21 Flood damage (High FAR +20%) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation to align with NZTA EW policy | 523582 | 460752 | [5 empty] | 293121 |  | 132217
2024-09-26 | September 2024 Review | New approval | External funding | Emergency works | Gisborne District Council | EW Cyclone Gabrielle Recovery | Construction | Major Reinstatement - Drop out repairs | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | to restore LRs back to normal level of service after cyclone Gabrielle | 25000000 | 22000000 |  |  |  |  | Major Reinstatement -Drop out repairs | 291505 |  | 128749
2024-09-26 | September 2024 Review | New approval | External funding | Emergency works | Hastings District Council | EW Cyclone Gabrielle Recovery - FY24/25 | Construction | Recovery Works | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | This funding approval enables the transport services at this network to be reinstated to the appropriate levels of service | 2991716 | 1585609 | [5 empty] | 292770 |  | 131117
2024-09-26 | September 2024 Review | New approval | External funding | Emergency works | Hastings District Council | EW Cyclone Gabrielle Recovery - FY24/25 | Construction | Recovery Phase (+20% FAR) | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | This funding approval enables the transport services at this network to be reinstated to the appropriate levels of service | 20254598 | 14785857 | [5 empty] | 293302 |  | 132619
2024-09-04 | September 2024 Review | New approval | External funding | Emergency works | Kaipara District Council | EW Kaipara DC Feb 2023 Cyclone Gabrielle | Construction | Phase 3 - Major Remedial Work (NIWE) +20% FAR | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation to align with NZTA EW policy | 12539768 | 10282610 | [5 empty] | 293123 |  | 132222
2024-09-04 | September 2024 Review | New approval | External funding | Emergency works | Masterton District Council | EW Masterton District Council Cyclone Gabrielle Recovery | Construction | 2023/24 Recovery (NIWE) High FAR +20% | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation to align with NZTA EW policy | 5820823 | 4423825 | [5 empty] | 293122 |  | 132220
2024-09-26 | September 2024 Review | New approval | External funding | Emergency works | Wairoa District Council | EW - Cyclone Gabrielle - Recovery | Construction |  | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | To restore LRs back to normal level of service after cyclone Gabrielle | 5000000 | 4750000 | [5 empty] | 293119 |  | 132213
2024-09-04 | September 2024 Review | New approval | Local road operations | Emergency works | Wairoa District Council | EW: Emergency Works June 2023 | Construction | Recovery High FAR +20% | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation to align with NZTA EW policy | 1385747 | 1316460 | [5 empty] | 293120 |  | 132215
2024-09-04 | September 2024 Review | New approval | External funding | Emergency works | Whangarei District Council | EW February 2023 Cyclone Gabrielle | Construction | Permanent Reinstat- Phase2 (NIWE Recovery) FAR+20% | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation to align with NZTA EW policy | 4870348 | 4529424 | [5 empty] | 293124 |  | 132226
2024-09-30 | September 2024 Review | New approval | State highway improvements | Road improvements | NZTA (BOP) | BOP VfM Safety Imp â€“ Small Projects | Implementation | BOP VfM Safety Imp â€“ Small Infra Region | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | cost neutral cashflow. VfM Interphase Transfer - move $390000 ex admin from 60075222 to 60083170 | 425100 | 425100 |  |  | 6 | 6 | BOP VfM Safety Imp â€“ Small Infra Region | 292895 | 60083170 | 132635
2024-09-30 | September 2024 Review | New approval | State highway improvements | Road improvements | NZTA (Otago) | OTA VfM Safety Imp â€“ Small Projects | Implementation | OTA VfM Safety Imp â€“ Small Infra Region | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Cost neutral interphase. VfM Interphase Transfer - move $276000 ex admin from 60075581 to 60083227 | 300840 | 300840 |  |  | 6 | 6 | OTA VfM Safety Imp â€“ Small Infra Region | 292927 | 60083227 | 132636
2024-09-27 | September 2024 Review | New approval | State highway improvements | Road improvements | NZTA (Wellington) | SH1 Kapiti Expressway 110km SM | Implementation |  | MHH | HHH | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $861,000 ex admin from 60075638 to 60083367 | 938490 | 938490 |  |  | 6 | 6 |  | 292999 | 60083367 | 132631
2024-09-11 | September 2024 Review | New approval | Walking and cycling improvements |  | Auckland Transport | Audit Repayment | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Refund of overclaim identified during audit. | -1584167 | -807925 |  |  |  | 1 | 452.2932 | 293197 |  | 132338
2024-09-03 | September 2024 Review | New approval | Safety |  | NZ Transport Agency | Tackling Unsafe Speeds | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Remaining funds moved from R2Z to SH Improvements | 4406049 | 4406049 |  |  |  | 1.8 |  | 293097 |  | 132140
2024-09-13 | September 2024 Review | New approval | Safety |  | NZ Transport Agency | Temporary Traffic Management Acceleration | Implementation |  | ___ | HHH | N |  | Approved | Approved by Chief Financial Officer | The key benefit of this funding is to support the roll out of the NZ Temporary Traffic Management Guidance, which moves to a risk based approach to Traffic Management. | 1800000 | 1800000 |  |  | 1 | 1 | 60083500 Temporary Traffic Management Acceleration | 292880 |  | 132399
2024-09-04 | September 2024 Review | New approval | State highway improvements |  | NZTA (Auckland) | AKLD Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Chief Financial Officer | Early funding release of $3,050,422 (including 9% admin) from the total approved $200 million Value for Money Safety Improvements programme (VfM programme) to all regions. | 1860465 | 1860465 |  |  |  | 1 | 60075303 AKLD Share VFM Safety Imp Prog | 289798 | 60075303 | 132195
2024-09-04 | September 2024 Review | New approval | State highway improvements |  | NZTA (Canterbury) | CAN Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Chief Financial Officer | Early funding release of $3,050,422 (including 9% admin) from the total approved $200 million Value for Money Safety Improvements programme (VfM programme) to all regions. | 102693 | 102693 |  |  |  | 1 | 60075600 CAN Share VFM Safety Imp Prog | 289807 | 60075600 | 132200
2024-09-04 | September 2024 Review | New approval | State highway improvements |  | NZTA (Gisborne) | GIS Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Chief Financial Officer | Early funding release of $3,050,422 (including 9% admin) from the total approved $200 million Value for Money Safety Improvements programme (VfM programme) to all regions. | 4157 | 4157 |  |  |  | 1 | 60075397 GIS Share VFM Safety Imp Prog | 289809 | 60075397 | 132201
2024-09-04 | September 2024 Review | New approval | State highway improvements |  | NZTA (Hawkes Bay) | HAWK Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Chief Financial Officer | Early funding release of $3,050,422 (including 9% admin) from the total approved $200 million Value for Money Safety Improvements programme (VfM programme) to all regions. | 9389 | 9389 |  |  |  | 1 | 60075469 HAWK Share VFM Safety Imp Prog | 289811 | 60075469 | 132202
2024-09-04 | September 2024 Review | New approval | State highway improvements |  | NZTA (Manawatu/Whanganui) | MNWI Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Chief Financial Officer | Early funding release of $3,050,422 (including 9% admin) from the total approved $200 million Value for Money Safety Improvements programme (VfM programme) to all regions. | 93537 | 93537 |  |  |  | 1 | 60075295 MNWI Share VFM Safety Imp Prog | 291813 | 60075295 | 132212
2024-09-04 | September 2024 Review | New approval | State highway improvements |  | NZTA (Marlborough) | MARL Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Chief Financial Officer | Early funding release of $3,050,422 (including 9% admin) from the total approved $200 million Value for Money Safety Improvements programme (VfM programme) to all regions. | 8081 | 8081 |  |  |  | 1 | 60075526 MARL Share VFM Safety Imp Prog | 289818 | 60075526 | 132203
2024-09-04 | September 2024 Review | New approval | State highway improvements |  | NZTA (Nelson) | NEL Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Chief Financial Officer | Early funding release of $3,050,422 (including 9% admin) from the total approved $200 million Value for Money Safety Improvements programme (VfM programme) to all regions. | 4157 | 4157 |  |  |  | 1 | 60075473 NEL Share VFM Safety Imp Prog | 289819 | 60075473 | 132204
2024-09-04 | September 2024 Review | New approval | State highway improvements |  | NZTA (Northland) | NTLD Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Chief Financial Officer | Early funding release of $3,050,422 (including 9% admin) from the total approved $200 million Value for Money Safety Improvements programme (VfM programme) to all regions. | 10697 | 10697 |  |  |  | 1 | 60075196 NTLD Share VFM Safety Imp Prog | 289827 | 60075196 | 132205
2024-09-04 | September 2024 Review | New approval | State highway improvements |  | NZTA (Otago) | OTA Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Chief Financial Officer | Early funding release of $3,050,422 (including 9% admin) from the total approved $200 million Value for Money Safety Improvements programme (VfM programme) to all regions. | 389201 | 389201 |  |  |  | 1 | 60075581 OTA Share VFM Safety Imp Prog | 289831 | 60075581 | 132206
2024-09-04 | September 2024 Review | New approval | State highway improvements |  | NZTA (Southland) | STLD Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Chief Financial Officer | Early funding release of $3,050,422 (including 9% admin) from the total approved $200 million Value for Money Safety Improvements programme (VfM programme) to all regions. | 25085 | 25085 |  |  |  | 1 | 60075556 STLD Share VFM Safety Imp Prog | 289836 | 60075556 | 132207
2024-09-04 | September 2024 Review | New approval | State highway improvements |  | NZTA (Taranaki) | TAR Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Chief Financial Officer | Early funding release of $3,050,422 (including 9% admin) from the total approved $200 million Value for Money Safety Improvements programme (VfM programme) to all regions. | 23777 | 23777 |  |  |  | 1 | 60075244 TAR Share VFM Safety Imp Prog | 291784 | 60075244 | 132208
2024-09-04 | September 2024 Review | New approval | State highway improvements |  | NZTA (Tasman) | TAS Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Chief Financial Officer | Early funding release of $3,050,422 (including 9% admin) from the total approved $200 million Value for Money Safety Improvements programme (VfM programme) to all regions. | 8081 | 8081 |  |  |  | 1 | 60075545 TAS Share VFM Safety Imp Prog | 289915 | 60075545 | 132209
2024-09-04 | September 2024 Review | New approval | State highway improvements |  | NZTA (Waikato) | WAI Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Chief Financial Officer | Early funding release of $3,050,422 (including 9% admin) from the total approved $200 million Value for Money Safety Improvements programme (VfM programme) to all regions. | 113593 | 113593 |  |  |  | 1 | 60075459 WAI Share VFM Safety Imp Prog | 289918 | 60075459 | 132210
2024-09-04 | September 2024 Review | New approval | State highway improvements |  | NZTA (Wellington) | WGTN Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Chief Financial Officer | Early funding release of $3,050,422 (including 9% admin) from the total approved $200 million Value for Money Safety Improvements programme (VfM programme) to all regions. | 18779 | 18779 |  |  |  | 1 | 60075638 WGTN Share VFM Safety Imp Prog | 289923 | 60075638 | 132211
2024-09-20 | September 2024 Review | New approval | State highway improvements |  | NZTA (West Coast) | WTCT Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Implementaton Phase for WGTN Share Data Driven Struct Asset Mgmt | 10697 | 10697 |  |  |  | 1 | 60075625 WTCT Share VFM Safety Imp Prog | 289925 | 60075625 | 132382
2024-09-09 | August 2024 Review | Cash flow adjustment | Walking and cycling improvements | Property purchase (State highways) | NZTA (BOP) | Hairini Link - Stage 4 | Property |  | ___ | H_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow | cashflow to next year | 0 | 0 |  |  | 2.1 | 2.5 | 60462702 | 194904 | 60462702 | 131416
2024-09-09 | August 2024 Review | Cash flow adjustment | State highway improvements | Resilience improvements | NZTA (Otago) | RIO SH01S Kakanui Rvr Flood Mitigation | Pre-implementation* |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | project closed | 0 | 0 |  |  | 1 | 1 | 60056073 | 290997 | 60056073 | 131392
2024-09-09 | August 2024 Review | Cash flow adjustment | Road to Zero | Safety promotion, education and advertising | NZTA (Auckland) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  |  |  | 60065061 | 273190 | 60065061 | 131430
2024-09-09 | August 2024 Review | Cash flow adjustment | Road to Zero | Safety promotion, education and advertising | NZTA (BOP) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  |  |  | 60065069 | 273242 | 60065069 | 131432
2024-09-09 | August 2024 Review | Cash flow adjustment | Road to Zero | Safety promotion, education and advertising | NZTA (Hawkes Bay) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  |  |  | 60065077 | 273294 | 60065077 | 131433
2024-09-09 | August 2024 Review | Cash flow adjustment | Road to Zero | Safety promotion, education and advertising | NZTA (Manawatu/Whanganui) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  |  |  | 60065081 | 273346 | 60065081 | 131434
2024-09-09 | August 2024 Review | Cash flow adjustment | Road to Zero | Safety promotion, education and advertising | NZTA (Marlborough) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  |  |  | 60065093 | 273502 | 60065093 | 131436
2024-09-09 | August 2024 Review | Cash flow adjustment | Road to Zero | Safety promotion, education and advertising | NZTA (Nelson) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  |  |  | 60065089 | 273528 | 60065089 | 131435
2024-09-09 | August 2024 Review | Cash flow adjustment | Road to Zero | Safety promotion, education and advertising | NZTA (Northland) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  |  |  | 60065057 | 273164 | 60065057 | 131429
2024-09-09 | August 2024 Review | Cash flow adjustment | Road to Zero | Safety promotion, education and advertising | NZTA (Otago) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  |  |  | 60065111 | 273450 | 60065111 | 131426
2024-09-09 | August 2024 Review | Cash flow adjustment | Road to Zero | Safety promotion, education and advertising | NZTA (Southland) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  |  |  | 60065115 | 273476 | 60065115 | 131427
2024-09-09 | August 2024 Review | Cash flow adjustment | Road to Zero | Safety promotion, education and advertising | NZTA (Tasman) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  |  |  | 60065097 | 273554 | 60065097 | 131437
2024-09-09 | August 2024 Review | Cash flow adjustment | Road to Zero | Safety promotion, education and advertising | NZTA (Waikato) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 | [5 empty] | 273216 | 60065065 | 131431
2024-09-09 | August 2024 Review | Cash flow adjustment | Road to Zero | Safety promotion, education and advertising | NZTA (West Coast) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  |  |  | 60065107 | 273424 | 60065107 | 131425
2024-09-09 | August 2024 Review | Cash flow adjustment | State highway improvements |  | NZTA (Waikato) | SH3 Awakino to Mt Messenger Corridor Improvements (Waikato) | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | project pushed to next year | 0 | 0 |  |  | 1.5 | 1.5 |  | 292772 | 60082552 | 131415
2024-09-20 | September 2024 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | NZTA (Auckland) | Glen Innes to Tamaki Shared Path - Sections 1 and 2 NZTA | Implementation |  | ___ | H_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow Adjustment - Pls move $197,000 from CY to FY1 + $1,395,000 from CY to FY2 + $376,096 from CY to FY3 | 0 | 0 |  |  | 0 | 3.6 |  | 239838 | 60216416 | 132324
2024-09-17 | September 2024 Review | Cash flow adjustment | Local road operations | Emergency works | Gisborne District Council | EW: November 2023 Emergency Works | Construction | Initial Response | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy | 0 | 0 | [5 empty] | 291117 |  | 132468
2024-09-06 | September 2024 Review | Cash flow adjustment | External funding | Emergency works | NZTA (Northland) | EW Gabrielle Northland RW 20230213 | Construction | Construction NIWE Recovery | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving $6,532 into 2024/25 as 2023/24 included the NIWE Response in the total spend. | -1 | -1 | [5 empty] | 291643 | 60069832 | 132262
2024-09-04 | September 2024 Review | Cash flow adjustment | Local road operations | Emergency works | South Wairarapa District Council | Emergency Works Cyclone Hale Storm Event 2023 | Construction | Network reinstatement @ High FAR | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation to align with NZTA EW policy | -17 | -12 | [5 empty] | 293058 |  | 132194
2024-09-04 | September 2024 Review | Cash flow adjustment | Local road operations | Emergency works | South Wairarapa District Council | Emergency Works Cyclone Hale Storm Event 2023 | Construction | Network reinstatement | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation to align with NZTA EW policy | 17 | 9 | [5 empty] | 283605 |  | 132193
2024-09-19 | September 2024 Review | Cash flow adjustment | External funding | Emergency works | Tararua District Council | EW Cyclone Gabrielle | Construction | Cyclone Gabrielle - Recovery Phase (NIWE) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving part of 24-25 funds to high FAR as per NZTA EW policy | -28 | -20 |  |  |  |  | Draft Recovery | 284325 |  | 132501
2024-09-16 | September 2024 Review | Cash flow adjustment | Local road operations | Emergency works | Thames-Coromandel District Council | EW - Thames-Coromandel DC July 2023 | Construction | Initial Response, Investigation and Design | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy | 0 | 0 | [5 empty] | 289669 |  | 132432
2024-09-20 | September 2024 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Auckland) | RoNS East West Link | Pre-implementation* |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow adjustment - Pls move $752,310 from CY 24/25 to next FY1 2025/26 | 0 | 0 |  |  | 1.9 | 1.9 | 60026605 | 233292 | 60026605 | 132359
2024-09-12 | September 2024 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (Waikato) | SH1 Wex Huntly Section | Construction |  | ___ | M_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow $8,780,913 from CY to FY1 | 0 | 0 |  |  | 1.8 | 1.8 | 60203871 | 195982 | 60203871 | 132279
2024-09-20 | September 2024 Review | Cash flow adjustment | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | NZTA (Auckland) | NWBI SH16 Westgate & Brigham Stations | Implementation |  | ___ | VHLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow Adjustment - Please move $20,445,387 from CY to FY1 + move $15,673,264 from CY to FY2 | 0 | 0 |  |  | 1.1 | 1.3 | CIP Westgate | 291621 | 60075137 | 132322
2024-09-12 | September 2024 Review | Cash flow adjustment | Walking and cycling improvements | Property purchase (State highways) | NZTA (Auckland) | Northern Corridor Improvements (NCI) | Property |  | ___ | HHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow Adjustment - Pls move $2,668,000 from CY 24/25 to FY1 25/26 + move $3,785,216 from CY 24/25 to FY2 26/27. | 0 | 0 |  |  | 3 | 3 | 60027516 | 227710 | 60027516 | 132389
2024-09-12 | September 2024 Review | Cash flow adjustment | Walking and cycling improvements | Property purchase (State highways) | NZTA (Auckland) | RoNS East West Link | Property |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow Adjustment - Pls adjust allocation figures for all years. $7.5m to be allocated to each year starting from CY to Year 9 and for the balance allocation of $39,293,196 to be held in Year 10 | 1 | 1 |  |  | 1.9 | 1.9 | 60027281 | 269877 | 60027281 | 132258
2024-09-20 | September 2024 Review | Cash flow adjustment | Walking and cycling improvements | Property purchase (State highways) | NZTA (Auckland) | RoRS Penlink | Property |  | ___ | HML | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow adjustment - Pls move $681,317 from CY 24/25 to next FY1 25/26 | 0 | 0 |  |  | 13.4 | 7.8 | MCIP 60057700 | 269746 | 60057700 | 132481
2024-09-20 | September 2024 Review | Cash flow adjustment | Walking and cycling improvements | Property purchase (State highways) | NZTA (Auckland) | SH1 Dome Valley Safety Improvements | Property |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow Adjustment - Pls move $155,684 from CY 24/25 to next FY1 25/26. | -1 | -1 |  |  | 0 | 1 |  | 292433 | 60076192 | 132392
2024-09-09 | September 2024 Review | Cash flow adjustment | Walking and cycling improvements | Property purchase (State highways) | NZTA (BOP) | RoNS Takitimu North Link Stage 2 | Property |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | 60057027 | 0 | 0 |  |  | 1.3 | 1.3 | MCIP 60057027 | 270319 | 60057027 | 132231
2024-09-23 | September 2024 Review | Cash flow adjustment | Walking and cycling improvements | Property purchase (State highways) | NZTA (Northland) | SH1 Loop Road North to Smeatons Hill Safety Improvement | Property |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow Adjustment - Pls move $1,213,960 from CY 24/25 to next FY1 25/26. | 0 | 0 |  |  | 0 | 1.2 | 60437382 | 278792 | 60437382 | 132387
2024-09-23 | September 2024 Review | Cash flow adjustment | Walking and cycling improvements | Property purchase (State highways) | NZTA (Northland) | SH1 Whangarei to Wellsford - (Southern Section) | Property |  | ___ | HHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow Adjustment - Pls move $1,106,184 from CY 24/25 to FY2 26/27. | 0 | 0 |  |  | 0 | 1.6 |  | 292443 | 60076201 | 132388
2024-09-23 | September 2024 Review | Cash flow adjustment | Walking and cycling improvements | Property purchase (State highways) | NZTA (Northland) | SH10 Kaeo Bridge upgrade | Property |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow Adjustment - Pls move $274,638 from CY 24/25 to next FY1 25/26t. | -1 | -1 |  |  | 0.6 | 0.6 | 60040964 | 278787 | 60040964 | 132386
2024-09-12 | September 2024 Review | Cash flow adjustment | Walking and cycling improvements | Property purchase (State highways) | NZTA (Waikato) | RoNS SH1 Cambridge to Piarere | Property |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow allocation of $31,533,971 to CY from Y4 $1,925,003 and Y5 $29,608,968 | 0 | 0 |  |  | 0 | 0.9 | 60048204 | 252060 | 60048204 | 132341
2024-09-12 | September 2024 Review | Cash flow adjustment | Walking and cycling improvements | Property purchase (State highways) | NZTA (Waikato) | SH29 Piarere to SH28 | Property |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow $1,671,830 from CY to FL1 | 0 | 0 |  |  | 2.1 | 2.1 |  | 292536 | 60076270 | 132347
2024-09-20 | September 2024 Review | Cash flow adjustment | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH30 Kopaki Bridge Replacement | Detailed Business Case |  | ___ | H__ | N |  | Approved | Approved by Manager, Treasury & Cash Flow | project close | 0 | 0 |  |  | 99 | 99 |  | 258503 | 60049740 | 132344
2024-09-20 | September 2024 Review | Cash flow adjustment | State highway improvements | Resilience improvements | NZTA (Auckland) | SH16 Omeru Falls Underslip | Implementation |  | ___ | VHHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow - Please move $3,728,806 from CY 24/25 to next FY 25/26. | -1 | -1 |  |  |  | 1 | 60072024 | 288985 | 60072024 | 132358
2024-09-20 | September 2024 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Auckland) | Auck Accelerated Prog: Southern Corridor Improvements | Construction |  | ___ | H_H | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow Transfer - pls move $1,500,706 from CY to FY1 25/26 + pls move $35,000 from CY to FY2 26/27 | 1 | 1 |  |  | 0 | 6 | 60027490 moved to debt funds | 233295 | 60027490 | 132257
2024-09-12 | September 2024 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Auckland) | SH22 (Drury) Corridor Upgrade | Pre-implementation* |  | ___ | MML | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow adjustment - Pls move $458,547 from CY 24/25 to FY 1 25/26 | 0 | 0 |  |  |  | 1.7 | MCIP 60067768 | 281986 | 60067768 | 132367
2024-09-12 | September 2024 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (BOP) | RoNS Takitimu North Link Stage 1 | Implementation |  | ___ | HHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow $2,852,842 from Y2 to CY, $10,793,085 from Y2 to Y1, $3,827,013 from Y2 to Y3 and $5,325,241 from Y2 to Y4 | 0 | 0 |  |  | 2 | 2 | MCIP 60057025 | 270272 | 60057025 | 132349
2024-09-09 | September 2024 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Northland) | SH1 Loop Road North to Smeatons Hill Safety Improvement | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow transfer - Pls move $5,960,536 from CY 24/25 to next FY1 25/26 | 0 | 0 |  |  | 0 | 1.2 | 60210807 | 278791 | 60210807 | 132253
2024-09-20 | September 2024 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | SH1 ETA Corridor Improvements | Implementation |  | ___ | VHML | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow $41,750 contingency into Y1 | 0 | 0 |  |  | 2.6 | 2.6 |  | 292517 | 60076248 | 132346
2024-09-12 | September 2024 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | SH1 ETA Corridor Improvements | Implementation |  | ___ | VHML | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow $1,808,127 contingency into Y2 | 1 | 1 |  |  | 2.6 | 2.6 |  | 292518 | 60076249 | 132345
2024-09-12 | September 2024 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | SH1 Tokoroa to Taupo - CI Stage 2 | Pre-implementation* |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | cashflow $1,000,000 from CY to Y1 and $994,864 from CY to Y2 | 0 | 0 |  |  | 0 | 1.6 |  | 292531 | 60076265 | 132348
2024-09-09 | September 2024 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Wellington) | NZUP Programme Contingency | Implementation |  | ___ | M_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow: - FY24/25 $0 FY25/26 $124,208,360 FY26/27 $129,230,769 FY27/28 $36,730,769 The reason for cashflow - we donâ€™t plan on using any NZUP programme contingency allocation for FY24/25. | 0 | 0 |  |  | 0 | 0 |  | 271843 | 60059443 | 132300
2024-09-09 | August 2024 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Nelson City Council | SfP Hospital Connection | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -381471 | -343324 |  |  | 1 | 1 |  | 283075 |  | 131401
2024-09-09 | August 2024 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Tasman District Council | SfP Tasman Towns | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -78481 | -70633 |  |  |  | 1 |  | 282764 |  | 131402
2024-09-16 | August 2024 Review | Cost Increase | External funding | Emergency works | Auckland Transport | EW - AT Anniversary Weekend & Cyclone Gabrielle 2023 | Construction | E/W - Reinstatement @ 71% (NIWE) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation to align with EW NZTA policy | 3000180 | 2130128 |  |  |  |  | 141.2901 | 291177 |  | 131367
2024-09-09 | August 2024 Review | Cost Decrease | Local road operations | Emergency works | Christchurch City Council | EW - Earthquake Events - NLTP funding | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Procedural Audit refund. | -48238 | -48238 |  |  |  |  | 721* | 211617 |  | 131447
2024-09-04 | August 2024 Review | Cost Increase | External funding | Emergency works | NZTA (BOP) | EW BOP Extreme HR 20230127 | Construction | NIWE Recovery | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | This fits within the current PIKB guidance for emergency funding. I support Sandraâ€™s comments and recommend approval. | 323705 | 323705 | [5 empty] | 291642 | 60069770 | 131358
2024-09-09 | August 2024 Review | Cost Decrease | Local road operations | Emergency works | Whangarei District Council | EW Storm Events June 2020 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -40750 | -21598 | [5 empty] | 270904 |  | 131452
2024-09-09 | August 2024 Review | Cost Decrease | Safety | Network and asset management | NZ Transport Agency | Asset Management Data Standard- State Highways | Implementation |  | ___ | VHMM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | ELT requested | -8837114 | -8837114 |  |  |  | 4.4 | SAP Item 60067460 | 281639 |  | 131450
2024-09-09 | August 2024 Review | Cost Decrease | Safety | Network and asset management | NZ Transport Agency | Asset Management Data Standard- State Highways | Implementation |  | ___ | VHMM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | ELT requested | -3562886 | -3562886 |  |  |  | 4.4 | LR Maintenance part of funding, SAP item 60067372 | 277727 |  | 131449
2024-09-09 | August 2024 Review | Cost Decrease | Walking and cycling improvements | Property purchase (State highways) | NZTA (Waikato) | SH1 Piarere to Tokoroa Safer Corridor | Property |  | ___ | HHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | surplus and close as per PM email | -833745 | -833745 |  |  | 0 | 1.6 |  | 292544 | 60076278 | 131388
2024-09-09 | August 2024 Review | Cost Decrease | Public transport services | Public transport information supply, operations and maintenance | Greater Wellington | Real time information system replacement | Single-Stage Business Case |  | ___ | MHVH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -350000 | -178500 |  |  | 0 | 12 | RTI 2.0 business case | 269353 |  | 131376
2024-09-13 | August 2024 Review | Cost Increase | Public transport infrastructure | Rapid Transit Infrastructure | NZTA (Auckland) | North West Rapid Transit Improvements | Detailed Business Case |  | ___ | VHHL | N |  | Approved | Approved by Chief Financial Officer | PLA under review to complete the DBC, total additional funds requested are $9,074,462 | 9891163 | 9891163 |  |  | 1.1 | 1.3 | North West Rapid Transit Improvements | 269237 | 60055578 | 131270
2024-09-09 | August 2024 Review | Cost Decrease | Safety | Safety promotion, education and advertising | NZ Transport Agency | RtZ Work-Related Road Safety | Implementation |  | ___ | MHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Total $22.4m approved funding in TIO for 24-27 period â€“ please surplus funds to leave $650k allocation in 24/25. | -21768683 | -21768683 |  |  | 5.6 | 5.6 | SAP 60068924 | 283054 |  | 131451
2024-09-09 | August 2024 Review | Cost Decrease | Investment management (incl. Transport Planning) | Transport model development | Greater Wellington | Maintaining the Strategic Transport Models | Study |  | HM_ | HH_ | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project complete, please close | -8903 | -5041 |  |  |  |  | W.594/2220/1 | 220056 |  | 131374
2024-09-03 | September 2024 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | NZTA (Manawatu/Whanganui) | 2024-27 NLTP funds management | Repayment |  | ___ | LHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Add 2024/25 offset | 3570 | 3570 | [5 empty] | 279097 |  | 132150
2024-09-03 | September 2024 Review | Cost Increase | Walking and cycling improvements | Cycling facilities | NZTA (Manawatu/Whanganui) | 2024-27 NLTP funds management | Repayment |  | ___ | LHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Add 2024/25 offset | 264186 | 264186 | [5 empty] | 279097 |  | 132151
2024-09-12 | September 2024 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Napier City Council | SfP Walking and Cycling | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Removing funding from 24/25 of $211,836 (declaring surplus) and moving this to NZTA programme management cost (280336). Requested by Geoff Haines. | -211836 | -190652 |  |  | 1 | 1 | Implementation | 283079 |  | 132390
2024-09-19 | September 2024 Review | Cost Decrease | External funding | Emergency works | Auckland Transport | EW - AT Anniversary Weekend & Cyclone Gabrielle 2023 | Construction | E/W - Reinstatement @ 51% (NIWE) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Reversing earlier review to allow for PLA in progress | -2970180 | -1514792 |  |  |  |  | 141.2838 | 291176 |  | 132506
2024-09-19 | September 2024 Review | Cost Increase | External funding | Emergency works | Auckland Transport | EW - AT Anniversary Weekend & Cyclone Gabrielle 2023 | Construction | E/W - Reinstatement @ 71% (NIWE) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Reversing earlier review to allow for PLA in progress | 2970180 | 2108828 |  |  |  |  | 141.2901 | 291177 |  | 132505
2024-09-19 | September 2024 Review | Cost Decrease | External funding | Emergency works | Auckland Transport | EW - AT Anniversary Weekend & Cyclone Gabrielle 2023 | Construction | E/W - Reinstatement @ 71% (NIWE) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation to align with EW NZTA policy | -2970180 | -2108828 |  |  |  |  | 141.2901 | 291177 |  | 132474
2024-09-16 | September 2024 Review | Cost Decrease | External funding | Emergency works | Auckland Transport | EW - AT Anniversary Weekend & Cyclone Gabrielle 2023 | Construction | E/W - Reinstatement @ 51% (NIWE) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation to align with EW NZTA policy. | -3000180 | -1530092 |  |  |  |  | 141.2838 | 291176 |  | 132423
2024-09-30 | September 2024 Review | Cost Increase | External funding | Emergency works | Auckland Transport | EW - AT Anniversary Weekend & Cyclone Gabrielle 2023 | Construction | E/W - Reinstatement @ 71% (NIWE) | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | To complete AT's E/W reinstatement delivery programme moderated with NZTA counterparts and approved by acting CFO ($34M but in system - $39.9M) | 33999491 | 24139638 |  |  |  |  | 141.2901 | 291177 |  | 132507
2024-09-19 | September 2024 Review | Cost Increase | External funding | Emergency works | Auckland Transport | EW - AT Anniversary Weekend & Cyclone Gabrielle 2023 | Construction | E/W - Reinstatement @ 51% (NIWE) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to normal FAR as per NZTA EW policy | 2970180 | 1514792 |  |  |  |  | 141.2838 | 291176 |  | 132500
2024-09-04 | September 2024 Review | Cost Decrease | External funding | Emergency works | Carterton District Council | EW Carterton District Council Cyclone Gabrielle 2023 | Construction | Permanent Repairs/Network reinstatement (NIWE) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | amending allocation to align with NZTA EW policy | -352345 | -179696 | [5 empty] | 291179 |  | 132178
2024-09-16 | September 2024 Review | Cost Decrease | Local road operations | Emergency works | Central Hawkes Bay District Council | EW CHBDC 20220602 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to normal FAR as per NZTA EW policy | 0 | -3743 |  |  |  |  | construction (Normal FAR+20%) | 283095 |  | 132436
2024-09-04 | September 2024 Review | Cost Decrease | External funding | Emergency works | Central Hawkes Bay District Council | EW Cyclone Gabrielle | Construction | Recovery (NIWE) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Amending allocation to align with NZTA EW policy | -1699462 | -1002683 | [5 empty] | 291081 |  | 132180
2024-09-26 | September 2024 Review | Cost Increase | External funding | Emergency works | Central Hawkes Bay District Council | EW Cyclone Gabrielle | Construction | Recovery (NIWE) High FAR | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | to restore LRs back to normal level of service after cyclone Gabrielle | 8945000 | 7066550 | [5 empty] | 293118 |  | 132467
2024-09-04 | September 2024 Review | Cost Decrease | Local road operations | Emergency works | Far North District Council | EW - Far North DC August 2022 | Construction | Phase 2&3 - Major Remedial Works - EW August 2022 | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation to align with NZTA EW policy | -7026844 | -4989059 | [5 empty] | 283200 |  | 132228
2024-09-16 | September 2024 Review | Cost Increase | Local road operations | Emergency works | Far North District Council | EW - Far North DC August 2022 | Construction | Phase 2 - I & D and Practitioner Solutions Const. | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy | 0 | 495282 |  |  |  |  | Phase 2 (Normal FAR+20%) | 288986 |  | 132437
2024-09-16 | September 2024 Review | Cost Increase | External funding | Emergency works | Far North District Council | EW Far North DC Anniversary weekend & Cyclone Gabrielle 2023 | Construction | Major Works - Anniversary & Gabrielle (NIWE) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy | 0 | 361048 |  |  |  |  | Major Works - Anniversary & Cyclone Gabrielle | 291181 |  | 132438
2024-09-16 | September 2024 Review | Cost Increase | Local road operations | Emergency works | Far North District Council | EW Far North DC June 2023 | Construction | Phase 1 - Initial Response - EW June 2023 | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy | 0 | 102057 |  |  |  |  | Phase 1 - Initial Response - EW June 2023 | 288443 |  | 132440
2024-09-16 | September 2024 Review | Cost Increase | Local road operations | Emergency works | Far North District Council | EW Far North DC June 2023 | Construction | Phase 2 - Minor Remedial Works - EW June 2023 | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy | 0 | 157394 |  |  |  |  | Phase 2 - Minor Remedial Works - EW June 2023 | 288444 |  | 132441
2024-09-16 | September 2024 Review | Cost Increase | Local road operations | Emergency works | Far North District Council | EW Far North DC June 2023 | Construction | Phase 3 - Major Remedial Works - EW June 2023 | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy | 0 | 264960 |  |  |  |  | Phase 3 - Major Remedial Works - EW June 2023 | 288445 |  | 132442
2024-09-16 | September 2024 Review | Cost Increase | Local road operations | Emergency works | Far North District Council | EW Far North DC May 2023 | Construction | Phase 3 - Major Remedial Works - EW May 2023 | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy | 0 | 2303990 |  |  |  |  | Phase 3 - Major Remedial Works - EW May 2023 | 284263 |  | 132439
2024-09-16 | September 2024 Review | Cost Increase | Local road operations | Emergency works | Far North District Council | EW Far North DC October 2023 | Construction | Phase 1 - Initial Response - EW October 2023 | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy | 0 | 13437 |  |  |  |  | Phase 1 - Initial Response - EW October 2023 | 290477 |  | 132443
2024-09-16 | September 2024 Review | Cost Increase | Local road operations | Emergency works | Far North District Council | EW Far North DC October 2023 | Construction | Phase 2 - Minor Remedial Works - EW October 2023 | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy | 0 | 46860 |  |  |  |  | Phase 2 - Minor Remedial Works - EW October 2023 | 290906 |  | 132444
2024-09-04 | September 2024 Review | Cost Decrease | Local road operations | Emergency works | Gisborne District Council | EW 20 June 2021 Weather Event | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation to align with NZTA EW policy | -523582 | -741669 |  |  |  |  | Emergency Works: 20 June 2021 Flood Damage | 279377 |  | 132216
2024-09-17 | September 2024 Review | Cost Increase | External funding | Emergency works | Gisborne District Council | EW Cyclone Gabrielle | Construction | CSA #3 Tranche 2 - Repairs Recovery 603400-002 | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy | 0 | 120830 | [5 empty] | 290859 |  | 132461
2024-09-17 | September 2024 Review | Cost Increase | External funding | Emergency works | Gisborne District Council | EW Cyclone Gabrielle Recovery | Construction | CSA# 4 Tranche 3 Bridges - Recovery | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy | 0 | 350000 |  |  |  |  | Purchase of Bushy Knoll Bridge -Darren said dont touch this | 291638 |  | 132463
2024-09-17 | September 2024 Review | Cost Increase | External funding | Emergency works | Gisborne District Council | EW Cyclone Gabrielle Recovery | Construction | CSA# 4 Tranche 3 Dropouts Recovery | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy | 0 | 21037 | [5 empty] | 291637 |  | 132462
2024-09-17 | September 2024 Review | Cost Increase | Local road operations | Emergency works | Gisborne District Council | EW September 2023 Rain event | Construction | Immediate Response and Recovery costs | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy | 0 | 562 | [5 empty] | 291647 |  | 132469
2024-09-17 | September 2024 Review | Cost Increase | Local road operations | Emergency works | Gisborne District Council | EW Tiniroto Road Landslide | Construction | EW Tiniroto Road Landslide | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy | 0 | 30646 |  |  |  |  | 485271.12 | 290565 |  | 132466
2024-09-04 | September 2024 Review | Cost Increase | Local road operations | Emergency works | Gisborne District Council | EW: Emergency Works: June 2020 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation to align with NZTA EW policy | 0 | 1020000 |  |  |  |  | Construction -Emergency Works: June 2020 Flood Damage | 278152 |  | 132185
2024-09-04 | September 2024 Review | Cost Decrease | Local road operations | Emergency works | Gisborne District Council | EW: Emergency Works: June 2020 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation to align with NZTA EW policy | 0 | -1290000 |  |  |  |  | Construction -Emergency Works: June 2020 Flood Damage | 278152 |  | 132184
2024-09-19 | September 2024 Review | Cost Decrease | Local road operations | Emergency works | Gisborne District Council | EW: Emergency Works: June 2020 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to normal FAR as per NZTA EW policy | 0 | -52535 |  |  |  |  | Construction -Emergency Works: June 2020 Flood Damage (Normal FAR+20%) | 282974 |  | 132498
2024-09-17 | September 2024 Review | Cost Increase | Local road operations | Emergency works | Gisborne District Council | EW: June 2023 Emergency Works | Construction | Immediate Response costs (Normal FAR+20%) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy | 0 | 454 |  |  |  |  | Immediate response including Managment Services and Internal overheads | 290688 |  | 132464
2024-09-17 | September 2024 Review | Cost Increase | Local road operations | Emergency works | Gisborne District Council | EW: June 2023 Emergency Works | Construction | Phase 1 Recovery | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy | 0 | 614945 | [5 empty] | 291648 |  | 132465
2024-09-17 | September 2024 Review | Cost Increase | Local road operations | Emergency works | Gisborne District Council | EW: March/April 2022 Emergency Event | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy | 0 | 510316 |  |  |  |  | EW March 2022 Emergency Works Flood Event | 281440 |  | 132458
2024-09-17 | September 2024 Review | Cost Increase | Local road operations | Emergency works | Gisborne District Council | EW: March/April 2022 Emergency Event | Construction | Construction Phase + 20% | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy | 0 | 20587 | [5 empty] | 284657 |  | 132459
2024-09-17 | September 2024 Review | Cost Increase | Local road operations | Emergency works | Gisborne District Council | EW: November 2021 Emergency works | Construction | 2021-11-01 | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy | 0 | 144838 |  |  |  |  | construction | 282784 |  | 132460
2024-09-19 | September 2024 Review | Cost Increase | Local road operations | Emergency works | Gisborne District Council | EW: November 2023 Emergency Works | Construction | Initial Response | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy | 0 | 100676 | [5 empty] | 291117 |  | 132499
2024-09-04 | September 2024 Review | Cost Increase | Local road operations | Emergency works | Hauraki District Council | EW - Hauraki DC May 2023 | Construction | continuing cleanup and reinstatement | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation to align with NZTA EW policy | 0 | 8203 |  |  |  |  | W38708 | 284529 |  | 132189
2024-09-04 | September 2024 Review | Cost Decrease | External funding | Emergency works | Kaipara District Council | EW Kaipara DC Feb 2023 Cyclone Gabrielle | Construction | Phase 3 - Major Remedial Work (NIWE) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation to align with NZTA EW policy | -12539768 | -7774657 |  |  |  |  | Major Remedial Work | 283952 |  | 132221
2024-09-04 | September 2024 Review | Cost Increase | External funding | Emergency works | Kaipara District Council | EW Kaipara DC Feb 2023 Cyclone Gabrielle | Construction | Phase3 - Remedial Wk (NIWE) + 20% FAR | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation to align with NZTA EW policy | 0 | 78123 | [5 empty] | 292667 |  | 132223
2024-09-04 | September 2024 Review | Cost Increase | Local road operations | Emergency works | Kaipara District Council | EW Kaipara DC May 2023 | Construction | Phase 2 - Minor Remedial Works | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation to align with NZTA EW policy | 0 | 98246 |  |  |  |  | Minor Remedial Works | 289241 |  | 132224
2024-09-04 | September 2024 Review | Cost Increase | External funding | Emergency works | Manawatu District Council | EW - Cyclone Gabrielle February 2023 | Construction | Recovery Phase (NIWE) - Bridge (Normal FAR+20%) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Amending allocation to align with NZTA EW policy | -703773 | 556346 | [5 empty] | 291501 |  | 132197
2024-09-04 | September 2024 Review | Cost Increase | External funding | Emergency works | Manawatu District Council | EW - Cyclone Gabrielle February 2023 | Construction | Recovery Phase (NIWE) - Bridge (N+20%) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | adjusting allocation to align with NZTA EW policy | 703773 | 358924 | [5 empty] | 291500 |  | 132196
2024-09-04 | September 2024 Review | Cost Decrease | External funding | Emergency works | Masterton District Council | EW Masterton District Council Cyclone Gabrielle Recovery | Construction | 2023/24 Recovery (NIWE) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation to align with NZTA EW policy | -5820823 | -3259661 |  |  |  |  | 2023/24 Recovery | 292277 |  | 132219
2024-09-17 | September 2024 Review | Cost Decrease | State highway operations | Emergency works | NZTA (Manawatu/Whanganui) | EW Taranaki SH43 HR 20231229 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Closure requested by Nigel Hurley at Variance Meeting 17.9.24 | -11323 | -11323 | [5 empty] | 290905 | 60074478 | 132428
2024-09-30 | September 2024 Review | Cost Increase | Local road operations | Emergency works | Nelson City Council | EW Nelson City Council Storm Event August 2022 | Construction | Recovery | ___ |  | N |  | Approved | Approved by National Manager, Programmes and Standards (Transport Services) | Incorrect FAR calculation. MOR now indicates that the 71% should be $2,480,053 | -54413 | 468260 | [5 empty] | 290417 |  | 132639
2024-09-30 | September 2024 Review | Cost Increase | Local road operations | Emergency works | Nelson City Council | EW Nelson City Council Storm Event August 2022 | Construction | Recovery (Normal FAR+20%) | ___ |  | N |  | Approved | Approved by National Manager, Programmes and Standards (Transport Services) | Incorrect FAR calculation. MOR now indicates that the 71% should be $2,480,053 | 54413 | 27751 |  |  |  |  | (Normal FAR+20%) | 292652 |  | 132640
2024-09-16 | September 2024 Review | Cost Decrease | External funding | Emergency works | Tararua District Council | EW Cyclone Gabrielle | Construction | Cyclone Gabrielle - Recovery Phase - Normal FAR | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Removing funds and moving to phase 292679 | -484112 | -353402 | [5 empty] | 292699 |  | 132426
2024-09-16 | September 2024 Review | Cost Increase | External funding | Emergency works | Tararua District Council | EW Cyclone Gabrielle | Construction | Cyclone Gabrielle- Recovery Phase (NIWE) FAR +20% | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving funds $484,140 from phase 262699 | 484140 | 450250 | [5 empty] | 292679 |  | 132427
2024-09-16 | September 2024 Review | Cost Increase | External funding | Emergency works | Thames-Coromandel District Council | EW - Thames-Coromandel DC February 2023 (Cyclone Gabrielle) | Construction | Permanent Reinstatement & MSQA (NIWE) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving this phase to high FAR as per NZTA EW policy | 0 | 236674 | [5 empty] | 283961 |  | 132429
2024-09-16 | September 2024 Review | Cost Increase | Local road operations | Emergency works | Thames-Coromandel District Council | EW - Thames-Coromandel DC July 2023 | Construction | Initial Response, Investigation and Design (2) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy | 0 | 27964 |  |  |  |  | (Normal FAR+20%) | 291080 |  | 132433
2024-09-16 | September 2024 Review | Cost Increase | Local road operations | Emergency works | Thames-Coromandel District Council | EW - Thames-Coromandel DC July 2023 | Construction | Initial Response, Investigation and Design | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 23-24 funds to high FAR as per NZTA EW policy | 0 | 31000 | [5 empty] | 289669 |  | 132430
2024-09-16 | September 2024 Review | Cost Increase | Local road operations | Emergency works | Thames-Coromandel District Council | EW - Thames-Coromandel DC July 2023 | Construction | Permanent Reinstatement MSQA and Construction | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy | 0 | 160000 | [5 empty] | 289670 |  | 132431
2024-09-16 | September 2024 Review | Cost Increase | Local road operations | Emergency works | Thames-Coromandel District Council | EW - Thames-Coromandel DC October 2023 | Construction | Initial Response, Investigation and Design | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy | 0 | 19791 | [5 empty] | 291174 |  | 132434
2024-09-16 | September 2024 Review | Cost Increase | Local road operations | Emergency works | Thames-Coromandel District Council | EW - Thames-Coromandel DC October 2023 | Construction | Permanent Reinstatement MSQA and Construction | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy | 0 | 40000 | [5 empty] | 291175 |  | 132435
2024-09-20 | September 2024 Review | Cost Decrease | Local road operations | Emergency works | Thames-Coromandel District Council | EW TCDC 1 October 2022 | Construction | Permanent Reinstatement & MSQA | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -370813 | -189115 | [5 empty] | 283259 |  | 132504
2024-09-20 | September 2024 Review | Cost Decrease | Local road operations | Emergency works | Thames-Coromandel District Council | EW TCDC July 2022 | Construction | Initial Response, Investigation an Design | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -196983 | -100461 | [5 empty] | 282904 |  | 132503
2024-09-20 | September 2024 Review | Cost Decrease | Local road operations | Emergency works | Thames-Coromandel District Council | February 2021 Storm Event | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -190413 | -97111 |  |  |  |  | Reinstatement Works | 275926 |  | 132502
2024-09-04 | September 2024 Review | Cost Decrease | Local road operations | Emergency works | Wairoa District Council | EW: Emergency Works June 2023 | Construction | Recovery | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation to align with NZTA EW policy | -1385747 | -1039310 | [5 empty] | 290690 |  | 132214
2024-09-05 | September 2024 Review | Cost Decrease | Local road operations | Emergency works | Waitomo District Council | EW - Waitomo DC January 2023 (Auckland Anniversary) | Construction | Phase One - Initial response, I&D | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Remaining funds being moved to NIWE Response | -104741 | -104741 | [5 empty] | 283917 |  | 132260
2024-09-05 | September 2024 Review | Cost Increase | External funding | Emergency works | Waitomo District Council | EW - Waitomo DC January 2023 (Auckland Anniversary) | Construction | Phase One - Initial response, I&D-NIWE | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Remaining NLTF funds being moved to NIWE Response | 104741 | 104741 | [5 empty] | 291166 |  | 132261
2024-09-17 | September 2024 Review | Cost Increase | External funding | Emergency works | Whangarei District Council | EW February 2023 Cyclone Gabrielle | Construction | Permanent Reinstatement - Phase 2 (NIWE Recovery) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy | 579764 | 307275 | [5 empty] | 292309 |  | 132472
2024-09-17 | September 2024 Review | Cost Decrease | External funding | Emergency works | Whangarei District Council | EW February 2023 Cyclone Gabrielle | Construction | Permanent Reinstat- Phase2 (NIWE Recovery) FAR+20% | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 24-25 funds to high FAR as per NZTA EW policy. Previous review had an error as it was 93% FAR. | -579764 | -1397298 | [5 empty] | 293124 |  | 132471
2024-09-04 | September 2024 Review | Cost Decrease | External funding | Emergency works | Whangarei District Council | EW February 2023 Cyclone Gabrielle | Construction | Permanent Reinstatement - Phase 2 (NIWE Recovery) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation to align with NZTA EW policy | -4870348 | -2581284 | [5 empty] | 292309 |  | 132225
2024-09-04 | September 2024 Review | Cost Increase | Local road operations | Emergency works | Whangarei District Council | EW Whangarei DC May 2023 Storm Event | Construction | Immediate response and minor remedial | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Adjusting allocation to align with NZTA EW policy | 0 | 26897 |  |  |  |  | Immediate Response and minor remedial | 284559 |  | 132227
2024-09-11 | September 2024 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Auckland) | Low cost / low risk improvements 2024-27 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Original upload included admin and now updating so allocation is admin exclusive | 0 | -1261242 |  |  |  |  | LCLR SHI 2024-27 Auckland | 287859 | 60075768 | 132340
2024-09-12 | September 2024 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | NZTA (BOP) | Low cost / low risk improvements 2024-27 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Original upload included admin and now updating so allocation is admin exclusive | 0 | -659791 |  |  |  |  | LCLR SHI 2024-27 Bay of Plenty | 287867 | 60075771 | 132366
2024-09-12 | September 2024 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Canterbury) | Low cost / low risk improvements 2024-27 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Original upload included admin and now updating so allocation is admin exclusive | 0 | -1067728 |  |  |  |  | LCLR SHI 2024-27 Canterbury | 287874 | 60075774 | 132368
2024-09-12 | September 2024 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Gisborne) | Low cost / low risk improvements 2024-27 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Original upload included admin and now updating so allocation is admin exclusive | 0 | -293074 |  |  |  |  | LCLR SHI 2024-27 Gisborne | 287883 | 60075777 | 132369
2024-09-12 | September 2024 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Hawkes Bay) | Low cost / low risk improvements 2024-27 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Original upload included admin and now updating so allocation is admin exclusive | 0 | -422674 |  |  |  |  | LCLR SHI 2024-27 Hawkes Bay | 287891 | 60075780 | 132370
2024-09-12 | September 2024 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Manawatu/Whanganui) | Low cost / low risk improvements 2024-27 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Original upload included admin and now updating so allocation is admin exclusive | 0 | -662480 |  |  |  |  | LCLR SHI 2024-27 Manawatu | 287901 | 60075783 | 132371
2024-09-12 | September 2024 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Marlborough) | Low cost / low risk improvements 2024-27 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Original upload included admin and now updating so allocation is admin exclusive | 0 | -261738 |  |  |  |  | LCLR SHI 2024-27 Marlborough | 287908 | 60075786 | 132372
2024-09-12 | September 2024 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Nelson) | Low cost / low risk improvements 2024-27 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Original upload included admin and now updating so allocation is admin exclusive | 0 | -216299 |  |  |  |  | LCLR SHI 2024-27 Nelson | 287917 | 60075789 | 132373
2024-09-12 | September 2024 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Northland) | Low cost / low risk improvements 2024-27 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Original upload included admin and now updating so allocation is admin exclusive | 0 | -814433 |  |  |  |  | LCLR SHI 2024-27 Northland | 287922 | 60075792 | 132374
2024-09-12 | September 2024 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Otago) | Low cost / low risk improvements 2024-27 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Original upload included admin and now updating so allocation is admin exclusive | 0 | -553233 |  |  |  |  | LCLR SHI 2024-27 Otago | 287932 | 60075795 | 132375
2024-09-12 | September 2024 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Southland) | Low cost / low risk improvements 2024-27 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Original upload included admin and now updating so allocation is admin exclusive | 0 | -518841 |  |  |  |  | LCLR SHI 2024-27 Southland | 287938 | 60075798 | 132376
2024-09-12 | September 2024 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Taranaki) | Low cost / low risk improvements 2024-27 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Original upload included admin and now updating so allocation is admin exclusive | 0 | -725572 |  |  |  |  | LCLR SHI 2024-27 Taranaki | 287947 | 60075801 | 132377
2024-09-12 | September 2024 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Tasman) | Low cost / low risk improvements 2024-27 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Original upload included admin and now updating so allocation is admin exclusive | 0 | -144516 |  |  |  |  | LCLR SHI 2024-27 Tasman | 287955 | 60075804 | 132378
2024-09-12 | September 2024 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Waikato) | Low cost / low risk improvements 2024-27 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Original upload included admin and now updating so allocation is admin exclusive | 0 | -1896420 |  |  |  |  | LCLR SHI 2024-27 Waikato | 287964 | 60075807 | 132379
2024-09-12 | September 2024 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | NZTA (Wellington) | Low cost / low risk improvements 2024-27 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Original upload included admin and now updating so allocation is admin exclusive | 0 | -316485 | [5 empty] | 287970 | 60075810 | 132380
2024-09-12 | September 2024 Review | Cost Decrease | Walking and cycling improvements | Low cost / low risk improvements | NZTA (West Coast) | Low cost / low risk improvements 2024-27 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Original upload included admin and now updating so allocation is admin exclusive | 0 | -349109 |  |  |  |  | LCLR SHI 2024-27 West Coast | 287980 | 60075812 | 132381
2024-09-18 | September 2024 Review | Cost Decrease | Safety | Network and asset management | NZ Transport Agency | Asset Management Data Standard- State Highways | Implementation |  | ___ | VHMM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase change of -$7,759,525 from phase id 277727 to phase id 281639 - NDA AMDS Implementation +$5,624,855 | -7759525 | -7759525 |  |  |  | 4.4 | LR Maintenance part of funding, SAP item 60067372 | 277727 |  | 132418
2024-09-18 | September 2024 Review | Cost Increase | Safety | Network and asset management | NZ Transport Agency | Asset Management Data Standard- State Highways | Implementation |  | ___ | VHMM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase change of -$7,759,525 from phase id 277727 to phase id 281639 - NDA AMDS Implementation +$5,624,855 | 5624855 | 5624855 |  |  |  | 4.4 | SAP Item 60067460 | 281639 |  | 132419
2024-09-03 | September 2024 Review | Cost Increase | State highway operations | Network and asset management | NZTA (Gisborne) | 2024-27 NLTP funds management | Repayment |  | ___ | LHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Add 2024/25 offset | 1654546 | 1654546 | [5 empty] | 282285 |  | 132146
2024-09-03 | September 2024 Review | Cost Increase | State highway operations | Network and asset management | NZTA (Manawatu/Whanganui) | 2024-27 NLTP funds management | Repayment |  | ___ | LHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Add 2024/25 offset | 3809928 | 3809928 | [5 empty] | 279096 |  | 132149
2024-09-03 | September 2024 Review | Cost Increase | State highway operations | Network and asset management | NZTA (Northland) | 2024-27 NLTP funds management | Repayment |  | ___ | LHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Add 2024/25 offset | 398375 | 398375 | [5 empty] | 282286 |  | 132152
2024-09-03 | September 2024 Review | Cost Increase | State highway operations | Network and asset management | NZTA (Otago) | 2024-27 NLTP funds management | Repayment |  | ___ | LHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Add 2024/25 offset | 2088401 | 2088401 | [5 empty] | 282287 |  | 132153
2024-09-03 | September 2024 Review | Cost Increase | State highway operations | Network and asset management | NZTA (Taranaki) | 2024-27 NLTP funds management | Repayment |  | ___ | LHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Add 2024/25 offset | 54368 | 54368 | [5 empty] | 282289 |  | 132155
2024-09-03 | September 2024 Review | Cost Increase | State highway operations | Network and asset management | NZTA (Tasman) | 2024-27 NLTP funds management | Repayment |  | ___ | LHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Add 2024/25 offset | 3193879 | 3193879 | [5 empty] | 279273 |  | 132156
2024-09-06 | September 2024 Review | Cost Decrease | State highway improvements | New roads | NZTA (Auckland) | RoRS SH1 Papakura to Bombay | Implementation |  | ___ | VHHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow $61.45M to SAP Item ID - 60056232. | -61449865 | -61449865 |  |  | 2.5 |  | MCIP 60063236 | 278974 | 60063236 | 132242
2024-09-25 | September 2024 Review | Cost Decrease | Public transport services | Passenger services - ferry | Auckland Transport | AKL - Public Transport Service Improvements | Implementation |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | This is complete, new activity proposed for 2024 NLTP. | -1564157 | -797720 |  |  |  | 2.3 | 512.2776 | 277640 |  | 132605
2024-09-06 | September 2024 Review | Cost Decrease | Walking and cycling improvements | Property purchase (State highways) | NZTA (Auckland) | RoRS SH1 Papakura to Bombay | Property |  | ___ | VHHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow $26.167M to SAP Item ID 60056232. | -26167110 | -26167110 |  |  | 2.5 |  | MCIP Property Stage2 | 269800 | 60056231 | 132239
2024-09-20 | September 2024 Review | Cost Decrease | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH26 Onetai Stream Bridge Replacement | Implementation |  | ___ | MMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase transfer $3666 from construction phase 60052985 to pre imp 60052984and pre imp to close | -3996 | -3996 |  |  | 0 | 0 |  | 231694 | 60052985 | 132342
2024-09-20 | September 2024 Review | Cost Increase | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH26 Onetai Stream Bridge Replacement | Pre-implementation* |  | ___ | MMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase transfer $3666 from construction phase 60052985 to pre imp 60052984and pre imp to close | 3996 | 3996 |  |  | 0 | 0 |  | 231693 | 60052984 | 132343
2024-09-03 | September 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Auckland) | 2024-27 NLTP funds management | Repayment |  | ___ | LHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Add 2024/25 offset | 10823900 | 10823900 | [5 empty] | 278954 |  | 132142
2024-09-06 | September 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Auckland) | RoRS SH1 Papakura to Bombay | Implementation |  | ___ | VHHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow $26.167M from SAP Item ID 60056231 & $365M 60059443 (contingency) & $61.45M 60063236. | 452616974 | 452616974 |  |  | 2.5 |  | MCIP Implementation Stage | 269799 | 60056232 | 132241
2024-09-27 | September 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Auckland) | RoRS SH1 Papakura to Bombay | Implementation |  | ___ | VHHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer - Pls move $12,258,075 from CY of Implementation 60056232 to Pre-Imp 60057019 | -12748399 | -12748399 |  |  | 2.5 |  | MCIP Implementation Stage | 269799 | 60056232 | 132604
2024-09-27 | September 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Auckland) | RoRS SH1 Papakura to Bombay | Pre-implementation* |  | ___ | VHHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer - Pls move $12,258,075 from CY of Implementation 60056232 to Pre-Imp 60057019 | 12748398 | 12748398 |  |  | 2.5 |  | MCIP 60057019 | 270341 | 60057019 | 132620
2024-09-03 | September 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (BOP) | 2024-27 NLTP funds management | Repayment |  | ___ | LHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Add 2024/25 offset | 8066096 | 8066096 | [5 empty] | 278955 |  | 132143
2024-09-04 | September 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Canterbury) | 2024-27 NLTP funds management | Repayment |  | ___ | LHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Add 2024/25 offset | 10239347 | 10239347 | [5 empty] | 279052 |  | 132145
2024-09-23 | September 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Canterbury) | SH1 Templeton to Selwyn River | Implementation |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | To transfer $1,400,000 from Pre-imp (60076230) to Imp (60076232) phase to start the widening works from south of Dunns Crossing Road to Burnham. | 1526000 | 1526000 |  |  | 2.1 | 2.1 |  | 292493 | 60076232 | 132361
2024-09-23 | September 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Canterbury) | SH1 Templeton to Selwyn River | Pre-implementation* |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | To transfer $1,400,000 from Pre-imp (60076230) to Imp (60076232) phase to start the widening works from south of Dunns Crossing Road to Burnham. | -1526000 | -1526000 |  |  | 2.1 | 2.1 |  | 292491 | 60076230 | 132360
2024-09-23 | September 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Canterbury) | SH76 Brougham St Corridor Improvements | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | To transfer $171,636 from Imp (60056968) to Pre-imp phase (60032126) to close the imp phase. | -178501 | -178501 |  |  | 4 | 4 | MCIP 60056968 | 231610 | 60056968 | 132402
2024-09-23 | September 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Canterbury) | SH76 Brougham St Corridor Improvements | Pre-implementation* |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | To transfer $171,636 from Imp (60056968) to Pre-imp phase (60032126) to close the imp phase. | 178501 | 178501 |  |  | 4 | 4 | MCIP 60032126 | 231599 | 60032126 | 132403
2024-09-04 | September 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Hawkes Bay) | 2024-27 NLTP funds management | Repayment |  | ___ | LHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Add 2024/25 offset | 295316 | 295316 | [5 empty] | 279094 |  | 132147
2024-09-23 | September 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Northland) | SH1 Corridor Improvements - Whangarei | Construction |  | ___ | HMM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | project closure | -61722 | -61722 |  |  | 0 | 2.3 | 60218234 | 221192 | 60218234 | 132478
2024-09-03 | September 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Taranaki) | 2024-27 NLTP funds management | Repayment |  | ___ | LHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Add 2024/25 offset | 4984987 | 4984987 | [5 empty] | 288902 |  | 132154
2024-09-03 | September 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Waikato) | 2024-27 NLTP funds management | Repayment |  | ___ | LHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Add 2024/25 offset | 4932782 | 4932782 | [5 empty] | 279275 |  | 132157
2024-09-05 | September 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Waikato) | SH1 Wex Cambridge Section | Construction |  | ___ | M_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow | surplus 2.06m to aligned with board approval of 76m for SH1 WEx NgÄruawÄhia | -2069661 | -2069661 |  |  | 1.4 | 1.4 | 60203948 | 173265 | 60203948 | 132256
2024-09-05 | September 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Waikato) | Te Rapa Section | Construction |  | ___ | H_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow | surplus 11m to aligned with board approval of 76m for SH1 WEx NgÄruawÄhia | -11008891 | -11008891 |  |  | 0 | 1.4 |  | 268112 | 60054171 | 132255
2024-09-03 | September 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Wellington) | 2024-27 NLTP funds management | Repayment |  | ___ | LHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Add 2024/25 offset | 2738936 | 2738936 | [5 empty] | 279277 |  | 132158
2024-09-06 | September 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Wellington) | NZUP Programme Contingency | Implementation |  | ___ | M_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow $365M to 60056232- Papakura to Drury. | -365000000 | -365000000 |  |  | 0 | 0 |  | 271843 | 60059443 | 132243
2024-09-09 | September 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (West Coast) | RIO West Coast SL Bridge SFT IMPR | Implementation |  | ___ | M_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow | project to be closed as per PM | -1010743 | -1010743 |  |  | 1 | 1 | 60056046 | 269715 | 60056046 | 132230
2024-09-30 | September 2024 Review | Cost Decrease | Safety | Road policing | NZ Transport Agency | Safety cameras opex and capex | Implementation |  | ___ | VHMM | N |  | Approved | Approved by Manager, Treasury & Cash Flow |  | -11782874 | -11782874 |  |  | 1.1 | 1.1 | 60070818 | 284587 |  | 132613
2024-09-30 | September 2024 Review | Cost Decrease | Safety | Road policing | NZ Transport Agency | Safety cameras opex and capex | Implementation |  | ___ | VHMM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow to 60083605 | -27938289 | -27938289 |  |  | 1.1 | 1.1 | 60070819 | 284586 |  | 132611
2024-09-30 | September 2024 Review | Cost Decrease | Safety | Safety promotion, education and advertising | NZ Transport Agency | Road to Zero Public Awareness Campaign | Implementation |  | ___ | HHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Surplus - R2Z activity class is closed. | -3713358 | -3713358 |  |  |  | 2.2 | WBS 80002703 | 278947 |  | 132629
2024-09-30 | September 2024 Review | Cost Decrease | Safety | Safety promotion, education and advertising | NZ Transport Agency | RtZ Work-Related Road Safety | Implementation |  | ___ | MHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Surplus - new [phase created under new AC28. | -650000 | -650000 |  |  | 5.6 | 5.6 | SAP 60068924 | 283054 |  | 132630
2024-09-30 | September 2024 Review | Cost Decrease | Safety | Safety promotion, education and advertising | NZ Transport Agency | Safe Vehicles Programme 21-30 | Single-Stage Business Case |  | ___ | MHVH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Surplus- New phase created for 2024-27. | -3405896 | -3405896 |  |  | 17 | 17 | 80002708 (previously 80002367) | 280826 |  | 132628
2024-09-03 | September 2024 Review | Cost Increase | State highway pothole prevention | Sealed pavement maintenance | NZTA (BOP) | 2024-27 NLTP funds management | Implementation |  | ___ | LHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Add 2024/25 offset | 1875277 | 1875277 | [5 empty] | 288893 |  | 132144
2024-09-04 | September 2024 Review | Cost Increase | State highway pothole prevention | Sealed pavement maintenance | NZTA (Hawkes Bay) | 2024-27 NLTP funds management | Repayment |  | ___ | LHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Add 2024/25 offset | 6196 | 6196 | [5 empty] | 288901 |  | 132148
2024-09-03 | September 2024 Review | Cost Increase | State highway pothole prevention | Sealed pavement maintenance | NZTA (Wellington) | 2024-27 NLTP funds management | Repayment |  | ___ | LHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Add 2024/25 offset | 1851236 | 1851236 | [5 empty] | 288903 |  | 132159
2024-09-12 | September 2024 Review | Cost Increase | Walking and cycling improvements | Walking facilities | NZ Transport Agency | Innovating Streets Programme 2021-24 | Implementation |  | ___ | VHHVH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Moving funding from 24/25 of $211,836 from Napier CC (283079) - declared surplus) and moving this to NZTA programme management cost (280336) for $211,836.. Authorised by G Haines | 211836 | 211836 |  |  | 1 | 1 | WBS 80002706 | 280336 |  | 132391
2024-09-10 | September 2024 Review | Cost Decrease | Public transport services |  | Bay of Plenty Regional Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | -5867853 | -2992605 | [5 empty] | 292837 |  | 132280
2024-09-10 | September 2024 Review | Cost Decrease | Public transport infrastructure |  | Bay of Plenty Regional Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | -243242 | -124053 | [5 empty] | 292838 |  | 132281
2024-09-09 | September 2024 Review | Cost Decrease | Safety |  | Central Hawkes Bay District Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -769692 | -454118 | [5 empty] | 292802 |  | 132248
2024-09-09 | September 2024 Review | Cost Decrease | Local road pothole prevention |  | Central Hawkes Bay District Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -1572576 | -927820 | [5 empty] | 292801 |  | 132247
2024-09-09 | September 2024 Review | Cost Decrease | Public transport services |  | Environment Canterbury | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -17160440 | -8751824 | [5 empty] | 292887 |  | 132249
2024-09-09 | September 2024 Review | Cost Decrease | Public transport infrastructure |  | Environment Canterbury | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -957678 | -488416 | [5 empty] | 292888 |  | 132250
2024-09-04 | September 2024 Review | Cost Decrease | Safety |  | Far North District Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Council can claim from programme funding. | -2579659 | -1831558 | [5 empty] | 292781 |  | 132181
2024-09-04 | September 2024 Review | Cost Decrease | Local road pothole prevention |  | Far North District Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Council can claim from programme funding. | -5308256 | -3768862 | [5 empty] | 292780 |  | 132182
2024-09-09 | September 2024 Review | Cost Decrease | Local road pothole prevention |  | Hastings District Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -3393658 | -1798639 | [5 empty] | 292868 |  | 132251
2024-09-09 | September 2024 Review | Cost Decrease | Safety |  | Hastings District Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -1592702 | -844132 | [5 empty] | 292873 |  | 132252
2024-09-10 | September 2024 Review | Cost Decrease | Public transport infrastructure |  | Horizons Manawatu | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | -54667 | -27880 | [5 empty] | 292882 |  | 132318
2024-09-20 | September 2024 Review | Cost Decrease | Local road pothole prevention |  | Manawatu District Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -1265368 | -645338 | [5 empty] | 292821 |  | 132393
2024-09-20 | September 2024 Review | Cost Decrease | Safety |  | Manawatu District Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -839689 | -428241 | [5 empty] | 292822 |  | 132394
2024-09-13 | September 2024 Review | Cost Decrease | Safety |  | NZ Transport Agency | SIP - Programme Management | Pre-implementation* |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Surplus back to NLTF as funds not required. | -2543103 | -2543103 |  |  | 2.2 | 2.2 | 60079525 - Louise Capes | 292841 |  | 132406
2024-09-30 | September 2024 Review | Cost Decrease | State highway improvements |  | NZTA (BOP) | BOP Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $390000 ex admin from 60075222 to 60083170 | -425100 | -425100 |  |  |  | 1 | 60075222 BOP Share VFM Safety Imp Prog | 289802 | 60075222 | 132633
2024-09-30 | September 2024 Review | Cost Decrease | State highway improvements |  | NZTA (Otago) | OTA Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $276000 ex admin from 60075581 to 60083227 | -300840 | -300840 |  |  |  | 1 | 60075581 OTA Share VFM Safety Imp Prog | 289831 | 60075581 | 132634
2024-09-20 | September 2024 Review | Cost Decrease | State highway improvements |  | NZTA (Wellington) | WGTN Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Correction of allocation as per approval of $8,081 inc admin See supporting documents email. | -10698 | -10698 |  |  |  | 1 | 60075638 WGTN Share VFM Safety Imp Prog | 289923 | 60075638 | 132385
2024-09-27 | September 2024 Review | Cost Decrease | State highway improvements |  | NZTA (Wellington) | WGTN Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $861000 ex admin from 60075638 to 60083367 | -938490 | -938490 |  |  |  | 1 | 60075638 WGTN Share VFM Safety Imp Prog | 289923 | 60075638 | 132632
2024-09-20 | September 2024 Review | Cost Decrease | Safety |  | New Plymouth District Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -1422470 | -725460 | [5 empty] | 292850 |  | 132396
2024-09-20 | September 2024 Review | Cost Decrease | Local road pothole prevention |  | New Plymouth District Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -2733126 | -1393894 | [5 empty] | 292849 |  | 132395
2024-09-10 | September 2024 Review | Cost Decrease | Safety |  | South Taranaki District Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | -951089 | -618208 | [5 empty] | 292806 |  | 132320
2024-09-10 | September 2024 Review | Cost Decrease | Local road pothole prevention |  | South Taranaki District Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | -1929411 | -1254117 | [5 empty] | 292805 |  | 132319
2024-09-20 | September 2024 Review | Cost Decrease | Public transport services |  | Waikato Regional Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -4721655 | -2408044 | [5 empty] | 292835 |  | 132424
2024-09-10 | September 2024 Review | Cost Decrease | Public transport infrastructure |  | Waikato Regional Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | -583387 | -297527 | [5 empty] | 292836 |  | 132321
2024-09-27 | September 2024 Review | Cost Decrease | Safety |  | Wairoa District Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Council can claim from programme funding. | -725385 | -544039 | [5 empty] | 292839 |  | 132623
2024-09-27 | September 2024 Review | Cost Decrease | Local road pothole prevention |  | Wairoa District Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Council can claim from programme funding. | -1619845 | -1214884 | [5 empty] | 292840 |  | 132624