## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Phase Label | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Decision Status | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR | Your Phase reference | TIO Phase id | SAP item id | TIO Request id
2024-10-02 | October 2024 Review | New approval | External funding | Emergency works | Gisborne District Council | EW Cyclone Gabrielle | Construction | Data Validation - repay NIWE | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | New phase created to replace phase id 292771 - funding source was incorrect. It should have been NIWE Response. | -1191481 | -1191481 | [5 empty] | 293314 |  | 132664
2024-10-21 | October 2024 Review | New approval | Local road operations | Emergency works | Gisborne District Council | EW June 2024 Rain event | Construction | Immediate Response costs | ___ |  | N |  | Approved | Approved by National Manager, Programmes and Standards (Transport Services) | Funding required to reinstate access and other minor response works as permitted under WC141 | 1937266 | 1317341 | [5 empty] | 292876 |  | 132245
2024-10-21 | October 2024 Review | New approval | Local road operations | Emergency works | Manawatu District Council | EW May 2023 - Manawatu DC | Construction | Recovery (Normal FAR+20%) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Funds to move from normal FAR to higher FAR. Adjust emergency works funding (Higher FAR). | 802283 | 569621 |  |  |  |  | Recovery phase for May 2023 weather event (Normal FAR+20%) | 293375 |  | 132850
2024-10-21 | October 2024 Review | New approval | Local road operations | Emergency works | Tararua District Council | EW - Tararua DC June 2023 | Construction | Initial Response & Recovery (Normal +20%) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Board approved EW policy is to apply Higher FAR (plus 10% for Tararua) to the NIWE Recovery phases. This activity will be split between Normal and Higher FAR. | 125001 | 116251 | [5 empty] | 293376 |  | 132860
2024-10-03 | October 2024 Review | New approval | Local road operations | Emergency works | Thames-Coromandel District Council | EW - Thames-Coromandel DC May 2024 | Construction | Permanent Reinstatement MSQA and Construction | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | Investment is required to complete response and recovery works to restore LoS that existed prior to this weather event as detailed in the attached funding approval paper. | 162000 | 82620 | [5 empty] | 292673 |  | 129000
2024-10-03 | October 2024 Review | New approval | Local road operations | Emergency works | Thames-Coromandel District Council | EW - Thames-Coromandel DC May 2024 | Construction | Initial Response, Investigation and Design | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | Investment is required to complete response and recovery works to restore LoS that existed prior to this weather event as detailed in the attached funding approval paper. | 306767 | 156451 | [5 empty] | 292672 |  | 128999
2024-10-02 | October 2024 Review | New approval | External funding | Emergency works | Waikato District Council | EW - Waikato DC Storm Damage Jan-Feb 2023 | Construction | 23/24 Phase 2 - I&D @ High FAR | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Replacing phase id 293002 due to incorrect funding source. | 66278 | 47057 | [5 empty] | 293001 |  | 132663
2024-10-17 | October 2024 Review | New approval | External funding | Emergency works | Waitomo District Council | EW - Waitomo DC January 2023 (Auckland Anniversary) | Construction | NIWE 2023 Phase Two - I&D and Construction | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | Investment required to complete recovery works / restore LoS that existed prior to the weather event as detailed in the attached funding approval document. | 4079000 | 4079000 |  |  |  |  | NIWE 2023 Phase Two - I&D and Construction | 293027 |  | 132519
2024-10-09 | October 2024 Review | New approval | External funding | Emergency works | Western BoP District Council | EW - Western Bay of Plenty DC January & February 2023 (NIWE) | Construction | No4 Road Bridge Replacement (High FAR +20%) | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Investment required to reinstate the No. 4 Road bridge destroyed during this weather event. | 4888323 | 3470709 | [5 empty] | 293158 |  | 132299
2024-10-09 | October 2024 Review | New approval | External funding | Emergency works | Western BoP District Council | EW - Western Bay of Plenty DC January & February 2023 (NIWE) | Construction | No 4 Road bridge replacement NIWE | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Investment required to reinstate the No. 4 Road bridge destroyed during this weather event. | 1811677 | 923955 | [5 empty] | 292800 |  | 131131
2024-10-08 | October 2024 Review | New approval | State highway improvements | Road improvements | NZTA (Auckland) | AKLD VfM Safety Imp â€“ Small Projects | Implementation | AKLD VfM Safety Imp - Schools (Imp) | MHH | MHH | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $5014 ex admin from 60075303 to 60083162 AND $80900 ex admin from 60075303 to 60083164 | 5465 | 5465 |  |  | 6 | 6 | AKLD VfM Safety Imp - Schools (Imp) | 292891 | 60083162 | 132753
2024-10-08 | October 2024 Review | New approval | State highway improvements | Road improvements | NZTA (BOP) | BOP VfM Safety Imp â€“ Small Projects | Implementation | BOP VfM Safety Imp â€“ Schools (Imp) | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $15814 ex admin from 60075222 to 60083169 AND $903500 ex admin from 60075222 to 60083171 | 17237 | 17237 |  |  | 6 | 6 | BOP VfM Safety Imp â€“ Schools (Imp) | 292894 | 60083169 | 132772
2024-10-08 | October 2024 Review | New approval | State highway improvements | Road improvements | NZTA (Canterbury) | CAN VfM Safety Imp â€“ Small Projects | Implementation | CAN VfM Safety Imp â€“ Schools | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $94214 ex admin from 60075600 to 60083176 AND $397350 ex admin from 60075600 to 60083178 | 102693 | 102693 |  |  | 6 | 6 | CAN VfM Safety Imp â€“ Schools | 292897 | 60083176 | 132774
2024-10-08 | October 2024 Review | New approval | State highway improvements | Road improvements | NZTA (Gisborne) | GIS VfM Safety Imp â€“ Small Projects | Implementation | GIS VfM Safety Imp â€“ Schools | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $3814 ex admin from 60075397 to 60083183 AND $75000 ex admin from 60075397 to 60083185 | 4157 | 4157 |  |  | 6 | 6 | GIS VfM Safety Imp â€“ Schools | 292902 | 60083183 | 132755
2024-10-08 | October 2024 Review | New approval | State highway improvements | Road improvements | NZTA (Hawkes Bay) | HAWK VfM Safety Imp â€“ Small Projects | Implementation | HAWK VfM Safety Imp â€“ Schools | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $8614 ex admin from 60075469 to 60083190 AND $300000 ex admin from 60075469 to 60083192 | 9389 | 9389 |  |  | 6 | 6 | HAWK VfM Safety Imp â€“ Schools | 292906 | 60083190 | 132757
2024-10-08 | October 2024 Review | New approval | State highway improvements | Road improvements | NZTA (Manawatu/Whanganui) | MNWI VfM Safety Imp â€“ Small Projects | Implementation | MNWI VfM Safety Imp â€“ Schools | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $85814 ex admin from 60075295 to 60083204 AND $335000 ex admin from 60075295 to 60083206 | 93537 | 93537 |  |  | 6 | 6 | MNWI VfM Safety Imp â€“ Schools | 292914 | 60083204 | 132726
2024-10-08 | October 2024 Review | New approval | State highway improvements | Road improvements | NZTA (Marlborough) | MARL VfM Safety Imp â€“ Small Projects | Implementation | MARL VfM Safety Imp â€“ Schools | MHH | HHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $7414 ex admin from 60075526 to 60083198 AND $1110000 ex admin from 60075526 to 60083159 | 8081 | 8081 |  |  | 6 | 6 | MARL VfM Safety Imp â€“ Schools | 292909 | 60083198 | 132759
2024-10-08 | October 2024 Review | New approval | State highway improvements | Road improvements | NZTA (Nelson) | NEL VfM Safety Imp â€“ Small Projects | Implementation | NEL VfM Safety Imp â€“ Schools | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $3814 ex admin from 60075473 to 60083211 AND $5000 ex admin from 60075437 to 60083213 | 4157 | 4157 |  |  | 6 | 6 | NEL VfM Safety Imp â€“ Schools | 292918 | 60083211 | 132728
2024-10-08 | October 2024 Review | New approval | State highway improvements | Road improvements | NZTA (Northland) | NTLD VfM Safety Imp â€“ Small Projects | Implementation | NTLD VfM Safety Imp â€“ Schools | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $9814 ex admin from 60075196 to 60083219 AND $2815660 ex admin from 60075196 to 60083221 | 10697 | 10697 |  |  | 6 | 6 | NTLD VfM Safety Imp â€“ Schools | 292922 | 60083219 | 132730
2024-10-08 | October 2024 Review | New approval | State highway improvements | Road improvements | NZTA (Otago) | OTA VfM Safety Imp â€“ Small Projects | Implementation | OTA VfM Safety Imp â€“ Schools | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $25414 ex admin from 60075581 to 60083226 AND $40000 ex admin from 60075581 to 60083228 | 27701 | 27701 |  |  | 6 | 6 | OTA VfM Safety Imp â€“ Schools | 292926 | 60083226 | 132732
2024-10-08 | October 2024 Review | New approval | State highway improvements | Road improvements | NZTA (Southland) | STLD VfM Safety Imp â€“ Small Projects | Implementation | STLD VfM Safety Imp â€“ Schools | MHL | MHL | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $23014 ex admin from 60075556 to 60083234 AND $5000 ex admin from 60075556 to 60083236 | 25085 | 25085 |  |  | 6 | 6 | STLD VfM Safety Imp â€“ Schools | 292930 | 60083234 | 132734
2024-10-08 | October 2024 Review | New approval | State highway improvements | Road improvements | NZTA (Taranaki) | TAR VfM Safety Imp â€“ Small Projects | Implementation | TAR VfM Safety Imp â€“ Schools | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $21814 ex admin from 60075244 to 60083242 | 23777 | 23777 |  |  | 6 | 6 | TAR VfM Safety Imp â€“ Schools | 292934 | 60083242 | 132736
2024-10-08 | October 2024 Review | New approval | State highway improvements | Road improvements | NZTA (Tasman) | TAS VfM Safety Imp â€“ Small Projects | Implementation | TAS VfM Safety Imp â€“ Schools | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $7414 ex admin from 60075545 to 60083249 | 8081 | 8081 |  |  | 6 | 6 | TAS VfM Safety Imp â€“ Schools | 292938 | 60083249 | 132737
2024-10-08 | October 2024 Review | New approval | State highway improvements | Road improvements | NZTA (Waikato) | WAI VfM Safety Imp â€“ Small Projects | Implementation | WAI VfM Safety Imp â€“ Schools | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $104214 ex admin from 60075459 to 60083256 AND $1678000 ex admin from 60075459 to 60083258 | 113593 | 113593 |  |  | 6 | 6 | WAI VfM Safety Imp â€“ Schools | 292942 | 60083256 | 132738
2024-10-08 | October 2024 Review | New approval | State highway improvements | Road improvements | NZTA (Wellington) | WGTN VfM Safety Imp â€“ Small Projects | Implementation | WGTN VfM Safety Imp â€“ Schools | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $7414 ex admin from 60075638 to 60083264 AND $135000 ex admin from 60075638 to 60083266 | 8081 | 8081 |  |  | 6 | 6 | WGTN VfM Safety Imp â€“ Schools | 292946 | 60083264 | 132740
2024-10-08 | October 2024 Review | New approval | State highway improvements | Road improvements | NZTA (West Coast) | WTCT VfM Safety Imp â€“ Small Projects | Implementation | WTCT VfM Safety Imp â€“ Schools | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $9814 ex admin from 60075625 to 60083271 AND $142000 ex admin from 60075625 to 60083273 | 10697 | 10697 |  |  | 6 | 6 | WTCT VfM Safety Imp â€“ Schools | 292951 | 60083271 | 132742
2024-10-30 | October 2024 Review | New approval | Local road improvements |  | Christchurch City Council | Pages Road Bridge Renewal | Single-Stage Business Case |  | ___ | HHM | N |  | Approved with conditions | Approved with conditions by Chief Financial Officer | at a shared phase cost of $341,000 and funding for property purchase at a shared phase cost of $29,000 = $370,000 @ 51% | 370000 | 188700 | DBC is capped at $341,000. Any future cost increase request from Christchurch City Council may not be supported. |  |  | 15 |  | 290625 |  | 132668
2024-10-31 | October 2024 Review | New approval | Public transport infrastructure |  | Greater Wellington | CERF-Decarbonising the PT Bus Fleet - Lyall Bay Stage 1 | Implementation |  | ___ | VHHM | N |  | Approved | Approved by Minister for Crown Appropriation | This has a signed agreement as per the process for the CERF Bus Decarbonisation Contestable Fund. Work category has been corrected and cost profile reflects latest contract details. | 21250981 | 10838000 |  |  |  |  | funding depot stage 1 | 293412 |  | 132930
2024-10-21 | October 2024 Review | New approval | Public transport services |  | NZ Transport Agency | Rail Safety Regulator: Road-Rail Interaction | Implementation |  | ___ | MMM | N |  | Approved | Approved by Chief Financial Officer | These activities support sector innovation, improve value and efficiency by being implemented nationally, and align with the GPS | 2250000 | 2250000 |  |  | 1 | 1 | 60083499 Rail Regulation 2024-27 | 292846 |  | 131407
2024-10-24 | October 2024 Review | New approval | Safety |  | NZ Transport Agency | Road Safety Management | Implementation |  | ___ | MHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Three year NDA programme for 2024-27 not supported by ELT. Approve $600k in 2024/25 estimated to meet existing contractual obligations and permanent staff costs being redeployed from System Leadership. | 654000 | 654000 |  |  | 8 | 8 | Road Safety Management 2024-27 programme | 289181 |  | 132912
2024-10-24 | October 2024 Review | New approval | Safety |  | NZ Transport Agency | RtZ Work-Related Road Safety | Implementation |  | ___ | MHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Changed from R2Z activity class to Safety activity for 2024-27. | 1635000 | 1635000 |  |  | 5.6 | 5.6 | AC28 | 293098 |  | 132141
2024-10-24 | October 2024 Review | New approval | Safety |  | NZ Transport Agency | Safe Vehicles Programme 21-30 | Implementation |  | ___ | MHVH | N |  | Approved | Approved by Chief Financial Officer | R2Z activity class now changed to Safety activity class for 2024-27. | 3070422 | 3070422 |  |  | 17 | 17 | Initiaitive No. 170202024 Project Id: 60083006 | 289563 |  | 131189
2024-10-24 | October 2024 Review | New approval | Safety |  | NZ Transport Agency | Speed Management Planning | Implementation |  | ___ | VHHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow $5M (excl. admin) from 60070595 to 60084641. | 5450000 | 5450000 |  |  |  | 1.1 | Develop land transport rule and guide. | 292863 |  | 132923
2024-10-24 | October 2024 Review | New approval | Safety |  | NZ Transport Agency | Speed Management Planning | Implementation |  | ___ | VHHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow $2M from Speed Management Planning 2021-24 to 2024-27. | 2180000 | 2180000 |  |  |  | 1.1 | 60084640 | 293382 |  | 132924
2024-10-09 | October 2024 Review | New approval | Investment management (incl. Transport Planning) |  | NZ Transport Agency | Time of Use Charging | Programme business case |  | ___ | VHHVH | N |  | Approved | Approved by Chief Financial Officer | TouCh is a strategic component in the governmentâ€™s drive to develop a more sustainable revenue system that can help optimise investment in the transport network. The government has mandated NZTA to lead the development of frameworks and systems for time of use charging to enable the design and implementation of schemes with local councils. | 194459 | 194459 |  |  |  |  | SAP: 60083483 | 292848 | 60083483 | 131404
2024-10-02 | October 2024 Review | New approval | State highway improvements |  | NZTA (Auckland) | RoNS Mill Road | Detailed Business Case |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer - Pls move $2,801,400 from 60075346 to 60083893 | 3053526 | 3053526 |  |  | 1.2 | 1.2 |  | 293141 | 60083893 | 132323
2024-10-07 | October 2024 Review | New approval | State highway improvements |  | NZTA (BOP) | EOL SH36 Hauraki Stream Culvert | Pre-implementation* |  | ___ | HHH | N |  | Approved | Approved by Chief Financial Officer | The renewal of Hauraki Stream Culvert will provide an effective and efficient long-term sustainable solution for the safe continuity of SH36. The activity has been assessed as having priority 2 (H/H/H). The project meets the requirements of section 20 of the Land Transport Management Act 2003 | 1453000 | 1453000 |  |  |  | 4 |  | 290356 | 60073591 | 132689
2024-10-24 | October 2024 Review | New approval | State highway improvements |  | NZTA (Manawatu/Whanganui) | 2024-27 NLTP funds management | Repayment |  | ___ | LHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Prior year overspent funds show as a negative allocation in the current financial year. This activity offsets the negative allocation. | 1892065 | 1892065 | [5 empty] | 293381 |  | 132922
2024-10-07 | October 2024 Review | New approval | State highway improvements |  | NZTA (Manawatu/Whanganui) | EOL SH43 Kururau Stream Water Drive | Pre-implementation* |  | ___ | HHH | N |  | Approved | Approved by Chief Financial Officer | The construction of a new bridge in this location will provide an effective and efficient long-term sustainable solution for the safe continuity of SH43. The BCR for this initiative is N/A. The project meets the requirements of section 20 of the Land Transport Management Act 2003 | 149875 | 149875 |  |  |  | 1 |  | 290339 | 60073578 | 132684
2024-10-07 | October 2024 Review | New approval | State highway improvements |  | NZTA (Taranaki) | EOL SH3 Mangapepeki No. 2 Culvert | Pre-implementation* |  | ___ | HHH | N |  | Approved | Approved by Chief Financial Officer | The construction of a new bridge in this location will provide an effective and efficient long-term sustainable solution for the safe continuity of SH3. BCR for this initiative is N/A. The project meets the requirements of section 20 of the Land Transport Management Act 2003 | 89925 | 89925 |  |  |  | 1 |  | 290344 | 60073589 | 132690
2024-10-23 | October 2024 Review | New approval | State highway improvements |  | NZTA (Tasman) | SH6 Hope Saddle to SH65 Higgins Bluff | Pre-implementation* |  | ___ | HHL | N |  | Approved | Approved by Chief Financial Officer | Progressing this project to the pre-implementation will contribute to improved resilience on the SH6 Hope Saddle to SH65 Higgins Bluff corridor | 1600000 | 1600000 |  |  |  | 1 |  | 289906 | 60073350 | 132778
2024-10-08 | October 2024 Review | New approval | State highway improvements |  | NZTA (Waikato) | EOL SH25 Ramarama Stream Bridge | Pre-implementation* |  | ___ | HHH | N |  | Approved | Approved by Chief Financial Officer | The construction of a new bridge in this location will provide an effective and efficient long-term resilient solution for the safe continuity of SH25. The activity forms part of a road maintenance programme and is prioritised under the NZ Transport Agency Investment Prioritisation Method (IPM). The activity has a IPM rating of H-HH, priority 2. The project meets the requirements of section 20 of the Land Transport Management Act 2003 | 1304500 | 1304500 |  |  |  | 1 |  | 290355 | 60073573 | 132683
2024-10-08 | October 2024 Review | New approval | State highway improvements |  | NZTA (Waikato) | EOL SH27 Ohinekaua Stream Bridge | Pre-implementation* |  | ___ | HHH | N |  | Approved | Approved by Chief Financial Officer | The renewal of Ohinekaua Stream Bridge will provide an effective and efficient long-term sustainable solution for the safe continuity of SH27. The activity has been assessed as having priority 2 (H/H/H). The project meets the requirements of section 20 of the Land Transport Management Act 2003. | 631700 | 631700 |  |  |  | 1 |  | 290349 | 60073598 | 132682
2024-10-08 | October 2024 Review | New approval | State highway improvements |  | NZTA (Waikato) | SH25A rebuild improvements | Implementation |  | ___ | VHHL | N |  | Approved | Approved by Minister for Crown Appropriation | Correcting funding source | 1 | 1 |  |  | 0.5 | 0.5 |  | 292674 | 60075151 | 132760
2024-10-22 | October 2024 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | NZTA (Wellington) | Ngauranga to Petone Walking and Cycling Link | Implementation |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | To correct 2023-24 spend. | 0 | 0 |  |  | 0 | 1.2 |  | 250467 | 60045954 | 132880
2024-10-22 | October 2024 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | NZTA (Wellington) | Ngauranga to Petone Walking and Cycling Link | Implementation |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | To correct 2023-24 spend. | 0 | 0 |  |  | 0 | 1.2 |  | 284556 | 60045954 | 132884
2024-10-01 | October 2024 Review | Cash flow adjustment | External funding | Emergency works | Auckland Transport | EW - AT Anniversary Weekend & Cyclone Gabrielle 2023 | Construction | E/W - Reinstatement @ 71% (NIWE) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Fixing National Office Recommendation - To complete AT's E/W reinstatement delivery programme moderated with NZTA counterparts and approved by acting CFO ($34M but in system - $39.9M). | 0 | 0 |  |  |  |  | 141.2901 | 291177 |  | 132651
2024-10-04 | October 2024 Review | Cash flow adjustment | Local road operations | Emergency works | Auckland Transport | EW - AT Storm Event 9 May 2023 | Construction | E/W - Storm Event 9 May | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Approving allocation to align with NZTA EW policy. | 0 | 0 |  |  |  |  | 141.2846 | 284581 |  | 132421
2024-10-04 | October 2024 Review | Cash flow adjustment | Local road operations | Emergency works | Gisborne District Council | EW September 2023 Rain event | Construction | Immediate Response and Recovery costs | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | claiming complete project finished -return surplus funds | 0 | 0 | [5 empty] | 291647 |  | 132606
2024-10-16 | October 2024 Review | Cash flow adjustment | Local road operations | Financial grants | Auckland Transport | TNFG - Housing Infrastructure Fund (HIF) - Offset Payment | Implementation |  | ___ | H_H | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Updating cashflow to reflect the HIF Agreement (signed Oct 24). | 0 | 0 |  |  | 1 | 1 | 171.2665 | 266464 |  | 132789
2024-10-16 | October 2024 Review | Cash flow adjustment | Local road improvements | New roads | Auckland Transport | TNFG - North West HIF | Implementation |  | ___ | HLH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Updating cashflow to reflect current PM's projections and to align with HIF Agreement (signed Oct 24). | 0 | 0 |  |  | 5 | 1.4 | 323.264 | 263982 |  | 132786
2024-10-16 | October 2024 Review | Cash flow adjustment | Local road improvements | New roads | Auckland Transport | TNFG - North West HIF | Repayment |  | ___ | HLH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Updating cashflow to reflect the HIF Agreement (signed Oct 24). | 0 | 0 |  |  | 5 | 1.4 | 323.2665 | 266462 |  | 132788
2024-10-04 | October 2024 Review | Cash flow adjustment | Walking and cycling improvements | Property purchase (State highways) | NZTA (Auckland) | RoRS SH1 Papakura to Bombay | Property |  | ___ | VHHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow Adjustment - Pls move $700,200 from CY 24/25 to FY2 26/27. | 0 | 0 |  |  | 2.5 |  | MCIP Property Stage2 | 269800 | 60056231 | 132400
2024-10-04 | October 2024 Review | Cash flow adjustment | Walking and cycling improvements | Property purchase (State highways) | NZTA (Auckland) | RoRS SH1 Papakura to Bombay | Property |  | ___ | VHHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow Adjustment - Pls move $4,950,000 from CY 24/25 to next FY1 25/26. | 0 | 0 |  |  | 2.5 |  | Property Stage 2 SH1 Drury to Bombay - NLTF funded | 289266 | 60072763 | 132401
2024-10-16 | October 2024 Review | Cash flow adjustment | Safety | Property purchase (local roads) | Auckland Transport | TNFG - North West HIF | Property |  | ___ | HLH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Updating cashflow to reflect current PM's projections and to align with HIF Agreement (signed Oct 24). | 0 | 0 |  |  | 5 | 1.4 | 332.264 | 263983 |  | 132787
2024-10-04 | October 2024 Review | Cash flow adjustment | State highway improvements | Resilience improvements | NZTA (Southland) | TRF-STLD-SH1 Ocean Beach, Bluff | Implementation |  | ___ | LLVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | To move $590,000 from CY to Y1 as Imp phase is not expected to start until next FY. | 0 | 0 |  |  |  | 0 |  | 291457 | 60074848 | 132608
2024-10-21 | October 2024 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (BOP) | CIP SH30 Eastern Corridor, Rotorua | Construction |  | ___ | H_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Correcting error that occurred during EOY Close. | 0 | 0 |  |  | 0 | 4.1 |  | 271547 | 60059176 | 130843
2024-10-21 | October 2024 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | SH1 ETA Corridor Improvements | Implementation |  | ___ | VHML | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow adjustment to match allocation with forecast of respective financial years. | 0 | 0 |  |  | 2.6 | 2.6 |  | 292517 | 60076248 | 132829
2024-10-21 | October 2024 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | SH1 ETA Corridor Improvements | Implementation |  | ___ | VHML | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow adjustment to match allocation with forecast of respective financial years. | -2 | -2 |  |  | 2.6 | 2.6 |  | 292518 | 60076249 | 132830
2024-10-04 | October 2024 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | SH25A rebuild improvements | Implementation |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | close phase | 0 | 0 |  |  | 0.5 | 0.5 | SH25A Resilience Implementation Improvements | 290301 | 60073547 | 131316
2024-10-02 | October 2024 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Wellington) | NZUP Programme Contingency | Implementation |  | ___ | M_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Move allocation to after Y28 to avoid Portfolio Plan which is a 3 year plan. | 0 | 0 |  |  | 0 | 0 |  | 271843 | 60059443 | 132470
2024-10-16 | October 2024 Review | Cash flow adjustment | Road to Zero | Safety promotion, education and advertising | NZTA (Canterbury) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  |  |  | 60065103 | 273398 | 60065103 | 132776
2024-10-16 | October 2024 Review | Cash flow adjustment | Road to Zero | Safety promotion, education and advertising | NZTA (Wellington) | Road Safety Promotion 2021-24 | Implementation |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | project closure | 0 | 0 | [5 empty] | 273372 | 60065085 | 132785
2024-10-21 | October 2024 Review | Cash flow adjustment | Walking and cycling improvements | Walking facilities | NZTA (Otago) | SH6 SH8B SH8 Gibbston to Clyde Corridor Imps | Pre-implementation* |  | ___ | MML | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Project Close | -98 | -98 |  |  | 9.7 | 0.4 |  | 281000 | 60056371 | 132779
2024-10-02 | October 2024 Review | Cash flow adjustment | Public transport services |  | Auckland Transport | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | 0 | 0 |  |  |  |  | 511.1105 | 292763 |  | 132660
2024-10-02 | October 2024 Review | Cash flow adjustment | Safety |  | Auckland Transport | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | 0 | 0 |  |  |  |  | 151.1102 | 292761 |  | 132658
2024-10-02 | October 2024 Review | Cash flow adjustment | Local road pothole prevention |  | Auckland Transport | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | 0 | 0 |  |  |  |  | 111.1101 | 292762 |  | 132659
2024-10-02 | October 2024 Review | Cash flow adjustment | State highway improvements |  | NZTA (Auckland) | RoNS Mill Road | Detailed Business Case |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Funding approval has not flowed through to SAP. | 0 | 0 |  |  | 1.2 | 1.2 |  | 293141 | 60083893 | 132669
2024-10-04 | October 2024 Review | Cost Increase | Investment management (incl. Transport Planning) | Activity management planning improvement | NZ Transport Agency | AM Improvement for 18-21 NLTP | Programme business case |  | H__ | H__ | N | 3 | Approved | Approved by Chief Financial Officer (CFO) | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete; increase of admin cost + over spend. project is now complete | 81960 | 81960 |  |  |  |  | 60053329 | 267446 |  | 132625
2024-10-04 | October 2024 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Manawatu District Council | Walking and Cycling Improvements package | Implementation |  | ___ | M_H | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -67340 | -34343 |  |  | 0 | 6.5 |  | 246049 |  | 132398
2024-10-18 | October 2024 Review | Cost Increase | Local road pothole prevention | Drainage renewals | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | CHBDC identified an over claim after the end of financial year, this adjustment is required to repay the value over claimed. | 0 | 49524 | [5 empty] | 285286 |  | 132719
2024-10-21 | October 2024 Review | Cost Increase | External funding | Emergency works | Gisborne District Council | EW Cyclone Gabrielle | Construction | Data Validation - repay NIWE | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving funds to new phase 293314. Old phase funding source was incorrect. It should have been NIWE Response. | 1191481 | 1191481 | [5 empty] | 292771 |  | 132665
2024-10-22 | October 2024 Review | Cost Increase | Local road operations | Emergency works | Gisborne District Council | EW June 2024 Rain event | Construction | Immediate Response costs | ___ |  | N |  | Approved | Approved by National Manager, Programmes and Standards (Transport Services) | Qualifies for higher FAR rate. Initially approved at normal FAR. | 0 | 387453 | [5 empty] | 292876 |  | 132877
2024-10-21 | October 2024 Review | Cost Increase | Local road operations | Emergency works | Gisborne District Council | EW: November 2023 Emergency Works | Construction | Initial Response | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Higher FAR should be 88% | 0 | 11187 | [5 empty] | 291117 |  | 132846
2024-10-21 | October 2024 Review | Cost Increase | Local road operations | Emergency works | Hutt City Council | Emergency works - Heavy rain event Aug 2022 | Construction | Recovery | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Increased to match EW threshold. Higher FAR phase will be reduced and set to Higher FAR. | 49946 | 25472 | [5 empty] | 291200 |  | 132848
2024-10-21 | October 2024 Review | Cost Increase | Local road operations | Emergency works | Hutt City Council | Emergency works - Heavy rain event Aug 2022 | Construction | Recovery (Normal FAR+20%) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Funds moved to Normal FAR phase to match EW threshold. Updated this phase to Higher FAR. | -49946 | 19444 |  |  |  |  | (Normal FAR+20%) | 292656 |  | 132849
2024-10-21 | October 2024 Review | Cost Increase | External funding | Emergency works | Manawatu District Council | EW - Cyclone Gabrielle February 2023 | Construction | Recovery Phase (NIWE) - Bridge (N+20%) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | NIWE Recovery FAR policy is to use Higher FAR where possible. | 0 | 252603 | [5 empty] | 291500 |  | 132853
2024-10-21 | October 2024 Review | Cost Decrease | Local road operations | Emergency works | Manawatu District Council | EW May 2023 - Manawatu DC | Construction | Recovery | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) |  | -802283 | -409164 |  |  |  |  | Recovery phase for May 2023 weather event | 284580 |  | 132851
2024-10-09 | October 2024 Review | Cost Decrease | External funding | Emergency works | NZTA (BOP) | EW BOP Extreme HR 20230127 | Construction | NIWE Recovery | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Closure supported by AIA Malcolme Flatterey-Dongohue | -138535 | -138535 | [5 empty] | 291642 | 60069770 | 132238
2024-10-02 | October 2024 Review | Cost Decrease | State highway operations | Emergency works | NZTA (Canterbury) | Kaikoura Nov 2016 EQ: Reinstatement SH1 | Construction | Construction NLTF | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Reversal of costs due to journal as no longer required. Project closure. | -9308 | -9308 | [5 empty] | 280337 | 60042309 | 132666
2024-10-21 | October 2024 Review | Cost Decrease | Local road operations | Emergency works | Napier City Council | EW: November 2020 Napier Rain Event | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | EW threshold not met, reducing FAR. | 0 | -5106 |  |  |  |  | Construction of permanent works (3) | 279020 |  | 132855
2024-10-21 | October 2024 Review | Cost Increase | External funding | Emergency works | South Wairarapa District Council | EW South Wairarapa District Council Cyclone Gabrielle 2023 | Construction | Permanent Repairs/Network Reinstat (NIWE) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | EW threshold has been met. Board approved policy is to assign Higher FAR to NIWE Recovery phases where possible. | 0 | 46687 | [5 empty] | 291558 |  | 132858
2024-10-21 | October 2024 Review | Cost Decrease | Local road operations | Emergency works | Tararua District Council | EW - Tararua DC June 2023 | Construction | Initial Response & Recovery | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Board approved EW policy is to apply Higher FAR (plus 10% for Tararua) to the NIWE Recovery phases. This activity will be split between Normal and Higher FAR. | -125001 | -495872 | [5 empty] | 290944 |  | 132859
2024-10-21 | October 2024 Review | Cost Increase | External funding | Emergency works | Tararua District Council | EW Cyclone Gabrielle | Construction | Cyclone Gabrielle- Recovery Phase (NIWE) FAR +20% | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Board approved a bespoke FAR of normal FAR plus 30% up to a maximum of 97.5% for NIWE recovery work in 2023/24 and 2024/25 for Tararua District Council. | 0 | 855273 | [5 empty] | 292679 |  | 132862
2024-10-22 | October 2024 Review | Cost Decrease | Local road operations | Emergency works | Thames-Coromandel District Council | EW - Thames-Coromandel DC July 2023 | Construction | Initial Response, Investigation and Design (2) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | All NLTF EW funding will be at Normal FAR to push more of the NIWE Recovery funding into Higher FAR eligibility. Board has approved an additional 10% for NIWE Recovery Higher FAR. This will reduce TCDC local share. | 0 | -27964 |  |  |  |  | (Normal FAR+20%) | 291080 |  | 132881
2024-10-22 | October 2024 Review | Cost Decrease | Local road operations | Emergency works | Thames-Coromandel District Council | EW - Thames-Coromandel DC July 2023 | Construction | Permanent Reinstatement MSQA and Construction | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | All NLTF EW funding will be at Normal FAR to push more of the NIWE Recovery funding into Higher FAR eligibility. Board has approved an additional 10% for NIWE Recovery Higher FAR. This will reduce TCDC local share. | 0 | -160000 | [5 empty] | 289670 |  | 132879
2024-10-22 | October 2024 Review | Cost Decrease | Local road operations | Emergency works | Thames-Coromandel District Council | EW - Thames-Coromandel DC July 2023 | Construction | Initial Response, Investigation and Design | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | All NLTF EW funding will be at Normal FAR to push more of the NIWE Recovery funding into Higher FAR eligibility. Board has approved an additional 10% for NIWE Recovery Higher FAR. This will reduce TCDC local share. | 0 | -31000 | [5 empty] | 289669 |  | 132878
2024-10-22 | October 2024 Review | Cost Decrease | Local road operations | Emergency works | Thames-Coromandel District Council | EW - Thames-Coromandel DC October 2023 | Construction | Permanent Reinstatement MSQA and Construction | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | All NLTF EW funding will be at Normal FAR to push more of the NIWE Recovery funding into Higher FAR eligibility. Board has approved an additional 10% for NIWE Recovery Higher FAR. This will reduce TCDC local share. | 0 | -40000 | [5 empty] | 291175 |  | 132883
2024-10-22 | October 2024 Review | Cost Decrease | Local road operations | Emergency works | Thames-Coromandel District Council | EW - Thames-Coromandel DC October 2023 | Construction | Initial Response, Investigation and Design | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | All NLTF EW funding will be at Normal FAR to push more of the NIWE Recovery funding into Higher FAR eligibility. Board has approved an additional 10% for NIWE Recovery Higher FAR. This will reduce TCDC local share. | 0 | -19791 | [5 empty] | 291174 |  | 132882
2024-10-02 | October 2024 Review | Cost Decrease | Local road operations | Emergency works | Waikato District Council | EW - Waikato DC Storm Damage Jan-Feb 2023 | Construction | 23/24 Phase 2 - I&D (NIWE) @ High FAR | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | this is now moved to phase id 293001 due to incorrect funding source. | -66278 | -47057 | [5 empty] | 293002 |  | 132662
2024-10-21 | October 2024 Review | Cost Decrease | Local road operations | Emergency works | Wairoa District Council | EW: Emergency Works June 2023 | Construction | Recovery High FAR +20% | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Cost flow adjustment to reflect program. | 0 | -277150 | [5 empty] | 293120 |  | 132811
2024-10-16 | October 2024 Review | Cost Decrease | Local road operations | Emergency works | Waitomo District Council | EW - Waitomo DC February 2022 Cyclone Dovi | Construction | 23/24 - Professional Services and Physical Works | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Decreasing allocation to align with NZTA FAR policy | -934628 | -887897 | [5 empty] | 290769 |  | 132792
2024-10-16 | October 2024 Review | Cost Increase | Local road operations | Emergency works | Waitomo District Council | EW - Waitomo DC February 2022 Cyclone Dovi | Construction | Construction & MSQA Of Permanent (Normal FAR+20%) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Increasing allocation at normal FAR to align with NZTA FAR policy | 934628 | 700971 |  |  |  |  | (Normal FAR+20%) | 288936 |  | 132791
2024-10-17 | October 2024 Review | Cost Decrease | External funding | Emergency works | Waitomo District Council | EW - Waitomo DC January 2023 (Auckland Anniversary) | Construction | NIWE 2023 Phase Two - I&D and Construction | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | Fixing FAR rate that was approved at 100% | 0 | -203950 |  |  |  |  | NIWE 2023 Phase Two - I&D and Construction | 293027 |  | 132822
2024-10-16 | October 2024 Review | Cost Increase | Local road operations | Emergency works | Waitomo District Council | EW - Waitomo DC Winter 2022 Events | Construction | Construction & MSQA Of Permanent Construction Site | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Allocation adjusted to higher FAR rate to align with NZTA EW policy | 0 | 709715 | [5 empty] | 283094 |  | 132793
2024-10-21 | October 2024 Review | Cost Decrease | Local road operations | Emergency works | Whanganui District Council | Cyclone Dovi - 13 February 2022 Emergency Works | Construction | Major Repairs | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | EW threshold reached. Funds being moved to Higher FAR phase. | -216632 | -134312 |  |  |  |  | Request for emergency works funding | 281498 |  | 132865
2024-10-21 | October 2024 Review | Cost Increase | Local road operations | Emergency works | Whanganui District Council | Cyclone Dovi - 13 February 2022 Emergency Works | Construction | Major Repairs (Normal FAR + 20%) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | EW threshold reached. Funds being moved to Higher FAR phase. | 216632 | 177638 | [5 empty] | 290579 |  | 132866
2024-10-21 | October 2024 Review | Cost Increase | Local road operations | Emergency works | Whanganui District Council | EW - May 2022 Weather Event | Construction | Initial clean up and permanent repairs | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | EW threshold reached, funds eligible for Higher FAR. | 0 | 155057 |  |  |  |  | Initial clean up and permanent repairs | 282144 |  | 132867
2024-10-21 | October 2024 Review | Cost Increase | Local road operations | Emergency works | Whanganui District Council | EW - Whanganui DC 20 May 2023 Flood | Construction | Clean up and Minor Repairs | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | EW threshold reached, funds eligible for Higher FAR. | 0 | 112668 |  |  |  |  | Clean up and Minor Repairs | 284307 |  | 132868
2024-10-21 | October 2024 Review | Cost Increase | Local road operations | Emergency works | Whanganui District Council | EW Whanganui DC February 2023 Flood Event | Construction | Cleanup, Minor Repairs and Permanent Reinstatement | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | EW threshold reached, funds eligible for Higher FAR. | 0 | 22032 |  |  |  |  | Cleanup, Minor Repairs and Permanent Reinstatement | 283684 |  | 132869
2024-10-21 | October 2024 Review | Cost Increase | Local road operations | Emergency works | Whanganui District Council | EW Whanganui DC October 2022 | Construction | Emergency Response and Permanent Reinstatement | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | EW threshold reached, funds eligible for Higher FAR. | 0 | 125044 | [5 empty] | 283415 |  | 132870
2024-10-18 | October 2024 Review | Cost Decrease | Local road operations | Environmental maintenance | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | CHBDC identified an over claim after the end of financial year, this adjustment is required to repay the value over claimed, | 0 | -66259 | [5 empty] | 285279 |  | 132718
2024-10-18 | October 2024 Review | Cost Decrease | Walking and cycling improvements | Footpath maintenance | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 3 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | CHBDC identified an over claim after the end of financial year, this adjustment is required to repay the value over claimed, | 0 | -2513 | [5 empty] | 285277 |  | 132720
2024-10-18 | October 2024 Review | Cost Decrease | Walking and cycling improvements | Footpath renewal | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 3 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | CHBDC identified an over claim after the end of financial year, this adjustment is required to repay the value over claimed, | 0 | -54023 | [5 empty] | 285293 |  | 132720
2024-10-18 | October 2024 Review | Cost Decrease | Local road operations | Minor events | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | CHBDC identified an over claim after the end of financial year, this adjustment is required to repay the value over claimed, | 0 | -12196 | [5 empty] | 285278 |  | 132718
2024-10-18 | October 2024 Review | Cost Increase | Safety | Network and asset management | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | CHBDC identified an over claim after the end of financial year, this adjustment is required to repay the value over claimed, | 0 | 8668 | [5 empty] | 285283 |  | 132718
2024-10-04 | October 2024 Review | Cost Increase | Safety | Network and asset management | NZ Transport Agency | NLTP Funds Management | Repayment |  | ___ | LLVL | N |  | Approved | Approved by Chief Financial Officer | Adding Admin under recovery for 2023/24 | 948300 | 948300 | [5 empty] | 283279 |  | 132686
2024-10-18 | October 2024 Review | Cost Decrease | Local road operations | Network service maintenance | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | CHBDC identified an over claim after the end of financial year, this adjustment is required to repay the value over claimed, | 0 | -42819 | [5 empty] | 285280 |  | 132718
2024-10-04 | October 2024 Review | Cost Decrease | Public transport infrastructure | New activities influencing users of the transport system | NZ Transport Agency | National Mode Shift Campaign | Single-Stage Business Case |  | ___ | MHVH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -54388 | -54388 |  |  | 5 | 24.3 | 60067381 SAP ID | 281438 |  | 132384
2024-10-21 | October 2024 Review | Cost Decrease | Public transport infrastructure | New activities influencing users of the transport system | Queenstown-Lakes District Council | Travel Demand Management | Single-Stage Business Case |  | ___ | VHHVH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -83744 | -42709 |  |  |  | 8.5 |  | 277212 |  | 132790
2024-10-31 | October 2024 Review | Cost Decrease | Public transport services | Passenger services - bus | Greater Wellington | CERF-Decarbonising the PT Bus Fleet - Lyall Bay Stage 1 | Implementation |  | ___ | VHHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Funds being moved to a new phase with the correct WC. | -21250981 | -10838000 |  |  |  |  | Funding depot stage 1 | 291079 |  | 132915
2024-10-04 | October 2024 Review | Cost Decrease | Public transport infrastructure | Passenger transport infrastructure | NZ Transport Agency | National Total Mobility Administration System | Construction |  | ___ | H_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -115749 | -115749 |  |  |  | 1.4 | 80002257, 80002108 | 225068 |  | 132383
2024-10-23 | October 2024 Review | Cost Increase | Walking and cycling improvements | Property purchase (State highways) | NZTA (Canterbury) | Western Belfast By-Pass | Property |  | ___ | M_L | N |  | Approved | Approved by Chief Financial Officer | PLA request for $1.6M incl 6% admin due to unforeseen business loss claim | 1696000 | 1696000 |  |  | 2.1 | 2.1 | NB Includes pre-2013 costs which are missing in SAP | 200229 | 60444042 | 132259
2024-10-04 | October 2024 Review | Cost Decrease | Walking and cycling improvements | Property purchase (State highways) | NZTA (Northland) | SH1 Corridor Improvements - Whangarei | Property |  | ___ | HMM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | project closure | -2514 | -2514 |  |  | 0 | 2.3 | 60471902 | 224010 | 60471902 | 132479
2024-10-11 | October 2024 Review | Cost Decrease | Public transport services | Public transport information supply, operations and maintenance | NZ Transport Agency | Rail Safety Regulator: Road-Rail Interaction | Implementation |  | ___ | MMM | N |  | Approved | Approved by Manager, Treasury & Cash Flow |  | -74937 | -74937 |  |  | 1 | 1 | 80002347/ 80002378 | 264911 |  | 132782
2024-10-18 | October 2024 Review | Cost Decrease | Local road operations | Rail level crossing warning devices maintenance | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | CHBDC identified an over claim after the end of financial year, this adjustment is required to repay the value over claimed, | 0 | -598 | [5 empty] | 285282 |  | 132718
2024-10-04 | October 2024 Review | Cost Decrease | State highway improvements | Replacement of bridges and other structures | NZTA (Northland) | SH12 Matakohe Bridges | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | project closure | -68564 | -68564 |  |  | 1.3 | 1.3 | 60040765 | 278774 | 60040765 | 132480
2024-10-07 | October 2024 Review | Cost Decrease | State highway improvements | Resilience improvements | NZTA (Waikato) | SH25A rebuild improvements | Implementation |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Correcting funding source | -30000001 | -30000001 |  |  | 0.5 | 0.5 | NIWE | 291540 | 60075151 | 131304
2024-10-24 | October 2024 Review | Cost Increase | Safety | Road improvements | Auckland Transport | Hill Street Intersection Improvements | Pre-implementation* |  | ___ | MHM | N |  | Declined | Declined by regional office |  | 773000 | 394230 |  |  | 0 | 5.8 | 324.2696 | 269615 |  | 131089
2024-10-21 | October 2024 Review | Cost Decrease | Safety | Road improvements | Greater Wellington | LGWM - Rapid Transit - indicative business case | Indicative Business Case |  | ___ | H_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -49453 | -24727 |  |  | 1.5 | 1.5 |  | 241928 |  | 132781
2024-10-04 | October 2024 Review | Cost Increase | Safety | Road improvements | NZ Transport Agency | NLTP Funds Management | Repayment |  | ___ | LLVL | N |  | Approved | Approved by Chief Financial Officer | Adding Admin under recovery for 2023/24 | 632200 | 632200 | [5 empty] | 283277 |  | 132687
2024-10-08 | October 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Auckland) | AKLD VfM Safety Imp â€“ Small Projects | Implementation | AKLD VfM Safety Imp - RtZ Infra & Speed | MHH | MHH | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $80900 ex admin from 60075303 to 60083164 | 881807 | 881807 |  |  | 6 | 6 | AKLD VfM Safety Imp - RtZ Infra & Speed | 292890 | 60083164 | 132754
2024-10-18 | October 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Auckland) | ANO SH16 Te Atatu Interchange EB On Ramp | Single-Stage Business Case |  | ___ | MHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer - Please move remaining allocation of $20,779 from ANO item 60070103 to parent ANO Programme 60056410 | -22649 | -22649 |  |  | 5.3 | 5.3 |  | 284035 | 60070103 | 132325
2024-10-18 | October 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Auckland) | Auckland Network Optimisation (ANO) Programme | Pre-implementation* |  | ___ | HHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer - Please move remaining allocation of $20,779 from ANO item 60070103 to parent ANO Programme 60056410 | 22648 | 22648 |  |  |  | 3.2 | InfoHub ID 28116348 ¦ SAP 60056410 | 254838 | 60056410 | 132326
2024-10-08 | October 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (BOP) | BOP VfM Safety Imp â€“ Small Projects | Implementation | BOP VfM Safety Imp â€“ RtZ Infra & Speed | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $903500 ex admin from 60075222 to 60083171 | 984812 | 984812 |  |  | 6 | 6 | BOP VfM Safety Imp â€“ RtZ Infra & Speed | 292896 | 60083171 | 132773
2024-10-04 | October 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (BOP) | RoNS SH29 Tauriko West Network Connection | Detailed Business Case |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Next Phase funding request for Tauriko West - Investment Case $871,560 (excl admin fee) | 950000 | 950000 |  |  | 0 | 1.3 | 60041684 | 248953 | 60041684 | 132679
2024-10-08 | October 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Canterbury) | CAN VfM Safety Imp â€“ Small Projects | Implementation | CAN VfM Safety Imp â€“ RtZ Infra & Speed | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $397350 ex admin from 60075600 to 60083178 | 433109 | 433109 |  |  | 6 | 6 | CAN VfM Safety Imp â€“ RtZ Infra & Speed | 292900 | 60083178 | 132775
2024-10-08 | October 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Gisborne) | GIS VfM Safety Imp â€“ Small Projects | Implementation | GIS VfM Safety Imp â€“ RtZ Infra & Speed | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $3814 ex admin from 60075397 to 60083183 AND $75000 ex admin from 60075397 to 60083185 | 81747 | 81747 |  |  | 6 | 6 | GIS VfM Safety Imp â€“ RtZ Infra & Speed | 292904 | 60083185 | 132756
2024-10-08 | October 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Hawkes Bay) | HAWK VfM Safety Imp â€“ Small Projects | Implementation | HAWK VfM Safety Imp â€“ RtZ Infra & Speed | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $300000 ex admin from 60075469 to 60083192 | 326997 | 326997 |  |  | 6 | 6 | HAWK VfM Safety Imp â€“ RtZ Infra & Speed | 292908 | 60083192 | 132758
2024-10-08 | October 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Manawatu/Whanganui) | MNWI VfM Safety Imp â€“ Small Projects | Implementation | MNWI VfM Safety Imp â€“ RtZ Infra & Speed | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $335000 ex admin from 60075295 to 60083206 | 365147 | 365147 |  |  | 6 | 6 | MNWI VfM Safety Imp â€“ RtZ Infra & Speed | 292916 | 60083206 | 132727
2024-10-08 | October 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Marlborough) | MARL VfM Safety Imp â€“ Small Projects | Implementation | MARL VfM Safety Imp â€“ RtZ Infra & Speed | MHH | HHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $1110000 ex admin from 60075526 to 60083159 | 1209897 | 1209897 |  |  | 6 | 6 | MARL VfM Safety Imp â€“ RtZ Infra & Speed | 292912 | 60083159 | 132725
2024-10-08 | October 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Nelson) | NEL VfM Safety Imp â€“ Small Projects | Implementation | NEL VfM Safety Imp â€“ RtZ Infra & Speed | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $5000 ex admin from 60075437 to 60083213 | 5447 | 5447 |  |  | 6 | 6 | NEL VfM Safety Imp â€“ RtZ Infra & Speed | 292920 | 60083213 | 132729
2024-10-08 | October 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Northland) | NTLD VfM Safety Imp â€“ Small Projects | Implementation | NTLD VfM Safety Imp â€“ RtZ Infra & Speed | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $2815660 ex admin from 60075196 to 60083221 | 3069066 | 3069066 |  |  | 6 | 6 | NTLD VfM Safety Imp â€“ RtZ Infra & Speed | 292924 | 60083221 | 132731
2024-10-08 | October 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Otago) | OTA VfM Safety Imp â€“ Small Projects | Implementation | OTA VfM Safety Imp â€“ RtZ Infra & Speed | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | RtZ Small Infrastructure & Speed - RtZ Activity Class Transfer & Carryover from 21-24 NLTP | 43597 | 43597 |  |  | 6 | 6 | OTA VfM Safety Imp â€“ RtZ Infra & Speed | 292928 | 60083228 | 132733
2024-10-18 | October 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Otago) | SH6 Wanaka to Luggate Safer Corridor - SH84 IS | Implementation |  | ___ | VHML | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Correcting error due to admin inclusive amount under total cost without admin. Change from (-$283,858) to (-$260,420). | 25547 | 25547 |  |  | 0 | 1.6 |  | 292501 | 60076240 | 132844
2024-10-21 | October 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Southland) | CIP SH94 Homer Tunnel | Implementation |  | ___ | MHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Releasing $1,612,070 allocation to the CIP bucket and keeping the remaining allocation to cover payment to the contractor. | -2989896 | -2989896 |  |  | 0 | 0 |  | 275306 | 60059181 | 132810
2024-10-08 | October 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Southland) | STLD VfM Safety Imp â€“ Small Projects | Implementation | STLD VfM Safety Imp â€“ RtZ Infra & Speed | MHL | MHL | N | 7 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $5000 ex admin from 60075556 to 60083236 | 5447 | 5447 |  |  | 6 | 6 | STLD VfM Safety Imp â€“ RtZ Infra & Speed | 292932 | 60083236 | 132735
2024-10-24 | October 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Waikato) | 2024-27 NLTP funds management | Repayment |  | ___ | LHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Reduced to match overspends from 2023/24 | -4146417 | -4146417 | [5 empty] | 279275 |  | 132920
2024-10-09 | October 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Waikato) | SH3 and Raynes Rd IS | Pre-implementation* |  | ___ | VHHL | N |  | Approved | Approved by Chief Financial Officer | These funds will allow the completion of the Pre-implementation phase and prepare for Implementation | 39364 | 39364 |  |  | 2.1 | 2.1 |  | 292542 | 60076276 | 132425
2024-10-08 | October 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Waikato) | WAI VfM Safety Imp â€“ Small Projects | Implementation | WAI VfM Safety Imp â€“ RtZ Infra & Speed | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $1678000 ex admin from 60075459 to 60083258 | 1829017 | 1829017 |  |  | 6 | 6 | WAI VfM Safety Imp â€“ RtZ Infra & Speed | 292944 | 60083258 | 132739
2024-10-08 | October 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Wellington) | WGTN VfM Safety Imp â€“ Small Projects | Implementation | WGTN VfM Safety Imp â€“ RtZ Infra & Speed | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $135000 ex admin from 60075638 to 60083266 | 147147 | 147147 |  |  | 6 | 6 | WGTN VfM Safety Imp â€“ RtZ Infra & Speed | 292948 | 60083266 | 132741
2024-10-08 | October 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (West Coast) | WTCT VfM Safety Imp â€“ Small Projects | Implementation | WTCT VfM Safety Imp â€“ RtZ Infra & Speed | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $142000 ex admin from 60075625 to 60083273 | 154777 | 154777 |  |  | 6 | 6 | WTCT VfM Safety Imp â€“ RtZ Infra & Speed | 292950 | 60083273 | 132743
2024-10-18 | October 2024 Review | Cost Decrease | Local road pothole prevention | Routine drainage maintenance | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | CHBDC identified an over claim after the end of financial year, this adjustment is required to repay the value over claimed. | 0 | -25224 | [5 empty] | 285274 |  | 132719
2024-10-18 | October 2024 Review | Cost Decrease | Local road pothole prevention | Sealed pavement maintenance | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | CHBDC identified an over claim after the end of financial year, this adjustment is required to repay the value over claimed. | 0 | -41953 | [5 empty] | 285272 |  | 132719
2024-10-24 | October 2024 Review | Cost Decrease | State highway pothole prevention | Sealed pavement maintenance | NZTA (Wellington) | 2024-27 NLTP funds management | Repayment |  | ___ | LHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Reduced to match overspends from 2023/24 | -1851236 | -1851236 | [5 empty] | 288903 |  | 132921
2024-10-18 | October 2024 Review | Cost Decrease | Local road pothole prevention | Sealed road pavement rehabilitation | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | CHBDC identified an over claim after the end of financial year, this adjustment is required to repay the value over claimed. | 0 | -23183 | [5 empty] | 285287 |  | 132719
2024-10-18 | October 2024 Review | Cost Decrease | Local road pothole prevention | Sealed road resurfacing | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | CHBDC identified an over claim after the end of financial year, this adjustment is required to repay the value over claimed. | 0 | -36877 | [5 empty] | 285285 |  | 132719
2024-10-18 | October 2024 Review | Cost Decrease | Local road operations | Structures component replacements | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | CHBDC identified an over claim after the end of financial year, this adjustment is required to repay the value over claimed, | 0 | -300761 | [5 empty] | 285288 |  | 132718
2024-10-18 | October 2024 Review | Cost Decrease | Local road operations | Structures maintenance | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | CHBDC identified an over claim after the end of financial year, this adjustment is required to repay the value over claimed, | 0 | -10366 | [5 empty] | 285275 |  | 132718
2024-10-18 | October 2024 Review | Cost Decrease | Local road operations | Traffic services renewals | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | CHBDC identified an over claim after the end of financial year, this adjustment is required to repay the value over claimed, | 0 | -7767 | [5 empty] | 285291 |  | 132718
2024-10-16 | October 2024 Review | Cost Increase | Investment management (incl. Transport Planning) | Transport model development | NZ Transport Agency | Household Travel Survey Booster | Programme business case |  | V__ | V__ | N |  | Approved | Approved by Chief Financial Officer (CFO) | NDA batch board approvals for NLTP 24-27 - $4.5M inc admin | 4500000 | 4500000 |  |  |  |  | 60082812 (previously WBS 80002606) | 277908 |  | 131406
2024-10-18 | October 2024 Review | Cost Decrease | Local road pothole prevention | Unsealed pavement maintenance | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | CHBDC identified an over claim after the end of financial year, this adjustment is required to repay the value over claimed. | 0 | -16020 | [5 empty] | 285273 |  | 132719
2024-10-18 | October 2024 Review | Cost Decrease | Local road pothole prevention | Unsealed road metalling | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | CHBDC identified an over claim after the end of financial year, this adjustment is required to repay the value over claimed. | 0 | -51307 | [5 empty] | 285284 |  | 132719
2024-10-02 | October 2024 Review | Cost Decrease | Public transport infrastructure |  | Auckland Transport | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | -13259754 | -6762475 |  |  |  |  | 561.1106 | 292778 |  | 132661
2024-10-02 | October 2024 Review | Cost Decrease | Local road pothole prevention |  | Auckland Transport | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | -51132467 | -26077558 |  |  |  |  | 111.1101 | 292762 |  | 132671
2024-10-02 | October 2024 Review | Cost Decrease | Safety |  | Auckland Transport | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | -24165656 | -12324485 |  |  |  |  | 151.1102 | 292761 |  | 132672
2024-10-02 | October 2024 Review | Cost Decrease | Public transport services |  | Auckland Transport | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | -97060300 | -49500753 |  |  |  |  | 511.1105 | 292763 |  | 132670
2024-10-22 | October 2024 Review | Cost Decrease | Local road operations |  | Buller District Council | Buller District Council - 24-27 SPR MOR Programme | Implementation |  | ___ | HHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Wrong work category | -1323098 | -1323098 | [5 empty] | 292829 |  | 132874
2024-10-16 | October 2024 Review | Cost Decrease | Local road pothole prevention |  | Chatham Islands Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | -631644 | -555847 | [5 empty] | 292823 |  | 132794
2024-10-16 | October 2024 Review | Cost Decrease | Safety |  | Chatham Islands Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | -161202 | -141858 | [5 empty] | 292824 |  | 132795
2024-10-16 | October 2024 Review | Cost Decrease | Local road pothole prevention |  | Dunedin City Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | -4637222 | -2364983 | [5 empty] | 292825 |  | 132796
2024-10-16 | October 2024 Review | Cost Decrease | Public transport infrastructure |  | Greater Wellington | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | -2845017 | -1450959 | [5 empty] | 292783 |  | 132798
2024-10-16 | October 2024 Review | Cost Decrease | Public transport services |  | Greater Wellington | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | -41077017 | -20949279 | [5 empty] | 292782 |  | 132797
2024-10-16 | October 2024 Review | Cost Decrease | Public transport services |  | Horizons Manawatu | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | -1886790 | -962263 | [5 empty] | 292881 |  | 132783
2024-10-16 | October 2024 Review | Cost Decrease | Safety |  | Horowhenua District Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | -494375 | -301569 | [5 empty] | 292818 |  | 132800
2024-10-16 | October 2024 Review | Cost Decrease | Local road pothole prevention |  | Horowhenua District Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | -700051 | -427031 | [5 empty] | 292817 |  | 132799
2024-10-21 | October 2024 Review | Cost Increase | Safety |  | NZ Transport Agency | State Highway Speed Management Plan | Implementation |  | ___ | VHHL | N |  | Approved | Approved by Chief Financial Officer | addtional 4.686m including admin to response to the Governmentâ€™s new speed management Rule, which is currently in draft and due to be signed 23 September. Please make sure to remove the 577k from SAP item number 60069223 because it is included in the calculations The decision was made to use imp as representation of the whole project, pre imp and imp this doesnt include physical imp of speed limit changes | 4809553 | 4809553 |  |  |  | 2.1 | SAP-PPM Id 157902022 / 60083619 | 292794 |  | 132192
2024-10-02 | October 2024 Review | Cost Decrease | State highway improvements |  | NZTA (Auckland) | AKL Share RoNS Project Development | Detailed Business Case |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer - Pls move $2,801,400 from 60075346 to 60083893 | -3053526 | -3053526 |  |  |  | 1 | AKL Share RoNS Project Development | 291831 | 60075346 | 132667
2024-10-08 | October 2024 Review | Cost Decrease | State highway improvements |  | NZTA (Auckland) | AKLD Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $5014 ex admin from 60075303 to 60083162 AND $80900 ex admin from 60075303 to 60083164 | -887275 | -887275 |  |  |  | 1 | 60075303 AKLD Share VFM Safety Imp Prog | 289798 | 60075303 | 132746
2024-10-04 | October 2024 Review | Cost Decrease | State highway improvements |  | NZTA (BOP) | BOP Share RoNS Project Development | Detailed Business Case |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Moving $871,560(excl admin fee) to TNP SH29 Tauriko West Network Connection | -949999 | -949999 |  |  |  | 1 |  | 291786 | 60075252 | 132678
2024-10-08 | October 2024 Review | Cost Decrease | State highway improvements |  | NZTA (BOP) | BOP Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $15814 ex admin from 60075222 to 60083169 AND $903500 ex admin from 60075222 to 60083171 | -1002053 | -1002053 |  |  |  | 1 | 60075222 BOP Share VFM Safety Imp Prog | 289802 | 60075222 | 132769
2024-10-08 | October 2024 Review | Cost Decrease | State highway improvements |  | NZTA (Canterbury) | CAN Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $94214 ex admin from 60075600 to 60083176 AND $397350 ex admin from 60075600 to 60083178 | -535805 | -535805 |  |  |  | 1 | 60075600 CAN Share VFM Safety Imp Prog | 289807 | 60075600 | 132770
2024-10-08 | October 2024 Review | Cost Decrease | State highway improvements |  | NZTA (Gisborne) | GIS Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $3814 ex admin from 60075397 to 60083183 AND $75000 ex admin from 60075397 to 60083185 | -85907 | -85907 |  |  |  | 1 | 60075397 GIS Share VFM Safety Imp Prog | 289809 | 60075397 | 132747
2024-10-08 | October 2024 Review | Cost Decrease | State highway improvements |  | NZTA (Hawkes Bay) | HAWK Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $8614 ex admin from 60075469 to 60083190 AND $300000 ex admin from 60075469 to 60083192 | -336389 | -336389 |  |  |  | 1 | 60075469 HAWK Share VFM Safety Imp Prog | 289811 | 60075469 | 132722
2024-10-08 | October 2024 Review | Cost Decrease | State highway improvements |  | NZTA (Manawatu/Whanganui) | MNWI Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $85814 ex admin from 60075295 to 60083204 AND $335000 ex admin from 60075295 to 60083206 | -458688 | -458688 |  |  |  | 1 | 60075295 MNWI Share VFM Safety Imp Prog | 291813 | 60075295 | 132721
2024-10-08 | October 2024 Review | Cost Decrease | State highway improvements |  | NZTA (Marlborough) | MARL Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $7414 ex admin from 60075526 to 60083198 AND $1110000 ex admin from 60075526 to 60083159 | -1217981 | -1217981 |  |  |  | 1 | 60075526 MARL Share VFM Safety Imp Prog | 289818 | 60075526 | 132771
2024-10-08 | October 2024 Review | Cost Decrease | State highway improvements |  | NZTA (Nelson) | NEL Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $3814 ex admin from 60075473 to 60083211 AND $5000 ex admin from 60075437 to 60083213 | -9607 | -9607 |  |  |  | 1 | 60075473 NEL Share VFM Safety Imp Prog | 289819 | 60075473 | 132749
2024-10-08 | October 2024 Review | Cost Decrease | State highway improvements |  | NZTA (Northland) | NTLD Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $9814 ex admin from 60075196 to 60083219 AND $2815660 ex admin from 60075196 to 60083221 | -3079766 | -3079766 |  |  |  | 1 | 60075196 NTLD Share VFM Safety Imp Prog | 289827 | 60075196 | 132744
2024-10-08 | October 2024 Review | Cost Decrease | State highway improvements |  | NZTA (Otago) | OTA Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $25414 ex admin from 60075581 to 60083226 AND $40000 ex admin from 60075581 to 60083228 | -71301 | -71301 |  |  |  | 1 | 60075581 OTA Share VFM Safety Imp Prog | 289831 | 60075581 | 132751
2024-10-08 | October 2024 Review | Cost Decrease | State highway improvements |  | NZTA (Southland) | STLD Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $23014 ex admin from 60075556 to 60083234 AND $5000 ex admin from 60075556 to 60083236 | -30535 | -30535 |  |  |  | 1 | 60075556 STLD Share VFM Safety Imp Prog | 289836 | 60075556 | 132723
2024-10-08 | October 2024 Review | Cost Decrease | State highway improvements |  | NZTA (Taranaki) | TAR Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $21814 ex admin from 60075244 to 60083242 | -23777 | -23777 |  |  |  | 1 | 60075244 TAR Share VFM Safety Imp Prog | 291784 | 60075244 | 132745
2024-10-08 | October 2024 Review | Cost Decrease | State highway improvements |  | NZTA (Tasman) | TAS Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $7414 ex admin from 60075545 to 60083249 | -8081 | -8081 |  |  |  | 1 | 60075545 TAS Share VFM Safety Imp Prog | 289915 | 60075545 | 132750
2024-10-08 | October 2024 Review | Cost Increase | State highway improvements |  | NZTA (Waikato) | SH25A rebuild improvements | Implementation |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Updating funding source | 29999999 | 29999999 |  |  | 0.5 | 0.5 |  | 292674 | 60075151 | 132768
2024-10-08 | October 2024 Review | Cost Decrease | State highway improvements |  | NZTA (Waikato) | WAI Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $104214 ex admin from 60075459 to 60083256 AND $1678000 ex admin from 60075459 to 60083258 | -1942613 | -1942613 |  |  |  | 1 | 60075459 WAI Share VFM Safety Imp Prog | 289918 | 60075459 | 132748
2024-10-08 | October 2024 Review | Cost Decrease | State highway improvements |  | NZTA (Wellington) | WGTN Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $7414 ex admin from 60075638 to 60083264 AND $135000 ex admin from 60075638 to 60083266 | -155232 | -155232 |  |  |  | 1 | 60075638 WGTN Share VFM Safety Imp Prog | 289923 | 60075638 | 132752
2024-10-08 | October 2024 Review | Cost Decrease | State highway improvements |  | NZTA (West Coast) | WTCT Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $9814 ex admin from 60075625 to 60083271 AND $142000 ex admin from 60075625 to 60083273 | -165478 | -165478 |  |  |  | 1 | 60075625 WTCT Share VFM Safety Imp Prog | 289925 | 60075625 | 132724
2024-10-16 | October 2024 Review | Cost Decrease | Safety |  | Rangitikei District Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | -942625 | -622133 | [5 empty] | 292804 |  | 132802
2024-10-16 | October 2024 Review | Cost Decrease | Local road pothole prevention |  | Rangitikei District Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | -1512302 | -998119 | [5 empty] | 292803 |  | 132801
2024-10-18 | October 2024 Review | Cost Decrease | Local road operations |  | South Wairarapa District Council | South Wairarapa District Council - 24-27 SPR MOR Programme | Implementation |  | ___ | HHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Wrong WC | -836905 | -836905 |  |  | 4 | 4 |  | 293053 |  | 132835
2024-10-16 | October 2024 Review | Cost Decrease | Safety |  | Tararua District Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | -737890 | -538660 | [5 empty] | 292820 |  | 132804
2024-10-16 | October 2024 Review | Cost Decrease | Local road pothole prevention |  | Tararua District Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | -2425671 | -1770740 | [5 empty] | 292819 |  | 132803
2024-10-16 | October 2024 Review | Cost Decrease | Local road pothole prevention |  | Tauranga City Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | -4324865 | -2205681 | [5 empty] | 292785 |  | 132807
2024-10-16 | October 2024 Review | Cost Decrease | Safety |  | Tauranga City Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | -3248476 | -1656723 | [5 empty] | 292786 |  | 132808
2024-10-16 | October 2024 Review | Cost Decrease | Local road pothole prevention |  | Waitaki District Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | -2080923 | -1186126 | [5 empty] | 293037 |  | 132806
2024-10-16 | October 2024 Review | Cost Decrease | Safety |  | Waitaki District Council | 2024/25 Interim funding | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NLTP has been adopted. Claims have been moved to correct activity and interim funding can now be removed. | -810870 | -462196 | [5 empty] | 293036 |  | 132805
2024-10-22 | October 2024 Review | Cost Decrease | Local road improvements |  | Whakatane District Council | WhakatÄne District Council - 24-27 SPR MOR | Implementation |  | ___ | HHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Wrong work category | -150182 | -150182 | [5 empty] | 293049 |  | 132876
2024-10-18 | October 2024 Review | Cost Decrease | Local road pothole prevention |  | Whakatane District Council | WhakatÄne District Council - 24-27 SPR MOR | Implementation |  | ___ | HHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Wrong WC | -2688600 | -2688600 | [5 empty] | 293047 |  | 132841