## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Phase Label | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Decision Status | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR | Your Phase reference | TIO Phase id | SAP item id | TIO Request id
2024-12-18 | December 2024 Review | New approval | Local road operations | Emergency works | Central Otago District Council | EW Central Otago DC October 2024 | Construction | Response | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | Appropriate response to qualifying event | 51400 | 26214 | [5 empty] | 293404 |  | 132990
2024-12-18 | December 2024 Review | New approval | Local road operations | Emergency works | Central Otago District Council | EW Central Otago DC October 2024 | Construction | Recovery | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | appropriate response to qualifying event | 929200 | 473892 | [5 empty] | 293405 |  | 132991
2024-12-04 | December 2024 Review | New approval | Local road operations | Emergency works | Christchurch City Council | EW Christchurch CC July 2023 | Construction | EW July 23 - Reinstatement | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | That the Senior Manager, Maintenance & Operations, Transport Services: â€¢ Approves emergency works funding to Christchurch City Council â€¢ for the EW Christchurch CC July 2023 event â€¢ at a cost of $2,198,229 (including 0% admin) â€¢ at a normal funding assistance rate of 51% ($1,121,097 out of the NLTF) â€¢ for TIO Phase ID 292398 and 292399 â€¢ from activity class 8, work category 141. | 2082602 | 1062127 | [5 empty] | 292399 |  | 128585
2024-12-04 | December 2024 Review | New approval | Local road operations | Emergency works | Christchurch City Council | EW Christchurch CC July 2023 | Construction | EW - July 23 Initial Response | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | That the Senior Manager, Maintenance & Operations, Transport Services: â€¢ Approves emergency works funding to Christchurch City Council â€¢ for the EW Christchurch CC July 2023 event â€¢ at a cost of $2,198,229 (including 0% admin) â€¢ at a normal funding assistance rate of 51% ($1,121,097 out of the NLTF) â€¢ for TIO Phase ID 292398 and 292399 â€¢ from activity class 8, work category 141. | 115627 | 58970 | [5 empty] | 292398 |  | 128587
2024-12-18 | December 2024 Review | New approval | Local road operations | Emergency works | Kapiti Coast District Council | EW KCDC Mangaone South Underslip Storm Oct 2024 | Construction |  | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | That the Regional Manager, Maintenance & Operations, Transport Services: â€¢ Approves emergency works funding to Kapiti Coast District Council â€¢ for the EW Kapiti Coast DC Mangaone South Underslip Storm Oct 2024 â€¢ at a cost of $300,000 â€¢ at a funding assistance rate of 71% ($213,000 out of the NLTF) â€¢ For the response and recovery phases of the event from activity class 8, work category 141. | 300000 | 213000 | [5 empty] | 293481 |  | 133156
2024-12-05 | December 2024 Review | New approval | State highway operations | Emergency works | NZTA (Canterbury) | EW Sth Canty Rangitata Bridge 20240412 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | The works are appropriate for recovery. I am content that the damage to the piers was storm related and fits within the current PIKB guidance for recovery funding. I support the application and recommend approval. | 1419180 | 1419180 | [5 empty] | 293483 | 60085308 | 133203
2024-12-10 | December 2024 Review | New approval | State highway operations | Emergency works | NZTA (Waikato) | EW Response Coromandel Ruamahunga 240724 | Construction |  | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | Agree with the commentary, this work needs to be completed and fits within the current PIKB guidance for emergency works funding and therefore can be approved. Nick Cook | 196200 | 196200 | [5 empty] | 293373 | 60084528 | 133231
2024-12-03 | December 2024 Review | New approval | State highway operations | Emergency works | NZTA (Wellington) | EW Remutaka OS 20240917 | Construction | Initial Response | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | Response only, approved by Regional Manager, Maintenance & Operations | 306956 | 306956 | [5 empty] | 293337 | 60083912 | 133184
2024-12-06 | December 2024 Review | New approval | State highway operations | Emergency works | NZTA (West Coast) | EW SH73 Otira Shelter RF 20240820 | Construction | Response - EW SH73 Otira Shelter RF 20240820 | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | All recovery works are considered as response and fit within the current PIKB guidance. I recommend approval. This funding approval enables the transport network at this location to be reinstated to the appropriate levels of service. | 986636 | 986636 | [5 empty] | 293060 | 60083466 | 133230
2024-12-02 | December 2024 Review | New approval | Local road operations | Emergency works | Selwyn District Council | EW Selwyn DC October 2024 | Construction | EW Selwyn DC October 2024 Rain Event | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | That the Regional Manager, Maintenance & Operations, Transport Services: â€¢ Approves emergency works funding to Selwyn District Council â€¢ for the EW Selwyn DC October 2024 event â€¢ at a cost of $154,539 (including 0% admin) â€¢ at a normal funding assistance rate of 51% ($78,815 out of the NLTF) â€¢ for TIO Phase ID 293455 â€¢ from activity class 8, work category 141. | 154539 | 78815 |  |  |  |  | EW Selwyn DC October 2024 Rain Event | 293455 |  | 133155
2024-12-09 | December 2024 Review | New approval | Local road operations | Emergency works | Tararua District Council | EW - 18th August '24 | Construction | Initial Response & Recovery | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | To restore roads back to its original condition prior to event. evidence of programme tension is well documented, options checked, event return > 1:10 is evidence, correct delegations, and FAR calculation. | 650423 | 604893 | [5 empty] | 293313 |  | 132654
2024-12-09 | December 2024 Review | New approval | Local road operations | Emergency works | Tararua District Council | EW - 1st August '24 | Construction | Initial Response & Recovery | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | To bring the condition to the LOS prior to this event. This applications has been reviewed with evidence of tensioning response and recovery optioneering is documented, activities reviewed are emergency works activities and the repairs appear appropriate to WC141. FAR calculations and ACM confirmation values match this funding request. | 1522959 | 1367190 | [5 empty] | 293312 |  | 132653
2024-12-18 | December 2024 Review | New approval | Local road operations | Emergency works | Wairoa District Council | EW:Matariki Event -25 June 2024 | Construction |  | ___ |  | N |  | Approved with conditions | Approved with conditions by Manager, Treasury & Cash Flow (Commercial and Corporate) | Subject to a condition subsequent that funding cannot be brought forward from 27/28 into the 24-27 NLTP period without confirmation of funding availability for the local road operations activity class manager. | 12826238 | 11076596 | funding cannot be brought forward from 27/28 into the 24-27 NLTP period without confirmation of funding availability for the local road operations activity class manager |  |  |  |  | 293257 |  | 132473
2024-12-12 | December 2024 Review | New approval | Local road operations | Emergency works | Western BoP District Council | EW WBOPDC - October 2022 | Construction | Recovery - investigation, D&C&MSQA | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | Investment required to complete recovery works / reinstate appropriate LoS associated this weather event. | 1130000 | 690300 | [5 empty] | 283305 |  | 121567
2024-12-12 | December 2024 Review | New approval | Local road operations | Emergency works | Western BoP District Council | EW WBoPDC - June 2023 | Construction | Recovery - investigation, design, cnstrctn & MSQA | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | Investment required to repair storm damage / reinstate appropriate LoS agreed with regional investment advisor. | 1310000 | 818100 | [5 empty] | 284562 |  | 126089
2024-12-13 | December 2024 Review | New approval | Local road operations | Emergency works | Western BoP District Council | EW WBoPDC - June 2024 | Construction | Recovery - investigation, D&C&MSQA | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | Investment required to complete recovery works to reinstate an appropriate LoS at the Oropi Gorge Road site. | 1290000 | 915900 | [5 empty] | 293367 |  | 132831
2024-12-13 | December 2024 Review | New approval | Safety |  | Buller District Council | Payback for AMDS 23/24 claim and RTZ overclaim 23/24 | Repayment |  | ___ | VHHVH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Council repaying RtZ overclaim during FY 23/24. | -48628 | -48628 |  |  |  | 1 |  | 293446 |  | 133041
2024-12-13 | December 2024 Review | New approval | Safety |  | Buller District Council | Payback for AMDS 23/24 claim and RTZ overclaim 23/24 | Repayment |  | ___ | VHHVH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Council repaying AMDS costs incorrectly claimed against WC 003 during FY 23/24. | -8091 | -8091 |  |  |  | 1 |  | 293431 |  | 132998
2024-12-20 | December 2024 Review | New approval | Public transport services |  | Environment Canterbury | PT futures - Route 7 Service | Implementation |  | ___ | VHHM | N |  | Approved | Approved by Chief Financial Officer | Agreed by 13 June VOS and conditions met in December 2024. | 8320671 | 4243542 | The Activity Class Manager and Treasury & Cashflow Manager confirm funding priority and availability. That the activity is included and prioritised in the NLTP 2024-27. |  | 3.5 | 3.5 | PT futures Route 7 | 290276 |  | 129238
2024-12-03 | December 2024 Review | New approval | Public transport services |  | Horizons Manawatu | Palmerston North PT improvements | Implementation |  | ___ | VHHM | N |  | Approved | Approved by Chief Financial Officer | The key benefit of approving this funding request is improving access to economic and social opportunities. Activity has a BCR or 4.1 | 22945000 | 11701950 |  |  |  | 4.1 |  | 277851 |  | 115122
2024-12-09 | December 2024 Review | New approval | Investment management (incl. Transport Planning) |  | NZ Transport Agency | Transforming Project Development | Implementation |  | ___ | HHL | N |  | Approved with conditions | Approved with conditions by Chief Financial Officer | This request is recommended to meet the directive set by the GPS to make NZTA business cases more efficient. No BCR has been completed for this phase. â€¢ The request meets the requirements of section 20 of the Land Transport Management Act 2003. | 562911 | 562911 | â€¢ Subject to a condition subsequent that funding endorsement is sought from the Transport Services ESC at its next meeting, |  |  | 1 |  | 293426 | 60085129 | 133233
2024-12-17 | December 2024 Review | New approval | State highway improvements |  | NZTA (BOP) | RoNS Takitimu North Link Stage 2 | Implementation |  | ___ | VHHL | N |  | Approved | Approved by Chief Financial Officer | Enabling works for Takitimu Stage 2. | 5450000 | 5450000 |  |  | 1.3 | 1.3 | Enabling works for Takitimu Stage 2 | 293450 | 60085183 | 133326
2024-12-17 | December 2024 Review | New approval | State highway improvements |  | NZTA (BOP) | RoNS Takitimu North Link Stage 2 | Pre-implementation* |  | ___ | VHHL | N |  | Approved | Approved by Chief Financial Officer | Road of national significance identified in GPS. | 5450000 | 5450000 |  |  | 1.3 | 1.3 |  | 291738 | 60075190 | 133327
2024-12-17 | December 2024 Review | New approval | State highway improvements |  | NZTA (Canterbury) | EOL SH82 Elephant Hill Bridge | Pre-implementation* |  | ___ | HHH | N |  | Approved | Approved by Chief Financial Officer | The renewal of the Elephant Hill River Bridge will provide an effective and efficient long-term sustainable solution for the safe continuity of SH82 | 1318000 | 1318000 |  |  |  | 1 |  | 277569 | 60061466 | 133116
2024-12-05 | December 2024 Review | New approval | Walking and cycling improvements |  | NZTA (Canterbury) | SH1 Templeton to Selwyn River | Property |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | $4,006,800 (incl admin) transferred from CAN Share VFM Programme 60075600 to a new VfM Property phase 60085161 to cover for Property costs relating to Burnham Roundabout. | 4006800 | 4006800 |  |  | 2.1 | 2.1 |  | 293444 | 60085161 | 133222
2024-12-17 | December 2024 Review | New approval | State highway improvements |  | NZTA (Otago) | SH6 Frankton to Kingston Resilience | Pre-implementation* |  | ___ | HHL | N |  | Approved | Approved by Chief Financial Officer | Progressing this project to pre-implementation will contribute to improved resilience on the SH6 Frankton to Kingston corridor. The project demonstrates value for money with the preferred option outlined in the business case achieving a benefit cost ratio of 1.1 (1.2 with WEBs), with the updated costs. The requirements of the section 20 of the Land Transport Management Act 2003 have been met. There is likely to be public support for NZTA addressing the issues at this location, particularly given the resilience concerns that are present. | 1620001 | 1620001 |  |  |  | 1 |  | 277405 | 60061332 | 133226
2024-12-17 | December 2024 Review | New approval | Safety |  | Taupo District Council | Intersection of Wairakei Dr/Huka Falls Rd/Karapiti Rd | Implementation |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Remaining funds transferred from R2Z to LR Improvements | 1300720 | 663367 |  |  |  | 4.1 |  | 292721 |  | 133099
2024-12-16 | December 2024 Review | New approval | Safety |  | Wairoa District Council | Nuhaka Opoutama Road Coastal Erosion Protection Structures | Implementation |  | ___ | HMM | N |  | Approved | Approved by Minister for Crown Appropriation | Crown resilience programmed approved by Minister | 4000000 | 3520000 |  |  |  | 0.2 |  | 293177 |  | 133322
2024-12-17 | December 2024 Review | Cash flow adjustment | Public transport infrastructure | Advance property purchase | Hamilton City Council | 2018 Southern Links Peacocke Arterials HIF | Property |  | ___ | HML | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow adjustment to align with land valuation tribunal process | 0 | 0 |  |  | 2.4 | 2.4 | 3200.2, 3200.3, 3200.4, 3200.5 | 262016 |  | 133312
2024-12-16 | December 2024 Review | Cash flow adjustment | Walking and cycling improvements | Cycle path maintenance | Nelson City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 3 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Aligned with planned physical works plan change following publication of NLTP allocation. | 0 | 20110 | [5 empty] | 285851 |  | 133217
2024-12-16 | December 2024 Review | Cash flow adjustment | Walking and cycling improvements | Cycle path renewal | Nelson City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 3 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Aligned with planned physical works plan change following publication of NLTP allocation. | 0 | -26102 | [5 empty] | 285867 |  | 133217
2024-12-16 | December 2024 Review | Cash flow adjustment | Local road pothole prevention | Drainage renewals | Nelson City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Reprioritization of financial program align to preferred program of work. The reduction in drainage renewals and rehabilitation is a response that could become poorly aligned with GPS direction and availability of forward funding if this becomes the preferred pavement strategy (as opposed to a short term response). | 0 | -289707 | [5 empty] | 285861 |  | 133201
2024-12-05 | December 2024 Review | Cash flow adjustment | State highway operations | Emergency works | NZTA (Tasman) | EW SH6 Hira to Rai HR 20220204 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Confirm closure | 0 | 0 | [5 empty] | 280682 | 60066677 | 133219
2024-12-19 | December 2024 Review | Cash flow adjustment | State highway operations | Emergency works | NZTA (West Coast) | EW Reefton HR 20220210 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Project close | 0 | 0 | [5 empty] | 280720 | 60066794 | 133353
2024-12-16 | December 2024 Review | Cash flow adjustment | Walking and cycling improvements | Footpath maintenance | Nelson City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 3 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Aligned with planned physical works plan change following publication of NLTP allocation. | 0 | 282538 | [5 empty] | 285852 |  | 133217
2024-12-16 | December 2024 Review | Cash flow adjustment | Walking and cycling improvements | Footpath renewal | Nelson City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 3 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Aligned with planned physical works plan change following publication of NLTP allocation. | 0 | -276546 | [5 empty] | 285868 |  | 133217
2024-12-16 | December 2024 Review | Cash flow adjustment | Safety | Low cost / low risk improvements | Hamilton City Council | Low cost / low risk improvements 2024-27 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Council elected members delaying a project. Moving the majority of the funding into the 3rd FY. Has been reflected in Programme Monitor and LCLR spreadsheet. | 0 | 0 | [5 empty] | 287698 |  | 133266
2024-12-16 | December 2024 Review | Cash flow adjustment | State highway improvements | Low cost / low risk improvements | NZTA (Auckland) | Low cost / low risk improvements 2021-24 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 | [5 empty] | 276244 | 60061849 | 133283
2024-12-16 | December 2024 Review | Cash flow adjustment | State highway improvements | Low cost / low risk improvements | NZTA (BOP) | Low cost / low risk improvements 2021-24 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 | [5 empty] | 276247 | 60061854 | 133285
2024-12-16 | December 2024 Review | Cash flow adjustment | State highway improvements | Low cost / low risk improvements | NZTA (Gisborne) | Low cost / low risk improvements 2021-24 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 | [5 empty] | 276258 | 60061855 | 133286
2024-12-16 | December 2024 Review | Cash flow adjustment | State highway improvements | Low cost / low risk improvements | NZTA (Manawatu/Whanganui) | Low cost / low risk improvements 2021-24 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 |  |  |  |  | 60061773 | 276266 | 60061773 | 133289
2024-12-16 | December 2024 Review | Cash flow adjustment | State highway improvements | Low cost / low risk improvements | NZTA (Waikato) | Low cost / low risk improvements 2021-24 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 | [5 empty] | 276296 | 60061837 | 133282
2024-12-16 | December 2024 Review | Cash flow adjustment | State highway improvements | Low cost / low risk improvements | NZTA (Wellington) | Low cost / low risk improvements 2021-24 | State highway improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 | [5 empty] | 276300 | 60061879 | 133287
2024-12-09 | December 2024 Review | Cash flow adjustment | Safety | Low cost / low risk improvements | South Taranaki District Council | Low cost / low risk improvements 2024-27 | External funding - Crown Resilience Programme |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | No increase in funding requested but programme change to allow a ready project to be delivered before further issues arise | 0 | 0 | [5 empty] | 288122 |  | 133042
2024-12-16 | December 2024 Review | Cash flow adjustment | State highway improvements | New roads | NZTA (BOP) | Hairini Link - Stage 4 | Construction |  | ___ | H_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflopw 374,989 from CY and 611,768 from Y1 to Y2 | 0 | 0 |  |  | 2.1 | 2.5 | 60217219 | 194905 | 60217219 | 133224
2024-12-16 | December 2024 Review | Cash flow adjustment | State highway improvements | New traffic management facilities | NZTA (Waikato) | Waikato SEDF | Implementation |  | ___ | LHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | cashflow 743,320 from CY to FY1 | 0 | 0 |  |  | 12 | 12 | 60217125 | 278781 | 60217125 | 133223
2024-12-16 | December 2024 Review | Cash flow adjustment | Investment management (incl. Transport Planning) | Programme Business Case Development | NZTA (Waikato) | Waikato Hospital Travel Planning Initiat | Programme business case |  | HHM | HHL | N | 4 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | 0 | 0 | [5 empty] | 277992 | 60060874 | 133305
2024-12-16 | December 2024 Review | Cash flow adjustment | Walking and cycling improvements | Property purchase (State highways) | NZTA (BOP) | Poike Road Pedestrian & Cycle Facility | Property |  | ___ | H_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Project Close | 0 | 0 |  |  | 2.5 | 2.5 | 60039160 | 246968 | 60039160 | 133303
2024-12-16 | December 2024 Review | Cash flow adjustment | Walking and cycling improvements | Property purchase (State highways) | NZTA (BOP) | SH30A Urban Revitalisation, Conn Rotorua | Property |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Project Close | 0 | 0 |  |  | 0 | 1.1 | Property | 260622 | 60047970 | 133302
2024-12-17 | December 2024 Review | Cash flow adjustment | Safety | Property purchase (local roads) | Hamilton City Council | 2018 Southern Links Peacocke Arterials HIF | Property |  | ___ | HML | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Land Valuation Tribunal process mid-25, until this is over, unlikely to require funding until following year. | 0 | 0 |  |  | 2.4 | 2.4 | EW Arterial, Wairere extension | 262018 |  | 133311
2024-12-16 | December 2024 Review | Cash flow adjustment | Safety | Property purchase (local roads) | Hamilton City Council | 2018-28 Hamilton Southern Links | Property |  | ___ | VHHVH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | to align with land valuation tribunal process | 0 | 0 |  |  | 2.4 | 3 | Property purchased pre-HIF approval | 268912 |  | 133313
2024-12-16 | December 2024 Review | Cash flow adjustment | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | SH26 Onetai Stream Bridge Replacement | Single-Stage Business Case |  | ___ | MMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Project Close | 0 | 0 |  |  | 0 | 0 |  | 233000 | 60059216 | 133300
2024-12-16 | December 2024 Review | Cash flow adjustment | State highway improvements | Resilience improvements | NZTA (BOP) | Crown Resilience Programme LCLR BOP | Implementation |  | ___ | VHHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | cashflow $985,014 from CY to Y1 | -1 | -1 |  |  |  | 4 |  | 288942 | 60071720 | 133220
2024-12-18 | December 2024 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Auckland) | Auck Accelerated Prog: Southern Corridor Improvements | Repayment |  | ___ | H_H | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Update 2024/25 to match planned payment | 0 | 0 |  |  | 0 | 6 |  | 245968 |  | 133314
2024-12-16 | December 2024 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (BOP) | RoNS Takitimu North Link Stage 1 | Implementation |  | ___ | HHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow $5,563,169 allocation from Y4 to CY | 0 | 0 |  |  | 2 | 2 | MCIP 60057025 | 270272 | 60057025 | 133171
2024-12-16 | December 2024 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (BOP) | SH2 Wainui Rd to Opotiki, NSRRP | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow $8,910,000 from CY to y1 and $4,606,629 to Y2 | -2 | -2 |  |  | 1 | 1 |  | 292473 | 60076223 | 133263
2024-12-16 | December 2024 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | Hamilton Ring Road - Wairere/Cobham Interchange | Implementation |  | ___ | HHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | cashflow 191,331 from CY and 3,670 from Y3 to Y1 | 0 | 0 |  |  | 7.6 | 7.6 | 16-015 | 262942 | 60048597 | 133225
2024-12-16 | December 2024 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | RoRS SH1-29 Intersection Improvements | Construction |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow $3,831,580 allocation from Y1 to CY | 0 | 0 |  |  | 2.5 | 2.5 | MCIP 60213469 | 240049 | 60213469 | 133188
2024-12-16 | December 2024 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | SH1 Tokoroa to Taupo Safer Corridor | Implementation |  | ___ | MHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow $2,259,662 allocation from CY to Y1 | 1 | 1 |  |  | 0 | 1.6 |  | 292523 | 60076254 | 133186
2024-12-16 | December 2024 Review | Cash flow adjustment | Local road pothole prevention | Routine drainage maintenance | Nelson City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Reprioritization of financial program align to preferred program of work. The reduction in drainage renewals and rehabilitation is a response that could become poorly aligned with GPS direction and availability of forward funding if this becomes the preferred pavement strategy (as opposed to a short term response). | 0 | 120578 | [5 empty] | 285849 |  | 133201
2024-12-16 | December 2024 Review | Cash flow adjustment | Local road pothole prevention | Sealed pavement maintenance | Hastings District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | HDC revised forecast of works to match local share availability. No funding has been moved from WC113 or WC213 as per their condition of funding | 0 | -310989 | [5 empty] | 285295 |  | 133275
2024-12-16 | December 2024 Review | Cash flow adjustment | Local road pothole prevention | Sealed road pavement rehabilitation | Hastings District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | HDC revised forecast of works to match local share availability. No funding has been moved from WC113 or WC213 as per their condition of funding | 0 | 0 | [5 empty] | 285310 |  | 133275
2024-12-16 | December 2024 Review | Cash flow adjustment | Local road pothole prevention | Sealed road pavement rehabilitation | Nelson City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Reprioritization of financial program align to preferred program of work. The reduction in drainage renewals and rehabilitation is a response that could become poorly aligned with GPS direction and availability of forward funding if this becomes the preferred pavement strategy (as opposed to a short term response). | 0 | -247222 | [5 empty] | 285862 |  | 133201
2024-12-16 | December 2024 Review | Cash flow adjustment | Local road pothole prevention | Sealed road resurfacing | Hastings District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | HDC revised forecast of works to match local share availability. No funding has been moved from WC113 or WC213 as per their condition of funding | 0 | 524793 | [5 empty] | 285308 |  | 133275
2024-12-16 | December 2024 Review | Cash flow adjustment | Local road pothole prevention | Sealed road resurfacing | Nelson City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Reprioritization of financial program align to preferred program of work. The reduction in drainage renewals and rehabilitation is a response that could become poorly aligned with GPS direction and availability of forward funding if this becomes the preferred pavement strategy (as opposed to a short term response). | 0 | 368986 | [5 empty] | 285860 |  | 133201
2024-12-16 | December 2024 Review | Cash flow adjustment | Local road operations | Structures maintenance | Nelson City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Deferral of planned bridge work following escalation of preferred option. | 0 | 0 | [5 empty] | 285850 |  | 133202
2024-12-16 | December 2024 Review | Cash flow adjustment | Local road pothole prevention | Unsealed pavement maintenance | Hastings District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | HDC revised forecast of works to match local share availability. No funding has been moved from WC113 or WC213 as per their condition of funding | 0 | -213806 | [5 empty] | 285296 |  | 133275
2024-12-16 | December 2024 Review | Cash flow adjustment | Local road pothole prevention | Unsealed pavement maintenance | Nelson City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Reprioritization of financial program align to preferred program of work. The reduction in drainage renewals and rehabilitation is a response that could become poorly aligned with GPS direction and availability of forward funding if this becomes the preferred pavement strategy (as opposed to a short term response). | 0 | 65391 | [5 empty] | 285848 |  | 133201
2024-12-16 | December 2024 Review | Cash flow adjustment | Local road pothole prevention | Unsealed road metalling | Hastings District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | HDC revised forecast of works to match local share availability. No funding has been moved from WC113 or WC213 as per their condition of funding | 0 | 2 | [5 empty] | 285307 |  | 133275
2024-12-16 | December 2024 Review | Cash flow adjustment | Local road pothole prevention | Unsealed road metalling | Nelson City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Reprioritization of financial program align to preferred program of work. The reduction in drainage renewals and rehabilitation is a response that could become poorly aligned with GPS direction and availability of forward funding if this becomes the preferred pavement strategy (as opposed to a short term response). | 0 | -18028 | [5 empty] | 285859 |  | 133201
2024-12-16 | December 2024 Review | Cash flow adjustment | State highway improvements |  | NZTA (Waikato) | EOL SH25 Ramarama Stream Bridge | Pre-implementation* |  | ___ | HHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | cashflow 371,789 from CY to Y1 | 0 | 0 |  |  |  | 1 |  | 290355 | 60073573 | 133221
2024-12-16 | December 2024 Review | Cost Decrease | Safety | Activity management planning improvement | Northland Regional Council | Activity Management Planning | Implementation |  | ___ | HHVH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Surplus declaration for 2021-24, New AMP activity is being considered for the 2024-27 period | -788746 | -425923 |  |  | 1 | 1 |  | 277132 |  | 133277
2024-12-16 | December 2024 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Timaru District Council | SfP Timaru District Council 2021-24 | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -65953 | -59358 |  |  |  | 1 |  | 283235 |  | 133214
2024-12-18 | December 2024 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Wellington City Council | WCC Cycleways - Transformational Programme | Single-Stage Business Case |  | ___ | VHHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Project re-prioritised- funding to be returned | -435594 | -222153 |  |  |  | 3.5 | Tawa Connections â€“ SSBC Lite | 281920 |  | 133346
2024-12-18 | December 2024 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Wellington City Council | WCC Cycleways - Transformational Programme | Single-Stage Business Case |  | ___ | VHHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Project re-prioritised- funding to be returned | -2574903 | -1313201 |  |  |  | 3.5 | Middleton Road â€“ Transformation SSBC | 281919 |  | 133345
2024-12-18 | December 2024 Review | Cost Increase | External funding | Emergency works | Central Hawkes Bay District Council | EW Cyclone Gabrielle | Construction | Recovery (NIWE) High FAR | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Reasons for recommendation: This application has been considered to enable the advancement of Central Hawkes Bay District Council Cyclone Gabrielle Recovery programme capitalising on available local share as a result of the Board approved bespoke FAR+30% This funding approval enables the transport network at this location to be reinstated to the appropriate levels of service. | 6714000 | 5975460 | [5 empty] | 293118 |  | 133089
2024-12-16 | December 2024 Review | Cost Decrease | Local road operations | Emergency works | Central Otago District Council | Bridge 93 Emergency Works | Construction | Road Safety Audit | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -5000 | -2550 | [5 empty] | 283053 |  | 133257
2024-12-18 | December 2024 Review | Cost Increase | State highway operations | Emergency works | NZTA (Gisborne) | EW Tai Regionwide HR 20240626 | Construction |  | ___ |  | N |  | Approved | Approved by National Manager, Programmes and Standards (Transport Services) | I support the application; this covers all the event response and recovery. Itâ€™s taken a while to get this together, which is disappointing, but now that M7O is out of TREC I think things will get back to normal. I support the application and I have reviewed the recovery sites. They are in line with the current PIKB guidance for EW funding. I recommend approval. Nick Cook | 8987604 | 8987604 | [5 empty] | 292664 | 60081703 | 133101
2024-12-03 | December 2024 Review | Cost Increase | State highway operations | Emergency works | NZTA (Tasman) | EW SH6 Hira to Rai HR 20220204 | Construction |  | ___ |  | N |  | Approved | Approved by National Manager, Programmes and Standards (Transport Services) | This has turned out to be a complex project. Not helped by the close proximity of the rock fall site. Sequencing of the works has resulted in a detrimental impact on the slip site slowing the works. The PLA is a retrospective one. We are working with our teams to reduce these going forward. The addition of contingencies within the original estimates will help. Going forward, PLAs or Scope change request will be submitted as soon as the forecast exceeds the allocation. Iâ€™m content that the level of intervention is correct and that it provides a value for money solution. Our SME has been involved from the start. Its just the funding side of the project that we need to improve, and we are working hard to change that. I recommend approval. | 3266962 | 3266962 | [5 empty] | 280682 | 60066677 | 132896
2024-12-16 | December 2024 Review | Cost Decrease | External funding | Emergency works | NZTA (Waikato) | EW Waikato Region Extreme HR 20230127 | Construction | EW SH25a Extreme HR 20230127 (NIWE Recovery) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Surplus $1,001,127 re forecast and risk adjustment allows funds to be surplused | -1091228 | -1091228 | [5 empty] | 291201 | 60071632 | 133228
2024-12-06 | December 2024 Review | Cost Increase | State highway operations | Emergency works | NZTA (Waikato) | Ew East Waik Whalebone 20240610 | Construction |  | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | This event and the works carried out are in line with the current PIKB guidance for emergency work. There was no recovery works required, clean up and removal of loose material can be included as response. $ were used in 23/24 and during EOY process, due to no funding approved, -$148,200 rolled over into 24/25. This approval will get rid of -neg approval for 24/25 as discussed with Jo. | 161537 | 161537 | [5 empty] | 292666 | 60081717 | 133229
2024-12-17 | December 2024 Review | Cost Increase | State highway operations | Emergency works | NZTA (West Coast) | EW Reefton HR 20220210 | Construction |  | ___ |  | N |  | Approved | Approved by National Manager, Programmes and Standards (Transport Services) | Itâ€™s disappointing that spend has continued and exceeded the allocation. Measures are now in place to ensure this is flagged before expenditure runs over allocation. The works are complete. To enable the project to close, I recommend approval. | 1963201 | 1963201 | [5 empty] | 280720 | 60066794 | 133164
2024-12-11 | December 2024 Review | Cost Decrease | External funding | Emergency works | Thames-Coromandel District Council | EW - Thames-Coromandel DC February 2023 (Cyclone Gabrielle) | Construction | Initial Response, Investigation an Design-NIWE | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Review request reflects forecasted costs to complete the I & D phase in 2024/25. | -1469085 | -1336867 | [5 empty] | 291297 |  | 133091
2024-12-18 | December 2024 Review | Cost Increase | External funding | Emergency works | Thames-Coromandel District Council | EW - Thames-Coromandel DC February 2023 (Cyclone Gabrielle) | Construction | Permanent Reinstatement & MSQA (NIWE) | ___ |  | N |  | Approved | Approved by National Manager, Programmes and Standards (Transport Services) | $4,868,430 ($3,943,428 NLTF at 81%) for TCDC â€“ February 2023 (NIWE) â€“ Permanent Reinstatement and MSQA (TIO activity ID 161132 / phase ID 283961). This increases the phase funding for 2024/25 from $1,183,371 ($1,100,535 NLTF) to $6,051,801 ($5,043,963 NLTF), and the updated FAR across the phase for 2024/25 will be 83.3%. | 4868430 | 3943641 | [5 empty] | 283961 |  | 133090
2024-12-18 | December 2024 Review | Cost Increase | External funding | Emergency works | Thames-Coromandel District Council | EW - Thames-Coromandel DC January 2023 (NIWE) | Construction | Permanent Reinstatement MSQA & Cons (NIWE) @71% | ___ |  | N |  | Approved | Approved by National Manager, Programmes and Standards (Transport Services) | As part of Budget 24 the Crown approved an appropriation of $280M for local roads emergency works recovery in 24/25 for the January flooding and Cyclone Gabrielle. So far $222M of this has been approved, with $58M still to allocate. I can confirm funding availability for the following cost scope adjustments: â€¢ $3,092,288 ($2,504,753 NLTF at 81%) for Thames Coromandel DC (TCDC) â€“ January 2023 (NIWE) â€“ Permanent Reinstatement MSQA & Cons (TIO activity ID 160986 / phase ID 293056). This increases the phase funding from $2,423,773 ($2,254,109 NLTF) to $5,516,061 ($4,758,862 NLTF), and the updated FAR across the phase will be 86.3% | 3092288 | 2504597 |  |  |  |  | Permanent Reinstatement MSQA & Cons (NIWE) extra Higher FAR | 293056 |  | 133092
2024-12-16 | December 2024 Review | Cost Increase | Local road operations | Environmental maintenance | DOC (Wellington) | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Changes to reflect anticipated phasing of spend over the 3 years, and declaring a surplus where funding Franz Josef causeway strenthening under LCLR in 2024/25 removes the need for causeway renewal work in 2025/26 and 2026/27. | 0 | 18336 | [5 empty] | 287089 |  | 133174
2024-12-12 | December 2024 Review | Cost Increase | Safety | Low cost / low risk improvements | DOC (Manawatu-Whanganui) | Low cost / low risk improvements 2024-27 | Local road improvements |  | __ |  | N |  | Approved | Approved by Chief Financial Officer | CSA for LCLR 2024-27 committed activities omitted from NLTP | 0 | 243255 | [5 empty] | 291089 |  | 133192
2024-12-13 | December 2024 Review | Cost Increase | Safety | Low cost / low risk improvements | DOC (West Coast) | Low cost / low risk improvements 2024-27 | Local road improvements (SPR) |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Just in case this gets funds have added FARs. | 0 | 1252050 | [5 empty] | 287631 |  | 133309
2024-12-12 | December 2024 Review | Cost Increase | Safety | Low cost / low risk improvements | Far North District Council | Low cost / low risk improvements 2024-27 | Local road improvements |  | __ |  | N |  | Approved | Approved by Chief Financial Officer | CSA for LCLR 2024-27 committed activities omitted from NLTP as approved by CFO | 0 | 622921 | [5 empty] | 287652 |  | 133181
2024-12-12 | December 2024 Review | Cost Increase | Safety | Low cost / low risk improvements | Kaipara District Council | Low cost / low risk improvements 2024-27 | Local road improvements |  | __ |  | N |  | Approved | Approved by Chief Financial Officer | CSA for LCLR 2024-27 committed activities omitted from NLTP | 0 | 416276 | [5 empty] | 287787 |  | 133199
2024-12-20 | December 2024 Review | Cost Increase | Investment management (incl. Transport Planning) | Management of the funding allocation system | NZ Transport Agency | Planning & Investment Evidence Base | Implementation |  | ___ | VHHH | N |  | Approved | Approved by Chief Financial Officer | NZTA Board accepted into Nationally Delivered Programme -$8.720M. | 8945117 | 8945117 |  |  |  | 1 | SAP Item ID 60068457 | 278054 | 60068457 | 133379
2024-12-16 | December 2024 Review | Cost Decrease | Safety | Network and asset management | DOC (Wellington) | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Changes to reflect anticipated phasing of spend over the 3 years, and declaring a surplus where funding Franz Josef causeway strenthening under LCLR in 2024/25 removes the need for causeway renewal work in 2025/26 and 2026/27. | 0 | -52099 | [5 empty] | 287093 |  | 133174
2024-12-16 | December 2024 Review | Cost Increase | Local road operations | Network service maintenance | DOC (Wellington) | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Changes to reflect anticipated phasing of spend over the 3 years, and declaring a surplus where funding Franz Josef causeway strenthening under LCLR in 2024/25 removes the need for causeway renewal work in 2025/26 and 2026/27. | 0 | 3537 | [5 empty] | 287090 |  | 133174
2024-12-12 | December 2024 Review | Cost Increase | State highway improvements | New roads | NZTA (Auckland) | RoNS East West Link | Pre-implementation* |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | INTERPHASE TRANSFER: VOS Approval of $500,000(inc admin) from AKL RoNS Proj Dev 60075346 (DBC) to RoNS East West Link 60026605 (Pre-Imp). | 500000 | 500000 |  |  | 1.9 | 1.9 | 60026605 | 233292 | 60026605 | 133273
2024-12-18 | December 2024 Review | Cost Increase | State highway improvements | New roads | NZTA (Wellington) | Wellington RoNS (5) - Transmission Gully | Construction |  | ___ | HHL | N |  | Approved | Approved by Chief Financial Officer | Approval of $43M for additional funding to NZ Transport Agency Waka Kotahi - for Wellington RoNS (5) â€“ Transmission Gully - for the construction (enabling works) phase to support the completion of Transmission Gully following changes to commercial terms approved by the Board | 43000000 | 43000000 |  |  | 1.4 | 1.4 | 60216287 | 226528 | 60216287 | 133348
2024-12-16 | December 2024 Review | Cost Decrease | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | NZTA (BOP) | Combined PT services and infrastructure | Single-Stage Business Case |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Project Close | -9416 | -9416 |  |  |  |  | 60061346 | 277650 | 60061346 | 133281
2024-12-13 | December 2024 Review | Cost Increase | Public transport services | Passenger services - bus | Gisborne District Council | CERF-Bus Driver Ts & Cs | Implementation |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Update to new Normal FAR rate for 2024-27 NLTP | 0 | 3921 |  |  |  | 1 |  | 284198 |  | 133308
2024-12-16 | December 2024 Review | Cost Decrease | Investment management (incl. Transport Planning) | Programme Business Case Development | NZTA (Tasman) | Richmond Programme Business Case | Programme business case |  | H__ | M__ | N | 3 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Project Close | -71556 | -71556 |  |  |  |  | Stage 1 | 269651 | 60055919 | 133304
2024-12-16 | December 2024 Review | Cost Decrease | Walking and cycling improvements | Property purchase (State highways) | NZTA (Auckland) | SH1 Dome Valley Safety Improvements | Property |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Project Close | -209975 | -209975 |  |  | 0 | 1 |  | 292433 | 60076192 | 133183
2024-12-16 | December 2024 Review | Cost Decrease | Walking and cycling improvements | Property purchase (State highways) | NZTA (Marlborough) | Kaikoura Nov 2016 EQ - Lewis Pass Altern Rte Upgr -Marlborou | Property |  | ___ | H_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Project closure | -88080 | -88080 |  |  | 1.4 | 1.4 | 60042764 | 249706 | 60042764 | 133299
2024-12-16 | December 2024 Review | Cost Increase | Walking and cycling improvements | Property purchase (State highways) | NZTA (Otago) | RoRS Queenstown Package | Property |  | ___ | MHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | To transfer $2,500,000 from Queenstown project contingency [60063228] to Property phase [60057045] to tidy up and align budgets and forecast more closely at a phase level. | 2600001 | 2600001 |  |  | 3.5 | 3.5 | MCIP 60057045 | 259376 | 60057045 | 133298
2024-12-18 | December 2024 Review | Cost Increase | Walking and cycling improvements | Property purchase (State highways) | NZTA (Waikato) | RoNS SH1 Cambridge to Piarere | Property |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase transfer $69,880,924 from WAI Share RoNS Property 60075497 to RoNS SH1 Cambridge to Piarere LT Stage1 60048204 | 74073776 | 74073776 |  |  | 0 | 0.9 | 60048204 | 252060 | 60048204 | 133319
2024-12-16 | December 2024 Review | Cost Decrease | Walking and cycling improvements | Property purchase (State highways) | NZTA (Waikato) | SH1 Cambridge to Piarere online safety improvements | Property |  | ___ | VHLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | project close | -1844404 | -1844404 |  |  | 0 | 1.6 |  | 277656 | 60061524 | 133110
2024-12-11 | December 2024 Review | Cost Increase | Walking and cycling improvements | Property purchase (State highways) | NZTA (Waikato) | SH2 Pokeno to Mangatarata Improvement: Sec A | Property |  | ___ | H_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow | SAP_PPM still has funds so updated to match. | 473 | 473 |  |  | 1.3 | 1.3 | 60470502 | 224231 | 60470502 | 133268
2024-12-16 | December 2024 Review | Cost Decrease | Walking and cycling improvements | Property purchase (State highways) | NZTA (West Coast) | SH7 Ahaura River Bridge Replacement | Property |  | ___ | H__ | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Project completed. Surplus the remaining funding. | -54532 | -54532 |  |  | 0 | 0 | 60052054 | 250916 | 60052054 | 133187
2024-12-18 | December 2024 Review | Cost Decrease | State highway improvements | Replacement of bridges and other structures | NZTA (Manawatu/Whanganui) | EOL SH43 Kururau Stream Water Drive | Single-Stage Business Case |  | ___ | HHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase transfer allocation of $7419 from 60073583EOL SH25 Boundary Creek Bridge and $80,378 from 60073577 EOL SH43 Kururau Stream Water Drive to 60073597 EOL SH27 Ohinekaua Stream Bridge | -87612 | -87612 |  |  |  | 1 |  | 290338 | 60073577 | 133355
2024-12-18 | December 2024 Review | Cost Decrease | State highway improvements | Replacement of bridges and other structures | NZTA (Taranaki) | EOL SH3 Mangapepeki No. 2 Culvert | Single-Stage Business Case |  | ___ | HHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase transfer $55,806 from 60073588 EOL SH3 Mangapepeki No. 2 Culvert to 60073572 EOL SH25 Ramarama Stream Bridge | -60831 | -60831 |  |  |  | 1 |  | 290343 | 60073588 | 133357
2024-12-18 | December 2024 Review | Cost Decrease | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | EOL SH25 Boundary Creek Bridge | Single-Stage Business Case |  | ___ | HHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase transfer allocation of $7419 from 60073583EOL SH25 Boundary Creek Bridge and $80,378 from 60073577 EOL SH43 Kururau Stream Water Drive to 60073597 EOL SH27 Ohinekaua Stream Bridge | -8089 | -8089 |  |  |  | 3 |  | 290364 | 60073583 | 133356
2024-12-18 | December 2024 Review | Cost Increase | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | EOL SH25 Ramarama Stream Bridge | Single-Stage Business Case |  | ___ | HHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase transfer $55,806 from 60073588 EOL SH3 Mangapepeki No. 2 Culvert to 60073572 EOL SH25 Ramarama Stream Bridge | 60830 | 60830 |  |  |  | 1 |  | 290337 | 60073572 | 133354
2024-12-18 | December 2024 Review | Cost Increase | State highway improvements | Replacement of bridges and other structures | NZTA (Waikato) | EOL SH27 Ohinekaua Stream Bridge | Single-Stage Business Case |  | ___ | HHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase transfer allocation of $7419 from 60073583EOL SH25 Boundary Creek Bridge and $80,378 from 60073577 EOL SH43 Kururau Stream Water Drive to 60073597 EOL SH27 Ohinekaua Stream Bridge | 95700 | 95700 |  |  |  | 1 |  | 290348 | 60073597 | 133358
2024-12-16 | December 2024 Review | Cost Decrease | Local road improvements | Resilience improvements | Gisborne District Council | East Cape Road -Route Security | Implementation |  | ___ | LLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | As agreed with MIBE additional funds to PGF Route 2roject is complete and additional funds to PGF Route 2 | -631945 | -631945 |  |  | 0.8 | 0.8 | Implimentation | 278134 |  | 133279
2024-12-18 | December 2024 Review | Cost Increase | State highway improvements | Resilience improvements | NZTA (West Coast) | SH6 WTCT Haast to Hawea RESIL IMPR | Single-Stage Business Case |  | ___ | HHL | N |  | Approved | Approved by Chief Financial Officer | Variation request for additional $600k (excl 9% admin) due to increase in scope. | 653999 | 653999 |  |  |  | 1 |  | 277534 | 60069351 | 133332
2024-12-18 | December 2024 Review | Cost Increase | Safety | Road improvements | Ashburton District Council | Ashburton Tinwald Connectivity | Detailed Business Case |  | ___ | VHHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Reinstatement of previously returned funding to support completion of business case | 140000 | 71400 |  |  |  | 1.2 | Detailed Business Case | 264996 |  | 132889
2024-12-16 | December 2024 Review | Cost Increase | Safety | Road improvements | Gisborne District Council | Tairawhiti Roading - LOS improvements (PGF2) East Cape Road | Construction |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | cashflow transfer between projects as agreed with MIBE | 631945 | 631945 |  |  | 1 | 1 | PGF2 Route 2 Gisborne Urban Zone | 269597 |  | 133280
2024-12-16 | December 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Auckland) | ANO SH16 Te Atatu Interchange EB On Ramp | Pre-implementation* |  | ___ | MHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | INTERPHASE TRANSFER - Pls move $10,401 from 60070104 Te Atatu back to parent Prre-imp 60056410 | -11337 | -11337 |  |  | 5.3 | 5.3 |  | 284036 | 60070104 | 133288
2024-12-16 | December 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Auckland) | Auckland Network Optimisation (ANO) Programme | Pre-implementation* |  | ___ | HHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | INTERPHASE TRANSFER - Pls move $10,401 from 60070104 Te Atatu back to parent Prre-imp 60056410 | 11336 | 11336 |  |  |  | 3.2 | InfoHub ID 28116348 ¦ SAP 60056410 | 254838 | 60056410 | 133296
2024-12-16 | December 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Auckland) | SH1 Dome Valley Safety Improvements | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Project Close | -1597307 | -1597307 |  |  | 0 | 1 |  | 292434 | 60076191 | 133182
2024-12-16 | December 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (BOP) | CIP SH30 Eastern Corridor, Rotorua | Construction |  | ___ | HMM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase transfer $310,923 from construction 60059176 to pre imp 60059175 to close out pre imp | -310921 | -310921 |  |  | 0 | 4.1 |  | 271547 | 60059176 | 133265
2024-12-16 | December 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (BOP) | CIP SH30 Eastern Corridor, Rotorua | Pre-implementation* |  | ___ | HMM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase transfer $310,923 from construction 60059176 to pre imp 60059175 to close out pre imp | 310924 | 310924 |  |  | 0 | 4.1 |  | 271546 | 60059175 | 133264
2024-12-16 | December 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Canterbury) | RoRS SH75 Halswell Rd Imps | Implementation |  | ___ | HML | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Transfer $4,073,208 to Imp phase (SAP item ID 60031611) from project contingency (SAP item ID 60063224) to cover the total certified variation amount included in the Contractors November 2024 Claim. | -4236136 | -4236136 |  |  | 2 | 2 | MCIP 60063224 | 278966 | 60063224 | 133290
2024-12-16 | December 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Canterbury) | RoRS SH75 Halswell Rd Imps | Implementation |  | ___ | HML | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Transfer $4,073,208 to Imp phase (SAP item ID 60031611) from project contingency (SAP item ID 60063224) to cover the total certified variation amount included in the Contractors November 2024 Claim. | 4236136 | 4236136 |  |  | 2 | 2 | MCIP 60031611 | 231955 | 60031611 | 133301
2024-12-16 | December 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Hawkes Bay) | SH38 Wairoa to Murupara | Detailed Business Case |  | ___ | MLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer: Please transfer $358,691 from 60055024 Pre-Implementation, $4,250 to 60055023 Detailed Busines Case and $354,441 to 60055025 Implementation, Pre-Imp & DBC projects can then be closed | 4633 | 4633 |  |  | 2.1 | 0.9 | 60055023 | 278804 | 60055023 | 133293
2024-12-16 | December 2024 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Otago) | RoRS Queenstown Package | Implementation |  | ___ | MHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | To transfer $9,400,000 from Queenstown project contingency [60063228] to Construction phase [60057044]to tidy up and align budgets and forecast more closely at a phase level. | 9775999 | 9775999 |  |  | 3.5 | 3.5 | MCIP 60057044 | 259377 | 60057044 | 133297
2024-12-16 | December 2024 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Otago) | RoRS Queenstown Package | Implementation |  | ___ | MHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | To transfer total of $11,900,000 Queenstown project contingency [SAP item ID 60063228] to 1) Property phase $2,500,000 [60057045]Â and 2) to Construction phase $9,400,000 [60057044] to tidy up and align budgets and forecast more closely at a phase level. | -12376000 | -12376000 |  |  | 3.5 | 3.5 | MCIP 60063228 | 278964 | 60063228 | 133291
2024-12-16 | December 2024 Review | Cost Increase | State highway improvements | Seal extension | NZTA (Hawkes Bay) | SH38 Wairoa to Murupara | Implementation |  | ___ | MLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer: Please transfer $358,691 from 60055024 Pre-Implementation, $4,250 to 60055023 Detailed Busines Case and $354,441 to 60055025 Implementation, Pre-Imp & DBC projects can then be closed | 386341 | 386341 |  |  | 2.1 | 0.9 | Implementation | 254943 | 60055025 | 133295
2024-12-16 | December 2024 Review | Cost Decrease | State highway improvements | Seal extension | NZTA (Hawkes Bay) | SH38 Wairoa to Murupara | Pre-implementation* |  | ___ | MLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer: Please transfer $358,691 from 60055024 Pre-Implementation, $4,250 to 60055023 Detailed Busines Case and $354,441 to 60055025 Implementation, Pre-Imp & DBC projects can then be closed | -390973 | -390973 |  |  | 2.1 | 0.9 | Pre Impl Trial | 254942 | 60055024 | 133294
2024-12-16 | December 2024 Review | Cost Decrease | Local road operations | Structures component replacements | DOC (Wellington) | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Changes to reflect anticipated phasing of spend over the 3 years, and declaring a surplus where funding Franz Josef causeway strenthening under LCLR in 2024/25 removes the need for causeway renewal work in 2025/26 and 2026/27. | 0 | -364116 | [5 empty] | 287098 |  | 133174
2024-12-16 | December 2024 Review | Cost Increase | Local road operations | Structures maintenance | DOC (Wellington) | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Changes to reflect anticipated phasing of spend over the 3 years, and declaring a surplus where funding Franz Josef causeway strenthening under LCLR in 2024/25 removes the need for causeway renewal work in 2025/26 and 2026/27. | 0 | 11330 | [5 empty] | 287085 |  | 133174
2024-12-16 | December 2024 Review | Cost Decrease | Walking and cycling improvements | Walking facilities | Timaru District Council | SfP Timaru District Council 2021-24 | Pre-implementation* |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -40000 | -36000 |  |  |  | 1 |  | 281446 |  | 133213
2024-12-18 | December 2024 Review | Cost Decrease | Walking and cycling improvements | Walking facilities | Wellington City Council | General Targeted Improvements | Implementation |  | ___ | VHHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Project re-prioritised- funding to be returned | -5968603 | -3043988 |  |  | 1.2 | 1 |  | 292651 |  | 133347
2024-12-12 | December 2024 Review | Cost Decrease | State highway improvements |  | NZTA (Auckland) | AKL Share RoNS Project Development | Detailed Business Case |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | INTERPHASE TRANSFER: VOS Approval of $500,000(inc admin) from AKL RoNS Proj Dev 60075346 (DBC) to RoNS East West Link 60026605 (Pre-Imp). | -500000 | -500000 |  |  |  | 1 | AKL Share RoNS Project Development | 291831 | 60075346 | 133272
2024-12-05 | December 2024 Review | Cost Decrease | State highway improvements |  | NZTA (Canterbury) | CAN Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | To transfer $4,006,800 (incl admin) from CAN Share VFM Programme 60075600 to a new VfM Property phase 60085161 to cover for Property costs relating to Burnham Roundabout. | -4006799 | -4006799 |  |  |  | 1 | 60075600 CAN Share VFM Safety Imp Prog | 289807 | 60075600 | 133218
2024-12-16 | December 2024 Review | Cost Decrease | State highway improvements |  | NZTA (Waikato) | SH3 Awakino to Mt Messenger Corridor Improvements (Waikato) | Property |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | close project | -95933 | -95933 |  |  | 1.5 | 1.5 |  | 292773 | 60082553 | 133274
2024-12-18 | December 2024 Review | Cost Decrease | Walking and cycling improvements |  | NZTA (Waikato) | WAI Share RoNS Property | Property |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase transfer $69,880,924 from WAI Share RoNS Property 60075497 to RoNS SH1 Cambridge to Piarere LT Stage1 60048204 | -74073779 | -74073779 |  |  |  | 1 |  | 291902 | 60075497 | 133318