## Monthly review decision report
Date of approval | Review Name | Request Type | Activity Class | Work Category | Organisation | Project name | Phase | Phase Label | NZTA profile | Owner profile | Approved by Owner | Priority | Request Decision | Decision Status | Reason | Total cost of change | NZTA share change | Condition | Latest NZTA BCR | Latest Government BCR | Latest National BCR | Your Phase reference | TIO Phase id | SAP item id | TIO Request id
2025-05-13 | May 2025 Review | New approval | Local road operations | Emergency works | Gisborne District Council | EW Dec 2024 Rain event | Construction |  | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | WC141 funding required to reinstate GDC's roading network to the appropriate level of service following a weather event | 885658 | 779379 | [5 empty] | 293729 |  | 134041
2025-05-13 | May 2025 Review | New approval | State highway operations | Emergency works | NZTA (West Coast) | EW West Coast HR 20241026 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | The recovery in response elements were discussed and agreed with the Activity Class Manager, as being in line with the current PIKB guidance. The works were required for safety to support the road from imminent failure, had little design, as they are rock filled edge supports and individually of low cost. This also included drainage and Culvert works. It should be noted that all physical works are now completed. I support the PLA application and recommend approval. This approval is both for a PLA as new approval. | 4509086 | 4509086 | [5 empty] | 293417 | 60084991 | 134239
2025-05-05 | May 2025 Review | New approval | Local road operations | Emergency works | Ruapehu District Council | EW - RDC Weather Event - Aug / Sept 2024 | Construction | Work Required | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | This work would enable the Ruapehu DC to undertake required work to return roads to a pre-existing or reduced level of service. This application complies with the requirements of WC 141 and AC8 | 244000 | 183000 |  |  |  |  | 2 | 293630 |  | 133697
2025-05-05 | May 2025 Review | New approval | Local road operations | Emergency works | Ruapehu District Council | EW - RDC Weather Event - Aug / Sept 2024 | Repayment | Works Completed | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | This work would enable the Ruapehu DC to undertake required work to return roads to a pre-existing or reduced level of service. This application complies with the requirements of WC 141 and AC8 | 184473 | 138355 |  |  |  |  | 1 | 293629 |  | 133696
2025-05-28 | May 2025 Review | New approval | External funding | Emergency works | Tararua District Council | EW Cyclone Gabrielle | Construction | Cyclone Gabrielle Recovery 2025-26 - Normal FAR | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Funding required under WC 141 to reinstate TDC network to the appropriate LOS post Cyclone Gabrielle | 1687088 | 1231574 | [5 empty] | 293862 |  | 134527
2025-05-28 | May 2025 Review | New approval | Local road operations | Emergency works | Wairoa District Council | EW event December 2024 | Construction |  | ___ |  | N |  | Approved | Approved by Senior Manager, Maintenance and Operations (Transport Services) | Funding required under WC141 to re-instate Wairoa DC roading network to an appropriate level of service post event | 2427031 | 2253018 | [5 empty] | 293738 |  | 133881
2025-05-07 | May 2025 Review | New approval | State highway improvements | Road improvements | NZTA (Waikato) | WAI VfM Safety Imp â€“ Small Projects | Implementation | WAI VfM Safety Imp â€“ Small Infra Region | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $8,478,000 ex admin from 60075459 to 60083257 | 9241020 | 9241020 |  |  | 6 | 6 | WAI VfM Safety Imp â€“ Small Infra Region | 292943 | 60083257 | 134385
2025-05-06 | May 2025 Review | New approval | Walking and cycling improvements |  | Auckland Transport | Airport Access - Short-term Improvements | Implementation |  | ___ | MHM | N |  | Declined | Declined by Chief Financial Officer | Recommend to be declined New Zealand Transport Agency as a crown entity takes its funding direction from the Government Policy Statement on land transport. An Investment Quality Assurance assessment has been undertaken using the GPS 2024-27 and concluded that this project doesn't prioritise to a level high enough to be funded in the current NLTP period. | 10170000 | 5186700 |  |  | 1.3 | 1.3 | 452.2627 | 262680 |  | 131162
2025-05-29 | May 2025 Review | New approval | Public transport infrastructure |  | Auckland Transport | Audit Repayment | Repayment |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | NZTA continues to retain a financial interest, and according to the funding conditions, any proceeds from the sale or transfer of surplus properties must be proportionally reimbursed to NZTA. The total amount recoverable by NZTA is $12,937,668. | -12937668 | -12937668 |  |  |  | 1 | 333.2939 | 293852 |  | 134454
2025-05-21 | May 2025 Review | New approval | Public transport infrastructure |  | Greater Wellington | Bus Driver Fund | Implementation |  | ___ | HHL | N |  | Approved | Approved by Minister for Crown Appropriation | See attachment. | 299000 | 224250 |  |  |  | 1 | 561.2938 | 293853 |  | 134611
2025-05-12 | May 2025 Review | New approval | Safety |  | NZ Transport Agency | Asset Management Data Standard (Deft) - Rollout | Implementation |  | ___ | VHMM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Funds being moved from phase 277727. | 9640000 | 9640000 |  |  |  | 4.4 |  | 293861 | 60084391 | 134489
2025-05-09 | May 2025 Review | New approval | State highway improvements |  | NZTA (Auckland) | AKLD VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $300,000 ex admin from 60075303 to 60083161 | 330000 | 330000 |  |  | 6 | 6 | AKLD VfM Safety Imp - Small Infra React | 292892 | 60083161 | 134474
2025-05-29 | May 2025 Review | New approval | Walking and cycling improvements |  | NZTA (Auckland) | RoNS NW Alternative State Highway (SH16) | Property |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | To interphase transfer $50M excl admin ($53.25M incl 6.5% admin) from AKL Property Share to RoNS ASH property phase | 53250000 | 53250000 |  |  |  | 1 |  | 292854 | 60083039 | 134458
2025-05-22 | May 2025 Review | New approval | State highway improvements |  | NZTA (Auckland) | RoRS SH1 Papakura to Bombay Stage 2 | Pre-implementation* |  | ___ | VHHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | The sponsor has requested for Papakura to Bombay project to be split into Stage 1 and Stage 2. Hence, we created separate/ new initiative 174102025 for stage 2 and have added the below listed phases under it. We need to journal costs from the old project phases into these newly created phases -- pre-Imp and Property item (Pre-imp 60087755 Property 60087756) WITHOUT allocation but I have given $10 for admin rate to work. | 11 | 11 |  |  | 2.5 |  |  | 293865 | 60087755 | 134637
2025-05-22 | May 2025 Review | New approval | Walking and cycling improvements |  | NZTA (Auckland) | RoRS SH1 Papakura to Bombay Stage 2 | Property |  | ___ | VHHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | The sponsor has requested for Papakura to Bombay project to be split into Stage 1 and Stage 2. Hence, we created separate/ new initiative 174102025 for stage 2 and have added the below listed phases under it. We need to journal costs from the old project phases into these newly created phases -- pre-Imp and Property item (Pre-imp 60087755 Property 60087756) WITHOUT allocation but I have given $50 for admin rate to work. | 11 | 11 |  |  | 2.5 |  |  | 293866 | 60087756 | 134638
2025-05-20 | May 2025 Review | New approval | Walking and cycling improvements |  | NZTA (BOP) | RoNS SH29 A Widening Tauriko West | Property |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase transfer a total of $20M excl admin ($21.3M incl 6.5% admin) to 60087155 of $5M excl admin and 60083050 of $15M excl admin - both are RoNS Tauriko West Projects. | 5325000 | 5325000 |  |  | 1.9 | 1.8 |  | 293754 | 60087155 | 134579
2025-05-20 | May 2025 Review | New approval | Walking and cycling improvements |  | NZTA (BOP) | RoNS SH29 Offline Tauriko West | Property |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase transfer a total of $20M excl admin ($21.3M incl 6.5% admin) to 60087155 of $5M excl admin and 60083050 of $15M excl admin - both are RoNS Tauriko West Projects. | 16295500 | 16295500 |  |  | 1.9 | 1.8 |  | 292851 | 60083050 | 134384
2025-05-02 | May 2025 Review | New approval | State highway improvements |  | NZTA (BOP) | Takitimu North Link Stage 1 Revocation | Pre-implementation* |  | ___ | LML | N |  | Approved | Approved by Chief Financial Officer | See attachment in TIO. | 1650000 | 1650000 |  |  |  | 1 | Takitimu North Link Stage 1 Revocation | 289312 | 60072823 | 132676
2025-05-12 | May 2025 Review | New approval | State highway improvements |  | NZTA (BOP) | W2T Waihi to Omokoroa (Safer Corridor) | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $5,000,000 ex admin from 60075222 to 60084936 | 5450000 | 5450000 |  |  | 0 | 1 |  | 293409 | 60084936 | 134483
2025-05-15 | May 2025 Review | New approval | State highway improvements |  | NZTA (Canterbury) | CAN VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $2,750,000 ex admin from 60075600 to 60083177 | 2997500 | 2997500 |  |  | 6 | 6 | CAN VfM Safety Imp â€“ Small Infra Region | 292899 | 60083177 | 134562
2025-05-15 | May 2025 Review | New approval | State highway improvements |  | NZTA (Canterbury) | SH73 and Waimakariri Gorge Rd IS | Implementation |  | ___ | HMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $1,710,000ex admin from 60075600 to 60083338 | 1863900 | 1863900 |  |  | 6 | 6 |  | 292972 | 60083338 | 134556
2025-05-15 | May 2025 Review | New approval | State highway improvements |  | NZTA (Canterbury) | SH73 and Waimakariri Gorge Rd IS | Pre-implementation* |  | ___ | HMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $190,000 ex admin from 60075600 to 60083337 | 207100 | 207100 |  |  | 6 | 6 |  | 292994 | 60083337 | 134555
2025-05-08 | May 2025 Review | New approval | State highway improvements |  | NZTA (Gisborne) | GIS VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $300,000 ex admin from 60075397 to 60083182 | 327000 | 327000 |  |  | 6 | 6 | GIS VfM Safety Imp â€“ Small Infra React | 292901 | 60083182 | 134409
2025-05-08 | May 2025 Review | New approval | State highway improvements |  | NZTA (Hawkes Bay) | HAWK VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $300,000 ex admin from 60075469 to 60083189 | 327000 | 327000 |  |  | 6 | 6 | HAWK VfM Safety Imp â€“ Small Infra React | 292905 | 60083189 | 134411
2025-05-08 | May 2025 Review | New approval | State highway improvements |  | NZTA (Hawkes Bay) | HAWK VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $2,510,000 ex admin from 60075469 to 60083191 | 2735901 | 2735901 |  |  | 6 | 6 | HAWK VfM Safety Imp â€“ Small Infra Region | 292907 | 60083191 | 134413
2025-05-28 | May 2025 Review | New approval | Walking and cycling improvements |  | NZTA (Manawatu/Whanganui) | Central â€“ Legacy Property Acquisition | Property |  | ___ | HHL | N |  | Approved | Approved by Chief Financial Officer | his investment enables NZ Transport Agency Waka Kotahi to complete Property purchases where there is no identified project in place, or the projects are complete and final property obligations need to be met | 3195000 | 3195000 |  |  |  | 1 |  | 289219 | 60072678 | 132616
2025-05-08 | May 2025 Review | New approval | State highway improvements |  | NZTA (Manawatu/Whanganui) | MNWI VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $2,120,000 ex admin from 60075295 to 60083205 | 2310800 | 2310800 |  |  | 6 | 6 | MNWI VfM Safety Imp â€“ Small Infra Region | 292915 | 60083205 | 134420
2025-05-08 | May 2025 Review | New approval | State highway improvements |  | NZTA (Manawatu/Whanganui) | MNWI VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $300,000ex admin from 60075295 to 60083203 | 327000 | 327000 |  |  | 6 | 6 | MNWI VfM Safety Imp â€“ Small Infra React | 292913 | 60083203 | 134418
2025-05-08 | May 2025 Review | New approval | State highway improvements |  | NZTA (Manawatu/Whanganui) | Otaki to North of Levin - SH1/SH57 - northern section | Implementation |  | ___ | HHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $9,000,000 ex admin from 60075295 to 60087505 | 9810000 | 9810000 |  |  | 0 | 1.6 |  | 293855 | 60087505 | 134422
2025-05-08 | May 2025 Review | New approval | State highway improvements |  | NZTA (Manawatu/Whanganui) | SH1 Bulls to Sanson CI - Pukenui Rd IS | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $1,350,000 ex admin from 60075295 to 60087504 | 1471500 | 1471500 |  |  | 0 | 1.6 |  | 293854 | 60087504 | 134421
2025-05-08 | May 2025 Review | New approval | State highway improvements |  | NZTA (Manawatu/Whanganui) | SH1 Sanson to Foxton | Implementation |  | ___ | HMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $1,800,000 ex admin from 60075295 to 60083323 | 1962000 | 1962000 |  |  | 6 | 6 |  | 292968 | 60083323 | 134401
2025-05-08 | May 2025 Review | New approval | State highway improvements |  | NZTA (Manawatu/Whanganui) | SH1 Sanson to Foxton | Pre-implementation* |  | ___ | HMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $200,000 ex admin from 60075295 to 60083322 $200,000 | 218000 | 218000 |  |  | 6 | 6 |  | 292992 | 60083322 | 134402
2025-05-16 | May 2025 Review | New approval | State highway improvements |  | NZTA (Manawatu/Whanganui) | SH3 Rangitikei Line and SH54 Int | Implementation |  | ___ | HMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $7,200,000 ex admin from 60075295 to 60083378 | 7848000 | 7848000 |  |  | 6 | 6 |  | 293003 | 60083378 | 134569
2025-05-16 | May 2025 Review | New approval | State highway improvements |  | NZTA (Manawatu/Whanganui) | SH3 Rangitikei Line and SH54 Int | Pre-implementation* |  | ___ | HMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $800,000 ex admin from 60075295 to 60083377 | 872000 | 872000 |  |  | 6 | 6 |  | 293000 | 60083377 | 134568
2025-05-08 | May 2025 Review | New approval | State highway improvements |  | NZTA (Manawatu/Whanganui) | SH54 & Milson Line IS SNP | Implementation |  | ___ | HMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $6,300,000 ex admin from 60075295 to 60083288 | 6867000 | 6867000 |  |  | 6 | 6 |  | 292990 | 60083288 | 134404
2025-05-08 | May 2025 Review | New approval | State highway improvements |  | NZTA (Manawatu/Whanganui) | SH54 & Milson Line IS SNP | Pre-implementation* |  | ___ | HMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $700,000 ex admin from 60075295 to 60083287 | 763000 | 763000 |  |  | 6 | 6 |  | 292955 | 60083287 | 134403
2025-05-14 | May 2025 Review | New approval | State highway improvements |  | NZTA (Marlborough) | MARL VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $300,000 ex admin from 60075526 to 60083197 | 327000 | 327000 |  |  | 6 | 6 | MARL VfM Safety Imp â€“ Small Infra React | 292910 | 60083197 | 134523
2025-05-14 | May 2025 Review | New approval | State highway improvements |  | NZTA (Marlborough) | MARL VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $1,370,000 ex admin from 60075526 to 60083157 | 1493300 | 1493300 |  |  | 6 | 6 | MARL VfM Safety Imp â€“ Small Infra Region | 292911 | 60083157 | 134513
2025-05-12 | May 2025 Review | New approval | State highway improvements |  | NZTA (Nelson) | NEL VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $300,000 ex admin from 60075473 to 60083210 | 327000 | 327000 |  |  | 6 | 6 | NEL VfM Safety Imp â€“ Small Infra React | 292917 | 60083210 | 134459
2025-05-09 | May 2025 Review | New approval | State highway improvements |  | NZTA (Northland) | NTLD VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $1,200,000 ex admin from 60075196 to 60083220 | 1320000 | 1320000 |  |  | 6 | 6 | NTLD VfM Safety Imp â€“ Small Infra Region | 292923 | 60083220 | 134463
2025-05-09 | May 2025 Review | New approval | State highway improvements |  | NZTA (Northland) | NTLD VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $300,000 ex admin from 60075196 to 60083217 | 330000 | 330000 |  |  | 6 | 6 | NTLD VfM Safety Imp â€“ Small Infra React | 292921 | 60083217 | 134461
2025-05-14 | May 2025 Review | New approval | State highway improvements |  | NZTA (Otago) | SH1 Mosgiel to Balclutha | Implementation |  | ___ | VHHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $6,000,000 ex admin from 60075581 | 6540000 | 6540000 |  |  | 2.1 | 2.1 |  | 284045 | 60070283 | 134519
2025-05-14 | May 2025 Review | New approval | State highway improvements |  | NZTA (Otago) | SH1 Waitati Valley Rd - Pine Hill Rd SNP | Implementation |  | ___ | HMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $ admin from to | 2781900 | 2781900 |  |  | 6 | 6 |  | 292963 | 60083308 | 134526
2025-05-14 | May 2025 Review | New approval | State highway improvements |  | NZTA (Otago) | SH1 Waitati Valley Rd - Pine Hill Rd SNP | Pre-implementation* |  | ___ | HMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $281,000 ex admin from 60075581 | 306290 | 306290 |  |  | 6 | 6 |  | 292962 | 60083307 | 134525
2025-05-15 | May 2025 Review | New approval | State highway improvements |  | NZTA (Southland) | SH1 & SH93 IS (Mataura) | Implementation |  | ___ | HMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $3,600,000 ex admin from 60075556 to 60083298 | 3924000 | 3924000 |  |  | 6 | 6 |  | 292959 | 60083298 | 134554
2025-05-15 | May 2025 Review | New approval | State highway improvements |  | NZTA (Southland) | SH1 & SH93 IS (Mataura) | Pre-implementation* |  | ___ | HMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $400,000 ex admin from 60075556 to 60083297 | 436000 | 436000 |  |  | 6 | 6 |  | 292958 | 60083297 | 134553
2025-05-15 | May 2025 Review | New approval | State highway improvements |  | NZTA (Southland) | STLD VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $488,000 ex admin from 60075556 to 60083235 | 531920 | 531920 |  |  | 6 | 6 | STLD VfM Safety Imp â€“ Small Infra Region | 292931 | 60083235 | 134544
2025-05-08 | May 2025 Review | New approval | State highway improvements |  | NZTA (Taranaki) | TAR VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $300,000 ex admin from 60075244 to 60083241 | 327000 | 327000 |  |  | 6 | 6 | TAR VfM Safety Imp â€“ Small Infra React | 292933 | 60083241 | 134414
2025-05-12 | May 2025 Review | New approval | State highway improvements |  | NZTA (Tasman) | SH60 & Pugh Rd & McShane Rd | Implementation |  | ___ | HMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $4,500,000 ex admin from 60075545 to 60083293 | 4905000 | 4905000 |  |  | 6 | 6 |  | 292957 | 60083293 | 134478
2025-05-12 | May 2025 Review | New approval | State highway improvements |  | NZTA (Tasman) | SH60 & Pugh Rd & McShane Rd | Pre-implementation* |  | ___ | HMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $500,000 ex admin from 60075545 to 60083292 | 545000 | 545000 |  |  | 6 | 6 |  | 292956 | 60083292 | 134477
2025-05-12 | May 2025 Review | New approval | State highway improvements |  | NZTA (Tasman) | TAS VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $300,000 ex admin from 60075545 to 60083248 | 327000 | 327000 |  |  | 6 | 6 | TAS VfM Safety Imp â€“ Small Infra React | 292937 | 60083248 | 134464
2025-05-12 | May 2025 Review | New approval | State highway improvements |  | NZTA (Tasman) | TAS VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $974,000 ex admin from 60075545 to 60083250 | 1061660 | 1061660 |  |  | 6 | 6 | TAS VfM Safety Imp â€“ Small Infra Region | 292939 | 60083250 | 134466
2025-05-08 | May 2025 Review | New approval | State highway improvements |  | NZTA (Waikato) | SH1B/Holland Road Int Interventions | Implementation |  | ___ | HMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $1,800,000 ex admin from 60075459 to 60083318 | 1962000 | 1962000 |  |  | 6 | 6 |  | 292967 | 60083318 | 134392
2025-05-08 | May 2025 Review | New approval | State highway improvements |  | NZTA (Waikato) | SH1B/Holland Road Int Interventions | Pre-implementation* |  | ___ | HMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $200,000 ex admin from 60075459 to 60083317 | 218000 | 218000 |  |  | 6 | 6 |  | 292966 | 60083317 | 134391
2025-05-08 | May 2025 Review | New approval | State highway improvements |  | NZTA (Waikato) | SH27/Kerone Road/Diagonal Road ISZ | Implementation |  | ___ | HMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $1,710,000 ex admin from 60075459 to 60083328 | 828400 | 828400 |  |  | 6 | 6 |  | 292993 | 60083328 | 134394
2025-05-08 | May 2025 Review | New approval | State highway improvements |  | NZTA (Waikato) | SH27/Kerone Road/Diagonal Road ISZ | Pre-implementation* |  | ___ | HMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $190,000 ex admin from 60075459 to 60083327 | 207100 | 207100 |  |  | 6 | 6 |  | 292969 | 60083327 | 134393
2025-05-14 | May 2025 Review | New approval | State highway improvements |  | NZTA (Wellington) | SH2 Hughes Line - Carterton | Implementation |  | ___ | HMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $1,998,000 ex admin from 60075638 to 60083313 | 2177820 | 2177820 |  |  | 6 | 6 |  | 292965 | 60083313 | 134480
2025-05-14 | May 2025 Review | New approval | State highway improvements |  | NZTA (Wellington) | SH2 Hughes Line - Carterton | Pre-implementation* |  | ___ | HMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $222,000 ex admin from 60075638 to 60083312 | 241980 | 241980 |  |  | 6 | 6 |  | 292964 | 60083312 | 134479
2025-05-14 | May 2025 Review | New approval | State highway improvements |  | NZTA (Wellington) | WGTN VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $525,000 ex admin from 60075638 to 60083265 | 572250 | 572250 |  |  | 6 | 6 | WGTN VfM Safety Imp â€“ Small Infra Region | 292947 | 60083265 | 134518
2025-05-14 | May 2025 Review | New approval | State highway improvements |  | NZTA (Wellington) | WGTN VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $600,000 ex admin from 60075638 to 60083262 | 654000 | 654000 |  |  | 6 | 6 | WGTN VfM Safety Imp â€“ Small Infra React | 292945 | 60083262 | 134516
2025-05-26 | May 2025 Review | New approval | Public transport infrastructure |  | Tasman District Council | Bus Driver Fund | Implementation |  | ___ | HHL | N |  | Approved | Approved by Minister for Crown Appropriation | See attachment. | 204509 | 153382 |  |  |  | 1 |  | 293877 |  | 134641
2025-05-27 | May 2025 Review | New Approval Programmes | Safety | Low cost / low risk improvements | DOC (Wellington) | Low cost / low risk improvements 2024-27 | Local Road Improvements 2024-27 LCLR Targeted Fund |  | __ |  | N |  | Approved | Approved by Chief Financial Officer | approved Targeted funded project Catchpool Rd Wgtn | 0 | 45900 | [5 empty] | 287625 |  | 134643
2025-05-27 | May 2025 Review | New Approval Programmes | Safety | Low cost / low risk improvements | Hurunui District Council | Low cost / low risk improvements 2024-27 | Local Road Improvements 2024-27 LCLR Targeted Fund |  | __ |  | N |  | Approved | Approved by Chief Financial Officer | LCLR projects recommended for funding are consistent with NZTA Boardâ€™s intended purpose for increasing the LRI Investment Target. | 0 | 255715 | [5 empty] | 287753 |  | 134656
2025-05-27 | May 2025 Review | New Approval Programmes | Safety | Low cost / low risk improvements | South Wairarapa District Council | Low cost / low risk improvements 2024-27 | Local road improvements (SPR) |  | __ |  | N |  | Approved | Approved by Chief Financial Officer | At the NZTA Board meeting (22 August 2024) to adopt the National Land Transport Programme 2024-27 (NLTP), the Board agreed to provide funding to Local Road Improvements LCLR Targeted Fund. Approval has now been provided for the allocation of funding to agreed projects by the NZTA Chief Financial Officer in his memo of 05-05-2025 | 0 | 2590000 |  |  |  |  | Targeted Fund | 288137 |  | 134600
2025-05-21 | May 2025 Review | Cash flow adjustment | Local road improvements | Bridge and structures renewals | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 12 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | re-prioritization of retaining structures post AMP development due to re inspections post CG | 0 | 0 | [5 empty] | 285289 |  | 134573
2025-05-30 | May 2025 Review | Cash flow adjustment | Local road improvements | Bridge and structures renewals | Masterton District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 12 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Moving funds to align and deliver the programme. | 0 | 1 | [5 empty] | 285726 |  | 133992
2025-05-30 | May 2025 Review | Cash flow adjustment | Local road improvements | Bridge and structures renewals | Whanganui District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 12 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Transfer of funds from 24 to 25 year with net zero effect on NLTP budget in this WC | 0 | 0 | [5 empty] | 285634 |  | 134331
2025-05-21 | May 2025 Review | Cash flow adjustment | Walking and cycling improvements | Cycle path maintenance | Hamilton City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 3 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Bringing forward funding from Year 3 to Year 1 to complete work earlier in the 3-year NLTP and to bring WCs in line with our forecast claims to NZTA: due to restricted Walking & Cycling funding, subsidy is being claimed for Maintenance only. Note that Year 2 will be addressed in the September 2025 Programme Monitor, as discussed with Rob Bullick. Email correspondence 12 May 2025. | 0 | 150457 | [5 empty] | 284885 |  | 134502
2025-05-30 | May 2025 Review | Cash flow adjustment | Walking and cycling improvements | Cycle path maintenance | Nelson City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 3 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Minor adjustment to align to agreed programme of works. | 0 | 12750 | [5 empty] | 285851 |  | 134316
2025-05-20 | May 2025 Review | Cash flow adjustment | Walking and cycling improvements | Cycle path maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 3 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Review recommended to advance NLTF share (from 2026/27 to 2024/25), ensuring co-investment allocation reflects the forecast cost of 2024/25 work programme. | 0 | -1 | [5 empty] | 285207 |  | 134348
2025-05-30 | May 2025 Review | Cash flow adjustment | Walking and cycling improvements | Cycle path renewal | Nelson City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 3 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Minor adjustment to align to agreed programme of works. | 0 | -10200 | [5 empty] | 285867 |  | 134316
2025-05-02 | May 2025 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Cycling Investment - Other AKL Focus Areas | Single-Stage Business Case |  | ___ | VHML | N |  | Approved | Approved by Manager, Treasury & Cash Flow | As per the Mar25 programme monitor, this is a cost neutral cashflow to reflect PMs current forecast. | 0 | 0 |  |  | 2.8 | 2.8 | 452.2778 | 277804 |  | 134300
2025-05-05 | May 2025 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Urban Cycleways Programme - Glen Innes to Tamaki Drive | Implementation |  | ___ | VHHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | As per the Mar25 programme monitor, the tender for the final stage of this activity has now been awarded and work is planned to commence. This cost neutral cashflow reflects the current forecast for the project. | 0 | 0 |  |  | 0 | 0.7 | 452.2465 | 246508 |  | 134274
2025-05-02 | May 2025 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Urban Cycleways Programme - Great North Road Cycleway | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | As per the Mar25 programme monitor, this activity is now in construction, however this cashflow adjustment reflects the current forecast. | 0 | 0 |  |  |  | 2.6 | 452.2777 | 277747 |  | 134275
2025-05-02 | May 2025 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Auckland Transport | Urban Cycleways Programme - Links to Glen Innes | Implementation |  | ___ | HML | N |  | Approved | Approved by Manager, Treasury & Cash Flow | As per the Mar25 programme monitor, there is some slippage in this activity. This cost neutral cashflow reflects the current project manager's forecast. | 0 | 0 |  |  | 1.5 | 1.5 | 452.2778 | 277812 |  | 134276
2025-05-09 | May 2025 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Tasman District Council | CERF TC - Motueka cycleways and slow streets | Implementation |  | ___ | HHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Update total cost and local share | -225383 | 0 |  |  |  | 0 | Motueka Transport Choices Stage 1 | 289667 |  | 134456
2025-05-09 | May 2025 Review | Cash flow adjustment | Walking and cycling improvements | Cycling facilities | Tasman District Council | CERF TC - Richmond Cycleways and slow streets | Implementation |  | ___ | HHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Total cost and local share reduced | -66166 | 0 |  |  | 0 | 0 | Richmond Transport Choices Part 1 - William Street | 288422 |  | 134455
2025-05-21 | May 2025 Review | Cash flow adjustment | Local road pothole prevention | Drainage renewals | Hamilton City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Bringing forward funding from Year 3 to Year 1 to complete work earlier in the 3-year NLTP and to bring WCs in line with our 2024/25 full year forecast, as discussed with Rob Bullick. Email correspondence 12 May 2025. | 0 | 255000 | [5 empty] | 284895 |  | 134501
2025-05-21 | May 2025 Review | Cash flow adjustment | Local road pothole prevention | Drainage renewals | Timaru District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Need to do more capital rural drainage - and make reductions in operational maintenance to cover the need to install more drainage | 0 | 238694 | [5 empty] | 286045 |  | 134115
2025-05-30 | May 2025 Review | Cash flow adjustment | Local road pothole prevention | Drainage renewals | Waitaki District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | cash flow reflect likely outcome | 0 | -45600 | [5 empty] | 286321 |  | 134644
2025-05-20 | May 2025 Review | Cash flow adjustment | Local road pothole prevention | Drainage renewals | Western BoP District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Review recommended to advance NLTF share (from 2026/27 to 2024/25), ensuring co-investment allocation reflects the forecast cost of 2024/25 work programme. | 0 | 0 | [5 empty] | 285217 |  | 134360
2025-05-30 | May 2025 Review | Cash flow adjustment | Local road operations | Emergency works | Marlborough District Council | Emergency Works -July 21 Storm Event - Response | Construction | Recovery Phase 3: Marlborough Sounds Future Access | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Cashflow updated to align with revised program of work. | 0 | 0 | [5 empty] | 292728 |  | 134581
2025-05-30 | May 2025 Review | Cash flow adjustment | Local road operations | Emergency works | Marlborough District Council | Emergency Works -July 21 Storm Event - Response | Construction | Recovery - (Phase Two) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Recovery program been delayed by design and property access issues | 0 | 0 |  |  |  |  | Phase 2 | 283683 |  | 134580
2025-05-27 | May 2025 Review | Cash flow adjustment |  | Emergency works | NZTA (BOP) | EW Gabrielle BOPE RW 20230213 | Construction |  | ___ |  | N |  | Declined | Declined by National Manager, Programmes and Standards (Transport Services) | I donâ€™t think this was identified in the PLA round up that Peter McDonald did in Jan 2024. We were blind to the structureâ€™s element. I believe this was agreed by NZTA senior leaders as a critical structure. And at the time the only freight link to Gisborne. Works are now complete. Nick Cook | 0 | 0 | [5 empty] | 283779 | 60069953 | 134235
2025-05-13 | May 2025 Review | Cash flow adjustment | State highway maintenance | Emergency works | NZTA (Manawatu/Whanganui) | EW SH1 South Utiku Slow Slip 20230816 | Construction |  | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | EW Project Complete - Moving to Resilience Project | 0 | 0 | [5 empty] | 289742 | 60073246 | 134494
2025-05-28 | May 2025 Review | Cash flow adjustment | State highway operations | Emergency works | NZTA (West Coast) | EW SH6 Barrytown HR 20241216 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Closure requested by Senior Network Manager Brittany Williams | 0 | 0 | [5 empty] | 293573 | 60085746 | 134645
2025-05-19 | May 2025 Review | Cash flow adjustment | Local road operations | Emergency works | Queenstown-Lakes District Council | EW Queenstown Lakes DC September 2024 | Construction | Phase 1 - Initial costs (Normal FAR+20%) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Move funds back to normal FAR phase. | -23 | -16 |  |  |  |  | (Normal FAR+20%) | 293752 |  | 134604
2025-05-19 | May 2025 Review | Cash flow adjustment | Local road operations | Emergency works | Queenstown-Lakes District Council | EW Queenstown Lakes DC September 2024 | Construction | Phase 1 - Initial costs | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | $23 moved from Higher FAR phase. | 23 | 12 | [5 empty] | 293374 |  | 134605
2025-05-26 | May 2025 Review | Cash flow adjustment | Local road operations | Emergency works | Wairoa District Council | EW Wairoa DC November 2023 | Construction | 2023-11-01 | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Updating delivery programme - cashflow neutral. | 0 | 0 |  |  |  |  | Initial Response and recovery construction | 290939 |  | 134664
2025-05-30 | May 2025 Review | Cash flow adjustment | Local road operations | Emergency works | Wairoa District Council | EW: Emergency Works June 2023 | Construction | Recovery | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Cost net neutral phase adjustment to align with programme of works | 0 | 0 | [5 empty] | 290690 |  | 134662
2025-05-30 | May 2025 Review | Cash flow adjustment | Local road operations | Emergency works | Wairoa District Council | EW: Emergency Works March 2022 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | As advised by WDC funding adjusted to the re-prioritised programme of works | 0 | 0 |  |  |  |  | RS5619_Emergency Works March 2022 Reinstatement Renewal_Local Roads | 281419 |  | 134661
2025-05-21 | May 2025 Review | Cash flow adjustment | Local road operations | Environmental maintenance | Hamilton City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Bringing forward funding from Year 3 to Year 1 to complete work earlier in the 3-year NLTP and to bring WCs in line with our 2024/25 full year forecast, as discussed with Rob Bullick. Email correspondence 12 May 2025. | 0 | 0 | [5 empty] | 284888 |  | 134500
2025-05-02 | May 2025 Review | Cash flow adjustment | Local road operations | Environmental maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Review recommended to advance NLTF share (from 2026/27 to 2024/25), ensuring co-investment allocation reflects the forecast cost of 2024/25 work programme. | 0 | 0 | [5 empty] | 285210 |  | 134330
2025-05-30 | May 2025 Review | Cash flow adjustment | Local road operations | Environmental maintenance | Whanganui District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Adjusted to reflect actual forecasted year end spend | 0 | 119040 | [5 empty] | 285624 |  | 134642
2025-05-21 | May 2025 Review | Cash flow adjustment | Local road operations | Environmental renewals | Hamilton City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Bringing forward funding from Year 3 to Year 1 to complete work earlier in the 3-year NLTP and to bring WCs in line with our 2024/25 full year forecast, as discussed with Rob Bullick. Email correspondence 12 May 2025. | 0 | 15300 | [5 empty] | 284899 |  | 134500
2025-05-02 | May 2025 Review | Cash flow adjustment | Local road operations | Environmental renewals | Western BoP District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Review recommended to advance NLTF share (from 2026/27 to 2024/25), ensuring co-investment allocation reflects the forecast cost of 2024/25 work programme. | 0 | 0 | [5 empty] | 285221 |  | 134330
2025-05-21 | May 2025 Review | Cash flow adjustment | Walking and cycling improvements | Footpath maintenance | Hamilton City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 3 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Bringing forward funding from Year 3 to Year 1 to complete work earlier in the 3-year NLTP and to bring WCs in line with our forecast claims to NZTA: due to restricted Walking & Cycling funding, subsidy is being claimed for Maintenance only. Note that Year 2 will be addressed in the September 2025 Programme Monitor, as discussed with Rob Bullick. Email correspondence 12 May 2025. | 0 | 828750 | [5 empty] | 284886 |  | 134502
2025-05-12 | May 2025 Review | Cash flow adjustment | Walking and cycling improvements | Footpath maintenance | Stratford District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 3 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | This will redistribute funds across the financial years to allow SDC to undertake the necessary renewals work with an effective nett zero | 0 | -12964 | [5 empty] | 285438 |  | 134441
2025-05-20 | May 2025 Review | Cash flow adjustment | Walking and cycling improvements | Footpath maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 3 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Review recommended to advance NLTF share (from 2026/27 to 2024/25), ensuring co-investment allocation reflects the forecast cost of 2024/25 work programme. | 0 | 0 | [5 empty] | 285208 |  | 134348
2025-05-21 | May 2025 Review | Cash flow adjustment | Walking and cycling improvements | Footpath renewal | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 3 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | alignment of programme with SH | 0 | -1 | [5 empty] | 285293 |  | 134575
2025-05-21 | May 2025 Review | Cash flow adjustment | Walking and cycling improvements | Footpath renewal | Hamilton City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 3 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Bringing forward funding from Year 3 to Year 1 to complete work earlier in the 3-year NLTP and to bring WCs in line with our forecast claims to NZTA: due to restricted Walking & Cycling funding, subsidy is being claimed for Maintenance only. Note that Year 2 will be addressed in the September 2025 Programme Monitor, as discussed with Rob Bullick. Email correspondence 12 May 2025. | 0 | -979207 | [5 empty] | 284902 |  | 134502
2025-05-30 | May 2025 Review | Cash flow adjustment | Walking and cycling improvements | Footpath renewal | Nelson City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 3 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Minor adjustment to align to agreed programme of works. | 0 | -2550 | [5 empty] | 285868 |  | 134316
2025-05-12 | May 2025 Review | Cash flow adjustment | Walking and cycling improvements | Footpath renewal | Stratford District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 3 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | This will redistribute funds across the financial years to allow SDC to undertake the necessary renewals work with an effective nett zero | 0 | 12963 | [5 empty] | 285454 |  | 134441
2025-05-20 | May 2025 Review | Cash flow adjustment | Walking and cycling improvements | Footpath renewal | Western BoP District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 3 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Review recommended to advance NLTF share (from 2026/27 to 2024/25), ensuring co-investment allocation reflects the forecast cost of 2024/25 work programme. | 0 | 0 | [5 empty] | 285224 |  | 134348
2025-05-30 | May 2025 Review | Cash flow adjustment | Safety | Low cost / low risk improvements | Chatham Islands Council | Low cost / low risk improvements 2024-27 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Carrying over the final funding where procurement of final components will occur after the end of the 24/25 FY | 0 | 0 | [5 empty] | 287498 |  | 134677
2025-05-30 | May 2025 Review | Cash flow adjustment | Safety | Low cost / low risk improvements | Far North District Council | Low cost / low risk improvements 2024-27 | Local Road Improvements 2024-27 LCLR Targeted Fund |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | TF was released late during 2024/25 therefore late approval of projects. Reforecasting into 2025/26 for delivery. | 0 | 0 | [5 empty] | 287658 |  | 134679
2025-05-30 | May 2025 Review | Cash flow adjustment | Safety | Low cost / low risk improvements | Far North District Council | Low cost / low risk improvements 2024-27 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Late commencement with bridge programme, and late funding approval of LCLR carry forwards from 2023/2024. Reforecasting budget into 2025/26 for delivery. | 0 | 0 | [5 empty] | 287652 |  | 134681
2025-05-30 | May 2025 Review | Cash flow adjustment | Safety | Low cost / low risk improvements | Queenstown-Lakes District Council | Low cost / low risk improvements 2024-27 | External funding - Crown Resilience Programme |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Reallocation of funding from 2024/25 into 25/26 to represent estimated spend. | 0 | -1 | [5 empty] | 288075 |  | 134429
2025-05-16 | May 2025 Review | Cash flow adjustment | Safety | Low cost / low risk improvements | South Taranaki District Council | Low cost / low risk improvements 2024-27 | External funding - Crown Resilience Programme |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Scheduling of the work on Waitotara Valley Road is completed and ready to tender. Therefore, request fund to be released earlier. | 0 | 0 | [5 empty] | 288122 |  | 134511
2025-05-30 | May 2025 Review | Cash flow adjustment | Safety | Low cost / low risk improvements | Wairoa District Council | Low cost / low risk improvements 2024-27 | External funding - Crown Resilience Programme |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Net neutral adjustment to align with programme of works | 0 | 0 | [5 empty] | 288293 |  | 134659
2025-05-02 | May 2025 Review | Cash flow adjustment | Local road operations | Minor events | Western BoP District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Review recommended to advance NLTF share (from 2026/27 to 2024/25), ensuring co-investment allocation reflects the forecast cost of 2024/25 work programme. | 0 | 0 | [5 empty] | 285209 |  | 134330
2025-05-30 | May 2025 Review | Cash flow adjustment | Local road operations | Minor events | Whanganui District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Adjusted to reflect actual forecasted year end spend | 0 | -183474 | [5 empty] | 285623 |  | 134642
2025-05-30 | May 2025 Review | Cash flow adjustment | Safety | Network and asset management | Gisborne District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cost Net Neutral transfer to align with revised prioritised program | 0 | -204000 | [5 empty] | 285260 |  | 134616
2025-05-21 | May 2025 Review | Cash flow adjustment | Safety | Network and asset management | Hamilton City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Bringing forward funding from Year 3 to Year 1 to complete work earlier in the 3-year NLTP and to bring WCs in line with our 2024/25 full year forecast, as discussed with Rob Bullick. Email correspondence 12 May 2025. | 0 | 0 | [5 empty] | 284892 |  | 134500
2025-05-30 | May 2025 Review | Cash flow adjustment | Safety | Network and asset management | Waitaki District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | movement to reflect likely outcome. | 0 | -145070 | [5 empty] | 286318 |  | 134627
2025-05-02 | May 2025 Review | Cash flow adjustment | Safety | Network and asset management | Western BoP District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Review recommended to advance NLTF share (from 2026/27 to 2024/25), ensuring co-investment allocation reflects the forecast cost of 2024/25 work programme. | 0 | 0 | [5 empty] | 285214 |  | 134330
2025-05-30 | May 2025 Review | Cash flow adjustment | Safety | Network and asset management | Whanganui District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Adjusted to reflect actual forecasted year end spend | 0 | -83988 | [5 empty] | 285628 |  | 134642
2025-05-30 | May 2025 Review | Cash flow adjustment | Safety | Network operations | Grey District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | cash flow to reflect likely outcome | 0 | 1 | [5 empty] | 286155 |  | 134682
2025-05-21 | May 2025 Review | Cash flow adjustment | Safety | Network operations | Hamilton City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Bringing forward funding from Year 3 to Year 1 to complete work earlier in the 3-year NLTP and to bring WCs in line with our 2024/25 full year forecast, as discussed with Rob Bullick. Email correspondence 12 May 2025. | 0 | 0 | [5 empty] | 284890 |  | 134500
2025-05-02 | May 2025 Review | Cash flow adjustment | Safety | Network operations | Western BoP District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Review recommended to advance NLTF share (from 2026/27 to 2024/25), ensuring co-investment allocation reflects the forecast cost of 2024/25 work programme. | 0 | 0 | [5 empty] | 285212 |  | 134330
2025-05-30 | May 2025 Review | Cash flow adjustment | Safety | Network operations | Whanganui District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Adjusted to reflect actual forecasted year end spend | 0 | 27108 | [5 empty] | 285626 |  | 134642
2025-05-30 | May 2025 Review | Cash flow adjustment | Local road operations | Network service maintenance | Grey District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | cash flow to reflect likely outcome | 0 | 38400 | [5 empty] | 286154 |  | 134682
2025-05-21 | May 2025 Review | Cash flow adjustment | Local road operations | Network service maintenance | Hamilton City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Bringing forward funding from Year 3 to Year 1 to complete work earlier in the 3-year NLTP and to bring WCs in line with our 2024/25 full year forecast, as discussed with Rob Bullick. Email correspondence 12 May 2025. | 0 | 0 | [5 empty] | 284889 |  | 134500
2025-05-02 | May 2025 Review | Cash flow adjustment | Local road operations | Network service maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Review recommended to advance NLTF share (from 2026/27 to 2024/25), ensuring co-investment allocation reflects the forecast cost of 2024/25 work programme. | 0 | 0 | [5 empty] | 285211 |  | 134330
2025-05-30 | May 2025 Review | Cash flow adjustment | Local road operations | Network service maintenance | Whanganui District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Adjusted to reflect actual forecasted year end spend | 0 | 43561 | [5 empty] | 285625 |  | 134642
2025-05-09 | May 2025 Review | Cash flow adjustment | Public transport infrastructure | New activities influencing users of the transport system | Tasman District Council | CERF TC - Motueka cycleways and slow streets | Pre-implementation* |  | ___ | HHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Update total cost and local share | -248000 | 0 |  |  |  | 0 |  | 284365 |  | 134457
2025-05-02 | May 2025 Review | Cash flow adjustment | Local road improvements | New roads | Auckland Transport | TNFG - North | Pre-implementation* |  | ___ | HML | N |  | Approved | Approved by Manager, Treasury & Cash Flow | As per the Mar25 programme monitor, this is to adjust the cashflow to reflect the current PMs forecast. | 0 | 0 |  |  |  |  | 323.2505 | 250456 |  | 134295
2025-05-02 | May 2025 Review | Cash flow adjustment | Local road improvements | New roads | Porirua City Council | PCC Link Roads | Construction |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | PCC has notified that they intend the final seal will be completed in 2026. One the final claim has been submitted, any funding not required will be surplused. | 0 | 0 |  |  | 1 | 1 |  | 224001 |  | 134334
2025-05-01 | May 2025 Review | Cash flow adjustment | Public transport services | Operations & maintenance of real-time and ticketing systems | NZ Transport Agency | National Ticketing Solution (NTS) | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Update TIO admin rate. NB Diretc cost should be ex-admin at 6.5% | 0 | 0 |  |  | 1.7 | 1.7 | SAP Item ID 60068485 | 281638 | 60068485 | 133954
2025-05-02 | May 2025 Review | Cash flow adjustment | Public transport infrastructure | Passenger facilities and infrastructure improvements - rail | Auckland Transport | AKL Metro Train Capacity - Tranche 3 | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | As per the March programme monitor, the timing for this activity is slipping, but still aiming for completion in FY26. This is a cost neutral cashflow. | 0 | 0 |  |  |  | 2.1 | 563.2605 | 260527 |  | 134271
2025-05-16 | May 2025 Review | Cash flow adjustment | Investment management (incl. Transport Planning) | Programme Business Case Development | Porirua City Council | Eastern Porirua Regeneration PBC | Programme business case |  | VHHL | VHHL | N | 2 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | Due to the restructures of both PCC and KO they have requested that this funding be carried forward to 2025/26 when the new structures are in place and operational. | 0 | 0 | [5 empty] | 279777 |  | 134373
2025-05-16 | May 2025 Review | Cash flow adjustment | Walking and cycling improvements | Property purchase (State highways) | NZTA (Otago) | SH8 Beaumont bridge replacement | Property |  | ___ | MMM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Project Close | 0 | 0 |  |  | 0 | 12 | 60465362 | 214531 | 60465362 | 134499
2025-05-16 | May 2025 Review | Cash flow adjustment | Safety | Property purchase (local roads) | Porirua City Council | Access Kenepuru | Property |  | ___ | VHHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Legal fee that wont be finalised in 24/25 - expected to finalised in early 25/26. | 0 | 0 |  |  | 2.7 | 5.6 | Stage 2A - Property | 271921 |  | 134537
2025-05-02 | May 2025 Review | Cash flow adjustment | Public transport infrastructure | Public transport infrastructure and major renewals | Auckland Transport | AMETI - Eastern Busway 1 (Previously part of AMETI Stage 2A) | Construction |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | As per the Mar25 programme monitor, this activity is tracking slightly behind. This is a cost neutral cashflow to reflect current forecast. | 0 | 0 |  |  | 0 | 1.1 | 531.228 | 227971 |  | 134272
2025-05-21 | May 2025 Review | Cash flow adjustment | Local road operations | Rail level crossing warning devices maintenance | Hamilton City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Bringing forward funding from Year 3 to Year 1 to complete work earlier in the 3-year NLTP and to bring WCs in line with our 2024/25 full year forecast, as discussed with Rob Bullick. Email correspondence 12 May 2025. | 0 | 0 | [5 empty] | 284891 |  | 134500
2025-05-02 | May 2025 Review | Cash flow adjustment | Local road operations | Rail level crossing warning devices maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Review recommended to advance NLTF share (from 2026/27 to 2024/25), ensuring co-investment allocation reflects the forecast cost of 2024/25 work programme. | 0 | 0 | [5 empty] | 285213 |  | 134330
2025-05-30 | May 2025 Review | Cash flow adjustment | Local road operations | Rail level crossing warning devices maintenance | Whanganui District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Adjusted to reflect actual forecasted year end spend | 0 | 11169 | [5 empty] | 285627 |  | 134642
2025-05-30 | May 2025 Review | Cash flow adjustment | State highway improvements | Resilience improvements | NZTA (West Coast) | TRF-WTCT-Gates of Haast River Erosion | Implementation |  | ___ | VHHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | To transfer $150,000 excl admin from 2024/25 to 2025/26 as construction is not expected to start in 2024/25. | 0 | 0 |  |  | 1 | 1 |  | 288499 | 60071595 | 134467
2025-05-02 | May 2025 Review | Cash flow adjustment | Safety | Road improvements | Auckland Transport | TNFG - North West | Pre-implementation* |  | ___ | VHHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | As per the Mar25 programme monitor, this is to adjust the cashflow to reflect the current PMs forecast. | 0 | 0 |  |  |  | 0.7 | 324.2505 | 250457 |  | 134296
2025-05-02 | May 2025 Review | Cash flow adjustment | Safety | Road improvements | Auckland Transport | TNFG - South - Pukekohe | Pre-implementation* |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | As per the Mar25 programme monitor, this is to adjust the cashflow to reflect the current PMs forecast. | 0 | 0 |  |  |  |  | 324.2777 | 277748 |  | 134297
2025-05-02 | May 2025 Review | Cash flow adjustment | Safety | Road improvements | Auckland Transport | TNFG - South - SGA Takanini | Pre-implementation* |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | As per the Mar25 programme monitor, this is to adjust the cashflow to reflect the current PMs forecast. | 0 | 0 |  |  |  |  | 324.2505 | 250458 |  | 134298
2025-05-30 | May 2025 Review | Cash flow adjustment | Safety | Road improvements | Marlborough District Council | Dublin Street Rail Crossing Grade Separation | Implementation |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | This project has been delayed with changes to the Irex project | 0 | 0 |  |  | 1.1 |  |  | 276828 |  | 134590
2025-05-30 | May 2025 Review | Cash flow adjustment | Safety | Road improvements | Marlborough District Council | Dublin Street Rail Crossing Grade Separation | Pre-implementation* |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Work has been delayed on this project | 0 | 0 |  |  | 1.1 |  |  | 276827 |  | 134589
2025-05-12 | May 2025 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Auckland) | ANO SH1 NB Princes Street On Ramp | Pre-implementation* |  | ___ | MHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Project close 2nd time. | 0 | 0 |  |  |  | 2.9 |  | 283882 | 60070066 | 134503
2025-05-02 | May 2025 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Auckland) | ANO SH16 Royal Road Active Improvements | Implementation |  | ___ | MHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Project Close | 0 | 0 |  |  | 2.9 | 2.9 |  | 283885 | 60070095 | 134309
2025-05-02 | May 2025 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Auckland) | ANO SH16 Royal Road Active Improvements | Pre-implementation* |  | ___ | MHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Project Close | 0 | 0 |  |  | 2.9 | 2.9 |  | 283884 | 60070094 | 134308
2025-05-02 | May 2025 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (BOP) | RoNS Takitimu North Link Stage 1 | Pre-implementation* |  | ___ | HHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Project Close | 0 | 0 |  |  | 2 | 2 | MCIP 60057020 | 173210 | 60057020 | 134281
2025-05-16 | May 2025 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (BOP) | SH2 Wainui Rd to Opotiki, NSRRP | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow Adjustment: Transfer of Allocation from FY 25/26 to FY 24/25 & FY 26/27 | -3 | -3 |  |  | 1 | 1 |  | 292473 | 60076223 | 134424
2025-05-30 | May 2025 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Otago) | SH1 Oamaru to Dunedin - (Hampden to Palmerston) | Pre-implementation* |  | ___ | HHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Project close | 0 | 0 |  |  | 0 | 1.6 |  | 292502 | 60076241 | 134703
2025-05-16 | May 2025 Review | Cash flow adjustment | State highway improvements | Road improvements | NZTA (Waikato) | SH1 South-East Hamilton improvements | Construction |  | ___ | MMM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow $90,563 to FY2026 | 0 | 0 |  |  | 5.9 | 5.9 | 60033606 | 239051 | 60033606 | 134558
2025-05-21 | May 2025 Review | Cash flow adjustment | Local road pothole prevention | Routine drainage maintenance | Hamilton City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Bringing forward funding from Year 3 to Year 1 to complete work earlier in the 3-year NLTP and to bring WCs in line with our 2024/25 full year forecast, as discussed with Rob Bullick. Email correspondence 12 May 2025. | 0 | 0 | [5 empty] | 284883 |  | 134501
2025-05-21 | May 2025 Review | Cash flow adjustment | Local road pothole prevention | Routine drainage maintenance | Timaru District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Need to do more capital rural drainage - and make reductions in operational maintenance to cover the need to install more drainage | 0 | -238694 | [5 empty] | 286033 |  | 134115
2025-05-20 | May 2025 Review | Cash flow adjustment | Local road pothole prevention | Routine drainage maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Review recommended to advance NLTF share (from 2026/27 to 2024/25), ensuring co-investment allocation reflects the forecast cost of 2024/25 work programme. | 0 | 0 | [5 empty] | 285205 |  | 134360
2025-05-21 | May 2025 Review | Cash flow adjustment | Local road pothole prevention | Sealed pavement maintenance | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Redistributing unsealed into sealed maintenance to address emerging potholes over winter, Pavement renewals pushed due to timing of testing and designed - to ensure better long term outcome. | 0 | 118000 | [5 empty] | 285272 |  | 134574
2025-05-21 | May 2025 Review | Cash flow adjustment | Local road pothole prevention | Sealed pavement maintenance | Hamilton City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Bringing forward funding from Year 3 to Year 1 to complete work earlier in the 3-year NLTP and to bring WCs in line with our 2024/25 full year forecast, as discussed with Rob Bullick. Email correspondence 12 May 2025. | 0 | 0 | [5 empty] | 284881 |  | 134501
2025-05-20 | May 2025 Review | Cash flow adjustment | Local road pothole prevention | Sealed pavement maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Review recommended to advance NLTF share (from 2026/27 to 2024/25), ensuring co-investment allocation reflects the forecast cost of 2024/25 work programme. | 0 | -1 | [5 empty] | 285203 |  | 134360
2025-05-21 | May 2025 Review | Cash flow adjustment | Local road pothole prevention | Sealed road pavement rehabilitation | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Redistributing unsealed into sealed maintenance to address emerging potholes over winter, Pavement renewals pushed due to timing of testing and designed - to ensure better long term outcome. | 0 | 0 | [5 empty] | 285287 |  | 134574
2025-05-21 | May 2025 Review | Cash flow adjustment | Local road pothole prevention | Sealed road pavement rehabilitation | Hamilton City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Bringing forward funding from Year 3 to Year 1 to complete work earlier in the 3-year NLTP and to bring WCs in line with our 2024/25 full year forecast, as discussed with Rob Bullick. Email correspondence 12 May 2025. | 0 | 0 | [5 empty] | 284896 |  | 134501
2025-05-30 | May 2025 Review | Cash flow adjustment | Local road pothole prevention | Sealed road pavement rehabilitation | Waitaki District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | cash flow reflect likely outcome | 0 | 171000 | [5 empty] | 286322 |  | 134644
2025-05-20 | May 2025 Review | Cash flow adjustment | Local road pothole prevention | Sealed road pavement rehabilitation | Western BoP District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Review recommended to advance NLTF share (from 2026/27 to 2024/25), ensuring co-investment allocation reflects the forecast cost of 2024/25 work programme. | 0 | 0 | [5 empty] | 285218 |  | 134360
2025-05-21 | May 2025 Review | Cash flow adjustment | Local road pothole prevention | Sealed road resurfacing | Hamilton City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Bringing forward funding from Year 3 to Year 1 to complete work earlier in the 3-year NLTP and to bring WCs in line with our 2024/25 full year forecast, as discussed with Rob Bullick. Email correspondence 12 May 2025. | 0 | -255000 | [5 empty] | 284894 |  | 134501
2025-05-30 | May 2025 Review | Cash flow adjustment | Local road pothole prevention | Sealed road resurfacing | Waitaki District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | cash flow reflect likely outcome | 0 | -171000 | [5 empty] | 286320 |  | 134644
2025-05-20 | May 2025 Review | Cash flow adjustment | Local road pothole prevention | Sealed road resurfacing | Western BoP District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Review recommended to advance NLTF share (from 2026/27 to 2024/25), ensuring co-investment allocation reflects the forecast cost of 2024/25 work programme. | 0 | 0 | [5 empty] | 285216 |  | 134360
2025-05-30 | May 2025 Review | Cash flow adjustment | Local road operations | Structures component replacements | Gisborne District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cost Net Neutral transfer to align with revised prioritised program | 0 | -136000 | [5 empty] | 285265 |  | 134616
2025-05-21 | May 2025 Review | Cash flow adjustment | Local road operations | Structures component replacements | Hamilton City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Bringing forward funding from Year 3 to Year 1 to complete work earlier in the 3-year NLTP and to bring WCs in line with our 2024/25 full year forecast, as discussed with Rob Bullick. Email correspondence 12 May 2025. | 0 | 0 | [5 empty] | 284897 |  | 134500
2025-05-02 | May 2025 Review | Cash flow adjustment | Local road operations | Structures component replacements | Western BoP District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Review recommended to advance NLTF share (from 2026/27 to 2024/25), ensuring co-investment allocation reflects the forecast cost of 2024/25 work programme. | 0 | 0 | [5 empty] | 285219 |  | 134330
2025-05-30 | May 2025 Review | Cash flow adjustment | Local road operations | Structures component replacements | Whanganui District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Adjusted to reflect actual forecasted year end spend | 0 | -232718 | [5 empty] | 285633 |  | 134642
2025-05-30 | May 2025 Review | Cash flow adjustment | Local road operations | Structures maintenance | Grey District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | cash flow to reflect likely outcome | 0 | -38400 | [5 empty] | 286149 |  | 134682
2025-05-21 | May 2025 Review | Cash flow adjustment | Local road operations | Structures maintenance | Hamilton City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Bringing forward funding from Year 3 to Year 1 to complete work earlier in the 3-year NLTP and to bring WCs in line with our 2024/25 full year forecast, as discussed with Rob Bullick. Email correspondence 12 May 2025. | 0 | -15300 | [5 empty] | 284884 |  | 134500
2025-05-02 | May 2025 Review | Cash flow adjustment | Local road operations | Structures maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Review recommended to advance NLTF share (from 2026/27 to 2024/25), ensuring co-investment allocation reflects the forecast cost of 2024/25 work programme. | 0 | -1 | [5 empty] | 285206 |  | 134330
2025-05-30 | May 2025 Review | Cash flow adjustment | Local road operations | Structures maintenance | Whanganui District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Adjusted to reflect actual forecasted year end spend | 0 | 57760 | [5 empty] | 285620 |  | 134642
2025-05-01 | May 2025 Review | Cash flow adjustment | Public transport infrastructure | Technology to improve effectiveness of public transport systems | NZ Transport Agency | National Ticketing Solution (NTS) | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Update TIO admin. Note that direct cost should ex-admin at 6.5% | 0 | 0 |  |  | 1.7 | 1.7 | SAP Item ID 60068497 | 280395 | 60068497 | 133960
2025-05-16 | May 2025 Review | Cash flow adjustment | Public transport services | Total Mobility wheelchair hoists and ramps | Nelson City Council | Public Transport Programme 2024-27 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | A request for a hoist claim has been presented for this year and expecting another one next year. | 0 | 22725 | [5 empty] | 287154 |  | 134356
2025-05-16 | May 2025 Review | Cash flow adjustment | Public transport services | Total mobility operations | Nelson City Council | Public Transport Programme 2024-27 - AC 4 | Operations |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | A request for a hoist claim has been presented for this year and expecting another one next year. | 0 | -22725 | [5 empty] | 287153 |  | 134356
2025-05-30 | May 2025 Review | Cash flow adjustment | Local road operations | Traffic services renewals | Gisborne District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cost Net Neutral transfer to align with revised prioritised program | 0 | 340000 | [5 empty] | 285268 |  | 134616
2025-05-21 | May 2025 Review | Cash flow adjustment | Local road operations | Traffic services renewals | Hamilton City Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Bringing forward funding from Year 3 to Year 1 to complete work earlier in the 3-year NLTP and to bring WCs in line with our 2024/25 full year forecast, as discussed with Rob Bullick. Email correspondence 12 May 2025. | 0 | 0 | [5 empty] | 284900 |  | 134500
2025-05-30 | May 2025 Review | Cash flow adjustment | Local road operations | Traffic services renewals | Waitaki District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | movement to reflect likely outcome. | 0 | 145070 | [5 empty] | 286326 |  | 134627
2025-05-02 | May 2025 Review | Cash flow adjustment | Local road operations | Traffic services renewals | Western BoP District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Review recommended to advance NLTF share (from 2026/27 to 2024/25), ensuring co-investment allocation reflects the forecast cost of 2024/25 work programme. | 0 | 0 | [5 empty] | 285222 |  | 134330
2025-05-30 | May 2025 Review | Cash flow adjustment | Local road operations | Traffic services renewals | Whanganui District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Adjusted to reflect actual forecasted year end spend | 0 | 241541 | [5 empty] | 285636 |  | 134642
2025-05-21 | May 2025 Review | Cash flow adjustment | Local road pothole prevention | Unsealed pavement maintenance | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Redistributing unsealed into sealed maintenance to address emerging potholes over winter, Pavement renewals pushed due to timing of testing and designed - to ensure better long term outcome. | 0 | -59000 | [5 empty] | 285273 |  | 134574
2025-05-20 | May 2025 Review | Cash flow adjustment | Local road pothole prevention | Unsealed pavement maintenance | Western BoP District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Review recommended to advance NLTF share (from 2026/27 to 2024/25), ensuring co-investment allocation reflects the forecast cost of 2024/25 work programme. | 0 | 0 | [5 empty] | 285204 |  | 134360
2025-05-21 | May 2025 Review | Cash flow adjustment | Local road pothole prevention | Unsealed road metalling | Central Hawkes Bay District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Redistributing unsealed into sealed maintenance to address emerging potholes over winter, Pavement renewals pushed due to timing of testing and designed - to ensure better long term outcome. | 0 | -59000 | [5 empty] | 285284 |  | 134574
2025-05-30 | May 2025 Review | Cash flow adjustment | Local road pothole prevention | Unsealed road metalling | Waitaki District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | cash flow reflect likely outcome | 0 | 45600 | [5 empty] | 286319 |  | 134644
2025-05-20 | May 2025 Review | Cash flow adjustment | Local road pothole prevention | Unsealed road metalling | Western BoP District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 26 | Local Roads |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Review recommended to advance NLTF share (from 2026/27 to 2024/25), ensuring co-investment allocation reflects the forecast cost of 2024/25 work programme. | 0 | -1 | [5 empty] | 285215 |  | 134360
2025-05-02 | May 2025 Review | Cash flow adjustment | Safety |  | Auckland Transport | High Risk Intersections and Corridors | Implementation |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | As per the Mar25 programme monitor, this cost neutral cashflow is to align with the PMs current forecast. Note, this is no longer able to be approved via AT's DFA as it is not valid for the 2024 NLTP period. | 0 | 0 |  |  |  | 4.5 | 324.2909 | 292719 |  | 134301
2025-05-16 | May 2025 Review | Cash flow adjustment | Safety |  | Auckland Transport | High Risk Intersections and Corridors | Implementation |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | As per the Mar25 programme monitor, this cost neutral cashflow is to align with the PMs current forecast. | 0 | 0 |  |  |  | 4.5 | 324.2838 | 292718 |  | 134302
2025-05-16 | May 2025 Review | Cash flow adjustment | Public transport infrastructure |  | Auckland Transport | National Ticketing Solution (NTS) | Implementation |  | ___ | MMM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | As per the Mar25 programme monitor, the design elements relating the early integration are tracking slightly behind, so doing a cost neutral cashflow to reflect the current position. | 0 | 0 |  |  |  | 3.2 | 554.29 | 289979 |  | 134491
2025-05-30 | May 2025 Review | Cash flow adjustment | Local road improvements |  | Marlborough District Council | MSFAS Road Resilience Improvements SSBC | Single-Stage Business Case |  | ___ | VHHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | This phase of work has been off to a slow start due to limited resourcing on both sides. While it is progressing, we do not expect to begin incurring spend until next FY. | 0 | 0 |  |  |  | 1 | Sounds Resilience Study | 291417 |  | 134588
2025-05-16 | May 2025 Review | Cash flow adjustment | Safety |  | NZ Transport Agency | REG National Partnership- Programme development & delivery | Implementation |  | ___ | HHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Correct the admin rate in TIO. Total cost unchanged | 0 | 0 |  |  | 99 | 99 | 60083531 CCDC Contract Delivery 2024 - 27 | 288391 | 60083531 | 134585
2025-05-16 | May 2025 Review | Cash flow adjustment | State highway improvements |  | NZTA (Auckland) | RoNS East West Link | Indicative Business Case |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow Transfer - Pls bring forward $600k from Year 1 to current FY. | -1 | -1 |  |  | 1.9 | 1.9 | RONS | 293490 | 60085359 | 134546
2025-05-02 | May 2025 Review | Cash flow adjustment | State highway improvements |  | NZTA (Auckland) | RoNS Mill Road | Pre-implementation* |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | bring $1,520,000 from Y1 to CY | 0 | 0 |  |  | 1.2 | 1.2 | RoNS Stage 1 | 291774 | 60075223 | 134311
2025-05-09 | May 2025 Review | Cash flow adjustment | State highway improvements |  | NZTA (Auckland) | RoNS Warkworth to Te Hana | Pre-implementation* |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Change of admin rate from 9% to 6.5%. Total Costs remain the same | 2 | 2 |  |  | 1.1 | 1.1 |  | 279187 | 60216908 | 134485
2025-05-02 | May 2025 Review | Cash flow adjustment | Walking and cycling improvements |  | NZTA (BOP) | BOP Share RoNS Property | Property |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow adjustment for BOP Property RoNS Share | 0 | 0 |  |  |  | 1 |  | 291787 | 60075256 | 134324
2025-05-30 | May 2025 Review | Cash flow adjustment | State highway improvements |  | NZTA (Canterbury) | RoNS SH1 Belfast to Pegasus & Woodend BP | Indicative Business Case |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Project Close | 0 | 0 |  |  | 1.1 | 1.1 |  | 293238 | 60083871 | 134586
2025-05-09 | May 2025 Review | Cash flow adjustment | State highway improvements |  | NZTA (Northland) | RoNS Northland Corridor Programme Mgmt | Indicative Business Case |  | ___ | VHHVL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Change of admin rate from 9% to 6.5%.Total Costs remain the same. | -4 | -4 |  |  |  | 1 | Investigation & Project Development 60083879 | 293239 | 60083879 | 134482
2025-05-16 | May 2025 Review | Cash flow adjustment | State highway improvements |  | NZTA (Waikato) | EOL SH27 Ohinekaua Stream Bridge | Pre-implementation* |  | ___ | HHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow $394,541 to FY2026 | 0 | 0 |  |  |  | 1 |  | 290349 | 60073598 | 134549
2025-05-02 | May 2025 Review | Cash flow adjustment | State highway improvements |  | NZTA (Wellington) | RoNS Petone to Grenada Link Road and CVL | Indicative Business Case |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow adjustment from Y1 to Current year to match the revise forecast | -2 | -2 |  |  | 1.3 | 1 |  | 293491 | 60085379 | 134322
2025-05-30 | May 2025 Review | Cash flow adjustment | Safety |  | Wairoa District Council | Nuhaka Opoutama Road Coastal Erosion Protection Structures | Implementation |  | ___ | HMM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Updating programme delivery | 0 | 0 |  |  |  | 0.2 |  | 293177 |  | 134660
2025-05-16 | May 2025 Review | Cost Increase | Safety | Activity management planning improvement | NZ Transport Agency | REG National Partnership- Programme development & delivery | Implementation |  | ___ | HHH | N |  | Approved | Approved by Chief Financial Officer | Project Close | 41135 | 41135 |  |  | 99 | 99 | CCDC Contract establishment 2023/24 60076101 | 288390 | 60076101 | 134061
2025-05-02 | May 2025 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | NZ Transport Agency | CERF - Transport Choices Council Support Package (OPEX) | Implementation |  | ___ | VHHVH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Reforecast & update admin rate in TIO | -831471 | -831471 |  |  |  | 1 | 60069916 | 283320 | 60069916 | 134339
2025-05-06 | May 2025 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Wellington City Council | Thorndon Quay and Hutt Road Upgrade | Pre-implementation* |  | ___ | VHHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow funds to TIO ID 293730. This is to correct the Output class from PT to WC (Waka Kotahi Recommendation). | -2434156 | -2434156 |  |  | 1.2 | 1 |  | 292256 |  | 133953
2025-05-15 | May 2025 Review | Cost Decrease | Walking and cycling improvements | Cycling facilities | Whangarei District Council | CERF-TC - WDC Transport Choices Package | Implementation |  | ___ | HHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Approved by review committee 15 May 2025. Funds going to WHGR04/WDC03 (City Bus Improvements) | -338125 | -338125 |  |  |  | 0 | WHGR03: Raumanga Shared Path Extension and CBD Cycle Parking | 284202 |  | 134577
2025-05-28 | May 2025 Review | Cost Increase | External funding | Emergency works | Auckland Transport | EW - AT Anniversary Weekend & Cyclone Gabrielle 2023 | Construction | E/W - Reinstatement @ 71% (NIWE) | ___ |  | N |  | Declined | Declined by regional office | The September 2024 CSA approved emergency works recovery co-investment from NZTA included 20% contingency. A substantial portion of the recovery work has now been completed. Taking into consideration the new overall total (with NZTA agreed increases), a 5% contingency (across all projects, even those completed), and admin; the overall recovery total is $1.4 million less than what has been approved in TIO already. A number of cost increases reviewed found: - No information provided to support cost increase - Sits outside NZTA emergency works funding criteria, such as resilience improvements - Includes $720,000 of sites identified previously as not eligible for NZTA funding | 9171232 | 6511575 |  |  |  |  | 141.2901 | 291177 |  | 133976
2025-05-06 | May 2025 Review | Cost Decrease | Local road operations | Emergency works | Far North District Council | EW Far North DC June 2023 | Construction | Phase 2 - Minor Remedial Works - EW June 2023 | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving 786,970 to Phase 3 Major Remedial works. | -786970 | -716143 |  |  |  |  | Phase 2 - Minor Remedial Works - EW June 2023 | 288444 |  | 134364
2025-05-02 | May 2025 Review | Cost Increase | Local road operations | Emergency works | Far North District Council | EW Far North DC June 2023 | Construction | Phase 3 - Major Remedial Works - EW June 2023 | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | $1,277,253 moved from Phase 1 & Phase 2 to Phase 3 | 1297253 | 1180500 |  |  |  |  | Phase 3 - Major Remedial Works - EW June 2023 | 288445 |  | 134365
2025-05-02 | May 2025 Review | Cost Decrease | Local road operations | Emergency works | Far North District Council | EW Far North DC June 2023 | Construction | Phase 1 - Initial Response - EW June 2023 | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Moving $510,283 to Phase 3 Major Remedial works | -510283 | -464358 |  |  |  |  | Phase 1 - Initial Response - EW June 2023 | 288443 |  | 134363
2025-05-02 | May 2025 Review | Cost Decrease | Local road operations | Emergency works | Far North District Council | EW September/October 2021 | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -80617 | -57238 |  |  |  |  | EW September/October 2021 | 280429 |  | 134233
2025-05-02 | May 2025 Review | Cost Decrease | External funding | Emergency works | Gisborne District Council | EW Cyclone Gabrielle Recovery | Construction | Major Reinstatement - Drop out repairs | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Re forecasting based on revised programme of works - NLTF cash decrease dependent on FAR Board Decision | 0 | -475000 |  |  |  |  | Major Reinstatement -Drop out repairs | 291505 |  | 134286
2025-05-02 | May 2025 Review | Cost Decrease | External funding | Emergency works | Gisborne District Council | EW Cyclone Gabrielle Recovery | Construction | Bridge rebuild programme (black bridges) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Re forecasting based on revised programme of works - NLTF cash decrease dependent on FAR Board Decision | 0 | -190000 |  |  |  |  | Black Bridges - 6031XX | 291504 |  | 134285
2025-05-13 | May 2025 Review | Cost Decrease | External funding | Emergency works | Gisborne District Council | EW Cyclone Gabrielle Recovery | Construction | Bridge repair-programme (red/orange bridges) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Re forecasting based on revised programme of works - NLTF cash decrease dependent on FAR Board Decision | 0 | -355229 |  |  |  |  | Bridge repair -programme (red/orange bridges) - 6032XX | 291503 |  | 134284
2025-05-13 | May 2025 Review | Cost Decrease | External funding | Emergency works | Hastings District Council | EW Cyclone Gabrielle Recovery - FY24/25 | Construction | Recovery Phase (+30% FAR) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | HDC have requested to transfer the remaining approved funding into 25/26 for the reasons stated above and to mitigate poor outcomes with costs construction and quality risks over the winter period. Set at FAR +20% pending outcome of board decision on bespoke FAR request | 0 | -3000000 | [5 empty] | 293302 |  | 134492
2025-05-30 | May 2025 Review | Cost Decrease | Local road operations | Emergency works | Hutt City Council | Emergency works - Heavy rain event Aug 2022 | Construction | Recovery (Normal FAR+20%) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Confirmation from council of no more claiming required under enhanced FAR | -224581 | -159453 |  |  |  |  | (Normal FAR+20%) | 292656 |  | 134593
2025-05-02 | May 2025 Review | Cost Decrease | Local road operations | Emergency works | Kapiti Coast District Council | Emergency Works August Storm Event 2022 | Construction | Build permanent rock wall | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Consent compliance report issued. Closing in under budget, reducing claim and increasing programme to complete remaining planting and monitoring in accordance with consent. | -62406 | -31827 | [5 empty] | 284158 |  | 134273
2025-05-30 | May 2025 Review | Cost Decrease | External funding | Emergency works | NZTA (Auckland) | EW Gabrielle Auckland 20230212 | Construction | NIWE Recovery SH (CAPEX) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Project Close | -506319 | -506319 | [5 empty] | 292329 | 60069969 | 134591
2025-05-22 | May 2025 Review | Cost Increase | State highway operations | Emergency works | NZTA (West Coast) | EW SH6 Barrytown HR 20241216 | Construction |  | ___ |  | N |  | Approved | Approved by Regional Manager, Maintenance and Operations (Transport Services) | I support the PLA, this is an admin/pricing error. Nick Cook. Increasing the approved response cost from $141,700 to $168,214 (including admin). | 26514 | 26514 | [5 empty] | 293573 | 60085746 | 134570
2025-05-02 | May 2025 Review | Cost Decrease | Local road operations | Emergency works | Napier City Council | EW: November 2020 Napier Rain Event | Construction |  | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | NCC has advised claiming complete and no additional funds required | -12057 | -6149 |  |  |  |  | Construction of permanent works (3) | 279020 |  | 134237
2025-05-02 | May 2025 Review | Cost Increase | Local road operations | Emergency works | Nelson City Council | EW Nelson City Council Storm Event August 2022 | Construction | Recovery | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Assuming project completion will carry into next FY | 0 | 204827 | [5 empty] | 290417 |  | 134283
2025-05-16 | May 2025 Review | Cost Decrease | Local road operations | Emergency works | Rotorua Lakes Council | EW - Rotorua LC Storm Damage July 2022 | Construction | Phase 2 - Construction (Normal FAR+20%) | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Project complete. | -56365 | -32128 |  |  |  |  | (Normal FAR+20%) | 283356 |  | 134427
2025-05-16 | May 2025 Review | Cost Decrease | Local road operations | Emergency works | Rotorua Lakes Council | EW - Rotorua LC Storm Damage May 2023 | Construction | Phase 1 - Initial response, investigation & design | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Project substantially complete. | -466637 | -265983 | [5 empty] | 284389 |  | 134428
2025-05-16 | May 2025 Review | Cost Decrease | Local road operations | Emergency works | Rotorua Lakes Council | EW - Rotorua LC Storm Damage Sep 2023 | Construction | Phase 1 - Initial response and clean up | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Project completed, therefore declaring surplus funds | -98503 | -56147 | [5 empty] | 290482 |  | 134426
2025-05-28 | May 2025 Review | Cost Increase | External funding | Emergency works | Tararua District Council | EW Cyclone Gabrielle | Construction | Cyclone Gabrielle- Recovery Phase (NIWE) FAR +20% | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | Funding required under WC 141 to reinstate TDC network to the appropriate LOS post Cyclone Gabrielle | 6598313 | 6433355 | [5 empty] | 292679 |  | 134687
2025-05-23 | May 2025 Review | Cost Increase | External funding | Emergency works | Wairoa District Council | EW - Cyclone Gabrielle - Recovery | Construction |  | ___ |  | N |  | Approved | Approved by Chief Financial Officer (CFO) | This funding approval enables the transport network at this location to be reinstated to the appropriate levels of service. for Construction (TIO Phase 293119) â–ª $16,452,108 ($15,629,503 NLTF in 2025/26) â–ª $10,552,723 ($9,996,587 NLTF in 2026/27 | 26974831 | 25626090 | [5 empty] | 293119 |  | 133980
2025-05-15 | May 2025 Review | Cost Increase | Local road operations | Emergency works | Wairoa District Council | EW: Emergency Works June 2023 | Construction | Recovery High FAR +20% | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | As advised by WDC project cost neutral request to re align funding with programme of works - decrease in phase 290690 | 312140 | 234105 | [5 empty] | 293120 |  | 133940
2025-05-30 | May 2025 Review | Cost Decrease | Local road operations | Emergency works | Whanganui District Council | EW - May 2022 Weather Event | Construction | Initial clean up and permanent repairs | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Revised the scope of works to assist in a cost neutral cost/scope adjustment across emergency events. As per attached document we request a neutral cost/scope adjustment of $1,768,238 Total expected cost for this event $187,737 | -587551 | -481792 |  |  |  |  | Initial clean up and permanent repairs | 282144 |  | 134023
2025-05-16 | May 2025 Review | Cost Decrease | Local road operations | Emergency works | Whanganui District Council | EW - Whanganui DC 20 May 2023 Flood | Construction | Clean up and Minor Repairs | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Revised the scope of works to assist in a cost neutral cost/scope adjustment across emergency events. As per attached spreadsheet we request a neutral cost/scope adjustment of $1,987,682.00 across six events and five projects. | -553576 | -453932 |  |  |  |  | Clean up and Minor Repairs | 284307 |  | 134024
2025-05-30 | May 2025 Review | Cost Decrease | Local road operations | Emergency works | Whanganui District Council | EW Whanganui DC October 2022 | Construction | Emergency Response and Permanent Reinstatement | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | declaration of surplus funds | -535219 | -438880 | [5 empty] | 283415 |  | 134026
2025-05-30 | May 2025 Review | Cost Decrease | Local road operations | Emergency works | Whangarei District Council | EW Whangarei DC May 2023 Storm Event | Construction | Immediate response and minor remedial | ___ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow (Commercial and Corporate) | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -134485 | -98174 |  |  |  |  | Immediate Response and minor remedial | 284559 |  | 134530
2025-05-30 | May 2025 Review | Cost Decrease | Safety | Low cost / low risk improvements | Gisborne District Council | Low cost / low risk improvements 2024-27 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | GDC have confirmed the indicative funding is not required post GDC legal review | 0 | -78200 | [5 empty] | 287665 |  | 134613
2025-05-30 | May 2025 Review | Cost Increase | Safety | Low cost / low risk improvements | Invercargill City Council | Low cost / low risk improvements 2024-27 | Local road improvements |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Speed reversal funding approved on the 1 April 2025 | 0 | 7650 | [5 empty] | 287768 |  | 134204
2025-05-27 | May 2025 Review | Cost Increase | Safety | Low cost / low risk improvements | South Taranaki District Council | Low cost / low risk improvements 2024-27 | Local Road Improvements 2024-27 LCLR Targeted Fund |  | __ |  | N |  | Approved | Approved by Manager, Treasury & Cash Flow | This increase will allow STDC to undertake revetment resilience work in alignment with the conditions of LCLR - Targeted Fund and has been endorsed and approved by Howard Cattermole (see supporting doc for e-mail and recommendation | 0 | 136500 |  |  |  |  | LCLRTF | 288120 |  | 134510
2025-05-19 | May 2025 Review | Cost Increase | Investment management (incl. Transport Planning) | Management of the funding allocation system | NZ Transport Agency | CERF - Public Transport Initiatives (OPEX) | Implementation |  | ___ | VHHVH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Updating to reflect forecast & increase due to admin fix | 19950 | 19950 |  |  |  | 1 | 60070143 | 283543 | 60070143 | 134383
2025-05-21 | May 2025 Review | Cost Decrease | Investment management (incl. Transport Planning) | Management of the funding allocation system | NZ Transport Agency | MÄori Engagement: Meet LTMA obligations | Implementation |  | ___ | HHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Indirect cost unchanged. Update admin in TIO | -50000 | -50000 |  |  |  | 3 | 60074686 | 291219 | 60074686 | 134622
2025-05-06 | May 2025 Review | Cost Increase | Investment management (incl. Transport Planning) | Management of the funding allocation system | NZ Transport Agency | MÄori Engagement: Meet LTMA obligations | Implementation |  | ___ | HHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Total direct cost $2m being transferred to SAP-PPM. Temp increase due to wrong admin rate which will be fixed in the next review. | 50000 | 50000 |  |  |  | 3 | 60074686 | 291219 | 60074686 | 134398
2025-05-12 | May 2025 Review | Cost Decrease | Safety | Network and asset management | NZ Transport Agency | Asset Management Data Standard (Deft) - Rollout | Implementation |  | ___ | VHMM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Funds being moved to new phase (293861) which maps to SAP item with the correct output class. | -9640000 | -9640000 |  |  |  | 4.4 | LR Maintenance part of funding, SAP item 60067372 | 277727 | 60067372 | 134490
2025-05-30 | May 2025 Review | Cost Decrease | Public transport infrastructure | New activities influencing users of the transport system | Hastings District Council | SfP Streets for Schools | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Council have confirmed claiming has been completed on Tuesday, 13 May 2025 9:10 am | -19524 | -17571 |  |  |  | 4.5 |  | 283319 |  | 134532
2025-05-19 | May 2025 Review | Cost Decrease | Public transport infrastructure | New activities influencing users of the transport system | NZ Transport Agency | CERF - Public Transport Initiatives (OPEX) | Implementation |  | ___ | VHHVH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Updating to reflect forecast. | -4635858 | -4635858 |  |  |  | 1 | 60069914 | 283542 | 60069914 | 134386
2025-05-02 | May 2025 Review | Cost Decrease | Public transport infrastructure | New activities influencing users of the transport system | NZ Transport Agency | CERF - Transport Choices Council Support Package (OPEX) | Implementation |  | ___ | VHHVH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Reforecast and update admin rate in TIO | -340629 | -340629 |  |  |  | 1 | 60069862 | 283629 | 60069862 | 134336
2025-05-08 | May 2025 Review | Cost Increase | Public transport services | New activities influencing users of the transport system | NZTA (Canterbury) | Waimakariri Bridge safety and reliability improvements | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Small increase to complete this work. Funds being transferred from item 60047792 | 129967 | 129967 |  |  | 2 | 2 | 60059020 | 278776 | 60066681 | 134430
2025-05-19 | May 2025 Review | Cost Decrease | State highway improvements | New roads | NZTA (Auckland) | RoRS SH1 Papakura to Bombay | Implementation |  | ___ | VHHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase transfer - Pls move a total of $20,526,733 from Imp contingency 60063236 to Implementation 60056232 ($17,026,733 to current year and remaining $3.5m to next FY) | -21347802 | -21347802 |  |  | 2.5 |  | MCIP 60063236 | 278974 | 60063236 | 134567
2025-05-19 | May 2025 Review | Cost Decrease | Local road improvements | New roads | Queenstown-Lakes District Council | HIF - Ladies Mile | Construction |  | ___ | VH__ | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Marked as claiming complete - QLDC had agreements with HIF that are no longer in place. | -12294118 | -6270000 |  |  | 0 | 0 | Construction | 258241 |  | 134504
2025-05-19 | May 2025 Review | Cost Decrease | Local road improvements | New roads | Queenstown-Lakes District Council | HIF - Ladies Mile | Repayment |  | ___ | VH__ | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Marked as claiming complete - QLDC had agreements with HIF that are no longer in place. | -6474000 | -6474000 |  |  | 0 | 0 | HIF Ladies Mile Repayment | 266801 |  | 134505
2025-05-19 | May 2025 Review | Cost Decrease | Local road improvements | New roads | Queenstown-Lakes District Council | HIF Quail Rise to Hawthorne Drive | Construction |  | ___ | VH_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Marked as claiming complete - QLDC had agreements with HIF that are no longer in place. | -7872627 | -4015040 |  |  | 0 | 0 |  | 258238 |  | 134507
2025-05-19 | May 2025 Review | Cost Decrease | Local road improvements | New roads | Queenstown-Lakes District Council | HIF Quail Rise to Hawthorne Drive | Pre-implementation* |  | ___ | VH_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Marked as claiming complete - QLDC had agreements with HIF that are no longer in place. | -343507 | -175189 |  |  | 0 | 0 |  | 258236 |  | 134506
2025-05-23 | May 2025 Review | Cost Decrease | Local road improvements | New roads | Queenstown-Lakes District Council | HIF Quail Rise to Hawthorne Drive | Repayment |  | ___ | VH_M | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Marked as claiming complete - QLDC had agreements with HIF that are no longer in place. | -4344212 | -4344212 |  |  | 0 | 0 | HIF Quail Rise Repayment | 260627 |  | 134508
2025-05-02 | May 2025 Review | Cost Decrease | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | NZTA (Auckland) | NWBI SH16 Westgate & Brigham Stations | Pre-implementation* |  | ___ | VHLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase transfer - pls move remaining balance of $2,385,712 from Pre-imp 60075138 to property phase 60075139 of the same project. rate type for both is CIP. | -2385712 | -2385712 |  |  | 1.1 | 1.3 | CIP Brigham | 291617 | 60075138 | 134319
2025-05-02 | May 2025 Review | Cost Increase | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | NZTA (Auckland) | NWBI SH16 Westgate & Brigham Stations | Property |  | ___ | VHLL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase transfer - pls move remaining balance of $2,385,712 from Pre-imp 60075138 to property phase 60075139 of the same project. rate type for both is CIP. | 2385712 | 2385712 |  |  | 1.1 | 1.3 | CIP Brigham | 291618 | 60075139 | 134320
2025-05-15 | May 2025 Review | Cost Increase | Public transport infrastructure | Passenger facilities and infrastructure improvements - bus | Whangarei District Council | CERF-TC - WDC Transport Choices Package | Implementation |  | ___ | HHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Approved by review committee 15 May 2025. Funds coming from WHGR03WDC01 (Raumanga Shared Path) | 338125 | 338125 |  |  |  | 0 |  | 284206 |  | 134576
2025-05-19 | May 2025 Review | Cost Decrease | Public transport services | Passenger services - bus | NZ Transport Agency | CERF - Public Transport Initiatives (OPEX) | Implementation |  | ___ | VHHVH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Updating to reflect recent appropriation updates and correcting to show only Waka Kotahi spend, not PTA and AO spend as well. | -591283 | -591283 |  |  |  | 1 | 60069915 | 283544 | 60069915 | 134387
2025-05-28 | May 2025 Review | Cost Increase | Walking and cycling improvements | Property purchase (State highways) | NZTA (Auckland) | Legacy Property Acquisition - Auckland | Property |  | ___ | HHM | N |  | Approved | Approved by Chief Financial Officer | This investment enables NZ Transport Agency Waka Kotahi to complete Property purchases where there is no identified project in place, or the projects are complete and final property obligations need to be met | 2129995 | 2129995 |  |  | 4 |  |  | 277839 | 60061615 | 134547
2025-05-19 | May 2025 Review | Cost Increase | Walking and cycling improvements | Property purchase (State highways) | NZTA (Auckland) | SH22 (Drury) Corridor Upgrade | Property |  | ___ | MML | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer - Pls move $4,828,120 from the MCIP Pre-Implementation Phase (SAP Item 60067768) to the MCIP Property phase (SAP Item 60067986) | 5021247 | 5021247 |  |  |  | 1.7 | MCIP 60067986 | 282184 | 60067986 | 134406
2025-05-28 | May 2025 Review | Cost Increase | Walking and cycling improvements | Property purchase (State highways) | NZTA (Canterbury) | Legacy Property Acquisition - Canterbury | Property |  | ___ | HHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | CSA request for Legacy Canterbury of $5M excl admin for 24-27 period | 5324965 | 5324965 | [5 empty] | 277874 | 60061628 | 134548
2025-05-30 | May 2025 Review | Cost Increase | Walking and cycling improvements | Property purchase (State highways) | NZTA (Canterbury) | RoRS SH1 Tinwald Corridor Improvements | Property |  | ___ | MMM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Transfer contingency ( 60063227) to Imp $112,00 (60057077) & to Property $255,000 (60057076) to cover additional actuals & Forecast costs | 265200 | 265200 |  |  | 4.6 | 4.6 | MCIP 60057076 | 270288 | 60057076 | 134598
2025-05-30 | May 2025 Review | Cost Increase | Walking and cycling improvements | Property purchase (State highways) | NZTA (Canterbury) | RoRS Walnut Avenue Intersection Improvements | Property |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Transfer contingency (60063226) to IMP $2,230,000 (60211591)additional costs depot-yardÂ & to Property $2,150,000 (60057032)to reinstate allocation | 2236004 | 2236004 |  |  | 1.8 | 1.8 | MCIP 60057032 | 270286 | 60057032 | 134597
2025-05-06 | May 2025 Review | Cost Increase | Walking and cycling improvements | Property purchase (State highways) | NZTA (Otago) | SH8 Beaumont bridge replacement | Property |  | ___ | MMM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | To transfer $30,795 excl admin ($32,797 incl admin) to Property 60465362 from Imp 60217046 to enable closure of the Property phase. | 32794 | 32794 |  |  | 0 | 12 | 60465362 | 214531 | 60465362 | 134368
2025-05-28 | May 2025 Review | Cost Increase | Walking and cycling improvements | Property purchase (State highways) | NZTA (Waikato) | Legacy Property Acquisition Waikato 21-24 | Property |  | ___ | HHM | N |  | Approved | Approved by Chief Financial Officer | CSA request for Legacy Waikato of $3M excl admin for 24-27 period | 3194993 | 3194993 | [5 empty] | 277605 | 60061512 | 134539
2025-05-30 | May 2025 Review | Cost Increase | Walking and cycling improvements | Property purchase (State highways) | NZTA (Waikato) | RoRS SH1-29 Intersection Improvements | Property |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer: Please Transfer $25,116 from 60213469 Implementation to 60445502 Property, Property phase can then be closed. | 26121 | 26121 |  |  | 2.5 | 2.5 | MCIP 60445502 | 270649 | 60445502 | 134668
2025-05-28 | May 2025 Review | Cost Increase | Walking and cycling improvements | Property purchase (State highways) | NZTA (Wellington) | Legacy Property Acquisition - Wellington | Property |  | ___ | HHM | N |  | Approved | Approved by Chief Financial Officer | CSA request for Legacy Wellington of $4M excl admin for 24-27 period | 4259989 | 4259989 | [5 empty] | 277389 | 60061250 | 134560
2025-05-05 | May 2025 Review | Cost Increase | Walking and cycling improvements | Property purchase (State highways) | NZTA (Wellington) | RoNS Petone to Grenada Link Road and CVL | Property |  | ___ | VHHL | N |  | Declined | Declined by regional office |  | 1597249 | 1597249 |  |  | 1.3 | 1 | 60465812 | 269931 | 60465812 | 134034
2025-05-07 | May 2025 Review | Cost Increase | Walking and cycling improvements | Property purchase (State highways) | NZTA (Wellington) | RoNS Petone to Grenada Link Road and CVL | Property |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow adjustments Conversations with the advance purchase owner and if negotiations go smoothly the purchase may fall within the current financial year. Admin rate change in 26/27 so shows slight increase. | 266207 | 266207 |  |  | 1.3 | 1 | 60465812 | 269931 | 60465812 | 134395
2025-05-02 | May 2025 Review | Cost Decrease | Public transport infrastructure | Public transport improvements, major renewals and minor improvements | Greater Wellington | National Ticketing Solution (NTS) | Construction |  | ___ | MHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -85553 | -43632 |  |  | 3 | 3 | GRETS | 251496 |  | 134290
2025-05-02 | May 2025 Review | Cost Decrease | Public transport services | Public transport operations and management | NZ Transport Agency | CERF - Transport Choices Council Support Package (OPEX) | Implementation |  | ___ | VHHVH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Reforecast and update admin rate in TIO | -42287 | -42287 |  |  |  | 1 | 60069863 | 283630 | 60069863 | 134337
2025-05-19 | May 2025 Review | Cost Decrease | State highway improvements | Replacement of bridges and other structures | NZTA (Gisborne) | EOL SH35 Mangahauini No. 1 Bridge | Single-Stage Business Case |  | ___ | HHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Project close requested by PM and RPM. | -51845 | -51845 |  |  |  | 1 |  | 290346 | 60073595 | 134468
2025-05-19 | May 2025 Review | Cost Decrease | State highway improvements | Replacement of bridges and other structures | NZTA (Hawkes Bay) | EOL SH38 Frasertown Bridge | Single-Stage Business Case |  | ___ | HHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Project close requested by PM and RPM. | -58656 | -58656 |  |  |  | 1 |  | 290350 | 60073602 | 134469
2025-05-06 | May 2025 Review | Cost Decrease | State highway improvements | Replacement of bridges and other structures | NZTA (Otago) | SH8 Beaumont bridge replacement | Implementation |  | ___ | MMM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | To transfer $30,795 excl admin ($32,797 incl admin) to Property 60465362 from Imp 60217046 to enable closure of the Property phase. | -32797 | -32797 |  |  | 0 | 12 | 60217046 | 213142 | 60217046 | 134367
2025-05-30 | May 2025 Review | Cost Decrease | State highway improvements | Resilience improvements | NZTA (Canterbury) | Crown Resilience Programme LCLR CAN | Implementation |  | ___ | VHHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | To transfer $317,762 excl admin from 60071724 to 60071767 to cover additional fund required for Ormon Falls project. | -338415 | -338415 |  |  |  | 4 |  | 290389 | 60071724 | 134583
2025-05-30 | May 2025 Review | Cost Decrease | State highway improvements | Resilience improvements | NZTA (Waikato) | Crown Resilience Programme LCLR WAI | Implementation |  | ___ | VHHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Cashflow Adjustment: Please Transfer $4,952,101 of allocation from FY 24/25 to FY 25/25 | -409893 | -409893 |  |  |  | 4 |  | 288949 | 60071759 | 134610
2025-05-30 | May 2025 Review | Cost Increase | State highway improvements | Resilience improvements | NZTA (West Coast) | Crown Resilience Programme LCLR WTCT | Implementation |  | ___ | VHHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | To transfer $317,762 excl admin from 60071724 to 60071767 to cover additional fund required for Ormon Falls project. | 338413 | 338413 |  |  |  | 4 |  | 290390 | 60071767 | 134584
2025-05-02 | May 2025 Review | Cost Decrease | Safety | Road improvements | Clutha District Council | Streetlight LED Upgrade | Construction |  | ___ | M_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Claiming has been marked as complete. | -1144 | -766 |  |  | 0 | 1.2 | CDC/LED/2017-18 | 250374 |  | 134289
2025-05-16 | May 2025 Review | Cost Decrease | Safety | Road improvements | Dunedin City Council | Peninsula Roading - Portobello Rd | Construction |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | This clears the remaining budgets and phase will be marked as claiming complete when a few more checks have been done. | -6123 | -3123 |  |  | 1.7 | 1.7 | Company Bay to King George St | 220554 |  | 134353
2025-05-16 | May 2025 Review | Cost Decrease | Safety | Road improvements | Dunedin City Council | Peninsula Roading - Portobello Rd | Construction |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | The reduction in cost is as a result of efficiencies being found (less consultant work than originality planned) not as a result of a reduced scope so all of the original benefits will still be delivered. | -700000 | -357000 |  |  | 1.7 | 1.7 | Bacon St to Hereweka St | 215897 |  | 134354
2025-05-30 | May 2025 Review | Cost Decrease | Safety | Road improvements | Invercargill City Council | 11 Yr Streetlighting Renewal Programme for Invercargill City | Construction |  | ___ | M_H | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Automatic reconciliation of approved costs with claimed costs for 2024/25 as activity is claiming complete | -11585 | -8110 |  |  | 8.7 |  |  | 202383 |  | 134628
2025-05-30 | May 2025 Review | Cost Decrease | Safety | Road improvements | Invercargill City Council | LED Streetlight Upgrade 2017-2018 | Construction |  | ___ | M_L | N |  | Approved | Approved by Manager, Treasury & Cash Flow | completed & surplus | -124947 | -63723 |  |  | 1.4 | 1.4 |  | 262997 |  | 134629
2025-05-02 | May 2025 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Auckland) | ANO VMS Infrastructure Expansion | Implementation |  | ___ | HHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer - Pls move $1,083,680 from ANO Trench 2 implementation 60066153 to the ANO VMS Infrastructure implementation 60081821 | 1181212 | 1181212 |  |  | 3.2 | 3.2 |  | 292685 | 60081821 | 134312
2025-05-02 | May 2025 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Auckland) | RoNS East West Link | Implementation |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Project Close | -733886997 | -733886997 |  |  | 1.9 | 1.9 | 60028552 | 233288 | 60028552 | 134325
2025-05-19 | May 2025 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Auckland) | RoRS SH1 Papakura to Bombay | Implementation |  | ___ | VHHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase transfer - Pls move a total of $20,526,733 from Imp contingency 60063236 to Implementation 60056232 ($17,026,733 to current year and remaining $3.5m to next FY) | 21347804 | 21347804 |  |  | 2.5 |  | MCIP Implementation Stage | 269799 | 60056232 | 134572
2025-05-19 | May 2025 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Auckland) | SH22 (Drury) Corridor Upgrade | Pre-implementation* |  | ___ | MML | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer - Pls move $4,828,120 from the MCIP Pre-Implementation Phase (SAP Item 60067768) to the MCIP Property phase (SAP Item 60067986) | -5021246 | -5021246 |  |  |  | 1.7 | MCIP 60067768 | 281986 | 60067768 | 134405
2025-05-12 | May 2025 Review | Cost Increase | State highway improvements | Road improvements | NZTA (BOP) | BOP VfM Safety Imp â€“ Small Projects | Implementation | BOP VfM Safety Imp â€“ Small Infra Region | MHH | MHL | N | 6 | Approved | Approved by Manager, Treasury & Cash Flow (Corporate Support) | VfM Interphase Transfer - move $2,591,000 ex admin from 60075222 and $415,000 ex admin from 60083341 to 60083170 (total $3,006,000) | 3276540 | 3276540 |  |  | 6 | 6 | BOP VfM Safety Imp â€“ Small Infra Region | 292895 | 60083170 | 134476
2025-05-01 | May 2025 Review | Cost Increase | State highway improvements | Road improvements | NZTA (BOP) | SH2 Wainui Rd to Opotiki, NSRRP | Implementation |  | ___ | HHL | N |  | Approved | Approved by Chief Financial Officer | Increase in cost of project phase - PLA submission $6,968,083. | 7595210 | 7595210 |  |  | 1 | 1 |  | 292473 | 60076223 | 134031
2025-05-01 | May 2025 Review | Cost Increase | State highway improvements | Road improvements | NZTA (BOP) | SH2 Wainui Rd to Opotiki, NSRRP | Pre-implementation* |  | ___ | HHL | N |  | Approved | Approved by Chief Financial Officer | Increase in cost of project phase - PLA request $610,827. | 665800 | 665800 |  |  | 1 | 1 |  | 292474 | 60076224 | 134032
2025-05-19 | May 2025 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Canterbury) | RoRS Rolleston Access Improvements | Detailed Business Case |  | ___ | VHHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Transfer 26,957 from DBC 60057113 to pre-imp 60057114 as the DBC phase is now complete | -28035 | -28035 |  |  | 3.6 | 3.6 | MCIP 60057113 | 263129 | 60057113 | 134369
2025-05-30 | May 2025 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Canterbury) | RoRS Rolleston Access Improvements | Implementation |  | ___ | VHHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase transfer from Pre Imp Phase 60057114 to Imp phase 60057117 for 5M. Correcting part of allocation for MSQA etc which was incorrectly allocated to the Pre-Imp phase | 5200001 | 5200001 |  |  | 3.6 | 3.6 | MCIP 60057117 | 231732 | 60057117 | 134654
2025-05-30 | May 2025 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Canterbury) | RoRS Rolleston Access Improvements | Pre-implementation* |  | ___ | VHHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase transfer from Pre Imp Phase 60057114 to Imp phase 60057117 for 5M. Correcting part of allocation for MSQA etc which was incorrectly allocated to the Pre-Imp phase | -5200002 | -5200002 |  |  | 3.6 | 3.6 | MCIP 60057114 | 231731 | 60057114 | 134653
2025-05-19 | May 2025 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Canterbury) | RoRS Rolleston Access Improvements | Pre-implementation* |  | ___ | VHHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Transfer 26,957 from DBC 60057113 to pre-imp 60057114 as the DBC phase is now complete | 28033 | 28033 |  |  | 3.6 | 3.6 | MCIP 60057114 | 231731 | 60057114 | 134370
2025-05-30 | May 2025 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Canterbury) | RoRS SH1 Tinwald Corridor Improvements | Implementation |  | ___ | MMM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Transfer contingency ( 60063227) to Imp $112,00 (60057077) & to Property $255,000 (60057076) to cover additional actuals & Forecast costs | -381680 | -381680 |  |  | 4.6 | 4.6 | MCIP 60063227 | 278980 | 60063227 | 134595
2025-05-30 | May 2025 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Canterbury) | RoRS SH1 Tinwald Corridor Improvements | Implementation |  | ___ | MMM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Transfer contingency ( 60063227) to Imp $112,00 (60057077) & to Property $255,000 (60057076) to cover additional actuals & Forecast costs | 116482 | 116482 |  |  | 4.6 | 4.6 | MCIP 60057077 | 238976 | 60057077 | 134599
2025-05-30 | May 2025 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Canterbury) | RoRS Walnut Avenue Intersection Improvements | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Transfer contingency (60063226) to IMP $2,230,000 (60211591)additional costs depot-yardÂ & to Property $2,150,000 (60057032)to reinstate allocation | 2319201 | 2319201 |  |  | 1.8 | 1.8 | MCIP 60211591 | 231796 | 60211591 | 134596
2025-05-30 | May 2025 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Canterbury) | RoRS Walnut Avenue Intersection Improvements | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Transfer contingency (60063226) to IMP $2,230,000 (60211591)additional costs depot-yardÂ & to Property $2,150,000 (60057032)to reinstate allocation | -4555200 | -4555200 |  |  | 1.8 | 1.8 | MCIP 60063226 | 278975 | 60063226 | 134606
2025-05-08 | May 2025 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Canterbury) | Waimakariri Bridge safety and reliability improvements | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Remaining funds not required. Some to be transferred to the TDM item 60066681 | -2376410 | -2376410 |  |  | 2 | 2 |  | 254758 | 60047792 | 134431
2025-05-30 | May 2025 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Otago) | SH1 Oamaru to Dunedin - (Hampden to Palmerston) | Pre-implementation* |  | ___ | HHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Project close, surplus remaining allocation | -1474830 | -1474830 |  |  | 0 | 1.6 |  | 292502 | 60076241 | 134551
2025-05-19 | May 2025 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Waikato) | Hamilton Ring Road - Wairere/Cobham Interchange | Implementation |  | ___ | HHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Reduced Allocation: Please Surplus $97,124 from FY 24/25 and $210,000 from FY25/26 | -334768 | -334768 |  |  | 7.6 | 7.6 | 16-015 | 262942 | 60048597 | 134557
2025-05-30 | May 2025 Review | Cost Decrease | State highway improvements | Road improvements | NZTA (Waikato) | RoRS SH1-29 Intersection Improvements | Construction |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer: Please Transfer $25,116 from 60213469 Implementation to 60445502 Property, Property phase can then be closed. | -26121 | -26121 |  |  | 2.5 | 2.5 | MCIP 60213469 | 240049 | 60213469 | 134671
2025-05-22 | May 2025 Review | Cost Increase | State highway improvements | Road improvements | NZTA (Wellington) | RoRS SH2 Melling Efficiency & Safety Imp | Implementation |  | ___ | MMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Board approved increase, with funds transferred from 60471352 and 60063250. NB All NZUP funding | 549801358 | 549801358 |  |  | 0 | 1.3 | MCIP 60218122 | 270320 | 60218122 | 134624
2025-05-07 | May 2025 Review | Cost Increase | Local road operations | Structures component replacements | South Wairarapa District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Senior Manager I&F - Operational Policy, Planning & Performance | Supported - The Riddifords bridge requires component replacement. | 0 | 481950 | [5 empty] | 285771 |  | 134346
2025-05-16 | May 2025 Review | Cost Decrease | Public transport infrastructure | Technology to improve effectiveness of public transport systems | NZ Transport Agency | CERF - Transport Choices Council Support Package (OPEX) | Implementation |  | ___ | VHHVH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Reforecast and update admin rate in TIO | -297341 | -297341 |  |  |  | 1 | 60069864 | 283631 | 60069864 | 134582
2025-05-07 | May 2025 Review | Cost Increase | Local road operations | Traffic services renewals | South Wairarapa District Council | Maintenance, Operations and Renewals Programme 2024-27 - AC 8 | Local Roads |  | __ |  | N |  | Approved | Approved by Senior Manager I&F - Operational Policy, Planning & Performance | Supported - The Riddifords bridge requires component replacement. | 0 | 0 | [5 empty] | 285774 |  | 134346
2025-05-02 | May 2025 Review | Cost Decrease | Walking and cycling improvements | Walking facilities | NZ Transport Agency | CERF - Transport Choices Council Support Package (OPEX) | Implementation |  | ___ | VHHVH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Reforecast and update of admin rate in TIO | -469490 | -469490 |  |  |  | 1 | 60069781 | 283628 | 60069781 | 134335
2025-05-26 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (Auckland) | AKL Share RoNS Project Development | Detailed Business Case |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase transfer: $366,972 from 60075346 to 60083893. | -400000 | -400000 |  |  |  | 1 | AKL Share RoNS Project Development | 291831 | 60075346 | 134623
2025-05-29 | May 2025 Review | Cost Decrease | Walking and cycling improvements |  | NZTA (Auckland) | AKL Share RoNS Property | Property |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | To interpahse transfer $50M excl admin ($53.25M incl 6.5% admin) from AKL Property Share to RoNS ASH property phase | -53250000 | -53250000 |  |  |  | 1 | AKL Share RoNS Property | 291833 | 60075354 | 134472
2025-05-06 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (Auckland) | AKLD Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer - Pls move $6,005 from VFM funding bucket 60075303 to 60083164 AKLD VfM Safety Imp (to cover overspend of WBS 60084152 Princes St SBD Road Side Barrier VfM ) | -6545 | -6545 |  |  |  | 1 | 60075303 AKLD Share VFM Safety Imp Prog | 289798 | 60075303 | 134375
2025-05-09 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (Auckland) | AKLD Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $302,050 ex admin from 60075303 to 60083161 ($300,000) and 60083162 ($2,050) | -329234 | -329234 |  |  |  | 1 | 60075303 AKLD Share VFM Safety Imp Prog | 289798 | 60075303 | 134471
2025-05-06 | May 2025 Review | Cost Increase | State highway improvements |  | NZTA (Auckland) | AKLD VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer - Pls move $6,005 from VFM funding bucket 60075303 to 60083164 AKLD VfM Safety Imp (to cover overspend of WBS 60084152 Princes St SBD Road Side Barrier VfM ) | 6545 | 6545 |  |  | 6 | 6 | AKLD VfM Safety Imp - RtZ Infra & Speed | 292890 | 60083164 | 134376
2025-05-09 | May 2025 Review | Cost Increase | State highway improvements |  | NZTA (Auckland) | AKLD VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $2050 ex admin from 60075303 to 60083162 | 2234 | 2234 |  |  | 6 | 6 | AKLD VfM Safety Imp - Schools (Imp) | 292891 | 60083162 | 134475
2025-05-15 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (Auckland) | AKLD VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Fixing admin rate | -3000 | -3000 |  |  | 6 | 6 | AKLD VfM Safety Imp - Small Infra React | 292892 | 60083161 | 134565
2025-05-02 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (Auckland) | Auckland Network Optimisation (ANO) Programme | Implementation |  | ___ | HHM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer - Pls move $1,083,680 from ANO Trench 2 implementation 60066153 to the ANO VMS Infrastructure implementation 60081821 | -1181211 | -1181211 |  |  |  | 3.2 | ANO Programme Tranche 2 | 280258 | 60066153 | 134307
2025-05-26 | May 2025 Review | Cost Increase | State highway improvements |  | NZTA (Auckland) | RoNS Mill Road | Detailed Business Case |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Funding increase for Urgent Mill Rd Stage 2 NOR. Transfer $400K(9% included) from RONS bulk funding(60075346) to Mill Rd(60083893). | 399996 | 399996 |  |  | 1.2 | 1.2 |  | 293141 | 60083893 | 134620
2025-05-20 | May 2025 Review | Cost Decrease | Walking and cycling improvements |  | NZTA (BOP) | BOP Share RoNS Property | Property |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase transfer a total of $20M excl admin ($21.3M incl 6.5% admin) to 60087155 of $5M excl admin and 60083050 of $15M excl admin - both are RoNS Tauriko West Projects. | -21300000 | -21300000 |  |  |  | 1 |  | 291787 | 60075256 | 134388
2025-05-12 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (BOP) | BOP Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $7,591,000 ex admin from 60075222 to 60083170 ($2,591,000) and 60084936 ($5,000,000) | -8274190 | -8274190 |  |  |  | 1 | 60075222 BOP Share VFM Safety Imp Prog | 289802 | 60075222 | 134486
2025-05-12 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (BOP) | BOP Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $415,000 ex admin from 60083341 to 60083170 | -452350 | -452350 |  |  |  | 1 | 60083341 BOP Share VFM Safety Imp-CONTINGENCY | 289801 | 60083341 | 134481
2025-05-21 | May 2025 Review | Cost Decrease | Walking and cycling improvements |  | NZTA (BOP) | RoNS SH29 Offline Tauriko West | Property |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Total under review should have been $15M in total but 24/25 allocation missed out at $50K. | -320500 | -320500 |  |  | 1.9 | 1.8 |  | 292851 | 60083050 | 134617
2025-05-15 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (Canterbury) | CAN Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $11,880,206 ex admin from 60075600 to 60083176 ($1,010,206), 60083177 ($2,750,000), 60083337 ($190,000), 60083338 ($1,710,000) and 60060948 ($6,220,000) | -12949425 | -12949425 |  |  |  | 1 | 60075600 CAN Share VFM Safety Imp Prog | 289807 | 60075600 | 134541
2025-05-15 | May 2025 Review | Cost Increase | State highway improvements |  | NZTA (Canterbury) | CAN VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $1,010,206 ex admin from 60075600 to 60083176 | 1101124 | 1101124 |  |  | 6 | 6 | CAN VfM Safety Imp â€“ Schools | 292897 | 60083176 | 134552
2025-05-02 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (Canterbury) | RoNS SH1 Belfast to Pegasus & Woodend BP | Indicative Business Case |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | To transfer $14,604 (excl admin) remaining allocation from IBC (60083871) to Pre-Imp (60210539) as IBC phase is now complete. | -15920 | -15920 |  |  | 1.1 | 1.1 |  | 293238 | 60083871 | 134349
2025-05-02 | May 2025 Review | Cost Increase | State highway improvements |  | NZTA (Canterbury) | RoNS SH1 Belfast to Pegasus & Woodend BP | Pre-implementation* |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | To transfer $14,604 (excl admin) remaining allocation from IBC (60083871) to Pre-Imp (60210539) as IBC phase is now complete, and cashflow adjustment request to match yearly forecast. | 15919 | 15919 |  |  | 1.1 | 1.1 | RoNS 60210539 | 194063 | 60210539 | 134315
2025-05-23 | May 2025 Review | Cost Increase | State highway improvements |  | NZTA (Canterbury) | RoRS Second Ashburton Bridge | Pre-implementation* |  | ___ | HMM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | TIO cost neutral Interphase transfer from property phase 60085995 $1,490,566 to pre-imp phase 60085994 $1,456,379 to allow closure of property phase and mgmt from pre-imp | 1587453 | 1587453 |  |  |  | 3.6 |  | 293633 | 60085994 | 134646
2025-05-23 | May 2025 Review | Cost Decrease | Walking and cycling improvements |  | NZTA (Canterbury) | RoRS Second Ashburton Bridge | Property |  | ___ | HMM | N |  | Approved | Approved by Manager, Treasury & Cash Flow | TIO cost neutral Interphase transfer from property phase 60085995 $1,490,566 to pre-imp phase 60085994 $1,456,379 to allow closure of property phase and mgmt from pre-imp | -1587453 | -1587453 |  |  |  | 3.6 |  | 293632 | 60085995 | 134647
2025-05-15 | May 2025 Review | Cost Increase | State highway improvements |  | NZTA (Canterbury) | SH1 Templeton to Selwyn River | Implementation |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $6,220,000 ex admin from 60075600 to 60060948 | 6779800 | 6779800 |  |  | 2.1 | 2.1 | 22867 | 277306 | 60060948 | 134559
2025-05-08 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (Gisborne) | GIS Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $441,185 ex admin from 60075397 to 60083183 ($141,185) and 60083182 ($300,000) | -480892 | -480892 |  |  |  | 1 | 60075397 GIS Share VFM Safety Imp Prog | 289809 | 60075397 | 134408
2025-05-08 | May 2025 Review | Cost Increase | State highway improvements |  | NZTA (Gisborne) | GIS VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $441,185 ex admin from 60075397 to 60083183 ($141,185) and 60083182 ($300,000) | 153892 | 153892 |  |  | 6 | 6 | GIS VfM Safety Imp â€“ Schools | 292902 | 60083183 | 134390
2025-05-08 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (Hawkes Bay) | HAWK Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $3,213,284 ex admin from 60075469 to 60083190 ($403,284), 60083191 ($2,510,000) & 60083189 ($300,000) | -3502480 | -3502480 |  |  |  | 1 | 60075469 HAWK Share VFM Safety Imp Prog | 289811 | 60075469 | 134410
2025-05-08 | May 2025 Review | Cost Increase | State highway improvements |  | NZTA (Hawkes Bay) | HAWK VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $3,213,284 ex admin from 60075469 to 60083190 ($403,284), 60083191 ($2,510,000) & 60083189 ($300,000) | 439580 | 439580 |  |  | 6 | 6 | HAWK VfM Safety Imp â€“ Schools | 292906 | 60083190 | 134412
2025-05-16 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (Manawatu/Whanganui) | MNWI Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $8,000,000 ex admin from 60075295 to 60083377 ($800,000) and 60083378 ($7,200,000) | -8720000 | -8720000 |  |  |  | 1 | 60075295 MNWI Share VFM Safety Imp Prog | 291813 | 60075295 | 134578
2025-05-08 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (Manawatu/Whanganui) | MNWI Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $23,221,663 ex admin from 60075295 to 60083204 ($1,451,663), 60083203 ($300,000), 60083205 ($2,120,000), 60083322 ($200,000), 60083323 ($1,800,000), 60083287 ($700,000) & 60083288 ($6,300,000), 60087504 ($1,350,000), 60087505 ( $9,000,000) | -25311611 | -25311611 |  |  |  | 1 | 60075295 MNWI Share VFM Safety Imp Prog | 291813 | 60075295 | 134417
2025-05-08 | May 2025 Review | Cost Increase | State highway improvements |  | NZTA (Manawatu/Whanganui) | MNWI VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $1,451,663 ex admin from 60075295 to 60083204 | 1582313 | 1582313 |  |  | 6 | 6 | MNWI VfM Safety Imp â€“ Schools | 292914 | 60083204 | 134419
2025-05-14 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (Marlborough) | MARL Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $1,992,185 ex admin from 60075526 to 60083198 ($322,185), 60083197 ($300,000) and 60083157 ($1,370,000) | -2171483 | -2171483 |  |  |  | 1 | 60075526 MARL Share VFM Safety Imp Prog | 289818 | 60075526 | 134520
2025-05-13 | May 2025 Review | Cost Increase | State highway improvements |  | NZTA (Marlborough) | MARL Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $70k ex admin from 60083159 (WBS 60083776 Freeths Rd) to 60075526 | 76300 | 76300 |  |  |  | 1 | 60075526 MARL Share VFM Safety Imp Prog | 289818 | 60075526 | 134495
2025-05-14 | May 2025 Review | Cost Increase | State highway improvements |  | NZTA (Marlborough) | MARL VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $322,185 ex admin from 60075526 to 60083198 | 343100 | 343100 |  |  | 6 | 6 | MARL VfM Safety Imp â€“ Schools | 292909 | 60083198 | 134524
2025-05-14 | May 2025 Review | Cost Increase | State highway improvements |  | NZTA (Marlborough) | MARL VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Adjusting 2024/25 $ as requested by Pia | 8082 | 8082 |  |  | 6 | 6 | MARL VfM Safety Imp â€“ Schools | 292909 | 60083198 | 134535
2025-05-13 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (Marlborough) | MARL VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | HHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $70k ex admin from 60083159 (WBS 60083776 Freeths Rd) to 60075526 | -76300 | -76300 |  |  | 6 | 6 | MARL VfM Safety Imp â€“ RtZ Infra & Speed | 292912 | 60083159 | 134493
2025-05-12 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (Nelson) | NEL Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $368,686 ex admin from 60075437 to 60083210 ($300,000) and 60083211 ($68,686) | -401868 | -401868 |  |  |  | 1 | 60075473 NEL Share VFM Safety Imp Prog | 289819 | 60075473 | 134473
2025-05-12 | May 2025 Review | Cost Increase | State highway improvements |  | NZTA (Nelson) | NEL VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $68,686 ex admin from 60075473 to 60083211 | 74868 | 74868 |  |  | 6 | 6 | NEL VfM Safety Imp â€“ Schools | 292918 | 60083211 | 134460
2025-05-09 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (Northland) | NTLD Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $1,841,207 ex admin from 60075196 to 60083219 ($341,207), 60083217 ($300,000) and 60083220 ($1,200,000) | -2006917 | -2006917 |  |  |  | 1 | 60075196 NTLD Share VFM Safety Imp Prog | 289827 | 60075196 | 134470
2025-05-09 | May 2025 Review | Cost Increase | State highway improvements |  | NZTA (Northland) | NTLD VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $341,207 ex admin from 60075196 to 60083219 | 371916 | 371916 |  |  | 6 | 6 | NTLD VfM Safety Imp â€“ Schools | 292922 | 60083219 | 134462
2025-05-14 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (Northland) | NTLD VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Fix the admin | -12000 | -12000 |  |  | 6 | 6 | NTLD VfM Safety Imp â€“ Small Infra Region | 292923 | 60083220 | 134536
2025-05-14 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (Northland) | NTLD VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Auckland Transport Chief Financial Officer | Fixing admin rate | -3000 | -3000 |  |  | 6 | 6 | NTLD VfM Safety Imp â€“ Small Infra React | 292921 | 60083217 | 134561
2025-05-14 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (Otago) | OTA Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $12,524,567 ex admin from 60075581 to 60083226 ($924,567), 60083227 ($2,790,000), 60083307 ($281,000), 60083308 ($2,529,000) and 60070283 ($6,000,000) | -13651778 | -13651778 |  |  |  | 1 | 60075581 OTA Share VFM Safety Imp Prog | 289831 | 60075581 | 134521
2025-05-14 | May 2025 Review | Cost Increase | State highway improvements |  | NZTA (Otago) | OTA VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $924,567 ex admin from 60075581 to 60083226 | 1007778 | 1007778 |  |  | 6 | 6 | OTA VfM Safety Imp â€“ Schools | 292926 | 60083226 | 134514
2025-05-14 | May 2025 Review | Cost Increase | State highway improvements |  | NZTA (Otago) | OTA VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $2,790,000 ex admin from 60075581 to 60083227 | 3041100 | 3041100 |  |  | 6 | 6 | OTA VfM Safety Imp â€“ Small Infra Region | 292927 | 60083227 | 134515
2025-05-14 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (Otago) | SH1 Waitati Valley Rd - Pine Hill Rd SNP | Implementation |  | ___ | HMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Fix admin rate | -25290 | -25290 |  |  | 6 | 6 |  | 292963 | 60083308 | 134538
2025-05-15 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (Southland) | STLD Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $5,697,480 ex admin from 60075556 to 60083234 ($1,209,480), 60083235 ($488,000), 60083297 ($400,000), 60083297 ($3,600,000) | -6210253 | -6210253 |  |  |  | 1 | 60075556 STLD Share VFM Safety Imp Prog | 289836 | 60075556 | 134540
2025-05-15 | May 2025 Review | Cost Increase | State highway improvements |  | NZTA (Southland) | STLD VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $1,209,480 ex admin from 60075556 to 60083234 | 1318334 | 1318334 |  |  | 6 | 6 | STLD VfM Safety Imp â€“ Schools | 292930 | 60083234 | 134543
2025-05-08 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (Taranaki) | TAR Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $1,375,713 ex admin from 60075244 to 60083242 ($1075713) & 60083241 ($300000) | -1499527 | -1499527 |  |  |  | 1 | 60075244 TAR Share VFM Safety Imp Prog | 291784 | 60075244 | 134416
2025-05-08 | May 2025 Review | Cost Increase | State highway improvements |  | NZTA (Taranaki) | TAR VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $1,375,713 ex admin from 60075244 to 60083242 ($1075713) & 60083241 ($300000) | 1172528 | 1172528 |  |  | 6 | 6 | TAR VfM Safety Imp â€“ Schools | 292934 | 60083242 | 134415
2025-05-12 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (Tasman) | TAS Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $6,658,784 ex admin from 60075545 to 60083248 ($300,000), 60083249 ($384,784), 60083250 ($974,000), 60083292 ($500,000) and 60083293 ($4,500,000) | -7258075 | -7258075 |  |  |  | 1 | 60075545 TAS Share VFM Safety Imp Prog | 289915 | 60075545 | 134487
2025-05-12 | May 2025 Review | Cost Increase | State highway improvements |  | NZTA (Tasman) | TAS VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $384,784 ex admin from 60075545 to 60083249 | 419415 | 419415 |  |  | 6 | 6 | TAS VfM Safety Imp â€“ Schools | 292938 | 60083249 | 134465
2025-05-30 | May 2025 Review | Cost Increase | State highway improvements |  | NZTA (Waikato) | SH1B/Holland Road Int Interventions | Implementation |  | ___ | HMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer: Please transfer $1,100,000 from 60083353 VfM Contingency to 60083318 Implementation. | 1199000 | 1199000 |  |  | 6 | 6 |  | 292967 | 60083318 | 134630
2025-05-19 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (Waikato) | SH25A rebuild improvements | Implementation |  | ___ | VHHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Update admin rate in TIO. Direct cost unchanged | -138444 | -138444 |  |  | 0.5 | 0.5 |  | 292674 | 60075151 | 134423
2025-05-09 | May 2025 Review | Cost Increase | State highway improvements |  | NZTA (Waikato) | SH27/Kerone Road/Diagonal Road ISZ | Implementation |  | ___ | HMH | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Correction of interphase transfer that did push through interphase transfer an amount for 26/27 - VfM Interphase Transfer - move $1,710,000 ex admin from 60075459 to 60083328 | 1035500 | 1035500 |  |  | 6 | 6 |  | 292993 | 60083328 | 134436
2025-05-30 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (Waikato) | WAI Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | Interphase Transfer: Please transfer $1,100,000 from 60083353 VfM Contingency to 60083318 Implementation. | -1199000 | -1199000 |  |  |  | 1 | 60083353 WAI Share VFM Safety Imp-CONTINGENCY | 289917 | 60083353 | 134631
2025-05-07 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (Waikato) | WAI Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $12,378,000 ex admin from 60075459 to 60083257 ($8,478,000), 60083317 ($200,000), 60083318 ($1,800,000), 60083327 ($190,000) & 60083328 ($1,710,000) | -13492021 | -13492021 |  |  |  | 1 | 60075459 WAI Share VFM Safety Imp Prog | 289918 | 60075459 | 134389
2025-05-14 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (Wellington) | WGTN Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $3,555,085 ex admin from 60075638 to 60083262 ($600,000), 60083264 ($210,085), 60083265 ($525,000), 60083312 ($222,000) and 60083313 ($1,998,000) | -3875043 | -3875043 |  |  |  | 1 | 60075638 WGTN Share VFM Safety Imp Prog | 289923 | 60075638 | 134522
2025-05-14 | May 2025 Review | Cost Increase | State highway improvements |  | NZTA (Wellington) | WGTN VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move$210,085 ex admin from 60075638 to 60083264 | 228993 | 228993 |  |  | 6 | 6 | WGTN VfM Safety Imp â€“ Schools | 292946 | 60083264 | 134517
2025-05-15 | May 2025 Review | Cost Decrease | State highway improvements |  | NZTA (West Coast) | WTCT Share VFM Safety Imp Prog | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $589,983 ex admin from 60075625 to 60083271 | -643081 | -643081 |  |  |  | 1 | 60075625 WTCT Share VFM Safety Imp Prog | 289925 | 60075625 | 134542
2025-05-15 | May 2025 Review | Cost Increase | State highway improvements |  | NZTA (West Coast) | WTCT VfM Safety Imp â€“ Small Projects | Implementation |  | ___ | MHL | N |  | Approved | Approved by Manager, Treasury & Cash Flow | VfM Interphase Transfer - move $589,983 ex admin from 60075625 to 60083271 | 643081 | 643081 |  |  | 6 | 6 | WTCT VfM Safety Imp â€“ Schools | 292951 | 60083271 | 134545